## Projects
Project_ID | Project_Name | Project_Type | Location | Client | Main_Contractor | Consultant | Building_Type | Total_Floors | Total_Built_Up_Area_sqft | Start_Date | Planned_End_Date | Total_Budget_INR | Project_Status
P001 | Green Heights Residential Tower | Residential | Kolkata | Bengal Horizon Developers | Apex Buildcon Private Limited | Design Matrix Consultants | G+10 | 11 | 150000 | 2025-01-01 | 2025-12-31 | 57580000 | In Progress

## Contractors
Contractor_ID | Contractor_Name | Specialization | Contact_Person | Contractor_Type | Activities_Handled
C001 | Apex Buildcon (Main) | Civil Works | Ravi Sharma | Main Contractor | Prelims, Earthwork
C002 | SteelStrong Pvt Ltd | RCC Works | Amit Patel | Subcontractor | Reinforcement, Concrete
C003 | BrickMasters | Masonry | S. K. Das | Subcontractor | Brickwork, Blockwork
C004 | SmoothFinish Ltd | Plastering | Priya Singh | Subcontractor | Plastering, Painting
C005 | AquaSeal Tech | Waterproofing | Manoj Tiwari | Subcontractor | Waterproofing
C006 | Spark Electricals | Electrical | Tariq Anwar | Subcontractor | Electrical, Fire Alarm
C007 | FlowRight Plumbing | Plumbing | Vikram Reddy | Subcontractor | Plumbing, Sanitary
C008 | Elegance Floorings | Flooring | Neha Gupta | Subcontractor | Tiles, Marble
C009 | WoodCraft Doors | Carpentry | Sandeep Ghosh | Subcontractor | Doors, Windows

## Activities
Activity_ID | Project_ID | WBS_Code | Activity_Name | Category | Subcategory | Unit | Planned_Quantity | Unit_Rate_INR | Budget_Cost_INR | Duration_Days | Predecessor_ID | Contractor_ID | Planned_Start_Date | Planned_End_Date
A001 | P001 | 1.1 | Site Mobilization | Preliminaries | Mobilization | LS | 1 | 500000 | 500000 | 7 |  | C001 | 2025-01-01 | 2025-01-08
A002 | P001 | 1.2 | Site Clearance | Earthwork | Clearance | m2 | 2000 | 50 | 100000 | 5 | A001 | C001 | 2025-01-08 | 2025-01-13
A003 | P001 | 1.3 | Excavation | Earthwork | Excavation | m3 | 3500 | 150 | 525000 | 15 | A002 | C001 | 2025-01-13 | 2025-01-28
A004 | P001 | 1.4 | Foundation PCC | Foundation | PCC | m3 | 150 | 4500 | 675000 | 5 | A003 | C002 | 2025-01-28 | 2025-02-02
A005 | P001 | 1.5 | Footing RCC | Foundation | RCC works | m3 | 400 | 8500 | 3400000 | 14 | A004 | C002 | 2025-02-02 | 2025-02-16
A006 | P001 | 1.6 | Basement Waterproofing | Waterproofing | Foundation | m2 | 1200 | 300 | 360000 | 7 | A005 | C005 | 2025-02-16 | 2025-02-23
A007 | P001 | 1.7 | Earth Filling & Compaction | Earthwork | Filling | m3 | 1000 | 250 | 250000 | 10 | A006 | C001 | 2025-02-23 | 2025-03-05
A008 | P001 | 1.8 | Plinth Beam | Foundation | RCC works | m3 | 120 | 9000 | 1080000 | 10 | A007 | C002 | 2025-03-05 | 2025-03-15
A009 | P001 | 1.9 | Columns - Ground | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A008 | C002 | 2025-03-15 | 2025-03-22
A010 | P001 | 1.10 | Beams & Slab - Ground | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A009 | C002 | 2025-03-22 | 2025-04-01
A011 | P001 | 1.11 | Columns - Floor 1 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A010 | C002 | 2025-04-01 | 2025-04-08
A012 | P001 | 1.12 | Beams & Slab - Floor 1 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A011 | C002 | 2025-04-08 | 2025-04-18
A013 | P001 | 1.13 | Columns - Floor 2 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A012 | C002 | 2025-04-18 | 2025-04-25
A014 | P001 | 1.14 | Beams & Slab - Floor 2 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A013 | C002 | 2025-04-25 | 2025-05-05
A015 | P001 | 1.15 | Columns - Floor 3 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A014 | C002 | 2025-05-05 | 2025-05-12
A016 | P001 | 1.16 | Beams & Slab - Floor 3 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A015 | C002 | 2025-05-12 | 2025-05-22
A017 | P001 | 1.17 | Columns - Floor 4 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A016 | C002 | 2025-05-22 | 2025-05-29
A018 | P001 | 1.18 | Beams & Slab - Floor 4 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A017 | C002 | 2025-05-29 | 2025-06-08
A019 | P001 | 1.19 | Columns - Floor 5 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A018 | C002 | 2025-06-08 | 2025-06-15
A020 | P001 | 1.20 | Beams & Slab - Floor 5 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A019 | C002 | 2025-06-15 | 2025-06-25
A021 | P001 | 1.21 | Columns - Floor 6 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A020 | C002 | 2025-06-25 | 2025-07-02
A022 | P001 | 1.22 | Beams & Slab - Floor 6 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A021 | C002 | 2025-07-02 | 2025-07-12
A023 | P001 | 1.23 | Columns - Floor 7 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A022 | C002 | 2025-07-12 | 2025-07-19
A024 | P001 | 1.24 | Beams & Slab - Floor 7 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A023 | C002 | 2025-07-19 | 2025-07-29
A025 | P001 | 1.25 | Columns - Floor 8 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A024 | C002 | 2025-07-29 | 2025-08-05
A026 | P001 | 1.26 | Beams & Slab - Floor 8 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A025 | C002 | 2025-08-05 | 2025-08-15
A027 | P001 | 1.27 | Columns - Floor 9 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A026 | C002 | 2025-08-15 | 2025-08-22
A028 | P001 | 1.28 | Beams & Slab - Floor 9 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A027 | C002 | 2025-08-22 | 2025-09-01
A029 | P001 | 1.29 | Columns - Floor 10 | Structural works | Columns | m3 | 60 | 12000 | 720000 | 7 | A028 | C002 | 2025-09-01 | 2025-09-08
A030 | P001 | 1.30 | Beams & Slab - Floor 10 | Structural works | Slabs | m3 | 180 | 11000 | 1980000 | 10 | A029 | C002 | 2025-09-08 | 2025-09-18
A031 | P001 | 1.31 | External Brickwork (G-F3) | Masonry | External | m2 | 2000 | 850 | 1700000 | 30 | A016 | C003 | 2025-05-22 | 2025-06-21
A032 | P001 | 1.32 | External Brickwork (F4-F7) | Masonry | External | m2 | 2000 | 850 | 1700000 | 30 | A024 | C003 | 2025-07-29 | 2025-08-28
A033 | P001 | 1.33 | External Brickwork (F8-F10) | Masonry | External | m2 | 1500 | 850 | 1275000 | 20 | A030 | C003 | 2025-09-18 | 2025-10-08
A034 | P001 | 1.34 | Internal Plastering (G-F5) | Plastering | Internal | m2 | 4500 | 250 | 1125000 | 40 | A031 | C004 | 2025-06-21 | 2025-07-31
A035 | P001 | 1.35 | Internal Plastering (F6-F10) | Plastering | Internal | m2 | 4000 | 250 | 1000000 | 35 | A033 | C004 | 2025-10-08 | 2025-11-12
A036 | P001 | 1.36 | Electrical Rough-in | MEP | Electrical | m | 5000 | 120 | 600000 | 60 | A031 | C006 | 2025-06-21 | 2025-08-20
A037 | P001 | 1.37 | Plumbing Rough-in | MEP | Plumbing | m | 3000 | 200 | 600000 | 50 | A031 | C007 | 2025-06-21 | 2025-08-10
A038 | P001 | 1.38 | Floor Tiling (G-F5) | Flooring | Tiles | m2 | 3000 | 1200 | 3600000 | 30 | A034 | C008 | 2025-07-31 | 2025-08-30
A039 | P001 | 1.39 | Floor Tiling (F6-F10) | Flooring | Tiles | m2 | 3000 | 1200 | 3600000 | 30 | A035 | C008 | 2025-11-12 | 2025-12-12
A040 | P001 | 1.40 | Internal Painting | Painting | Internal | m2 | 8500 | 180 | 1530000 | 45 | A038 | C004 | 2025-08-30 | 2025-10-14
A041 | P001 | 1.41 | External Painting | Painting | External | m2 | 5500 | 220 | 1210000 | 30 | A035 | C004 | 2025-11-12 | 2025-12-12
A042 | P001 | 1.42 | Doors & Windows Installation | Doors and windows | Installation | Nos | 300 | 4500 | 1350000 | 40 | A034 | C009 | 2025-07-31 | 2025-09-09
A043 | P001 | 1.43 | MEP Fixtures & Testing | MEP | Electrical | LS | 1 | 1500000 | 1500000 | 20 | A040 | C006 | 2025-10-14 | 2025-11-03
A044 | P001 | 1.44 | Final Cleaning & Handover | Preliminaries | Cleaning | LS | 1 | 200000 | 200000 | 10 | A043 | C001 | 2025-11-03 | 2025-11-13

## Progress
Progress_ID | Project_ID | Activity_ID | Date | Planned_Quantity_To_Date | Actual_Quantity_To_Date | Planned_Percentage | Actual_Percentage | Quantity_Completed_This_Period | Status | Delay_Days
PRG0001 | P001 | A001 | 2025-01-03 | 0.29 | 0.24 | 2857% | 2351% | 0.24 | In Progress | 0
PRG0002 | P001 | A001 | 2025-01-10 | 1 | 1 | 10000% | 10000% | 0.76 | Completed | 0
PRG0003 | P001 | A001 | 2025-01-17 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0004 | P001 | A001 | 2025-01-24 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0005 | P001 | A001 | 2025-01-31 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0006 | P001 | A001 | 2025-02-07 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0007 | P001 | A001 | 2025-02-14 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0008 | P001 | A001 | 2025-02-21 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0009 | P001 | A001 | 2025-02-28 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0010 | P001 | A001 | 2025-03-07 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0011 | P001 | A001 | 2025-03-14 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0012 | P001 | A001 | 2025-03-21 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0013 | P001 | A001 | 2025-03-28 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0014 | P001 | A001 | 2025-04-04 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0015 | P001 | A001 | 2025-04-11 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0016 | P001 | A001 | 2025-04-18 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0017 | P001 | A001 | 2025-04-25 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0018 | P001 | A001 | 2025-05-02 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0019 | P001 | A001 | 2025-05-09 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0020 | P001 | A001 | 2025-05-16 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0021 | P001 | A001 | 2025-05-23 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0022 | P001 | A001 | 2025-05-30 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0023 | P001 | A001 | 2025-06-06 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0024 | P001 | A001 | 2025-06-13 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0025 | P001 | A001 | 2025-06-20 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0026 | P001 | A001 | 2025-06-27 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0027 | P001 | A001 | 2025-07-04 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0028 | P001 | A001 | 2025-07-11 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0029 | P001 | A001 | 2025-07-18 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0030 | P001 | A001 | 2025-07-25 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0031 | P001 | A001 | 2025-08-01 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0032 | P001 | A001 | 2025-08-08 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0033 | P001 | A001 | 2025-08-15 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0034 | P001 | A001 | 2025-08-22 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0035 | P001 | A001 | 2025-08-29 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0036 | P001 | A001 | 2025-09-05 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0037 | P001 | A001 | 2025-09-12 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0038 | P001 | A001 | 2025-09-19 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0039 | P001 | A001 | 2025-09-26 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0040 | P001 | A001 | 2025-10-03 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0041 | P001 | A001 | 2025-10-10 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0042 | P001 | A001 | 2025-10-17 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0043 | P001 | A001 | 2025-10-24 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0044 | P001 | A001 | 2025-10-31 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0045 | P001 | A001 | 2025-11-07 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0046 | P001 | A001 | 2025-11-14 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0047 | P001 | A001 | 2025-11-21 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0048 | P001 | A001 | 2025-11-28 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0049 | P001 | A001 | 2025-12-05 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0050 | P001 | A001 | 2025-12-12 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0051 | P001 | A001 | 2025-12-19 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0052 | P001 | A001 | 2025-12-26 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG0053 | P001 | A002 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0054 | P001 | A002 | 2025-01-10 | 800 | 732.78 | 4000% | 3664% | 732.78 | In Progress | 0
PRG0055 | P001 | A002 | 2025-01-17 | 2000 | 2000 | 10000% | 10000% | 1267.22 | Completed | 0
PRG0056 | P001 | A002 | 2025-01-24 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0057 | P001 | A002 | 2025-01-31 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0058 | P001 | A002 | 2025-02-07 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0059 | P001 | A002 | 2025-02-14 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0060 | P001 | A002 | 2025-02-21 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0061 | P001 | A002 | 2025-02-28 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0062 | P001 | A002 | 2025-03-07 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0063 | P001 | A002 | 2025-03-14 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0064 | P001 | A002 | 2025-03-21 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0065 | P001 | A002 | 2025-03-28 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0066 | P001 | A002 | 2025-04-04 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0067 | P001 | A002 | 2025-04-11 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0068 | P001 | A002 | 2025-04-18 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0069 | P001 | A002 | 2025-04-25 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0070 | P001 | A002 | 2025-05-02 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0071 | P001 | A002 | 2025-05-09 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0072 | P001 | A002 | 2025-05-16 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0073 | P001 | A002 | 2025-05-23 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0074 | P001 | A002 | 2025-05-30 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0075 | P001 | A002 | 2025-06-06 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0076 | P001 | A002 | 2025-06-13 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0077 | P001 | A002 | 2025-06-20 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0078 | P001 | A002 | 2025-06-27 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0079 | P001 | A002 | 2025-07-04 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0080 | P001 | A002 | 2025-07-11 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0081 | P001 | A002 | 2025-07-18 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0082 | P001 | A002 | 2025-07-25 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0083 | P001 | A002 | 2025-08-01 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0084 | P001 | A002 | 2025-08-08 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0085 | P001 | A002 | 2025-08-15 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0086 | P001 | A002 | 2025-08-22 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0087 | P001 | A002 | 2025-08-29 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0088 | P001 | A002 | 2025-09-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0089 | P001 | A002 | 2025-09-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0090 | P001 | A002 | 2025-09-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0091 | P001 | A002 | 2025-09-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0092 | P001 | A002 | 2025-10-03 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0093 | P001 | A002 | 2025-10-10 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0094 | P001 | A002 | 2025-10-17 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0095 | P001 | A002 | 2025-10-24 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0096 | P001 | A002 | 2025-10-31 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0097 | P001 | A002 | 2025-11-07 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0098 | P001 | A002 | 2025-11-14 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0099 | P001 | A002 | 2025-11-21 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0100 | P001 | A002 | 2025-11-28 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0101 | P001 | A002 | 2025-12-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0102 | P001 | A002 | 2025-12-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0103 | P001 | A002 | 2025-12-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0104 | P001 | A002 | 2025-12-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG0105 | P001 | A003 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0106 | P001 | A003 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0107 | P001 | A003 | 2025-01-17 | 933.33 | 0 | 2667% | 0% | 0 | Not Started | 4
PRG0108 | P001 | A003 | 2025-01-24 | 2566.67 | 618.82 | 7333% | 1768% | 618.82 | In Progress | 8
PRG0109 | P001 | A003 | 2025-01-31 | 3500 | 1916.83 | 10000% | 5477% | 1298.01 | In Progress | 6
PRG0110 | P001 | A003 | 2025-02-07 | 3500 | 2969.2 | 10000% | 8483% | 1052.37 | In Progress | 2
PRG0111 | P001 | A003 | 2025-02-14 | 3500 | 3500 | 10000% | 10000% | 530.8 | Completed | 0
PRG0112 | P001 | A003 | 2025-02-21 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0113 | P001 | A003 | 2025-02-28 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0114 | P001 | A003 | 2025-03-07 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0115 | P001 | A003 | 2025-03-14 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0116 | P001 | A003 | 2025-03-21 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0117 | P001 | A003 | 2025-03-28 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0118 | P001 | A003 | 2025-04-04 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0119 | P001 | A003 | 2025-04-11 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0120 | P001 | A003 | 2025-04-18 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0121 | P001 | A003 | 2025-04-25 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0122 | P001 | A003 | 2025-05-02 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0123 | P001 | A003 | 2025-05-09 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0124 | P001 | A003 | 2025-05-16 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0125 | P001 | A003 | 2025-05-23 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0126 | P001 | A003 | 2025-05-30 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0127 | P001 | A003 | 2025-06-06 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0128 | P001 | A003 | 2025-06-13 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0129 | P001 | A003 | 2025-06-20 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0130 | P001 | A003 | 2025-06-27 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0131 | P001 | A003 | 2025-07-04 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0132 | P001 | A003 | 2025-07-11 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0133 | P001 | A003 | 2025-07-18 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0134 | P001 | A003 | 2025-07-25 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0135 | P001 | A003 | 2025-08-01 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0136 | P001 | A003 | 2025-08-08 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0137 | P001 | A003 | 2025-08-15 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0138 | P001 | A003 | 2025-08-22 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0139 | P001 | A003 | 2025-08-29 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0140 | P001 | A003 | 2025-09-05 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0141 | P001 | A003 | 2025-09-12 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0142 | P001 | A003 | 2025-09-19 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0143 | P001 | A003 | 2025-09-26 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0144 | P001 | A003 | 2025-10-03 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0145 | P001 | A003 | 2025-10-10 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0146 | P001 | A003 | 2025-10-17 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0147 | P001 | A003 | 2025-10-24 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0148 | P001 | A003 | 2025-10-31 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0149 | P001 | A003 | 2025-11-07 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0150 | P001 | A003 | 2025-11-14 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0151 | P001 | A003 | 2025-11-21 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0152 | P001 | A003 | 2025-11-28 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0153 | P001 | A003 | 2025-12-05 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0154 | P001 | A003 | 2025-12-12 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0155 | P001 | A003 | 2025-12-19 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0156 | P001 | A003 | 2025-12-26 | 3500 | 3500 | 10000% | 10000% | 0 | Completed | 0
PRG0157 | P001 | A004 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0158 | P001 | A004 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0159 | P001 | A004 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0160 | P001 | A004 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0161 | P001 | A004 | 2025-01-31 | 90 | 86.47 | 6000% | 5765% | 86.47 | In Progress | 0
PRG0162 | P001 | A004 | 2025-02-07 | 150 | 150 | 10000% | 10000% | 63.53 | Completed | 0
PRG0163 | P001 | A004 | 2025-02-14 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0164 | P001 | A004 | 2025-02-21 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0165 | P001 | A004 | 2025-02-28 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0166 | P001 | A004 | 2025-03-07 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0167 | P001 | A004 | 2025-03-14 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0168 | P001 | A004 | 2025-03-21 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0169 | P001 | A004 | 2025-03-28 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0170 | P001 | A004 | 2025-04-04 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0171 | P001 | A004 | 2025-04-11 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0172 | P001 | A004 | 2025-04-18 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0173 | P001 | A004 | 2025-04-25 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0174 | P001 | A004 | 2025-05-02 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0175 | P001 | A004 | 2025-05-09 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0176 | P001 | A004 | 2025-05-16 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0177 | P001 | A004 | 2025-05-23 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0178 | P001 | A004 | 2025-05-30 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0179 | P001 | A004 | 2025-06-06 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0180 | P001 | A004 | 2025-06-13 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0181 | P001 | A004 | 2025-06-20 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0182 | P001 | A004 | 2025-06-27 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0183 | P001 | A004 | 2025-07-04 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0184 | P001 | A004 | 2025-07-11 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0185 | P001 | A004 | 2025-07-18 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0186 | P001 | A004 | 2025-07-25 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0187 | P001 | A004 | 2025-08-01 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0188 | P001 | A004 | 2025-08-08 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0189 | P001 | A004 | 2025-08-15 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0190 | P001 | A004 | 2025-08-22 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0191 | P001 | A004 | 2025-08-29 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0192 | P001 | A004 | 2025-09-05 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0193 | P001 | A004 | 2025-09-12 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0194 | P001 | A004 | 2025-09-19 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0195 | P001 | A004 | 2025-09-26 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0196 | P001 | A004 | 2025-10-03 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0197 | P001 | A004 | 2025-10-10 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0198 | P001 | A004 | 2025-10-17 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0199 | P001 | A004 | 2025-10-24 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0200 | P001 | A004 | 2025-10-31 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0201 | P001 | A004 | 2025-11-07 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0202 | P001 | A004 | 2025-11-14 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0203 | P001 | A004 | 2025-11-21 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0204 | P001 | A004 | 2025-11-28 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0205 | P001 | A004 | 2025-12-05 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0206 | P001 | A004 | 2025-12-12 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0207 | P001 | A004 | 2025-12-19 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0208 | P001 | A004 | 2025-12-26 | 150 | 150 | 10000% | 10000% | 0 | Completed | 0
PRG0209 | P001 | A005 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0210 | P001 | A005 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0211 | P001 | A005 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0212 | P001 | A005 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0213 | P001 | A005 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0214 | P001 | A005 | 2025-02-07 | 142.86 | 62.35 | 3571% | 1559% | 62.35 | In Progress | 2
PRG0215 | P001 | A005 | 2025-02-14 | 342.86 | 293.36 | 8571% | 7334% | 231 | In Progress | 1
PRG0216 | P001 | A005 | 2025-02-21 | 400 | 400 | 10000% | 10000% | 106.64 | Completed | 0
PRG0217 | P001 | A005 | 2025-02-28 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0218 | P001 | A005 | 2025-03-07 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0219 | P001 | A005 | 2025-03-14 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0220 | P001 | A005 | 2025-03-21 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0221 | P001 | A005 | 2025-03-28 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0222 | P001 | A005 | 2025-04-04 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0223 | P001 | A005 | 2025-04-11 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0224 | P001 | A005 | 2025-04-18 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0225 | P001 | A005 | 2025-04-25 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0226 | P001 | A005 | 2025-05-02 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0227 | P001 | A005 | 2025-05-09 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0228 | P001 | A005 | 2025-05-16 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0229 | P001 | A005 | 2025-05-23 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0230 | P001 | A005 | 2025-05-30 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0231 | P001 | A005 | 2025-06-06 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0232 | P001 | A005 | 2025-06-13 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0233 | P001 | A005 | 2025-06-20 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0234 | P001 | A005 | 2025-06-27 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0235 | P001 | A005 | 2025-07-04 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0236 | P001 | A005 | 2025-07-11 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0237 | P001 | A005 | 2025-07-18 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0238 | P001 | A005 | 2025-07-25 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0239 | P001 | A005 | 2025-08-01 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0240 | P001 | A005 | 2025-08-08 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0241 | P001 | A005 | 2025-08-15 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0242 | P001 | A005 | 2025-08-22 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0243 | P001 | A005 | 2025-08-29 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0244 | P001 | A005 | 2025-09-05 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0245 | P001 | A005 | 2025-09-12 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0246 | P001 | A005 | 2025-09-19 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0247 | P001 | A005 | 2025-09-26 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0248 | P001 | A005 | 2025-10-03 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0249 | P001 | A005 | 2025-10-10 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0250 | P001 | A005 | 2025-10-17 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0251 | P001 | A005 | 2025-10-24 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0252 | P001 | A005 | 2025-10-31 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0253 | P001 | A005 | 2025-11-07 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0254 | P001 | A005 | 2025-11-14 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0255 | P001 | A005 | 2025-11-21 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0256 | P001 | A005 | 2025-11-28 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0257 | P001 | A005 | 2025-12-05 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0258 | P001 | A005 | 2025-12-12 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0259 | P001 | A005 | 2025-12-19 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0260 | P001 | A005 | 2025-12-26 | 400 | 400 | 10000% | 10000% | 0 | Completed | 0
PRG0261 | P001 | A006 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0262 | P001 | A006 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0263 | P001 | A006 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0264 | P001 | A006 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0265 | P001 | A006 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0266 | P001 | A006 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0267 | P001 | A006 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0268 | P001 | A006 | 2025-02-21 | 857.14 | 748.49 | 7143% | 6237% | 748.49 | In Progress | 0
PRG0269 | P001 | A006 | 2025-02-28 | 1200 | 1200 | 10000% | 10000% | 451.51 | Completed | 0
PRG0270 | P001 | A006 | 2025-03-07 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0271 | P001 | A006 | 2025-03-14 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0272 | P001 | A006 | 2025-03-21 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0273 | P001 | A006 | 2025-03-28 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0274 | P001 | A006 | 2025-04-04 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0275 | P001 | A006 | 2025-04-11 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0276 | P001 | A006 | 2025-04-18 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0277 | P001 | A006 | 2025-04-25 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0278 | P001 | A006 | 2025-05-02 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0279 | P001 | A006 | 2025-05-09 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0280 | P001 | A006 | 2025-05-16 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0281 | P001 | A006 | 2025-05-23 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0282 | P001 | A006 | 2025-05-30 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0283 | P001 | A006 | 2025-06-06 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0284 | P001 | A006 | 2025-06-13 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0285 | P001 | A006 | 2025-06-20 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0286 | P001 | A006 | 2025-06-27 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0287 | P001 | A006 | 2025-07-04 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0288 | P001 | A006 | 2025-07-11 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0289 | P001 | A006 | 2025-07-18 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0290 | P001 | A006 | 2025-07-25 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0291 | P001 | A006 | 2025-08-01 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0292 | P001 | A006 | 2025-08-08 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0293 | P001 | A006 | 2025-08-15 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0294 | P001 | A006 | 2025-08-22 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0295 | P001 | A006 | 2025-08-29 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0296 | P001 | A006 | 2025-09-05 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0297 | P001 | A006 | 2025-09-12 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0298 | P001 | A006 | 2025-09-19 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0299 | P001 | A006 | 2025-09-26 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0300 | P001 | A006 | 2025-10-03 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0301 | P001 | A006 | 2025-10-10 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0302 | P001 | A006 | 2025-10-17 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0303 | P001 | A006 | 2025-10-24 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0304 | P001 | A006 | 2025-10-31 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0305 | P001 | A006 | 2025-11-07 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0306 | P001 | A006 | 2025-11-14 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0307 | P001 | A006 | 2025-11-21 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0308 | P001 | A006 | 2025-11-28 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0309 | P001 | A006 | 2025-12-05 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0310 | P001 | A006 | 2025-12-12 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0311 | P001 | A006 | 2025-12-19 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0312 | P001 | A006 | 2025-12-26 | 1200 | 1200 | 10000% | 10000% | 0 | Completed | 0
PRG0313 | P001 | A007 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0314 | P001 | A007 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0315 | P001 | A007 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0316 | P001 | A007 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0317 | P001 | A007 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0318 | P001 | A007 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0319 | P001 | A007 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0320 | P001 | A007 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0321 | P001 | A007 | 2025-02-28 | 500 | 96.07 | 5000% | 961% | 96.07 | In Progress | 4
PRG0322 | P001 | A007 | 2025-03-07 | 1000 | 519.64 | 10000% | 5196% | 423.57 | In Progress | 4
PRG0323 | P001 | A007 | 2025-03-14 | 1000 | 867.6 | 10000% | 8676% | 347.96 | In Progress | 1
PRG0324 | P001 | A007 | 2025-03-21 | 1000 | 1000 | 10000% | 10000% | 132.4 | Completed | 0
PRG0325 | P001 | A007 | 2025-03-28 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0326 | P001 | A007 | 2025-04-04 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0327 | P001 | A007 | 2025-04-11 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0328 | P001 | A007 | 2025-04-18 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0329 | P001 | A007 | 2025-04-25 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0330 | P001 | A007 | 2025-05-02 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0331 | P001 | A007 | 2025-05-09 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0332 | P001 | A007 | 2025-05-16 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0333 | P001 | A007 | 2025-05-23 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0334 | P001 | A007 | 2025-05-30 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0335 | P001 | A007 | 2025-06-06 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0336 | P001 | A007 | 2025-06-13 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0337 | P001 | A007 | 2025-06-20 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0338 | P001 | A007 | 2025-06-27 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0339 | P001 | A007 | 2025-07-04 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0340 | P001 | A007 | 2025-07-11 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0341 | P001 | A007 | 2025-07-18 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0342 | P001 | A007 | 2025-07-25 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0343 | P001 | A007 | 2025-08-01 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0344 | P001 | A007 | 2025-08-08 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0345 | P001 | A007 | 2025-08-15 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0346 | P001 | A007 | 2025-08-22 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0347 | P001 | A007 | 2025-08-29 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0348 | P001 | A007 | 2025-09-05 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0349 | P001 | A007 | 2025-09-12 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0350 | P001 | A007 | 2025-09-19 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0351 | P001 | A007 | 2025-09-26 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0352 | P001 | A007 | 2025-10-03 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0353 | P001 | A007 | 2025-10-10 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0354 | P001 | A007 | 2025-10-17 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0355 | P001 | A007 | 2025-10-24 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0356 | P001 | A007 | 2025-10-31 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0357 | P001 | A007 | 2025-11-07 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0358 | P001 | A007 | 2025-11-14 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0359 | P001 | A007 | 2025-11-21 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0360 | P001 | A007 | 2025-11-28 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0361 | P001 | A007 | 2025-12-05 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0362 | P001 | A007 | 2025-12-12 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0363 | P001 | A007 | 2025-12-19 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0364 | P001 | A007 | 2025-12-26 | 1000 | 1000 | 10000% | 10000% | 0 | Completed | 0
PRG0365 | P001 | A008 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0366 | P001 | A008 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0367 | P001 | A008 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0368 | P001 | A008 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0369 | P001 | A008 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0370 | P001 | A008 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0371 | P001 | A008 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0372 | P001 | A008 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0373 | P001 | A008 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0374 | P001 | A008 | 2025-03-07 | 24 | 0 | 2000% | 0% | 0 | Not Started | 2
PRG0375 | P001 | A008 | 2025-03-14 | 108 | 93.57 | 9000% | 7798% | 93.57 | In Progress | 1
PRG0376 | P001 | A008 | 2025-03-21 | 120 | 120 | 10000% | 10000% | 26.43 | Completed | 0
PRG0377 | P001 | A008 | 2025-03-28 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0378 | P001 | A008 | 2025-04-04 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0379 | P001 | A008 | 2025-04-11 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0380 | P001 | A008 | 2025-04-18 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0381 | P001 | A008 | 2025-04-25 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0382 | P001 | A008 | 2025-05-02 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0383 | P001 | A008 | 2025-05-09 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0384 | P001 | A008 | 2025-05-16 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0385 | P001 | A008 | 2025-05-23 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0386 | P001 | A008 | 2025-05-30 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0387 | P001 | A008 | 2025-06-06 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0388 | P001 | A008 | 2025-06-13 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0389 | P001 | A008 | 2025-06-20 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0390 | P001 | A008 | 2025-06-27 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0391 | P001 | A008 | 2025-07-04 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0392 | P001 | A008 | 2025-07-11 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0393 | P001 | A008 | 2025-07-18 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0394 | P001 | A008 | 2025-07-25 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0395 | P001 | A008 | 2025-08-01 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0396 | P001 | A008 | 2025-08-08 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0397 | P001 | A008 | 2025-08-15 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0398 | P001 | A008 | 2025-08-22 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0399 | P001 | A008 | 2025-08-29 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0400 | P001 | A008 | 2025-09-05 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0401 | P001 | A008 | 2025-09-12 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0402 | P001 | A008 | 2025-09-19 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0403 | P001 | A008 | 2025-09-26 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0404 | P001 | A008 | 2025-10-03 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0405 | P001 | A008 | 2025-10-10 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0406 | P001 | A008 | 2025-10-17 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0407 | P001 | A008 | 2025-10-24 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0408 | P001 | A008 | 2025-10-31 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0409 | P001 | A008 | 2025-11-07 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0410 | P001 | A008 | 2025-11-14 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0411 | P001 | A008 | 2025-11-21 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0412 | P001 | A008 | 2025-11-28 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0413 | P001 | A008 | 2025-12-05 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0414 | P001 | A008 | 2025-12-12 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0415 | P001 | A008 | 2025-12-19 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0416 | P001 | A008 | 2025-12-26 | 120 | 120 | 10000% | 10000% | 0 | Completed | 0
PRG0417 | P001 | A009 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0418 | P001 | A009 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0419 | P001 | A009 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0420 | P001 | A009 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0421 | P001 | A009 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0422 | P001 | A009 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0423 | P001 | A009 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0424 | P001 | A009 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0425 | P001 | A009 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0426 | P001 | A009 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0427 | P001 | A009 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0428 | P001 | A009 | 2025-03-21 | 51.43 | 51.26 | 8571% | 8543% | 51.26 | In Progress | 0
PRG0429 | P001 | A009 | 2025-03-28 | 60 | 60 | 10000% | 10000% | 8.74 | Completed | 0
PRG0430 | P001 | A009 | 2025-04-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0431 | P001 | A009 | 2025-04-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0432 | P001 | A009 | 2025-04-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0433 | P001 | A009 | 2025-04-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0434 | P001 | A009 | 2025-05-02 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0435 | P001 | A009 | 2025-05-09 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0436 | P001 | A009 | 2025-05-16 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0437 | P001 | A009 | 2025-05-23 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0438 | P001 | A009 | 2025-05-30 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0439 | P001 | A009 | 2025-06-06 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0440 | P001 | A009 | 2025-06-13 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0441 | P001 | A009 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0442 | P001 | A009 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0443 | P001 | A009 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0444 | P001 | A009 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0445 | P001 | A009 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0446 | P001 | A009 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0447 | P001 | A009 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0448 | P001 | A009 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0449 | P001 | A009 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0450 | P001 | A009 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0451 | P001 | A009 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0452 | P001 | A009 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0453 | P001 | A009 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0454 | P001 | A009 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0455 | P001 | A009 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0456 | P001 | A009 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0457 | P001 | A009 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0458 | P001 | A009 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0459 | P001 | A009 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0460 | P001 | A009 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0461 | P001 | A009 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0462 | P001 | A009 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0463 | P001 | A009 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0464 | P001 | A009 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0465 | P001 | A009 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0466 | P001 | A009 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0467 | P001 | A009 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0468 | P001 | A009 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0469 | P001 | A010 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0470 | P001 | A010 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0471 | P001 | A010 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0472 | P001 | A010 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0473 | P001 | A010 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0474 | P001 | A010 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0475 | P001 | A010 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0476 | P001 | A010 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0477 | P001 | A010 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0478 | P001 | A010 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0479 | P001 | A010 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0480 | P001 | A010 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0481 | P001 | A010 | 2025-03-28 | 108 | 43.33 | 6000% | 2407% | 43.33 | In Progress | 3
PRG0482 | P001 | A010 | 2025-04-04 | 180 | 180 | 10000% | 10000% | 136.67 | Completed | 0
PRG0483 | P001 | A010 | 2025-04-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0484 | P001 | A010 | 2025-04-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0485 | P001 | A010 | 2025-04-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0486 | P001 | A010 | 2025-05-02 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0487 | P001 | A010 | 2025-05-09 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0488 | P001 | A010 | 2025-05-16 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0489 | P001 | A010 | 2025-05-23 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0490 | P001 | A010 | 2025-05-30 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0491 | P001 | A010 | 2025-06-06 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0492 | P001 | A010 | 2025-06-13 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0493 | P001 | A010 | 2025-06-20 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0494 | P001 | A010 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0495 | P001 | A010 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0496 | P001 | A010 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0497 | P001 | A010 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0498 | P001 | A010 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0499 | P001 | A010 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0500 | P001 | A010 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0501 | P001 | A010 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0502 | P001 | A010 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0503 | P001 | A010 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0504 | P001 | A010 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0505 | P001 | A010 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0506 | P001 | A010 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0507 | P001 | A010 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0508 | P001 | A010 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0509 | P001 | A010 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0510 | P001 | A010 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0511 | P001 | A010 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0512 | P001 | A010 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0513 | P001 | A010 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0514 | P001 | A010 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0515 | P001 | A010 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0516 | P001 | A010 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0517 | P001 | A010 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0518 | P001 | A010 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0519 | P001 | A010 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0520 | P001 | A010 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0521 | P001 | A011 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0522 | P001 | A011 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0523 | P001 | A011 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0524 | P001 | A011 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0525 | P001 | A011 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0526 | P001 | A011 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0527 | P001 | A011 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0528 | P001 | A011 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0529 | P001 | A011 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0530 | P001 | A011 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0531 | P001 | A011 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0532 | P001 | A011 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0533 | P001 | A011 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0534 | P001 | A011 | 2025-04-04 | 25.71 | 24.39 | 4286% | 4065% | 24.39 | In Progress | 0
PRG0535 | P001 | A011 | 2025-04-11 | 60 | 60 | 10000% | 10000% | 35.61 | Completed | 0
PRG0536 | P001 | A011 | 2025-04-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0537 | P001 | A011 | 2025-04-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0538 | P001 | A011 | 2025-05-02 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0539 | P001 | A011 | 2025-05-09 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0540 | P001 | A011 | 2025-05-16 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0541 | P001 | A011 | 2025-05-23 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0542 | P001 | A011 | 2025-05-30 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0543 | P001 | A011 | 2025-06-06 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0544 | P001 | A011 | 2025-06-13 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0545 | P001 | A011 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0546 | P001 | A011 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0547 | P001 | A011 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0548 | P001 | A011 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0549 | P001 | A011 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0550 | P001 | A011 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0551 | P001 | A011 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0552 | P001 | A011 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0553 | P001 | A011 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0554 | P001 | A011 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0555 | P001 | A011 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0556 | P001 | A011 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0557 | P001 | A011 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0558 | P001 | A011 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0559 | P001 | A011 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0560 | P001 | A011 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0561 | P001 | A011 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0562 | P001 | A011 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0563 | P001 | A011 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0564 | P001 | A011 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0565 | P001 | A011 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0566 | P001 | A011 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0567 | P001 | A011 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0568 | P001 | A011 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0569 | P001 | A011 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0570 | P001 | A011 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0571 | P001 | A011 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0572 | P001 | A011 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0573 | P001 | A012 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0574 | P001 | A012 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0575 | P001 | A012 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0576 | P001 | A012 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0577 | P001 | A012 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0578 | P001 | A012 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0579 | P001 | A012 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0580 | P001 | A012 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0581 | P001 | A012 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0582 | P001 | A012 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0583 | P001 | A012 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0584 | P001 | A012 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0585 | P001 | A012 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0586 | P001 | A012 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0587 | P001 | A012 | 2025-04-11 | 54 | 24.35 | 3000% | 1353% | 24.35 | In Progress | 1
PRG0588 | P001 | A012 | 2025-04-18 | 180 | 180 | 10000% | 10000% | 155.65 | Completed | 0
PRG0589 | P001 | A012 | 2025-04-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0590 | P001 | A012 | 2025-05-02 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0591 | P001 | A012 | 2025-05-09 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0592 | P001 | A012 | 2025-05-16 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0593 | P001 | A012 | 2025-05-23 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0594 | P001 | A012 | 2025-05-30 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0595 | P001 | A012 | 2025-06-06 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0596 | P001 | A012 | 2025-06-13 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0597 | P001 | A012 | 2025-06-20 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0598 | P001 | A012 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0599 | P001 | A012 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0600 | P001 | A012 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0601 | P001 | A012 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0602 | P001 | A012 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0603 | P001 | A012 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0604 | P001 | A012 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0605 | P001 | A012 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0606 | P001 | A012 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0607 | P001 | A012 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0608 | P001 | A012 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0609 | P001 | A012 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0610 | P001 | A012 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0611 | P001 | A012 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0612 | P001 | A012 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0613 | P001 | A012 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0614 | P001 | A012 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0615 | P001 | A012 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0616 | P001 | A012 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0617 | P001 | A012 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0618 | P001 | A012 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0619 | P001 | A012 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0620 | P001 | A012 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0621 | P001 | A012 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0622 | P001 | A012 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0623 | P001 | A012 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0624 | P001 | A012 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0625 | P001 | A013 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0626 | P001 | A013 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0627 | P001 | A013 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0628 | P001 | A013 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0629 | P001 | A013 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0630 | P001 | A013 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0631 | P001 | A013 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0632 | P001 | A013 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0633 | P001 | A013 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0634 | P001 | A013 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0635 | P001 | A013 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0636 | P001 | A013 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0637 | P001 | A013 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0638 | P001 | A013 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0639 | P001 | A013 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0640 | P001 | A013 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0641 | P001 | A013 | 2025-04-25 | 60 | 10.09 | 10000% | 1681% | 10.09 | In Progress | 5
PRG0642 | P001 | A013 | 2025-05-02 | 60 | 25.02 | 10000% | 4171% | 14.94 | In Progress | 4
PRG0643 | P001 | A013 | 2025-05-09 | 60 | 39.69 | 10000% | 6614% | 14.66 | In Progress | 2
PRG0644 | P001 | A013 | 2025-05-16 | 60 | 60 | 10000% | 10000% | 20.31 | Completed | 0
PRG0645 | P001 | A013 | 2025-05-23 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0646 | P001 | A013 | 2025-05-30 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0647 | P001 | A013 | 2025-06-06 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0648 | P001 | A013 | 2025-06-13 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0649 | P001 | A013 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0650 | P001 | A013 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0651 | P001 | A013 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0652 | P001 | A013 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0653 | P001 | A013 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0654 | P001 | A013 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0655 | P001 | A013 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0656 | P001 | A013 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0657 | P001 | A013 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0658 | P001 | A013 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0659 | P001 | A013 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0660 | P001 | A013 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0661 | P001 | A013 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0662 | P001 | A013 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0663 | P001 | A013 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0664 | P001 | A013 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0665 | P001 | A013 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0666 | P001 | A013 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0667 | P001 | A013 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0668 | P001 | A013 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0669 | P001 | A013 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0670 | P001 | A013 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0671 | P001 | A013 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0672 | P001 | A013 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0673 | P001 | A013 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0674 | P001 | A013 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0675 | P001 | A013 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0676 | P001 | A013 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0677 | P001 | A014 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0678 | P001 | A014 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0679 | P001 | A014 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0680 | P001 | A014 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0681 | P001 | A014 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0682 | P001 | A014 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0683 | P001 | A014 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0684 | P001 | A014 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0685 | P001 | A014 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0686 | P001 | A014 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0687 | P001 | A014 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0688 | P001 | A014 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0689 | P001 | A014 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0690 | P001 | A014 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0691 | P001 | A014 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0692 | P001 | A014 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0693 | P001 | A014 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0694 | P001 | A014 | 2025-05-02 | 126 | 121.92 | 7000% | 6774% | 121.92 | In Progress | 0
PRG0695 | P001 | A014 | 2025-05-09 | 180 | 180 | 10000% | 10000% | 58.08 | Completed | 0
PRG0696 | P001 | A014 | 2025-05-16 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0697 | P001 | A014 | 2025-05-23 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0698 | P001 | A014 | 2025-05-30 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0699 | P001 | A014 | 2025-06-06 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0700 | P001 | A014 | 2025-06-13 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0701 | P001 | A014 | 2025-06-20 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0702 | P001 | A014 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0703 | P001 | A014 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0704 | P001 | A014 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0705 | P001 | A014 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0706 | P001 | A014 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0707 | P001 | A014 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0708 | P001 | A014 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0709 | P001 | A014 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0710 | P001 | A014 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0711 | P001 | A014 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0712 | P001 | A014 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0713 | P001 | A014 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0714 | P001 | A014 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0715 | P001 | A014 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0716 | P001 | A014 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0717 | P001 | A014 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0718 | P001 | A014 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0719 | P001 | A014 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0720 | P001 | A014 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0721 | P001 | A014 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0722 | P001 | A014 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0723 | P001 | A014 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0724 | P001 | A014 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0725 | P001 | A014 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0726 | P001 | A014 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0727 | P001 | A014 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0728 | P001 | A014 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0729 | P001 | A015 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0730 | P001 | A015 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0731 | P001 | A015 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0732 | P001 | A015 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0733 | P001 | A015 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0734 | P001 | A015 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0735 | P001 | A015 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0736 | P001 | A015 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0737 | P001 | A015 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0738 | P001 | A015 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0739 | P001 | A015 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0740 | P001 | A015 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0741 | P001 | A015 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0742 | P001 | A015 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0743 | P001 | A015 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0744 | P001 | A015 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0745 | P001 | A015 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0746 | P001 | A015 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0747 | P001 | A015 | 2025-05-09 | 34.29 | 13.58 | 5714% | 2264% | 13.58 | In Progress | 2
PRG0748 | P001 | A015 | 2025-05-16 | 60 | 60 | 10000% | 10000% | 46.42 | Completed | 0
PRG0749 | P001 | A015 | 2025-05-23 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0750 | P001 | A015 | 2025-05-30 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0751 | P001 | A015 | 2025-06-06 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0752 | P001 | A015 | 2025-06-13 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0753 | P001 | A015 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0754 | P001 | A015 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0755 | P001 | A015 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0756 | P001 | A015 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0757 | P001 | A015 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0758 | P001 | A015 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0759 | P001 | A015 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0760 | P001 | A015 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0761 | P001 | A015 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0762 | P001 | A015 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0763 | P001 | A015 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0764 | P001 | A015 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0765 | P001 | A015 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0766 | P001 | A015 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0767 | P001 | A015 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0768 | P001 | A015 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0769 | P001 | A015 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0770 | P001 | A015 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0771 | P001 | A015 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0772 | P001 | A015 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0773 | P001 | A015 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0774 | P001 | A015 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0775 | P001 | A015 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0776 | P001 | A015 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0777 | P001 | A015 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0778 | P001 | A015 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0779 | P001 | A015 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0780 | P001 | A015 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0781 | P001 | A016 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0782 | P001 | A016 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0783 | P001 | A016 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0784 | P001 | A016 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0785 | P001 | A016 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0786 | P001 | A016 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0787 | P001 | A016 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0788 | P001 | A016 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0789 | P001 | A016 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0790 | P001 | A016 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0791 | P001 | A016 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0792 | P001 | A016 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0793 | P001 | A016 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0794 | P001 | A016 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0795 | P001 | A016 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0796 | P001 | A016 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0797 | P001 | A016 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0798 | P001 | A016 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0799 | P001 | A016 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0800 | P001 | A016 | 2025-05-16 | 72 | 63.66 | 4000% | 3536% | 63.66 | In Progress | 0
PRG0801 | P001 | A016 | 2025-05-23 | 180 | 180 | 10000% | 10000% | 116.34 | Completed | 0
PRG0802 | P001 | A016 | 2025-05-30 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0803 | P001 | A016 | 2025-06-06 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0804 | P001 | A016 | 2025-06-13 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0805 | P001 | A016 | 2025-06-20 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0806 | P001 | A016 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0807 | P001 | A016 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0808 | P001 | A016 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0809 | P001 | A016 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0810 | P001 | A016 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0811 | P001 | A016 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0812 | P001 | A016 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0813 | P001 | A016 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0814 | P001 | A016 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0815 | P001 | A016 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0816 | P001 | A016 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0817 | P001 | A016 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0818 | P001 | A016 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0819 | P001 | A016 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0820 | P001 | A016 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0821 | P001 | A016 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0822 | P001 | A016 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0823 | P001 | A016 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0824 | P001 | A016 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0825 | P001 | A016 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0826 | P001 | A016 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0827 | P001 | A016 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0828 | P001 | A016 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0829 | P001 | A016 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0830 | P001 | A016 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0831 | P001 | A016 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0832 | P001 | A016 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0833 | P001 | A017 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0834 | P001 | A017 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0835 | P001 | A017 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0836 | P001 | A017 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0837 | P001 | A017 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0838 | P001 | A017 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0839 | P001 | A017 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0840 | P001 | A017 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0841 | P001 | A017 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0842 | P001 | A017 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0843 | P001 | A017 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0844 | P001 | A017 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0845 | P001 | A017 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0846 | P001 | A017 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0847 | P001 | A017 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0848 | P001 | A017 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0849 | P001 | A017 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0850 | P001 | A017 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0851 | P001 | A017 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0852 | P001 | A017 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0853 | P001 | A017 | 2025-05-23 | 8.57 | 4.01 | 1429% | 668% | 4.01 | In Progress | 0
PRG0854 | P001 | A017 | 2025-05-30 | 60 | 60 | 10000% | 10000% | 55.99 | Completed | 0
PRG0855 | P001 | A017 | 2025-06-06 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0856 | P001 | A017 | 2025-06-13 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0857 | P001 | A017 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0858 | P001 | A017 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0859 | P001 | A017 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0860 | P001 | A017 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0861 | P001 | A017 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0862 | P001 | A017 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0863 | P001 | A017 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0864 | P001 | A017 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0865 | P001 | A017 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0866 | P001 | A017 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0867 | P001 | A017 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0868 | P001 | A017 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0869 | P001 | A017 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0870 | P001 | A017 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0871 | P001 | A017 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0872 | P001 | A017 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0873 | P001 | A017 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0874 | P001 | A017 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0875 | P001 | A017 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0876 | P001 | A017 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0877 | P001 | A017 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0878 | P001 | A017 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0879 | P001 | A017 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0880 | P001 | A017 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0881 | P001 | A017 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0882 | P001 | A017 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0883 | P001 | A017 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0884 | P001 | A017 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0885 | P001 | A018 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0886 | P001 | A018 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0887 | P001 | A018 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0888 | P001 | A018 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0889 | P001 | A018 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0890 | P001 | A018 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0891 | P001 | A018 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0892 | P001 | A018 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0893 | P001 | A018 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0894 | P001 | A018 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0895 | P001 | A018 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0896 | P001 | A018 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0897 | P001 | A018 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0898 | P001 | A018 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0899 | P001 | A018 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0900 | P001 | A018 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0901 | P001 | A018 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0902 | P001 | A018 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0903 | P001 | A018 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0904 | P001 | A018 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0905 | P001 | A018 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0906 | P001 | A018 | 2025-05-30 | 18 | 0 | 1000% | 0% | 0 | Not Started | 1
PRG0907 | P001 | A018 | 2025-06-06 | 144 | 63.67 | 8000% | 3537% | 63.67 | In Progress | 4
PRG0908 | P001 | A018 | 2025-06-13 | 180 | 180 | 10000% | 10000% | 116.33 | Completed | 0
PRG0909 | P001 | A018 | 2025-06-20 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0910 | P001 | A018 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0911 | P001 | A018 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0912 | P001 | A018 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0913 | P001 | A018 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0914 | P001 | A018 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0915 | P001 | A018 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0916 | P001 | A018 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0917 | P001 | A018 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0918 | P001 | A018 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0919 | P001 | A018 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0920 | P001 | A018 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0921 | P001 | A018 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0922 | P001 | A018 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0923 | P001 | A018 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0924 | P001 | A018 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0925 | P001 | A018 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0926 | P001 | A018 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0927 | P001 | A018 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0928 | P001 | A018 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0929 | P001 | A018 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0930 | P001 | A018 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0931 | P001 | A018 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0932 | P001 | A018 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0933 | P001 | A018 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0934 | P001 | A018 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0935 | P001 | A018 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0936 | P001 | A018 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG0937 | P001 | A019 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0938 | P001 | A019 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0939 | P001 | A019 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0940 | P001 | A019 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0941 | P001 | A019 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0942 | P001 | A019 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0943 | P001 | A019 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0944 | P001 | A019 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0945 | P001 | A019 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0946 | P001 | A019 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0947 | P001 | A019 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0948 | P001 | A019 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0949 | P001 | A019 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0950 | P001 | A019 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0951 | P001 | A019 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0952 | P001 | A019 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0953 | P001 | A019 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0954 | P001 | A019 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0955 | P001 | A019 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0956 | P001 | A019 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0957 | P001 | A019 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0958 | P001 | A019 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0959 | P001 | A019 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0960 | P001 | A019 | 2025-06-13 | 42.86 | 18.05 | 7143% | 3009% | 18.05 | In Progress | 2
PRG0961 | P001 | A019 | 2025-06-20 | 60 | 60 | 10000% | 10000% | 41.95 | Completed | 0
PRG0962 | P001 | A019 | 2025-06-27 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0963 | P001 | A019 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0964 | P001 | A019 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0965 | P001 | A019 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0966 | P001 | A019 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0967 | P001 | A019 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0968 | P001 | A019 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0969 | P001 | A019 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0970 | P001 | A019 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0971 | P001 | A019 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0972 | P001 | A019 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0973 | P001 | A019 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0974 | P001 | A019 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0975 | P001 | A019 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0976 | P001 | A019 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0977 | P001 | A019 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0978 | P001 | A019 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0979 | P001 | A019 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0980 | P001 | A019 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0981 | P001 | A019 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0982 | P001 | A019 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0983 | P001 | A019 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0984 | P001 | A019 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0985 | P001 | A019 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0986 | P001 | A019 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0987 | P001 | A019 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0988 | P001 | A019 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG0989 | P001 | A020 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0990 | P001 | A020 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0991 | P001 | A020 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0992 | P001 | A020 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0993 | P001 | A020 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0994 | P001 | A020 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0995 | P001 | A020 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0996 | P001 | A020 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0997 | P001 | A020 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0998 | P001 | A020 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG0999 | P001 | A020 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1000 | P001 | A020 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1001 | P001 | A020 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1002 | P001 | A020 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1003 | P001 | A020 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1004 | P001 | A020 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1005 | P001 | A020 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1006 | P001 | A020 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1007 | P001 | A020 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1008 | P001 | A020 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1009 | P001 | A020 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1010 | P001 | A020 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1011 | P001 | A020 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1012 | P001 | A020 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1013 | P001 | A020 | 2025-06-20 | 90 | 23.26 | 5000% | 1292% | 23.26 | In Progress | 3
PRG1014 | P001 | A020 | 2025-06-27 | 180 | 180 | 10000% | 10000% | 156.74 | Completed | 0
PRG1015 | P001 | A020 | 2025-07-04 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1016 | P001 | A020 | 2025-07-11 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1017 | P001 | A020 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1018 | P001 | A020 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1019 | P001 | A020 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1020 | P001 | A020 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1021 | P001 | A020 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1022 | P001 | A020 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1023 | P001 | A020 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1024 | P001 | A020 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1025 | P001 | A020 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1026 | P001 | A020 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1027 | P001 | A020 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1028 | P001 | A020 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1029 | P001 | A020 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1030 | P001 | A020 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1031 | P001 | A020 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1032 | P001 | A020 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1033 | P001 | A020 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1034 | P001 | A020 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1035 | P001 | A020 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1036 | P001 | A020 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1037 | P001 | A020 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1038 | P001 | A020 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1039 | P001 | A020 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1040 | P001 | A020 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1041 | P001 | A021 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1042 | P001 | A021 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1043 | P001 | A021 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1044 | P001 | A021 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1045 | P001 | A021 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1046 | P001 | A021 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1047 | P001 | A021 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1048 | P001 | A021 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1049 | P001 | A021 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1050 | P001 | A021 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1051 | P001 | A021 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1052 | P001 | A021 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1053 | P001 | A021 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1054 | P001 | A021 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1055 | P001 | A021 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1056 | P001 | A021 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1057 | P001 | A021 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1058 | P001 | A021 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1059 | P001 | A021 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1060 | P001 | A021 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1061 | P001 | A021 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1062 | P001 | A021 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1063 | P001 | A021 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1064 | P001 | A021 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1065 | P001 | A021 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1066 | P001 | A021 | 2025-06-27 | 17.14 | 7.42 | 2857% | 1237% | 7.42 | In Progress | 1
PRG1067 | P001 | A021 | 2025-07-04 | 60 | 60 | 10000% | 10000% | 52.58 | Completed | 0
PRG1068 | P001 | A021 | 2025-07-11 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1069 | P001 | A021 | 2025-07-18 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1070 | P001 | A021 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1071 | P001 | A021 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1072 | P001 | A021 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1073 | P001 | A021 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1074 | P001 | A021 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1075 | P001 | A021 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1076 | P001 | A021 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1077 | P001 | A021 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1078 | P001 | A021 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1079 | P001 | A021 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1080 | P001 | A021 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1081 | P001 | A021 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1082 | P001 | A021 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1083 | P001 | A021 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1084 | P001 | A021 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1085 | P001 | A021 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1086 | P001 | A021 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1087 | P001 | A021 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1088 | P001 | A021 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1089 | P001 | A021 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1090 | P001 | A021 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1091 | P001 | A021 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1092 | P001 | A021 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1093 | P001 | A022 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1094 | P001 | A022 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1095 | P001 | A022 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1096 | P001 | A022 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1097 | P001 | A022 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1098 | P001 | A022 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1099 | P001 | A022 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1100 | P001 | A022 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1101 | P001 | A022 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1102 | P001 | A022 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1103 | P001 | A022 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1104 | P001 | A022 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1105 | P001 | A022 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1106 | P001 | A022 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1107 | P001 | A022 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1108 | P001 | A022 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1109 | P001 | A022 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1110 | P001 | A022 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1111 | P001 | A022 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1112 | P001 | A022 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1113 | P001 | A022 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1114 | P001 | A022 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1115 | P001 | A022 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1116 | P001 | A022 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1117 | P001 | A022 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1118 | P001 | A022 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1119 | P001 | A022 | 2025-07-04 | 36 | 0 | 2000% | 0% | 0 | Not Started | 2
PRG1120 | P001 | A022 | 2025-07-11 | 162 | 67.93 | 9000% | 3774% | 67.93 | In Progress | 5
PRG1121 | P001 | A022 | 2025-07-18 | 180 | 180 | 10000% | 10000% | 112.07 | Completed | 0
PRG1122 | P001 | A022 | 2025-07-25 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1123 | P001 | A022 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1124 | P001 | A022 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1125 | P001 | A022 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1126 | P001 | A022 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1127 | P001 | A022 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1128 | P001 | A022 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1129 | P001 | A022 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1130 | P001 | A022 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1131 | P001 | A022 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1132 | P001 | A022 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1133 | P001 | A022 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1134 | P001 | A022 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1135 | P001 | A022 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1136 | P001 | A022 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1137 | P001 | A022 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1138 | P001 | A022 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1139 | P001 | A022 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1140 | P001 | A022 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1141 | P001 | A022 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1142 | P001 | A022 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1143 | P001 | A022 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1144 | P001 | A022 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1145 | P001 | A023 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1146 | P001 | A023 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1147 | P001 | A023 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1148 | P001 | A023 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1149 | P001 | A023 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1150 | P001 | A023 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1151 | P001 | A023 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1152 | P001 | A023 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1153 | P001 | A023 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1154 | P001 | A023 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1155 | P001 | A023 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1156 | P001 | A023 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1157 | P001 | A023 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1158 | P001 | A023 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1159 | P001 | A023 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1160 | P001 | A023 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1161 | P001 | A023 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1162 | P001 | A023 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1163 | P001 | A023 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1164 | P001 | A023 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1165 | P001 | A023 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1166 | P001 | A023 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1167 | P001 | A023 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1168 | P001 | A023 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1169 | P001 | A023 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1170 | P001 | A023 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1171 | P001 | A023 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1172 | P001 | A023 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1173 | P001 | A023 | 2025-07-18 | 51.43 | 46.2 | 8571% | 7699% | 46.2 | In Progress | 0
PRG1174 | P001 | A023 | 2025-07-25 | 60 | 60 | 10000% | 10000% | 13.8 | Completed | 0
PRG1175 | P001 | A023 | 2025-08-01 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1176 | P001 | A023 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1177 | P001 | A023 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1178 | P001 | A023 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1179 | P001 | A023 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1180 | P001 | A023 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1181 | P001 | A023 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1182 | P001 | A023 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1183 | P001 | A023 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1184 | P001 | A023 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1185 | P001 | A023 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1186 | P001 | A023 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1187 | P001 | A023 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1188 | P001 | A023 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1189 | P001 | A023 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1190 | P001 | A023 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1191 | P001 | A023 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1192 | P001 | A023 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1193 | P001 | A023 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1194 | P001 | A023 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1195 | P001 | A023 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1196 | P001 | A023 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1197 | P001 | A024 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1198 | P001 | A024 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1199 | P001 | A024 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1200 | P001 | A024 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1201 | P001 | A024 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1202 | P001 | A024 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1203 | P001 | A024 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1204 | P001 | A024 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1205 | P001 | A024 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1206 | P001 | A024 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1207 | P001 | A024 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1208 | P001 | A024 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1209 | P001 | A024 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1210 | P001 | A024 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1211 | P001 | A024 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1212 | P001 | A024 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1213 | P001 | A024 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1214 | P001 | A024 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1215 | P001 | A024 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1216 | P001 | A024 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1217 | P001 | A024 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1218 | P001 | A024 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1219 | P001 | A024 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1220 | P001 | A024 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1221 | P001 | A024 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1222 | P001 | A024 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1223 | P001 | A024 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1224 | P001 | A024 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1225 | P001 | A024 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1226 | P001 | A024 | 2025-07-25 | 108 | 48.09 | 6000% | 2671% | 48.09 | In Progress | 3
PRG1227 | P001 | A024 | 2025-08-01 | 180 | 180 | 10000% | 10000% | 131.91 | Completed | 0
PRG1228 | P001 | A024 | 2025-08-08 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1229 | P001 | A024 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1230 | P001 | A024 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1231 | P001 | A024 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1232 | P001 | A024 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1233 | P001 | A024 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1234 | P001 | A024 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1235 | P001 | A024 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1236 | P001 | A024 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1237 | P001 | A024 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1238 | P001 | A024 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1239 | P001 | A024 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1240 | P001 | A024 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1241 | P001 | A024 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1242 | P001 | A024 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1243 | P001 | A024 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1244 | P001 | A024 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1245 | P001 | A024 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1246 | P001 | A024 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1247 | P001 | A024 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1248 | P001 | A024 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1249 | P001 | A025 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1250 | P001 | A025 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1251 | P001 | A025 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1252 | P001 | A025 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1253 | P001 | A025 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1254 | P001 | A025 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1255 | P001 | A025 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1256 | P001 | A025 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1257 | P001 | A025 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1258 | P001 | A025 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1259 | P001 | A025 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1260 | P001 | A025 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1261 | P001 | A025 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1262 | P001 | A025 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1263 | P001 | A025 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1264 | P001 | A025 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1265 | P001 | A025 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1266 | P001 | A025 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1267 | P001 | A025 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1268 | P001 | A025 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1269 | P001 | A025 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1270 | P001 | A025 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1271 | P001 | A025 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1272 | P001 | A025 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1273 | P001 | A025 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1274 | P001 | A025 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1275 | P001 | A025 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1276 | P001 | A025 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1277 | P001 | A025 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1278 | P001 | A025 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1279 | P001 | A025 | 2025-08-01 | 25.71 | 13.96 | 4286% | 2327% | 13.96 | In Progress | 1
PRG1280 | P001 | A025 | 2025-08-08 | 60 | 60 | 10000% | 10000% | 46.04 | Completed | 0
PRG1281 | P001 | A025 | 2025-08-15 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1282 | P001 | A025 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1283 | P001 | A025 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1284 | P001 | A025 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1285 | P001 | A025 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1286 | P001 | A025 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1287 | P001 | A025 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1288 | P001 | A025 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1289 | P001 | A025 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1290 | P001 | A025 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1291 | P001 | A025 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1292 | P001 | A025 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1293 | P001 | A025 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1294 | P001 | A025 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1295 | P001 | A025 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1296 | P001 | A025 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1297 | P001 | A025 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1298 | P001 | A025 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1299 | P001 | A025 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1300 | P001 | A025 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1301 | P001 | A026 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1302 | P001 | A026 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1303 | P001 | A026 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1304 | P001 | A026 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1305 | P001 | A026 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1306 | P001 | A026 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1307 | P001 | A026 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1308 | P001 | A026 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1309 | P001 | A026 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1310 | P001 | A026 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1311 | P001 | A026 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1312 | P001 | A026 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1313 | P001 | A026 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1314 | P001 | A026 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1315 | P001 | A026 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1316 | P001 | A026 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1317 | P001 | A026 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1318 | P001 | A026 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1319 | P001 | A026 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1320 | P001 | A026 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1321 | P001 | A026 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1322 | P001 | A026 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1323 | P001 | A026 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1324 | P001 | A026 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1325 | P001 | A026 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1326 | P001 | A026 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1327 | P001 | A026 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1328 | P001 | A026 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1329 | P001 | A026 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1330 | P001 | A026 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1331 | P001 | A026 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1332 | P001 | A026 | 2025-08-08 | 54 | 16.28 | 3000% | 904% | 16.28 | In Progress | 2
PRG1333 | P001 | A026 | 2025-08-15 | 180 | 180 | 10000% | 10000% | 163.72 | Completed | 0
PRG1334 | P001 | A026 | 2025-08-22 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1335 | P001 | A026 | 2025-08-29 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1336 | P001 | A026 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1337 | P001 | A026 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1338 | P001 | A026 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1339 | P001 | A026 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1340 | P001 | A026 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1341 | P001 | A026 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1342 | P001 | A026 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1343 | P001 | A026 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1344 | P001 | A026 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1345 | P001 | A026 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1346 | P001 | A026 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1347 | P001 | A026 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1348 | P001 | A026 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1349 | P001 | A026 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1350 | P001 | A026 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1351 | P001 | A026 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1352 | P001 | A026 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1353 | P001 | A027 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1354 | P001 | A027 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1355 | P001 | A027 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1356 | P001 | A027 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1357 | P001 | A027 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1358 | P001 | A027 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1359 | P001 | A027 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1360 | P001 | A027 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1361 | P001 | A027 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1362 | P001 | A027 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1363 | P001 | A027 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1364 | P001 | A027 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1365 | P001 | A027 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1366 | P001 | A027 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1367 | P001 | A027 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1368 | P001 | A027 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1369 | P001 | A027 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1370 | P001 | A027 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1371 | P001 | A027 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1372 | P001 | A027 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1373 | P001 | A027 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1374 | P001 | A027 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1375 | P001 | A027 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1376 | P001 | A027 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1377 | P001 | A027 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1378 | P001 | A027 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1379 | P001 | A027 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1380 | P001 | A027 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1381 | P001 | A027 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1382 | P001 | A027 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1383 | P001 | A027 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1384 | P001 | A027 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1385 | P001 | A027 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1386 | P001 | A027 | 2025-08-22 | 60 | 60 | 10000% | 10000% | 60 | Completed | 0
PRG1387 | P001 | A027 | 2025-08-29 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1388 | P001 | A027 | 2025-09-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1389 | P001 | A027 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1390 | P001 | A027 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1391 | P001 | A027 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1392 | P001 | A027 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1393 | P001 | A027 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1394 | P001 | A027 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1395 | P001 | A027 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1396 | P001 | A027 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1397 | P001 | A027 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1398 | P001 | A027 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1399 | P001 | A027 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1400 | P001 | A027 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1401 | P001 | A027 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1402 | P001 | A027 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1403 | P001 | A027 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1404 | P001 | A027 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1405 | P001 | A028 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1406 | P001 | A028 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1407 | P001 | A028 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1408 | P001 | A028 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1409 | P001 | A028 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1410 | P001 | A028 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1411 | P001 | A028 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1412 | P001 | A028 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1413 | P001 | A028 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1414 | P001 | A028 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1415 | P001 | A028 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1416 | P001 | A028 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1417 | P001 | A028 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1418 | P001 | A028 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1419 | P001 | A028 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1420 | P001 | A028 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1421 | P001 | A028 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1422 | P001 | A028 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1423 | P001 | A028 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1424 | P001 | A028 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1425 | P001 | A028 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1426 | P001 | A028 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1427 | P001 | A028 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1428 | P001 | A028 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1429 | P001 | A028 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1430 | P001 | A028 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1431 | P001 | A028 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1432 | P001 | A028 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1433 | P001 | A028 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1434 | P001 | A028 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1435 | P001 | A028 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1436 | P001 | A028 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1437 | P001 | A028 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1438 | P001 | A028 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1439 | P001 | A028 | 2025-08-29 | 126 | 51.33 | 7000% | 2851% | 51.33 | In Progress | 4
PRG1440 | P001 | A028 | 2025-09-05 | 180 | 180 | 10000% | 10000% | 128.67 | Completed | 0
PRG1441 | P001 | A028 | 2025-09-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1442 | P001 | A028 | 2025-09-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1443 | P001 | A028 | 2025-09-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1444 | P001 | A028 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1445 | P001 | A028 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1446 | P001 | A028 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1447 | P001 | A028 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1448 | P001 | A028 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1449 | P001 | A028 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1450 | P001 | A028 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1451 | P001 | A028 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1452 | P001 | A028 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1453 | P001 | A028 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1454 | P001 | A028 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1455 | P001 | A028 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1456 | P001 | A028 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1457 | P001 | A029 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1458 | P001 | A029 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1459 | P001 | A029 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1460 | P001 | A029 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1461 | P001 | A029 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1462 | P001 | A029 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1463 | P001 | A029 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1464 | P001 | A029 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1465 | P001 | A029 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1466 | P001 | A029 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1467 | P001 | A029 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1468 | P001 | A029 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1469 | P001 | A029 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1470 | P001 | A029 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1471 | P001 | A029 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1472 | P001 | A029 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1473 | P001 | A029 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1474 | P001 | A029 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1475 | P001 | A029 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1476 | P001 | A029 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1477 | P001 | A029 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1478 | P001 | A029 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1479 | P001 | A029 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1480 | P001 | A029 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1481 | P001 | A029 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1482 | P001 | A029 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1483 | P001 | A029 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1484 | P001 | A029 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1485 | P001 | A029 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1486 | P001 | A029 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1487 | P001 | A029 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1488 | P001 | A029 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1489 | P001 | A029 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1490 | P001 | A029 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1491 | P001 | A029 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1492 | P001 | A029 | 2025-09-05 | 34.29 | 15.87 | 5714% | 2645% | 15.87 | In Progress | 2
PRG1493 | P001 | A029 | 2025-09-12 | 60 | 60 | 10000% | 10000% | 44.13 | Completed | 0
PRG1494 | P001 | A029 | 2025-09-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1495 | P001 | A029 | 2025-09-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1496 | P001 | A029 | 2025-10-03 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1497 | P001 | A029 | 2025-10-10 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1498 | P001 | A029 | 2025-10-17 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1499 | P001 | A029 | 2025-10-24 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1500 | P001 | A029 | 2025-10-31 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1501 | P001 | A029 | 2025-11-07 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1502 | P001 | A029 | 2025-11-14 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1503 | P001 | A029 | 2025-11-21 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1504 | P001 | A029 | 2025-11-28 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1505 | P001 | A029 | 2025-12-05 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1506 | P001 | A029 | 2025-12-12 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1507 | P001 | A029 | 2025-12-19 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1508 | P001 | A029 | 2025-12-26 | 60 | 60 | 10000% | 10000% | 0 | Completed | 0
PRG1509 | P001 | A030 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1510 | P001 | A030 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1511 | P001 | A030 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1512 | P001 | A030 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1513 | P001 | A030 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1514 | P001 | A030 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1515 | P001 | A030 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1516 | P001 | A030 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1517 | P001 | A030 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1518 | P001 | A030 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1519 | P001 | A030 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1520 | P001 | A030 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1521 | P001 | A030 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1522 | P001 | A030 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1523 | P001 | A030 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1524 | P001 | A030 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1525 | P001 | A030 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1526 | P001 | A030 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1527 | P001 | A030 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1528 | P001 | A030 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1529 | P001 | A030 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1530 | P001 | A030 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1531 | P001 | A030 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1532 | P001 | A030 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1533 | P001 | A030 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1534 | P001 | A030 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1535 | P001 | A030 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1536 | P001 | A030 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1537 | P001 | A030 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1538 | P001 | A030 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1539 | P001 | A030 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1540 | P001 | A030 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1541 | P001 | A030 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1542 | P001 | A030 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1543 | P001 | A030 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1544 | P001 | A030 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1545 | P001 | A030 | 2025-09-12 | 72 | 0 | 4000% | 0% | 0 | Not Started | 4
PRG1546 | P001 | A030 | 2025-09-19 | 180 | 28.84 | 10000% | 1602% | 28.84 | In Progress | 8
PRG1547 | P001 | A030 | 2025-09-26 | 180 | 104.42 | 10000% | 5801% | 75.58 | In Progress | 4
PRG1548 | P001 | A030 | 2025-10-03 | 180 | 180 | 10000% | 10000% | 75.58 | Completed | 0
PRG1549 | P001 | A030 | 2025-10-10 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1550 | P001 | A030 | 2025-10-17 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1551 | P001 | A030 | 2025-10-24 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1552 | P001 | A030 | 2025-10-31 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1553 | P001 | A030 | 2025-11-07 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1554 | P001 | A030 | 2025-11-14 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1555 | P001 | A030 | 2025-11-21 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1556 | P001 | A030 | 2025-11-28 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1557 | P001 | A030 | 2025-12-05 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1558 | P001 | A030 | 2025-12-12 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1559 | P001 | A030 | 2025-12-19 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1560 | P001 | A030 | 2025-12-26 | 180 | 180 | 10000% | 10000% | 0 | Completed | 0
PRG1561 | P001 | A031 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1562 | P001 | A031 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1563 | P001 | A031 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1564 | P001 | A031 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1565 | P001 | A031 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1566 | P001 | A031 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1567 | P001 | A031 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1568 | P001 | A031 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1569 | P001 | A031 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1570 | P001 | A031 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1571 | P001 | A031 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1572 | P001 | A031 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1573 | P001 | A031 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1574 | P001 | A031 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1575 | P001 | A031 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1576 | P001 | A031 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1577 | P001 | A031 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1578 | P001 | A031 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1579 | P001 | A031 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1580 | P001 | A031 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1581 | P001 | A031 | 2025-05-23 | 66.67 | 0 | 333% | 0% | 0 | Not Started | 1
PRG1582 | P001 | A031 | 2025-05-30 | 533.33 | 48.85 | 2667% | 244% | 48.85 | In Progress | 7
PRG1583 | P001 | A031 | 2025-06-06 | 1000 | 307.25 | 5000% | 1536% | 258.41 | In Progress | 10
PRG1584 | P001 | A031 | 2025-06-13 | 1466.67 | 648.8 | 7333% | 3244% | 341.55 | In Progress | 12
PRG1585 | P001 | A031 | 2025-06-20 | 1933.33 | 1029.64 | 9667% | 5148% | 380.85 | In Progress | 13
PRG1586 | P001 | A031 | 2025-06-27 | 2000 | 1453.68 | 10000% | 7268% | 424.04 | In Progress | 8
PRG1587 | P001 | A031 | 2025-07-04 | 2000 | 2000 | 10000% | 10000% | 546.32 | Completed | 0
PRG1588 | P001 | A031 | 2025-07-11 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1589 | P001 | A031 | 2025-07-18 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1590 | P001 | A031 | 2025-07-25 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1591 | P001 | A031 | 2025-08-01 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1592 | P001 | A031 | 2025-08-08 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1593 | P001 | A031 | 2025-08-15 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1594 | P001 | A031 | 2025-08-22 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1595 | P001 | A031 | 2025-08-29 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1596 | P001 | A031 | 2025-09-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1597 | P001 | A031 | 2025-09-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1598 | P001 | A031 | 2025-09-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1599 | P001 | A031 | 2025-09-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1600 | P001 | A031 | 2025-10-03 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1601 | P001 | A031 | 2025-10-10 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1602 | P001 | A031 | 2025-10-17 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1603 | P001 | A031 | 2025-10-24 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1604 | P001 | A031 | 2025-10-31 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1605 | P001 | A031 | 2025-11-07 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1606 | P001 | A031 | 2025-11-14 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1607 | P001 | A031 | 2025-11-21 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1608 | P001 | A031 | 2025-11-28 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1609 | P001 | A031 | 2025-12-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1610 | P001 | A031 | 2025-12-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1611 | P001 | A031 | 2025-12-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1612 | P001 | A031 | 2025-12-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1613 | P001 | A032 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1614 | P001 | A032 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1615 | P001 | A032 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1616 | P001 | A032 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1617 | P001 | A032 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1618 | P001 | A032 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1619 | P001 | A032 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1620 | P001 | A032 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1621 | P001 | A032 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1622 | P001 | A032 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1623 | P001 | A032 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1624 | P001 | A032 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1625 | P001 | A032 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1626 | P001 | A032 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1627 | P001 | A032 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1628 | P001 | A032 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1629 | P001 | A032 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1630 | P001 | A032 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1631 | P001 | A032 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1632 | P001 | A032 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1633 | P001 | A032 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1634 | P001 | A032 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1635 | P001 | A032 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1636 | P001 | A032 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1637 | P001 | A032 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1638 | P001 | A032 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1639 | P001 | A032 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1640 | P001 | A032 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1641 | P001 | A032 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1642 | P001 | A032 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1643 | P001 | A032 | 2025-08-01 | 200 | 36.93 | 1000% | 185% | 36.93 | In Progress | 2
PRG1644 | P001 | A032 | 2025-08-08 | 666.67 | 267.78 | 3333% | 1339% | 230.84 | In Progress | 5
PRG1645 | P001 | A032 | 2025-08-15 | 1133.33 | 677.01 | 5667% | 3385% | 409.23 | In Progress | 6
PRG1646 | P001 | A032 | 2025-08-22 | 1600 | 980.46 | 8000% | 4902% | 303.45 | In Progress | 9
PRG1647 | P001 | A032 | 2025-08-29 | 2000 | 2000 | 10000% | 10000% | 1019.54 | Completed | 0
PRG1648 | P001 | A032 | 2025-09-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1649 | P001 | A032 | 2025-09-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1650 | P001 | A032 | 2025-09-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1651 | P001 | A032 | 2025-09-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1652 | P001 | A032 | 2025-10-03 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1653 | P001 | A032 | 2025-10-10 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1654 | P001 | A032 | 2025-10-17 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1655 | P001 | A032 | 2025-10-24 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1656 | P001 | A032 | 2025-10-31 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1657 | P001 | A032 | 2025-11-07 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1658 | P001 | A032 | 2025-11-14 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1659 | P001 | A032 | 2025-11-21 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1660 | P001 | A032 | 2025-11-28 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1661 | P001 | A032 | 2025-12-05 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1662 | P001 | A032 | 2025-12-12 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1663 | P001 | A032 | 2025-12-19 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1664 | P001 | A032 | 2025-12-26 | 2000 | 2000 | 10000% | 10000% | 0 | Completed | 0
PRG1665 | P001 | A033 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1666 | P001 | A033 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1667 | P001 | A033 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1668 | P001 | A033 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1669 | P001 | A033 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1670 | P001 | A033 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1671 | P001 | A033 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1672 | P001 | A033 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1673 | P001 | A033 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1674 | P001 | A033 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1675 | P001 | A033 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1676 | P001 | A033 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1677 | P001 | A033 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1678 | P001 | A033 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1679 | P001 | A033 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1680 | P001 | A033 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1681 | P001 | A033 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1682 | P001 | A033 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1683 | P001 | A033 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1684 | P001 | A033 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1685 | P001 | A033 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1686 | P001 | A033 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1687 | P001 | A033 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1688 | P001 | A033 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1689 | P001 | A033 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1690 | P001 | A033 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1691 | P001 | A033 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1692 | P001 | A033 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1693 | P001 | A033 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1694 | P001 | A033 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1695 | P001 | A033 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1696 | P001 | A033 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1697 | P001 | A033 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1698 | P001 | A033 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1699 | P001 | A033 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1700 | P001 | A033 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1701 | P001 | A033 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1702 | P001 | A033 | 2025-09-19 | 75 | 33.36 | 500% | 222% | 33.36 | In Progress | 0
PRG1703 | P001 | A033 | 2025-09-26 | 600 | 270.94 | 4000% | 1806% | 237.58 | In Progress | 4
PRG1704 | P001 | A033 | 2025-10-03 | 1125 | 643.58 | 7500% | 4291% | 372.64 | In Progress | 6
PRG1705 | P001 | A033 | 2025-10-10 | 1500 | 1500 | 10000% | 10000% | 856.42 | Completed | 0
PRG1706 | P001 | A033 | 2025-10-17 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1707 | P001 | A033 | 2025-10-24 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1708 | P001 | A033 | 2025-10-31 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1709 | P001 | A033 | 2025-11-07 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1710 | P001 | A033 | 2025-11-14 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1711 | P001 | A033 | 2025-11-21 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1712 | P001 | A033 | 2025-11-28 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1713 | P001 | A033 | 2025-12-05 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1714 | P001 | A033 | 2025-12-12 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1715 | P001 | A033 | 2025-12-19 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1716 | P001 | A033 | 2025-12-26 | 1500 | 1500 | 10000% | 10000% | 0 | Completed | 0
PRG1717 | P001 | A034 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1718 | P001 | A034 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1719 | P001 | A034 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1720 | P001 | A034 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1721 | P001 | A034 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1722 | P001 | A034 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1723 | P001 | A034 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1724 | P001 | A034 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1725 | P001 | A034 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1726 | P001 | A034 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1727 | P001 | A034 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1728 | P001 | A034 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1729 | P001 | A034 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1730 | P001 | A034 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1731 | P001 | A034 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1732 | P001 | A034 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1733 | P001 | A034 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1734 | P001 | A034 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1735 | P001 | A034 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1736 | P001 | A034 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1737 | P001 | A034 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1738 | P001 | A034 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1739 | P001 | A034 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1740 | P001 | A034 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1741 | P001 | A034 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1742 | P001 | A034 | 2025-06-27 | 675 | 275.04 | 1500% | 611% | 275.04 | In Progress | 3
PRG1743 | P001 | A034 | 2025-07-04 | 1462.5 | 786.23 | 3250% | 1747% | 511.19 | In Progress | 6
PRG1744 | P001 | A034 | 2025-07-11 | 2250 | 1564.2 | 5000% | 3476% | 777.97 | In Progress | 6
PRG1745 | P001 | A034 | 2025-07-18 | 3037.5 | 2362.06 | 6750% | 5249% | 797.86 | In Progress | 6
PRG1746 | P001 | A034 | 2025-07-25 | 3825 | 3091.31 | 8500% | 6870% | 729.25 | In Progress | 6
PRG1747 | P001 | A034 | 2025-08-01 | 4500 | 4500 | 10000% | 10000% | 1408.69 | Completed | 0
PRG1748 | P001 | A034 | 2025-08-08 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1749 | P001 | A034 | 2025-08-15 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1750 | P001 | A034 | 2025-08-22 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1751 | P001 | A034 | 2025-08-29 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1752 | P001 | A034 | 2025-09-05 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1753 | P001 | A034 | 2025-09-12 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1754 | P001 | A034 | 2025-09-19 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1755 | P001 | A034 | 2025-09-26 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1756 | P001 | A034 | 2025-10-03 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1757 | P001 | A034 | 2025-10-10 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1758 | P001 | A034 | 2025-10-17 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1759 | P001 | A034 | 2025-10-24 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1760 | P001 | A034 | 2025-10-31 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1761 | P001 | A034 | 2025-11-07 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1762 | P001 | A034 | 2025-11-14 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1763 | P001 | A034 | 2025-11-21 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1764 | P001 | A034 | 2025-11-28 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1765 | P001 | A034 | 2025-12-05 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1766 | P001 | A034 | 2025-12-12 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1767 | P001 | A034 | 2025-12-19 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1768 | P001 | A034 | 2025-12-26 | 4500 | 4500 | 10000% | 10000% | 0 | Completed | 0
PRG1769 | P001 | A035 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1770 | P001 | A035 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1771 | P001 | A035 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1772 | P001 | A035 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1773 | P001 | A035 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1774 | P001 | A035 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1775 | P001 | A035 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1776 | P001 | A035 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1777 | P001 | A035 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1778 | P001 | A035 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1779 | P001 | A035 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1780 | P001 | A035 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1781 | P001 | A035 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1782 | P001 | A035 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1783 | P001 | A035 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1784 | P001 | A035 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1785 | P001 | A035 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1786 | P001 | A035 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1787 | P001 | A035 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1788 | P001 | A035 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1789 | P001 | A035 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1790 | P001 | A035 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1791 | P001 | A035 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1792 | P001 | A035 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1793 | P001 | A035 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1794 | P001 | A035 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1795 | P001 | A035 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1796 | P001 | A035 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1797 | P001 | A035 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1798 | P001 | A035 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1799 | P001 | A035 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1800 | P001 | A035 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1801 | P001 | A035 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1802 | P001 | A035 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1803 | P001 | A035 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1804 | P001 | A035 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1805 | P001 | A035 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1806 | P001 | A035 | 2025-09-19 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1807 | P001 | A035 | 2025-09-26 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1808 | P001 | A035 | 2025-10-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1809 | P001 | A035 | 2025-10-10 | 228.57 | 221.06 | 571% | 553% | 221.06 | In Progress | 0
PRG1810 | P001 | A035 | 2025-10-17 | 1028.57 | 1069.69 | 2571% | 2674% | 848.63 | In Progress | 0
PRG1811 | P001 | A035 | 2025-10-24 | 1828.57 | 1709.99 | 4571% | 4275% | 640.3 | In Progress | 1
PRG1812 | P001 | A035 | 2025-10-31 | 2628.57 | 2208.03 | 6571% | 5520% | 498.04 | In Progress | 3
PRG1813 | P001 | A035 | 2025-11-07 | 3428.57 | 3662.26 | 8571% | 9156% | 1454.23 | In Progress | 0
PRG1814 | P001 | A035 | 2025-11-14 | 4000 | 4000 | 10000% | 10000% | 337.74 | Completed | 0
PRG1815 | P001 | A035 | 2025-11-21 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1816 | P001 | A035 | 2025-11-28 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1817 | P001 | A035 | 2025-12-05 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1818 | P001 | A035 | 2025-12-12 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1819 | P001 | A035 | 2025-12-19 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1820 | P001 | A035 | 2025-12-26 | 4000 | 4000 | 10000% | 10000% | 0 | Completed | 0
PRG1821 | P001 | A036 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1822 | P001 | A036 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1823 | P001 | A036 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1824 | P001 | A036 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1825 | P001 | A036 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1826 | P001 | A036 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1827 | P001 | A036 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1828 | P001 | A036 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1829 | P001 | A036 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1830 | P001 | A036 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1831 | P001 | A036 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1832 | P001 | A036 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1833 | P001 | A036 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1834 | P001 | A036 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1835 | P001 | A036 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1836 | P001 | A036 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1837 | P001 | A036 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1838 | P001 | A036 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1839 | P001 | A036 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1840 | P001 | A036 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1841 | P001 | A036 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1842 | P001 | A036 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1843 | P001 | A036 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1844 | P001 | A036 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1845 | P001 | A036 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1846 | P001 | A036 | 2025-06-27 | 500 | 148.44 | 1000% | 297% | 148.44 | In Progress | 4
PRG1847 | P001 | A036 | 2025-07-04 | 1083.33 | 472.03 | 2167% | 944% | 323.59 | In Progress | 7
PRG1848 | P001 | A036 | 2025-07-11 | 1666.67 | 1010.76 | 3333% | 2022% | 538.74 | In Progress | 7
PRG1849 | P001 | A036 | 2025-07-18 | 2250 | 1484.09 | 4500% | 2968% | 473.32 | In Progress | 9
PRG1850 | P001 | A036 | 2025-07-25 | 2833.33 | 2185.68 | 5667% | 4371% | 701.59 | In Progress | 7
PRG1851 | P001 | A036 | 2025-08-01 | 3416.67 | 2792.07 | 6833% | 5584% | 606.39 | In Progress | 7
PRG1852 | P001 | A036 | 2025-08-08 | 4000 | 3170.45 | 8000% | 6341% | 378.38 | In Progress | 9
PRG1853 | P001 | A036 | 2025-08-15 | 4583.33 | 3472.1 | 9167% | 6944% | 301.65 | In Progress | 13
PRG1854 | P001 | A036 | 2025-08-22 | 5000 | 5000 | 10000% | 10000% | 1527.9 | Completed | 0
PRG1855 | P001 | A036 | 2025-08-29 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1856 | P001 | A036 | 2025-09-05 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1857 | P001 | A036 | 2025-09-12 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1858 | P001 | A036 | 2025-09-19 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1859 | P001 | A036 | 2025-09-26 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1860 | P001 | A036 | 2025-10-03 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1861 | P001 | A036 | 2025-10-10 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1862 | P001 | A036 | 2025-10-17 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1863 | P001 | A036 | 2025-10-24 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1864 | P001 | A036 | 2025-10-31 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1865 | P001 | A036 | 2025-11-07 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1866 | P001 | A036 | 2025-11-14 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1867 | P001 | A036 | 2025-11-21 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1868 | P001 | A036 | 2025-11-28 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1869 | P001 | A036 | 2025-12-05 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1870 | P001 | A036 | 2025-12-12 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1871 | P001 | A036 | 2025-12-19 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1872 | P001 | A036 | 2025-12-26 | 5000 | 5000 | 10000% | 10000% | 0 | Completed | 0
PRG1873 | P001 | A037 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1874 | P001 | A037 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1875 | P001 | A037 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1876 | P001 | A037 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1877 | P001 | A037 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1878 | P001 | A037 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1879 | P001 | A037 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1880 | P001 | A037 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1881 | P001 | A037 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1882 | P001 | A037 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1883 | P001 | A037 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1884 | P001 | A037 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1885 | P001 | A037 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1886 | P001 | A037 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1887 | P001 | A037 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1888 | P001 | A037 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1889 | P001 | A037 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1890 | P001 | A037 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1891 | P001 | A037 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1892 | P001 | A037 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1893 | P001 | A037 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1894 | P001 | A037 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1895 | P001 | A037 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1896 | P001 | A037 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1897 | P001 | A037 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1898 | P001 | A037 | 2025-06-27 | 360 | 83.8 | 1200% | 279% | 83.8 | In Progress | 4
PRG1899 | P001 | A037 | 2025-07-04 | 780 | 365.41 | 2600% | 1218% | 281.61 | In Progress | 6
PRG1900 | P001 | A037 | 2025-07-11 | 1200 | 639.53 | 4000% | 2132% | 274.13 | In Progress | 9
PRG1901 | P001 | A037 | 2025-07-18 | 1620 | 1068.12 | 5400% | 3560% | 428.58 | In Progress | 9
PRG1902 | P001 | A037 | 2025-07-25 | 2040 | 1328.69 | 6800% | 4429% | 260.58 | In Progress | 11
PRG1903 | P001 | A037 | 2025-08-01 | 2460 | 1822.98 | 8200% | 6077% | 494.29 | In Progress | 10
PRG1904 | P001 | A037 | 2025-08-08 | 2880 | 2411.49 | 9600% | 8038% | 588.51 | In Progress | 7
PRG1905 | P001 | A037 | 2025-08-15 | 3000 | 3000 | 10000% | 10000% | 588.51 | Completed | 0
PRG1906 | P001 | A037 | 2025-08-22 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1907 | P001 | A037 | 2025-08-29 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1908 | P001 | A037 | 2025-09-05 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1909 | P001 | A037 | 2025-09-12 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1910 | P001 | A037 | 2025-09-19 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1911 | P001 | A037 | 2025-09-26 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1912 | P001 | A037 | 2025-10-03 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1913 | P001 | A037 | 2025-10-10 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1914 | P001 | A037 | 2025-10-17 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1915 | P001 | A037 | 2025-10-24 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1916 | P001 | A037 | 2025-10-31 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1917 | P001 | A037 | 2025-11-07 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1918 | P001 | A037 | 2025-11-14 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1919 | P001 | A037 | 2025-11-21 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1920 | P001 | A037 | 2025-11-28 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1921 | P001 | A037 | 2025-12-05 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1922 | P001 | A037 | 2025-12-12 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1923 | P001 | A037 | 2025-12-19 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1924 | P001 | A037 | 2025-12-26 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1925 | P001 | A038 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1926 | P001 | A038 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1927 | P001 | A038 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1928 | P001 | A038 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1929 | P001 | A038 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1930 | P001 | A038 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1931 | P001 | A038 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1932 | P001 | A038 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1933 | P001 | A038 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1934 | P001 | A038 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1935 | P001 | A038 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1936 | P001 | A038 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1937 | P001 | A038 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1938 | P001 | A038 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1939 | P001 | A038 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1940 | P001 | A038 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1941 | P001 | A038 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1942 | P001 | A038 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1943 | P001 | A038 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1944 | P001 | A038 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1945 | P001 | A038 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1946 | P001 | A038 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1947 | P001 | A038 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1948 | P001 | A038 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1949 | P001 | A038 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1950 | P001 | A038 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1951 | P001 | A038 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1952 | P001 | A038 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1953 | P001 | A038 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1954 | P001 | A038 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1955 | P001 | A038 | 2025-08-01 | 100 | 0 | 333% | 0% | 0 | Not Started | 1
PRG1956 | P001 | A038 | 2025-08-08 | 800 | 114.87 | 2667% | 383% | 114.87 | In Progress | 6
PRG1957 | P001 | A038 | 2025-08-15 | 1500 | 454.65 | 5000% | 1516% | 339.79 | In Progress | 10
PRG1958 | P001 | A038 | 2025-08-22 | 2200 | 849.53 | 7333% | 2832% | 394.87 | In Progress | 13
PRG1959 | P001 | A038 | 2025-08-29 | 2900 | 1358.26 | 9667% | 4528% | 508.73 | In Progress | 15
PRG1960 | P001 | A038 | 2025-09-05 | 3000 | 1728.96 | 10000% | 5763% | 370.7 | In Progress | 12
PRG1961 | P001 | A038 | 2025-09-12 | 3000 | 3000 | 10000% | 10000% | 1271.04 | Completed | 0
PRG1962 | P001 | A038 | 2025-09-19 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1963 | P001 | A038 | 2025-09-26 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1964 | P001 | A038 | 2025-10-03 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1965 | P001 | A038 | 2025-10-10 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1966 | P001 | A038 | 2025-10-17 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1967 | P001 | A038 | 2025-10-24 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1968 | P001 | A038 | 2025-10-31 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1969 | P001 | A038 | 2025-11-07 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1970 | P001 | A038 | 2025-11-14 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1971 | P001 | A038 | 2025-11-21 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1972 | P001 | A038 | 2025-11-28 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1973 | P001 | A038 | 2025-12-05 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1974 | P001 | A038 | 2025-12-12 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1975 | P001 | A038 | 2025-12-19 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1976 | P001 | A038 | 2025-12-26 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG1977 | P001 | A039 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1978 | P001 | A039 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1979 | P001 | A039 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1980 | P001 | A039 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1981 | P001 | A039 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1982 | P001 | A039 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1983 | P001 | A039 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1984 | P001 | A039 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1985 | P001 | A039 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1986 | P001 | A039 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1987 | P001 | A039 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1988 | P001 | A039 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1989 | P001 | A039 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1990 | P001 | A039 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1991 | P001 | A039 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1992 | P001 | A039 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1993 | P001 | A039 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1994 | P001 | A039 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1995 | P001 | A039 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1996 | P001 | A039 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1997 | P001 | A039 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1998 | P001 | A039 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG1999 | P001 | A039 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2000 | P001 | A039 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2001 | P001 | A039 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2002 | P001 | A039 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2003 | P001 | A039 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2004 | P001 | A039 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2005 | P001 | A039 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2006 | P001 | A039 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2007 | P001 | A039 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2008 | P001 | A039 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2009 | P001 | A039 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2010 | P001 | A039 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2011 | P001 | A039 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2012 | P001 | A039 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2013 | P001 | A039 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2014 | P001 | A039 | 2025-09-19 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2015 | P001 | A039 | 2025-09-26 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2016 | P001 | A039 | 2025-10-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2017 | P001 | A039 | 2025-10-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2018 | P001 | A039 | 2025-10-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2019 | P001 | A039 | 2025-10-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2020 | P001 | A039 | 2025-10-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2021 | P001 | A039 | 2025-11-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2022 | P001 | A039 | 2025-11-14 | 200 | 0 | 667% | 0% | 0 | Not Started | 2
PRG2023 | P001 | A039 | 2025-11-21 | 900 | 675.65 | 3000% | 2252% | 675.65 | In Progress | 2
PRG2024 | P001 | A039 | 2025-11-28 | 1600 | 1493.41 | 5333% | 4978% | 817.76 | In Progress | 1
PRG2025 | P001 | A039 | 2025-12-05 | 2300 | 2004.42 | 7667% | 6681% | 511.01 | In Progress | 2
PRG2026 | P001 | A039 | 2025-12-12 | 3000 | 3000 | 10000% | 10000% | 995.58 | Completed | 0
PRG2027 | P001 | A039 | 2025-12-19 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG2028 | P001 | A039 | 2025-12-26 | 3000 | 3000 | 10000% | 10000% | 0 | Completed | 0
PRG2029 | P001 | A040 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2030 | P001 | A040 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2031 | P001 | A040 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2032 | P001 | A040 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2033 | P001 | A040 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2034 | P001 | A040 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2035 | P001 | A040 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2036 | P001 | A040 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2037 | P001 | A040 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2038 | P001 | A040 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2039 | P001 | A040 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2040 | P001 | A040 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2041 | P001 | A040 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2042 | P001 | A040 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2043 | P001 | A040 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2044 | P001 | A040 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2045 | P001 | A040 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2046 | P001 | A040 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2047 | P001 | A040 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2048 | P001 | A040 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2049 | P001 | A040 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2050 | P001 | A040 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2051 | P001 | A040 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2052 | P001 | A040 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2053 | P001 | A040 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2054 | P001 | A040 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2055 | P001 | A040 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2056 | P001 | A040 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2057 | P001 | A040 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2058 | P001 | A040 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2059 | P001 | A040 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2060 | P001 | A040 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2061 | P001 | A040 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2062 | P001 | A040 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2063 | P001 | A040 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2064 | P001 | A040 | 2025-09-05 | 1133.33 | 460.52 | 1333% | 542% | 460.52 | In Progress | 3
PRG2065 | P001 | A040 | 2025-09-12 | 2455.56 | 1249.59 | 2889% | 1470% | 789.07 | In Progress | 6
PRG2066 | P001 | A040 | 2025-09-19 | 3777.78 | 2621.15 | 4444% | 3084% | 1371.56 | In Progress | 6
PRG2067 | P001 | A040 | 2025-09-26 | 5100 | 3424.24 | 6000% | 4029% | 803.1 | In Progress | 8
PRG2068 | P001 | A040 | 2025-10-03 | 6422.22 | 5202.53 | 7556% | 6121% | 1778.29 | In Progress | 6
PRG2069 | P001 | A040 | 2025-10-10 | 7744.44 | 6513.02 | 9111% | 7662% | 1310.49 | In Progress | 6
PRG2070 | P001 | A040 | 2025-10-17 | 8500 | 8500 | 10000% | 10000% | 1986.98 | Completed | 0
PRG2071 | P001 | A040 | 2025-10-24 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2072 | P001 | A040 | 2025-10-31 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2073 | P001 | A040 | 2025-11-07 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2074 | P001 | A040 | 2025-11-14 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2075 | P001 | A040 | 2025-11-21 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2076 | P001 | A040 | 2025-11-28 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2077 | P001 | A040 | 2025-12-05 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2078 | P001 | A040 | 2025-12-12 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2079 | P001 | A040 | 2025-12-19 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2080 | P001 | A040 | 2025-12-26 | 8500 | 8500 | 10000% | 10000% | 0 | Completed | 0
PRG2081 | P001 | A041 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2082 | P001 | A041 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2083 | P001 | A041 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2084 | P001 | A041 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2085 | P001 | A041 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2086 | P001 | A041 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2087 | P001 | A041 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2088 | P001 | A041 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2089 | P001 | A041 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2090 | P001 | A041 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2091 | P001 | A041 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2092 | P001 | A041 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2093 | P001 | A041 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2094 | P001 | A041 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2095 | P001 | A041 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2096 | P001 | A041 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2097 | P001 | A041 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2098 | P001 | A041 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2099 | P001 | A041 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2100 | P001 | A041 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2101 | P001 | A041 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2102 | P001 | A041 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2103 | P001 | A041 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2104 | P001 | A041 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2105 | P001 | A041 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2106 | P001 | A041 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2107 | P001 | A041 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2108 | P001 | A041 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2109 | P001 | A041 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2110 | P001 | A041 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2111 | P001 | A041 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2112 | P001 | A041 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2113 | P001 | A041 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2114 | P001 | A041 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2115 | P001 | A041 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2116 | P001 | A041 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2117 | P001 | A041 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2118 | P001 | A041 | 2025-09-19 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2119 | P001 | A041 | 2025-09-26 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2120 | P001 | A041 | 2025-10-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2121 | P001 | A041 | 2025-10-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2122 | P001 | A041 | 2025-10-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2123 | P001 | A041 | 2025-10-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2124 | P001 | A041 | 2025-10-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2125 | P001 | A041 | 2025-11-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2126 | P001 | A041 | 2025-11-14 | 366.67 | 386.61 | 667% | 703% | 386.61 | In Progress | 0
PRG2127 | P001 | A041 | 2025-11-21 | 1650 | 1438.58 | 3000% | 2616% | 1051.98 | In Progress | 1
PRG2128 | P001 | A041 | 2025-11-28 | 2933.33 | 2732.47 | 5333% | 4968% | 1293.89 | In Progress | 1
PRG2129 | P001 | A041 | 2025-12-05 | 4216.67 | 4421.07 | 7667% | 8038% | 1688.6 | In Progress | 0
PRG2130 | P001 | A041 | 2025-12-12 | 5500 | 5500 | 10000% | 10000% | 1078.93 | Completed | 0
PRG2131 | P001 | A041 | 2025-12-19 | 5500 | 5500 | 10000% | 10000% | 0 | Completed | 0
PRG2132 | P001 | A041 | 2025-12-26 | 5500 | 5500 | 10000% | 10000% | 0 | Completed | 0
PRG2133 | P001 | A042 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2134 | P001 | A042 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2135 | P001 | A042 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2136 | P001 | A042 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2137 | P001 | A042 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2138 | P001 | A042 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2139 | P001 | A042 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2140 | P001 | A042 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2141 | P001 | A042 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2142 | P001 | A042 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2143 | P001 | A042 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2144 | P001 | A042 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2145 | P001 | A042 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2146 | P001 | A042 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2147 | P001 | A042 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2148 | P001 | A042 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2149 | P001 | A042 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2150 | P001 | A042 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2151 | P001 | A042 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2152 | P001 | A042 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2153 | P001 | A042 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2154 | P001 | A042 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2155 | P001 | A042 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2156 | P001 | A042 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2157 | P001 | A042 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2158 | P001 | A042 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2159 | P001 | A042 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2160 | P001 | A042 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2161 | P001 | A042 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2162 | P001 | A042 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2163 | P001 | A042 | 2025-08-01 | 7.5 | 3.79 | 250% | 126% | 3.79 | In Progress | 0
PRG2164 | P001 | A042 | 2025-08-08 | 60 | 30.79 | 2000% | 1026% | 27 | In Progress | 3
PRG2165 | P001 | A042 | 2025-08-15 | 112.5 | 69.24 | 3750% | 2308% | 38.45 | In Progress | 5
PRG2166 | P001 | A042 | 2025-08-22 | 165 | 116.06 | 5500% | 3869% | 46.82 | In Progress | 6
PRG2167 | P001 | A042 | 2025-08-29 | 217.5 | 147.01 | 7250% | 4900% | 30.95 | In Progress | 9
PRG2168 | P001 | A042 | 2025-09-05 | 270 | 188.75 | 9000% | 6292% | 41.74 | In Progress | 10
PRG2169 | P001 | A042 | 2025-09-12 | 300 | 300 | 10000% | 10000% | 111.25 | Completed | 0
PRG2170 | P001 | A042 | 2025-09-19 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2171 | P001 | A042 | 2025-09-26 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2172 | P001 | A042 | 2025-10-03 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2173 | P001 | A042 | 2025-10-10 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2174 | P001 | A042 | 2025-10-17 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2175 | P001 | A042 | 2025-10-24 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2176 | P001 | A042 | 2025-10-31 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2177 | P001 | A042 | 2025-11-07 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2178 | P001 | A042 | 2025-11-14 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2179 | P001 | A042 | 2025-11-21 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2180 | P001 | A042 | 2025-11-28 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2181 | P001 | A042 | 2025-12-05 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2182 | P001 | A042 | 2025-12-12 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2183 | P001 | A042 | 2025-12-19 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2184 | P001 | A042 | 2025-12-26 | 300 | 300 | 10000% | 10000% | 0 | Completed | 0
PRG2185 | P001 | A043 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2186 | P001 | A043 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2187 | P001 | A043 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2188 | P001 | A043 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2189 | P001 | A043 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2190 | P001 | A043 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2191 | P001 | A043 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2192 | P001 | A043 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2193 | P001 | A043 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2194 | P001 | A043 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2195 | P001 | A043 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2196 | P001 | A043 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2197 | P001 | A043 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2198 | P001 | A043 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2199 | P001 | A043 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2200 | P001 | A043 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2201 | P001 | A043 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2202 | P001 | A043 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2203 | P001 | A043 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2204 | P001 | A043 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2205 | P001 | A043 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2206 | P001 | A043 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2207 | P001 | A043 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2208 | P001 | A043 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2209 | P001 | A043 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2210 | P001 | A043 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2211 | P001 | A043 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2212 | P001 | A043 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2213 | P001 | A043 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2214 | P001 | A043 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2215 | P001 | A043 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2216 | P001 | A043 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2217 | P001 | A043 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2218 | P001 | A043 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2219 | P001 | A043 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2220 | P001 | A043 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2221 | P001 | A043 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2222 | P001 | A043 | 2025-09-19 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2223 | P001 | A043 | 2025-09-26 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2224 | P001 | A043 | 2025-10-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2225 | P001 | A043 | 2025-10-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2226 | P001 | A043 | 2025-10-17 | 0.15 | 0.14 | 1500% | 1433% | 0.14 | In Progress | 0
PRG2227 | P001 | A043 | 2025-10-24 | 0.5 | 0.42 | 5000% | 4234% | 0.28 | In Progress | 1
PRG2228 | P001 | A043 | 2025-10-31 | 0.85 | 0.76 | 8500% | 7566% | 0.33 | In Progress | 1
PRG2229 | P001 | A043 | 2025-11-07 | 1 | 1 | 10000% | 10000% | 0.24 | Completed | 0
PRG2230 | P001 | A043 | 2025-11-14 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2231 | P001 | A043 | 2025-11-21 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2232 | P001 | A043 | 2025-11-28 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2233 | P001 | A043 | 2025-12-05 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2234 | P001 | A043 | 2025-12-12 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2235 | P001 | A043 | 2025-12-19 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2236 | P001 | A043 | 2025-12-26 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2237 | P001 | A044 | 2025-01-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2238 | P001 | A044 | 2025-01-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2239 | P001 | A044 | 2025-01-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2240 | P001 | A044 | 2025-01-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2241 | P001 | A044 | 2025-01-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2242 | P001 | A044 | 2025-02-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2243 | P001 | A044 | 2025-02-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2244 | P001 | A044 | 2025-02-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2245 | P001 | A044 | 2025-02-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2246 | P001 | A044 | 2025-03-07 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2247 | P001 | A044 | 2025-03-14 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2248 | P001 | A044 | 2025-03-21 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2249 | P001 | A044 | 2025-03-28 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2250 | P001 | A044 | 2025-04-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2251 | P001 | A044 | 2025-04-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2252 | P001 | A044 | 2025-04-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2253 | P001 | A044 | 2025-04-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2254 | P001 | A044 | 2025-05-02 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2255 | P001 | A044 | 2025-05-09 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2256 | P001 | A044 | 2025-05-16 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2257 | P001 | A044 | 2025-05-23 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2258 | P001 | A044 | 2025-05-30 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2259 | P001 | A044 | 2025-06-06 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2260 | P001 | A044 | 2025-06-13 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2261 | P001 | A044 | 2025-06-20 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2262 | P001 | A044 | 2025-06-27 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2263 | P001 | A044 | 2025-07-04 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2264 | P001 | A044 | 2025-07-11 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2265 | P001 | A044 | 2025-07-18 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2266 | P001 | A044 | 2025-07-25 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2267 | P001 | A044 | 2025-08-01 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2268 | P001 | A044 | 2025-08-08 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2269 | P001 | A044 | 2025-08-15 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2270 | P001 | A044 | 2025-08-22 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2271 | P001 | A044 | 2025-08-29 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2272 | P001 | A044 | 2025-09-05 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2273 | P001 | A044 | 2025-09-12 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2274 | P001 | A044 | 2025-09-19 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2275 | P001 | A044 | 2025-09-26 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2276 | P001 | A044 | 2025-10-03 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2277 | P001 | A044 | 2025-10-10 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2278 | P001 | A044 | 2025-10-17 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2279 | P001 | A044 | 2025-10-24 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2280 | P001 | A044 | 2025-10-31 | 0 | 0 | 0% | 0% | 0 | Not Started | 0
PRG2281 | P001 | A044 | 2025-11-07 | 0.4 | 0 | 4000% | 0% | 0 | Not Started | 4
PRG2282 | P001 | A044 | 2025-11-14 | 1 | 0.26 | 10000% | 2554% | 0.26 | In Progress | 7
PRG2283 | P001 | A044 | 2025-11-21 | 1 | 0.66 | 10000% | 6557% | 0.4 | In Progress | 3
PRG2284 | P001 | A044 | 2025-11-28 | 1 | 0.83 | 10000% | 8328% | 0.18 | In Progress | 1
PRG2285 | P001 | A044 | 2025-12-05 | 1 | 1 | 10000% | 10000% | 0.17 | Completed | 0
PRG2286 | P001 | A044 | 2025-12-12 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2287 | P001 | A044 | 2025-12-19 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0
PRG2288 | P001 | A044 | 2025-12-26 | 1 | 1 | 10000% | 10000% | 0 | Completed | 0

## Cost_Transactions
Cost_ID | Project_ID | Activity_ID | Date | Contractor_ID | Cost_Type | Description | Planned_Cost_INR | Actual_Cost_INR | Vendor_or_Source
CST00001 | P001 | A001 | 2025-01-03 | C001 | Material | Material cost for Site Mobilization | 58787.09 | 57300.97 | C001
CST00002 | P001 | A001 | 2025-01-03 | C001 | Labour | Labour cost for Site Mobilization | 35272.26 | 34323.17 | C001
CST00003 | P001 | A001 | 2025-01-03 | C001 | Equipment | Equipment cost for Site Mobilization | 17636.13 | 16391.57 | C001
CST00004 | P001 | A001 | 2025-01-03 | C001 | Other | Other cost for Site Mobilization | 5878.71 | 5348.55 | C001
CST00005 | P001 | A001 | 2025-01-10 | C001 | Material | Material cost for Site Mobilization | 191212.91 | 159280.99 | C001
CST00006 | P001 | A001 | 2025-01-10 | C001 | Labour | Labour cost for Site Mobilization | 114727.74 | 107280.28 | C001
CST00007 | P001 | A001 | 2025-01-10 | C001 | Equipment | Equipment cost for Site Mobilization | 57363.87 | 47313.29 | C001
CST00008 | P001 | A001 | 2025-01-10 | C001 | Other | Other cost for Site Mobilization | 19121.29 | 18093.71 | C001
CST00009 | P001 | A002 | 2025-01-10 | C001 | Material | Material cost for Site Clearance | 18319.39 | 16530.68 | C001
CST00010 | P001 | A002 | 2025-01-10 | C001 | Labour | Labour cost for Site Clearance | 10991.63 | 11169.84 | C001
CST00011 | P001 | A002 | 2025-01-10 | C001 | Equipment | Equipment cost for Site Clearance | 5495.82 | 5702.68 | C001
CST00012 | P001 | A002 | 2025-01-10 | C001 | Other | Other cost for Site Clearance | 1831.94 | 1775.07 | C001
CST00013 | P001 | A002 | 2025-01-17 | C001 | Material | Material cost for Site Clearance | 31680.61 | 29047.41 | C001
CST00014 | P001 | A002 | 2025-01-17 | C001 | Labour | Labour cost for Site Clearance | 19008.37 | 16704.08 | C001
CST00015 | P001 | A002 | 2025-01-17 | C001 | Equipment | Equipment cost for Site Clearance | 9504.18 | 9389.84 | C001
CST00016 | P001 | A002 | 2025-01-17 | C001 | Other | Other cost for Site Clearance | 3168.06 | 3276.9 | C001
CST00017 | P001 | A003 | 2025-01-24 | C001 | Material | Material cost for Excavation | 46411.87 | 45511.58 | C001
CST00018 | P001 | A003 | 2025-01-24 | C001 | Labour | Labour cost for Excavation (Idle Labour) | 27847.12 | 26998.36 | C001
CST00019 | P001 | A003 | 2025-01-24 | C001 | Equipment | Equipment cost for Excavation | 13923.56 | 13596.36 | C001
CST00020 | P001 | A003 | 2025-01-24 | C001 | Other | Other cost for Excavation | 4641.19 | 3982.79 | C001
CST00021 | P001 | A003 | 2025-01-31 | C001 | Material | Material cost for Excavation | 97350.45 | 88842.91 | C001
CST00022 | P001 | A003 | 2025-01-31 | C001 | Labour | Labour cost for Excavation (Idle Labour) | 58410.27 | 51372.9 | C001
CST00023 | P001 | A003 | 2025-01-31 | C001 | Equipment | Equipment cost for Excavation | 29205.13 | 26224.17 | C001
CST00024 | P001 | A003 | 2025-01-31 | C001 | Other | Other cost for Excavation | 9735.04 | 9002.07 | C001
CST00025 | P001 | A003 | 2025-02-07 | C001 | Material | Material cost for Excavation | 78927.87 | 67467.04 | C001
CST00026 | P001 | A003 | 2025-02-07 | C001 | Labour | Labour cost for Excavation (Idle Labour) | 47356.72 | 43007.32 | C001
CST00027 | P001 | A003 | 2025-02-07 | C001 | Equipment | Equipment cost for Excavation | 23678.36 | 23720.2 | C001
CST00028 | P001 | A003 | 2025-02-07 | C001 | Other | Other cost for Excavation | 7892.79 | 6855.13 | C001
CST00029 | P001 | A003 | 2025-02-14 | C001 | Material | Material cost for Excavation | 39809.82 | 38047.08 | C001
CST00030 | P001 | A003 | 2025-02-14 | C001 | Labour | Labour cost for Excavation | 23885.89 | 20379.92 | C001
CST00031 | P001 | A003 | 2025-02-14 | C001 | Equipment | Equipment cost for Excavation | 11942.94 | 11434.91 | C001
CST00032 | P001 | A003 | 2025-02-14 | C001 | Other | Other cost for Excavation | 3980.98 | 3623.5 | C001
CST00033 | P001 | A004 | 2025-01-31 | C002 | Material | Material cost for Foundation PCC | 194565.27 | 204793.02 | C002
CST00034 | P001 | A004 | 2025-01-31 | C002 | Labour | Labour cost for Foundation PCC | 116739.16 | 121513.26 | C002
CST00035 | P001 | A004 | 2025-01-31 | C002 | Equipment | Equipment cost for Foundation PCC | 58369.58 | 62474.52 | C002
CST00036 | P001 | A004 | 2025-01-31 | C002 | Other | Other cost for Foundation PCC | 19456.53 | 19119.79 | C002
CST00037 | P001 | A004 | 2025-02-07 | C002 | Material | Material cost for Foundation PCC | 142934.73 | 142390.58 | C002
CST00038 | P001 | A004 | 2025-02-07 | C002 | Labour | Labour cost for Foundation PCC | 85760.84 | 80341.56 | C002
CST00039 | P001 | A004 | 2025-02-07 | C002 | Equipment | Equipment cost for Foundation PCC | 42880.42 | 41697.26 | C002
CST00040 | P001 | A004 | 2025-02-07 | C002 | Other | Other cost for Foundation PCC | 14293.47 | 15118.57 | C002
CST00041 | P001 | A005 | 2025-02-07 | C002 | Material | Material cost for Footing RCC | 264993.23 | 241452.69 | C002
CST00042 | P001 | A005 | 2025-02-07 | C002 | Labour | Labour cost for Footing RCC (Idle Labour) | 158995.94 | 157514.54 | C002
CST00043 | P001 | A005 | 2025-02-07 | C002 | Equipment | Equipment cost for Footing RCC | 79497.97 | 80024.29 | C002
CST00044 | P001 | A005 | 2025-02-07 | C002 | Other | Other cost for Footing RCC | 26499.32 | 24020.74 | C002
CST00045 | P001 | A005 | 2025-02-14 | C002 | Material | Material cost for Footing RCC | 981766.81 | 843551.95 | C002
CST00046 | P001 | A005 | 2025-02-14 | C002 | Labour | Labour cost for Footing RCC (Idle Labour) | 589060.09 | 570319.39 | C002
CST00047 | P001 | A005 | 2025-02-14 | C002 | Equipment | Equipment cost for Footing RCC | 294530.04 | 265576.5 | C002
CST00048 | P001 | A005 | 2025-02-14 | C002 | Other | Other cost for Footing RCC | 98176.68 | 93979.51 | C002
CST00049 | P001 | A005 | 2025-02-21 | C002 | Material | Material cost for Footing RCC | 453239.96 | 434073.71 | C002
CST00050 | P001 | A005 | 2025-02-21 | C002 | Labour | Labour cost for Footing RCC | 271943.98 | 264217.78 | C002
CST00051 | P001 | A005 | 2025-02-21 | C002 | Equipment | Equipment cost for Footing RCC | 135971.99 | 138990.03 | C002
CST00052 | P001 | A005 | 2025-02-21 | C002 | Other | Other cost for Footing RCC | 45324 | 41425.54 | C002
CST00053 | P001 | A006 | 2025-02-21 | C005 | Material | Material cost for Basement Waterproofing | 112273.54 | 111333.2 | C005
CST00054 | P001 | A006 | 2025-02-21 | C005 | Labour | Labour cost for Basement Waterproofing | 67364.12 | 61187.75 | C005
CST00055 | P001 | A006 | 2025-02-21 | C005 | Equipment | Equipment cost for Basement Waterproofing | 33682.06 | 28383.25 | C005
CST00056 | P001 | A006 | 2025-02-21 | C005 | Other | Other cost for Basement Waterproofing | 11227.35 | 10686.33 | C005
CST00057 | P001 | A006 | 2025-02-28 | C005 | Material | Material cost for Basement Waterproofing | 67726.46 | 65832.97 | C005
CST00058 | P001 | A006 | 2025-02-28 | C005 | Labour | Labour cost for Basement Waterproofing | 40635.88 | 35354.82 | C005
CST00059 | P001 | A006 | 2025-02-28 | C005 | Equipment | Equipment cost for Basement Waterproofing | 20317.94 | 18637.6 | C005
CST00060 | P001 | A006 | 2025-02-28 | C005 | Other | Other cost for Basement Waterproofing | 6772.65 | 6046.92 | C005
CST00061 | P001 | A007 | 2025-02-28 | C001 | Material | Material cost for Earth Filling & Compaction | 12009.17 | 10716.55 | C001
CST00062 | P001 | A007 | 2025-02-28 | C001 | Labour | Labour cost for Earth Filling & Compaction (Idle Labour) | 7205.5 | 6470.05 | C001
CST00063 | P001 | A007 | 2025-02-28 | C001 | Equipment | Equipment cost for Earth Filling & Compaction | 3602.75 | 3243.12 | C001
CST00064 | P001 | A007 | 2025-02-28 | C001 | Other | Other cost for Earth Filling & Compaction | 1200.92 | 1117.66 | C001
CST00065 | P001 | A007 | 2025-03-07 | C001 | Material | Material cost for Earth Filling & Compaction | 52945.79 | 54586.77 | C001
CST00066 | P001 | A007 | 2025-03-07 | C001 | Labour | Labour cost for Earth Filling & Compaction (Idle Labour) | 31767.47 | 31042.21 | C001
CST00067 | P001 | A007 | 2025-03-07 | C001 | Equipment | Equipment cost for Earth Filling & Compaction | 15883.74 | 16323.02 | C001
CST00068 | P001 | A007 | 2025-03-07 | C001 | Other | Other cost for Earth Filling & Compaction | 5294.58 | 4626.82 | C001
CST00069 | P001 | A007 | 2025-03-14 | C001 | Material | Material cost for Earth Filling & Compaction | 43495.36 | 41578.42 | C001
CST00070 | P001 | A007 | 2025-03-14 | C001 | Labour | Labour cost for Earth Filling & Compaction (Idle Labour) | 26097.22 | 26130.91 | C001
CST00071 | P001 | A007 | 2025-03-14 | C001 | Equipment | Equipment cost for Earth Filling & Compaction | 13048.61 | 11729.52 | C001
CST00072 | P001 | A007 | 2025-03-14 | C001 | Other | Other cost for Earth Filling & Compaction | 4349.54 | 4126.01 | C001
CST00073 | P001 | A007 | 2025-03-21 | C001 | Material | Material cost for Earth Filling & Compaction | 16549.68 | 15164.7 | C001
CST00074 | P001 | A007 | 2025-03-21 | C001 | Labour | Labour cost for Earth Filling & Compaction | 9929.81 | 10281.21 | C001
CST00075 | P001 | A007 | 2025-03-21 | C001 | Equipment | Equipment cost for Earth Filling & Compaction | 4964.9 | 4464.55 | C001
CST00076 | P001 | A007 | 2025-03-21 | C001 | Other | Other cost for Earth Filling & Compaction | 1654.97 | 1541.75 | C001
CST00077 | P001 | A008 | 2025-03-14 | C002 | Material | Material cost for Plinth Beam | 421076.55 | 379932 | C002
CST00078 | P001 | A008 | 2025-03-14 | C002 | Labour | Labour cost for Plinth Beam (Idle Labour) | 252645.93 | 211314.73 | C002
CST00079 | P001 | A008 | 2025-03-14 | C002 | Equipment | Equipment cost for Plinth Beam | 126322.97 | 105794.87 | C002
CST00080 | P001 | A008 | 2025-03-14 | C002 | Other | Other cost for Plinth Beam | 42107.66 | 39221.83 | C002
CST00081 | P001 | A008 | 2025-03-21 | C002 | Material | Material cost for Plinth Beam | 118923.45 | 99469.69 | C002
CST00082 | P001 | A008 | 2025-03-21 | C002 | Labour | Labour cost for Plinth Beam | 71354.07 | 60886.31 | C002
CST00083 | P001 | A008 | 2025-03-21 | C002 | Equipment | Equipment cost for Plinth Beam | 35677.03 | 31729.97 | C002
CST00084 | P001 | A008 | 2025-03-21 | C002 | Other | Other cost for Plinth Beam | 11892.34 | 10884.57 | C002
CST00085 | P001 | A009 | 2025-03-21 | C002 | Material | Material cost for Columns - Ground | 307546.14 | 333060.14 | C002
CST00086 | P001 | A009 | 2025-03-21 | C002 | Labour | Labour cost for Columns - Ground | 184527.68 | 185462.7 | C002
CST00087 | P001 | A009 | 2025-03-21 | C002 | Equipment | Equipment cost for Columns - Ground | 92263.84 | 86323.46 | C002
CST00088 | P001 | A009 | 2025-03-21 | C002 | Other | Other cost for Columns - Ground | 30754.61 | 27702.11 | C002
CST00089 | P001 | A009 | 2025-03-28 | C002 | Material | Material cost for Columns - Ground | 52453.86 | 47361.05 | C002
CST00090 | P001 | A009 | 2025-03-28 | C002 | Labour | Labour cost for Columns - Ground | 31472.32 | 28888.77 | C002
CST00091 | P001 | A009 | 2025-03-28 | C002 | Equipment | Equipment cost for Columns - Ground | 15736.16 | 14660.08 | C002
CST00092 | P001 | A009 | 2025-03-28 | C002 | Other | Other cost for Columns - Ground | 5245.39 | 5008.88 | C002
CST00093 | P001 | A010 | 2025-03-28 | C002 | Material | Material cost for Beams & Slab - Ground | 238331.92 | 242579.51 | C002
CST00094 | P001 | A010 | 2025-03-28 | C002 | Labour | Labour cost for Beams & Slab - Ground (Idle Labour) | 142999.15 | 132027.35 | C002
CST00095 | P001 | A010 | 2025-03-28 | C002 | Equipment | Equipment cost for Beams & Slab - Ground | 71499.58 | 65347.44 | C002
CST00096 | P001 | A010 | 2025-03-28 | C002 | Other | Other cost for Beams & Slab - Ground | 23833.19 | 23706.34 | C002
CST00097 | P001 | A010 | 2025-04-04 | C002 | Material | Material cost for Beams & Slab - Ground | 751668.08 | 713350.95 | C002
CST00098 | P001 | A010 | 2025-04-04 | C002 | Labour | Labour cost for Beams & Slab - Ground | 451000.85 | 437105.24 | C002
CST00099 | P001 | A010 | 2025-04-04 | C002 | Equipment | Equipment cost for Beams & Slab - Ground | 225500.42 | 193649.2 | C002
CST00100 | P001 | A010 | 2025-04-04 | C002 | Other | Other cost for Beams & Slab - Ground | 75166.81 | 69665.66 | C002
CST00101 | P001 | A011 | 2025-04-04 | C002 | Material | Material cost for Columns - Floor 1 | 146357.77 | 167027.37 | C002
CST00102 | P001 | A011 | 2025-04-04 | C002 | Labour | Labour cost for Columns - Floor 1 | 87814.66 | 100686.9 | C002
CST00103 | P001 | A011 | 2025-04-04 | C002 | Equipment | Equipment cost for Columns - Floor 1 | 43907.33 | 50010.8 | C002
CST00104 | P001 | A011 | 2025-04-04 | C002 | Other | Other cost for Columns - Floor 1 | 14635.78 | 16518.81 | C002
CST00105 | P001 | A011 | 2025-04-11 | C002 | Material | Material cost for Columns - Floor 1 | 213642.23 | 234037.13 | C002
CST00106 | P001 | A011 | 2025-04-11 | C002 | Labour | Labour cost for Columns - Floor 1 | 128185.34 | 121465.18 | C002
CST00107 | P001 | A011 | 2025-04-11 | C002 | Equipment | Equipment cost for Columns - Floor 1 | 64092.67 | 65078.62 | C002
CST00108 | P001 | A011 | 2025-04-11 | C002 | Other | Other cost for Columns - Floor 1 | 21364.22 | 21504.12 | C002
CST00109 | P001 | A012 | 2025-04-11 | C002 | Material | Material cost for Beams & Slab - Floor 1 | 133921.1 | 130835.35 | C002
CST00110 | P001 | A012 | 2025-04-11 | C002 | Labour | Labour cost for Beams & Slab - Floor 1 (Idle Labour) | 80352.66 | 76135.39 | C002
CST00111 | P001 | A012 | 2025-04-11 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 1 | 40176.33 | 44006.73 | C002
CST00112 | P001 | A012 | 2025-04-11 | C002 | Other | Other cost for Beams & Slab - Floor 1 | 13392.11 | 13380.92 | C002
CST00113 | P001 | A012 | 2025-04-18 | C002 | Material | Material cost for Beams & Slab - Floor 1 | 856078.9 | 896383.85 | C002
CST00114 | P001 | A012 | 2025-04-18 | C002 | Labour | Labour cost for Beams & Slab - Floor 1 | 513647.34 | 514315.72 | C002
CST00115 | P001 | A012 | 2025-04-18 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 1 | 256823.67 | 278295.19 | C002
CST00116 | P001 | A012 | 2025-04-18 | C002 | Other | Other cost for Beams & Slab - Floor 1 | 85607.89 | 84974.52 | C002
CST00117 | P001 | A013 | 2025-04-25 | C002 | Material | Material cost for Columns - Floor 2 | 60525.26 | 58694.8 | C002
CST00118 | P001 | A013 | 2025-04-25 | C002 | Labour | Labour cost for Columns - Floor 2 (Idle Labour) | 36315.16 | 35818.02 | C002
CST00119 | P001 | A013 | 2025-04-25 | C002 | Equipment | Equipment cost for Columns - Floor 2 | 18157.58 | 18712.09 | C002
CST00120 | P001 | A013 | 2025-04-25 | C002 | Other | Other cost for Columns - Floor 2 | 6052.53 | 5564.6 | C002
CST00121 | P001 | A013 | 2025-05-02 | C002 | Material | Material cost for Columns - Floor 2 | 89620.52 | 83852.28 | C002
CST00122 | P001 | A013 | 2025-05-02 | C002 | Labour | Labour cost for Columns - Floor 2 (Idle Labour) | 53772.31 | 47212.9 | C002
CST00123 | P001 | A013 | 2025-05-02 | C002 | Equipment | Equipment cost for Columns - Floor 2 | 26886.16 | 23775.62 | C002
CST00124 | P001 | A013 | 2025-05-02 | C002 | Other | Other cost for Columns - Floor 2 | 8962.05 | 9086.02 | C002
CST00125 | P001 | A013 | 2025-05-09 | C002 | Material | Material cost for Columns - Floor 2 | 87968.78 | 78269.08 | C002
CST00126 | P001 | A013 | 2025-05-09 | C002 | Labour | Labour cost for Columns - Floor 2 (Idle Labour) | 52781.27 | 53397.11 | C002
CST00127 | P001 | A013 | 2025-05-09 | C002 | Equipment | Equipment cost for Columns - Floor 2 | 26390.63 | 22680.2 | C002
CST00128 | P001 | A013 | 2025-05-09 | C002 | Other | Other cost for Columns - Floor 2 | 8796.88 | 8302.48 | C002
CST00129 | P001 | A013 | 2025-05-16 | C002 | Material | Material cost for Columns - Floor 2 | 121885.43 | 115817.65 | C002
CST00130 | P001 | A013 | 2025-05-16 | C002 | Labour | Labour cost for Columns - Floor 2 | 73131.26 | 65394.48 | C002
CST00131 | P001 | A013 | 2025-05-16 | C002 | Equipment | Equipment cost for Columns - Floor 2 | 36565.63 | 32589.49 | C002
CST00132 | P001 | A013 | 2025-05-16 | C002 | Other | Other cost for Columns - Floor 2 | 12188.54 | 12316.53 | C002
CST00133 | P001 | A014 | 2025-05-02 | C002 | Material | Material cost for Beams & Slab - Floor 2 | 670585.01 | 619888.21 | C002
CST00134 | P001 | A014 | 2025-05-02 | C002 | Labour | Labour cost for Beams & Slab - Floor 2 | 402351.01 | 401069.69 | C002
CST00135 | P001 | A014 | 2025-05-02 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 2 | 201175.5 | 180497.71 | C002
CST00136 | P001 | A014 | 2025-05-02 | C002 | Other | Other cost for Beams & Slab - Floor 2 | 67058.5 | 67934.81 | C002
CST00137 | P001 | A014 | 2025-05-09 | C002 | Material | Material cost for Beams & Slab - Floor 2 | 319414.99 | 319188.71 | C002
CST00138 | P001 | A014 | 2025-05-09 | C002 | Labour | Labour cost for Beams & Slab - Floor 2 | 191648.99 | 176683.76 | C002
CST00139 | P001 | A014 | 2025-05-09 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 2 | 95824.5 | 94333.55 | C002
CST00140 | P001 | A014 | 2025-05-09 | C002 | Other | Other cost for Beams & Slab - Floor 2 | 31941.5 | 30967.74 | C002
CST00141 | P001 | A015 | 2025-05-09 | C002 | Material | Material cost for Columns - Floor 3 | 81508.76 | 73304.03 | C002
CST00142 | P001 | A015 | 2025-05-09 | C002 | Labour | Labour cost for Columns - Floor 3 (Idle Labour) | 48905.25 | 47836.49 | C002
CST00143 | P001 | A015 | 2025-05-09 | C002 | Equipment | Equipment cost for Columns - Floor 3 | 24452.63 | 22200.17 | C002
CST00144 | P001 | A015 | 2025-05-09 | C002 | Other | Other cost for Columns - Floor 3 | 8150.88 | 8514.35 | C002
CST00145 | P001 | A015 | 2025-05-16 | C002 | Material | Material cost for Columns - Floor 3 | 278491.24 | 248679.97 | C002
CST00146 | P001 | A015 | 2025-05-16 | C002 | Labour | Labour cost for Columns - Floor 3 | 167094.75 | 148861.36 | C002
CST00147 | P001 | A015 | 2025-05-16 | C002 | Equipment | Equipment cost for Columns - Floor 3 | 83547.37 | 75282.19 | C002
CST00148 | P001 | A015 | 2025-05-16 | C002 | Other | Other cost for Columns - Floor 3 | 27849.12 | 25326.36 | C002
CST00149 | P001 | A016 | 2025-05-16 | C002 | Material | Material cost for Beams & Slab - Floor 3 | 350108.31 | 366760.32 | C002
CST00150 | P001 | A016 | 2025-05-16 | C002 | Labour | Labour cost for Beams & Slab - Floor 3 | 210064.99 | 225077.72 | C002
CST00151 | P001 | A016 | 2025-05-16 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 3 | 105032.49 | 102093.46 | C002
CST00152 | P001 | A016 | 2025-05-16 | C002 | Other | Other cost for Beams & Slab - Floor 3 | 35010.83 | 38911.61 | C002
CST00153 | P001 | A016 | 2025-05-23 | C002 | Material | Material cost for Beams & Slab - Floor 3 | 639891.69 | 605283.52 | C002
CST00154 | P001 | A016 | 2025-05-23 | C002 | Labour | Labour cost for Beams & Slab - Floor 3 | 383935.01 | 393746.69 | C002
CST00155 | P001 | A016 | 2025-05-23 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 3 | 191967.51 | 212887.17 | C002
CST00156 | P001 | A016 | 2025-05-23 | C002 | Other | Other cost for Beams & Slab - Floor 3 | 63989.17 | 64341.82 | C002
CST00157 | P001 | A017 | 2025-05-23 | C002 | Material | Material cost for Columns - Floor 4 | 24033.94 | 22350.28 | C002
CST00158 | P001 | A017 | 2025-05-23 | C002 | Labour | Labour cost for Columns - Floor 4 | 14420.36 | 13020.99 | C002
CST00159 | P001 | A017 | 2025-05-23 | C002 | Equipment | Equipment cost for Columns - Floor 4 | 7210.18 | 6004.06 | C002
CST00160 | P001 | A017 | 2025-05-23 | C002 | Other | Other cost for Columns - Floor 4 | 2403.39 | 2146.23 | C002
CST00161 | P001 | A017 | 2025-05-30 | C002 | Material | Material cost for Columns - Floor 4 | 335966.06 | 326518.6 | C002
CST00162 | P001 | A017 | 2025-05-30 | C002 | Labour | Labour cost for Columns - Floor 4 | 201579.64 | 180278.01 | C002
CST00163 | P001 | A017 | 2025-05-30 | C002 | Equipment | Equipment cost for Columns - Floor 4 | 100789.82 | 100951.28 | C002
CST00164 | P001 | A017 | 2025-05-30 | C002 | Other | Other cost for Columns - Floor 4 | 33596.61 | 32270.08 | C002
CST00165 | P001 | A018 | 2025-06-06 | C002 | Material | Material cost for Beams & Slab - Floor 4 | 350159.29 | 360971.92 | C002
CST00166 | P001 | A018 | 2025-06-06 | C002 | Labour | Labour cost for Beams & Slab - Floor 4 (Idle Labour) | 210095.58 | 187386.77 | C002
CST00167 | P001 | A018 | 2025-06-06 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 4 | 105047.79 | 109591.33 | C002
CST00168 | P001 | A018 | 2025-06-06 | C002 | Other | Other cost for Beams & Slab - Floor 4 | 35015.93 | 31099.07 | C002
CST00169 | P001 | A018 | 2025-06-13 | C002 | Material | Material cost for Beams & Slab - Floor 4 | 639840.71 | 630412.52 | C002
CST00170 | P001 | A018 | 2025-06-13 | C002 | Labour | Labour cost for Beams & Slab - Floor 4 | 383904.42 | 367460.17 | C002
CST00171 | P001 | A018 | 2025-06-13 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 4 | 191952.21 | 192730.57 | C002
CST00172 | P001 | A018 | 2025-06-13 | C002 | Other | Other cost for Beams & Slab - Floor 4 | 63984.07 | 59007.7 | C002
CST00173 | P001 | A019 | 2025-06-13 | C002 | Material | Material cost for Columns - Floor 5 | 108321.76 | 95636.81 | C002
CST00174 | P001 | A019 | 2025-06-13 | C002 | Labour | Labour cost for Columns - Floor 5 (Idle Labour) | 64993.05 | 59092.64 | C002
CST00175 | P001 | A019 | 2025-06-13 | C002 | Equipment | Equipment cost for Columns - Floor 5 | 32496.53 | 28064.84 | C002
CST00176 | P001 | A019 | 2025-06-13 | C002 | Other | Other cost for Columns - Floor 5 | 10832.18 | 9903.62 | C002
CST00177 | P001 | A019 | 2025-06-20 | C002 | Material | Material cost for Columns - Floor 5 | 251678.24 | 244642.14 | C002
CST00178 | P001 | A019 | 2025-06-20 | C002 | Labour | Labour cost for Columns - Floor 5 | 151006.95 | 142130.62 | C002
CST00179 | P001 | A019 | 2025-06-20 | C002 | Equipment | Equipment cost for Columns - Floor 5 | 75503.47 | 64923.02 | C002
CST00180 | P001 | A019 | 2025-06-20 | C002 | Other | Other cost for Columns - Floor 5 | 25167.82 | 23815.65 | C002
CST00181 | P001 | A020 | 2025-06-20 | C002 | Material | Material cost for Beams & Slab - Floor 5 | 127904.8 | 135608 | C002
CST00182 | P001 | A020 | 2025-06-20 | C002 | Labour | Labour cost for Beams & Slab - Floor 5 (Idle Labour) | 76742.88 | 77892.02 | C002
CST00183 | P001 | A020 | 2025-06-20 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 5 | 38371.44 | 40440.54 | C002
CST00184 | P001 | A020 | 2025-06-20 | C002 | Other | Other cost for Beams & Slab - Floor 5 | 12790.48 | 13206.83 | C002
CST00185 | P001 | A020 | 2025-06-27 | C002 | Material | Material cost for Beams & Slab - Floor 5 | 862095.2 | 778609.77 | C002
CST00186 | P001 | A020 | 2025-06-27 | C002 | Labour | Labour cost for Beams & Slab - Floor 5 | 517257.12 | 498500.44 | C002
CST00187 | P001 | A020 | 2025-06-27 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 5 | 258628.56 | 231324.47 | C002
CST00188 | P001 | A020 | 2025-06-27 | C002 | Other | Other cost for Beams & Slab - Floor 5 | 86209.52 | 79278.86 | C002
CST00189 | P001 | A021 | 2025-06-27 | C002 | Material | Material cost for Columns - Floor 6 | 44514.65 | 44462.21 | C002
CST00190 | P001 | A021 | 2025-06-27 | C002 | Labour | Labour cost for Columns - Floor 6 (Idle Labour) | 26708.79 | 28360.97 | C002
CST00191 | P001 | A021 | 2025-06-27 | C002 | Equipment | Equipment cost for Columns - Floor 6 | 13354.39 | 13957.55 | C002
CST00192 | P001 | A021 | 2025-06-27 | C002 | Other | Other cost for Columns - Floor 6 | 4451.46 | 4285.87 | C002
CST00193 | P001 | A021 | 2025-07-04 | C002 | Material | Material cost for Columns - Floor 6 | 315485.35 | 339444.57 | C002
CST00194 | P001 | A021 | 2025-07-04 | C002 | Labour | Labour cost for Columns - Floor 6 | 189291.21 | 194631.44 | C002
CST00195 | P001 | A021 | 2025-07-04 | C002 | Equipment | Equipment cost for Columns - Floor 6 | 94645.61 | 96590.31 | C002
CST00196 | P001 | A021 | 2025-07-04 | C002 | Other | Other cost for Columns - Floor 6 | 31548.54 | 32609.93 | C002
CST00197 | P001 | A022 | 2025-07-11 | C002 | Material | Material cost for Beams & Slab - Floor 6 | 373632.43 | 357461.55 | C002
CST00198 | P001 | A022 | 2025-07-11 | C002 | Labour | Labour cost for Beams & Slab - Floor 6 (Idle Labour) | 224179.46 | 216125.22 | C002
CST00199 | P001 | A022 | 2025-07-11 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 6 | 112089.73 | 112026.28 | C002
CST00200 | P001 | A022 | 2025-07-11 | C002 | Other | Other cost for Beams & Slab - Floor 6 | 37363.24 | 39135.12 | C002
CST00201 | P001 | A022 | 2025-07-18 | C002 | Material | Material cost for Beams & Slab - Floor 6 | 616367.57 | 578728.18 | C002
CST00202 | P001 | A022 | 2025-07-18 | C002 | Labour | Labour cost for Beams & Slab - Floor 6 | 369820.54 | 344409.4 | C002
CST00203 | P001 | A022 | 2025-07-18 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 6 | 184910.27 | 181698.27 | C002
CST00204 | P001 | A022 | 2025-07-18 | C002 | Other | Other cost for Beams & Slab - Floor 6 | 61636.76 | 55565.63 | C002
CST00205 | P001 | A023 | 2025-07-18 | C002 | Material | Material cost for Columns - Floor 7 | 277173.8 | 271567.69 | C002
CST00206 | P001 | A023 | 2025-07-18 | C002 | Labour | Labour cost for Columns - Floor 7 | 166304.28 | 151766.64 | C002
CST00207 | P001 | A023 | 2025-07-18 | C002 | Equipment | Equipment cost for Columns - Floor 7 | 83152.14 | 75949.18 | C002
CST00208 | P001 | A023 | 2025-07-18 | C002 | Other | Other cost for Columns - Floor 7 | 27717.38 | 25967.8 | C002
CST00209 | P001 | A023 | 2025-07-25 | C002 | Material | Material cost for Columns - Floor 7 | 82826.2 | 79011.14 | C002
CST00210 | P001 | A023 | 2025-07-25 | C002 | Labour | Labour cost for Columns - Floor 7 | 49695.72 | 48231.15 | C002
CST00211 | P001 | A023 | 2025-07-25 | C002 | Equipment | Equipment cost for Columns - Floor 7 | 24847.86 | 26242.52 | C002
CST00212 | P001 | A023 | 2025-07-25 | C002 | Other | Other cost for Columns - Floor 7 | 8282.62 | 8848.15 | C002
CST00213 | P001 | A024 | 2025-07-25 | C002 | Material | Material cost for Beams & Slab - Floor 7 | 264476.96 | 272630.82 | C002
CST00214 | P001 | A024 | 2025-07-25 | C002 | Labour | Labour cost for Beams & Slab - Floor 7 (Idle Labour) | 158686.17 | 163310.3 | C002
CST00215 | P001 | A024 | 2025-07-25 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 7 | 79343.09 | 85539.78 | C002
CST00216 | P001 | A024 | 2025-07-25 | C002 | Other | Other cost for Beams & Slab - Floor 7 | 26447.7 | 26055.76 | C002
CST00217 | P001 | A024 | 2025-08-01 | C002 | Material | Material cost for Beams & Slab - Floor 7 | 725523.04 | 784404.6 | C002
CST00218 | P001 | A024 | 2025-08-01 | C002 | Labour | Labour cost for Beams & Slab - Floor 7 | 435313.83 | 487788.8 | C002
CST00219 | P001 | A024 | 2025-08-01 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 7 | 217656.91 | 235663.05 | C002
CST00220 | P001 | A024 | 2025-08-01 | C002 | Other | Other cost for Beams & Slab - Floor 7 | 72552.3 | 67320.85 | C002
CST00221 | P001 | A025 | 2025-08-01 | C002 | Material | Material cost for Columns - Floor 8 | 83779.33 | 75154.1 | C002
CST00222 | P001 | A025 | 2025-08-01 | C002 | Labour | Labour cost for Columns - Floor 8 (Idle Labour) | 50267.6 | 45148.05 | C002
CST00223 | P001 | A025 | 2025-08-01 | C002 | Equipment | Equipment cost for Columns - Floor 8 | 25133.8 | 25810.14 | C002
CST00224 | P001 | A025 | 2025-08-01 | C002 | Other | Other cost for Columns - Floor 8 | 8377.93 | 7320.89 | C002
CST00225 | P001 | A025 | 2025-08-08 | C002 | Material | Material cost for Columns - Floor 8 | 276220.67 | 268118.57 | C002
CST00226 | P001 | A025 | 2025-08-08 | C002 | Labour | Labour cost for Columns - Floor 8 | 165732.4 | 156749.06 | C002
CST00227 | P001 | A025 | 2025-08-08 | C002 | Equipment | Equipment cost for Columns - Floor 8 | 82866.2 | 78604.1 | C002
CST00228 | P001 | A025 | 2025-08-08 | C002 | Other | Other cost for Columns - Floor 8 | 27622.07 | 23820.38 | C002
CST00229 | P001 | A026 | 2025-08-08 | C002 | Material | Material cost for Beams & Slab - Floor 8 | 89515.64 | 81905.1 | C002
CST00230 | P001 | A026 | 2025-08-08 | C002 | Labour | Labour cost for Beams & Slab - Floor 8 (Idle Labour) | 53709.39 | 53916.72 | C002
CST00231 | P001 | A026 | 2025-08-08 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 8 | 26854.69 | 26903.42 | C002
CST00232 | P001 | A026 | 2025-08-08 | C002 | Other | Other cost for Beams & Slab - Floor 8 | 8951.56 | 8813.21 | C002
CST00233 | P001 | A026 | 2025-08-15 | C002 | Material | Material cost for Beams & Slab - Floor 8 | 900484.36 | 873106.06 | C002
CST00234 | P001 | A026 | 2025-08-15 | C002 | Labour | Labour cost for Beams & Slab - Floor 8 | 540290.61 | 454882.17 | C002
CST00235 | P001 | A026 | 2025-08-15 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 8 | 270145.31 | 243853.75 | C002
CST00236 | P001 | A026 | 2025-08-15 | C002 | Other | Other cost for Beams & Slab - Floor 8 | 90048.44 | 88411.24 | C002
CST00237 | P001 | A027 | 2025-08-22 | C002 | Material | Material cost for Columns - Floor 9 | 360000 | 330878.47 | C002
CST00238 | P001 | A027 | 2025-08-22 | C002 | Labour | Labour cost for Columns - Floor 9 | 216000 | 200779.56 | C002
CST00239 | P001 | A027 | 2025-08-22 | C002 | Equipment | Equipment cost for Columns - Floor 9 | 108000 | 110518.56 | C002
CST00240 | P001 | A027 | 2025-08-22 | C002 | Other | Other cost for Columns - Floor 9 | 36000 | 36143.91 | C002
CST00241 | P001 | A028 | 2025-08-29 | C002 | Material | Material cost for Beams & Slab - Floor 9 | 282288.42 | 272739.52 | C002
CST00242 | P001 | A028 | 2025-08-29 | C002 | Labour | Labour cost for Beams & Slab - Floor 9 (Idle Labour) | 169373.05 | 181418.65 | C002
CST00243 | P001 | A028 | 2025-08-29 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 9 | 84686.53 | 79691.02 | C002
CST00244 | P001 | A028 | 2025-08-29 | C002 | Other | Other cost for Beams & Slab - Floor 9 | 28228.84 | 30986.7 | C002
CST00245 | P001 | A028 | 2025-09-05 | C002 | Material | Material cost for Beams & Slab - Floor 9 | 707711.58 | 704374.28 | C002
CST00246 | P001 | A028 | 2025-09-05 | C002 | Labour | Labour cost for Beams & Slab - Floor 9 | 424626.95 | 395725.34 | C002
CST00247 | P001 | A028 | 2025-09-05 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 9 | 212313.47 | 231045.87 | C002
CST00248 | P001 | A028 | 2025-09-05 | C002 | Other | Other cost for Beams & Slab - Floor 9 | 70771.16 | 75936.35 | C002
CST00249 | P001 | A029 | 2025-09-05 | C002 | Material | Material cost for Columns - Floor 10 | 95222.1 | 89433.66 | C002
CST00250 | P001 | A029 | 2025-09-05 | C002 | Labour | Labour cost for Columns - Floor 10 (Idle Labour) | 57133.26 | 55272.77 | C002
CST00251 | P001 | A029 | 2025-09-05 | C002 | Equipment | Equipment cost for Columns - Floor 10 | 28566.63 | 24777.12 | C002
CST00252 | P001 | A029 | 2025-09-05 | C002 | Other | Other cost for Columns - Floor 10 | 9522.21 | 9554.53 | C002
CST00253 | P001 | A029 | 2025-09-12 | C002 | Material | Material cost for Columns - Floor 10 | 264777.9 | 234762.93 | C002
CST00254 | P001 | A029 | 2025-09-12 | C002 | Labour | Labour cost for Columns - Floor 10 | 158866.74 | 154912.7 | C002
CST00255 | P001 | A029 | 2025-09-12 | C002 | Equipment | Equipment cost for Columns - Floor 10 | 79433.37 | 77543.37 | C002
CST00256 | P001 | A029 | 2025-09-12 | C002 | Other | Other cost for Columns - Floor 10 | 26477.79 | 22612.14 | C002
CST00257 | P001 | A030 | 2025-09-19 | C002 | Material | Material cost for Beams & Slab - Floor 10 | 158642.96 | 160386.99 | C002
CST00258 | P001 | A030 | 2025-09-19 | C002 | Labour | Labour cost for Beams & Slab - Floor 10 (Idle Labour) | 95185.78 | 93141.98 | C002
CST00259 | P001 | A030 | 2025-09-19 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 10 | 47592.89 | 43772.28 | C002
CST00260 | P001 | A030 | 2025-09-19 | C002 | Other | Other cost for Beams & Slab - Floor 10 | 15864.3 | 16607.47 | C002
CST00261 | P001 | A030 | 2025-09-26 | C002 | Material | Material cost for Beams & Slab - Floor 10 | 415678.52 | 408986.54 | C002
CST00262 | P001 | A030 | 2025-09-26 | C002 | Labour | Labour cost for Beams & Slab - Floor 10 (Idle Labour) | 249407.11 | 275626.03 | C002
CST00263 | P001 | A030 | 2025-09-26 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 10 | 124703.56 | 137083.12 | C002
CST00264 | P001 | A030 | 2025-09-26 | C002 | Other | Other cost for Beams & Slab - Floor 10 | 41567.85 | 37895.23 | C002
CST00265 | P001 | A030 | 2025-10-03 | C002 | Material | Material cost for Beams & Slab - Floor 10 | 415678.52 | 417471.32 | C002
CST00266 | P001 | A030 | 2025-10-03 | C002 | Labour | Labour cost for Beams & Slab - Floor 10 | 249407.11 | 244745.34 | C002
CST00267 | P001 | A030 | 2025-10-03 | C002 | Equipment | Equipment cost for Beams & Slab - Floor 10 | 124703.56 | 126569.34 | C002
CST00268 | P001 | A030 | 2025-10-03 | C002 | Other | Other cost for Beams & Slab - Floor 10 | 41567.85 | 38472.52 | C002
CST00269 | P001 | A031 | 2025-05-30 | C003 | Material | Material cost for External Brickwork (G-F3) | 20759.43 | 20190.68 | C003
CST00270 | P001 | A031 | 2025-05-30 | C003 | Labour | Labour cost for External Brickwork (G-F3) (Idle Labour) | 12455.66 | 12074.33 | C003
CST00271 | P001 | A031 | 2025-05-30 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 6227.83 | 6690.07 | C003
CST00272 | P001 | A031 | 2025-05-30 | C003 | Other | Other cost for External Brickwork (G-F3) | 2075.94 | 2240.68 | C003
CST00273 | P001 | A031 | 2025-06-06 | C003 | Material | Material cost for External Brickwork (G-F3) | 109822.4 | 108163.11 | C003
CST00274 | P001 | A031 | 2025-06-06 | C003 | Labour | Labour cost for External Brickwork (G-F3) (Idle Labour) | 65893.44 | 70030.61 | C003
CST00275 | P001 | A031 | 2025-06-06 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 32946.72 | 33283.29 | C003
CST00276 | P001 | A031 | 2025-06-06 | C003 | Other | Other cost for External Brickwork (G-F3) | 10982.24 | 11056.96 | C003
CST00277 | P001 | A031 | 2025-06-13 | C003 | Material | Material cost for External Brickwork (G-F3) | 145156.91 | 159567.37 | C003
CST00278 | P001 | A031 | 2025-06-13 | C003 | Labour | Labour cost for External Brickwork (G-F3) (Idle Labour) | 87094.15 | 88543.82 | C003
CST00279 | P001 | A031 | 2025-06-13 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 43547.07 | 45323.95 | C003
CST00280 | P001 | A031 | 2025-06-13 | C003 | Other | Other cost for External Brickwork (G-F3) | 14515.69 | 16102.22 | C003
CST00281 | P001 | A031 | 2025-06-20 | C003 | Material | Material cost for External Brickwork (G-F3) | 161860.36 | 154770.62 | C003
CST00282 | P001 | A031 | 2025-06-20 | C003 | Labour | Labour cost for External Brickwork (G-F3) (Idle Labour) | 97116.22 | 98827.91 | C003
CST00283 | P001 | A031 | 2025-06-20 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 48558.11 | 55083.68 | C003
CST00284 | P001 | A031 | 2025-06-20 | C003 | Other | Other cost for External Brickwork (G-F3) | 16186.04 | 16511.53 | C003
CST00285 | P001 | A031 | 2025-06-27 | C003 | Material | Material cost for External Brickwork (G-F3) | 180215.72 | 200322.53 | C003
CST00286 | P001 | A031 | 2025-06-27 | C003 | Labour | Labour cost for External Brickwork (G-F3) (Idle Labour) | 108129.43 | 106476.33 | C003
CST00287 | P001 | A031 | 2025-06-27 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 54064.72 | 57603.6 | C003
CST00288 | P001 | A031 | 2025-06-27 | C003 | Other | Other cost for External Brickwork (G-F3) | 18021.57 | 18892.91 | C003
CST00289 | P001 | A031 | 2025-07-04 | C003 | Material | Material cost for External Brickwork (G-F3) | 232185.17 | 229413.41 | C003
CST00290 | P001 | A031 | 2025-07-04 | C003 | Labour | Labour cost for External Brickwork (G-F3) | 139311.1 | 143731.55 | C003
CST00291 | P001 | A031 | 2025-07-04 | C003 | Equipment | Equipment cost for External Brickwork (G-F3) | 69655.55 | 74810.93 | C003
CST00292 | P001 | A031 | 2025-07-04 | C003 | Other | Other cost for External Brickwork (G-F3) | 23218.52 | 22067.28 | C003
CST00293 | P001 | A032 | 2025-08-01 | C003 | Material | Material cost for External Brickwork (F4-F7) | 15696.99 | 15874.75 | C003
CST00294 | P001 | A032 | 2025-08-01 | C003 | Labour | Labour cost for External Brickwork (F4-F7) (Idle Labour) | 9418.2 | 9608.99 | C003
CST00295 | P001 | A032 | 2025-08-01 | C003 | Equipment | Equipment cost for External Brickwork (F4-F7) | 4709.1 | 4430.15 | C003
CST00296 | P001 | A032 | 2025-08-01 | C003 | Other | Other cost for External Brickwork (F4-F7) | 1569.7 | 1698.34 | C003
CST00297 | P001 | A032 | 2025-08-08 | C003 | Material | Material cost for External Brickwork (F4-F7) | 98107.82 | 98517.75 | C003
CST00298 | P001 | A032 | 2025-08-08 | C003 | Labour | Labour cost for External Brickwork (F4-F7) (Idle Labour) | 58864.69 | 58604.91 | C003
CST00299 | P001 | A032 | 2025-08-08 | C003 | Equipment | Equipment cost for External Brickwork (F4-F7) | 29432.35 | 32350.04 | C003
CST00300 | P001 | A032 | 2025-08-08 | C003 | Other | Other cost for External Brickwork (F4-F7) | 9810.78 | 9823.72 | C003
CST00301 | P001 | A032 | 2025-08-15 | C003 | Material | Material cost for External Brickwork (F4-F7) | 173923.17 | 182372.1 | C003
CST00302 | P001 | A032 | 2025-08-15 | C003 | Labour | Labour cost for External Brickwork (F4-F7) (Idle Labour) | 104353.9 | 100307.27 | C003
CST00303 | P001 | A032 | 2025-08-15 | C003 | Equipment | Equipment cost for External Brickwork (F4-F7) | 52176.95 | 56666.31 | C003
CST00304 | P001 | A032 | 2025-08-15 | C003 | Other | Other cost for External Brickwork (F4-F7) | 17392.32 | 18735.09 | C003
CST00305 | P001 | A032 | 2025-08-22 | C003 | Material | Material cost for External Brickwork (F4-F7) | 128966.47 | 139072.07 | C003
CST00306 | P001 | A032 | 2025-08-22 | C003 | Labour | Labour cost for External Brickwork (F4-F7) (Idle Labour) | 77379.88 | 82706.73 | C003
CST00307 | P001 | A032 | 2025-08-22 | C003 | Equipment | Equipment cost for External Brickwork (F4-F7) | 38689.94 | 38192.07 | C003
CST00308 | P001 | A032 | 2025-08-22 | C003 | Other | Other cost for External Brickwork (F4-F7) | 12896.65 | 12511.3 | C003
CST00309 | P001 | A032 | 2025-08-29 | C003 | Material | Material cost for External Brickwork (F4-F7) | 433305.54 | 451084.21 | C003
CST00310 | P001 | A032 | 2025-08-29 | C003 | Labour | Labour cost for External Brickwork (F4-F7) | 259983.33 | 262039.22 | C003
CST00311 | P001 | A032 | 2025-08-29 | C003 | Equipment | Equipment cost for External Brickwork (F4-F7) | 129991.66 | 139866.33 | C003
CST00312 | P001 | A032 | 2025-08-29 | C003 | Other | Other cost for External Brickwork (F4-F7) | 43330.55 | 46580.41 | C003
CST00313 | P001 | A033 | 2025-09-19 | C003 | Material | Material cost for External Brickwork (F8-F10) | 14176.51 | 13301.12 | C003
CST00314 | P001 | A033 | 2025-09-19 | C003 | Labour | Labour cost for External Brickwork (F8-F10) | 8505.91 | 9382.93 | C003
CST00315 | P001 | A033 | 2025-09-19 | C003 | Equipment | Equipment cost for External Brickwork (F8-F10) | 4252.95 | 4063.33 | C003
CST00316 | P001 | A033 | 2025-09-19 | C003 | Other | Other cost for External Brickwork (F8-F10) | 1417.65 | 1372.82 | C003
CST00317 | P001 | A033 | 2025-09-26 | C003 | Material | Material cost for External Brickwork (F8-F10) | 100971.89 | 109946.79 | C003
CST00318 | P001 | A033 | 2025-09-26 | C003 | Labour | Labour cost for External Brickwork (F8-F10) (Idle Labour) | 60583.13 | 65899.95 | C003
CST00319 | P001 | A033 | 2025-09-26 | C003 | Equipment | Equipment cost for External Brickwork (F8-F10) | 30291.57 | 28891.28 | C003
CST00320 | P001 | A033 | 2025-09-26 | C003 | Other | Other cost for External Brickwork (F8-F10) | 10097.19 | 10263.46 | C003
CST00321 | P001 | A033 | 2025-10-03 | C003 | Material | Material cost for External Brickwork (F8-F10) | 158372.14 | 151035.57 | C003
CST00322 | P001 | A033 | 2025-10-03 | C003 | Labour | Labour cost for External Brickwork (F8-F10) (Idle Labour) | 95023.28 | 95606.07 | C003
CST00323 | P001 | A033 | 2025-10-03 | C003 | Equipment | Equipment cost for External Brickwork (F8-F10) | 47511.64 | 49810.87 | C003
CST00324 | P001 | A033 | 2025-10-03 | C003 | Other | Other cost for External Brickwork (F8-F10) | 15837.21 | 15227.84 | C003
CST00325 | P001 | A033 | 2025-10-10 | C003 | Material | Material cost for External Brickwork (F8-F10) | 363979.46 | 353286.71 | C003
CST00326 | P001 | A033 | 2025-10-10 | C003 | Labour | Labour cost for External Brickwork (F8-F10) | 218387.68 | 203455.83 | C003
CST00327 | P001 | A033 | 2025-10-10 | C003 | Equipment | Equipment cost for External Brickwork (F8-F10) | 109193.84 | 112587.51 | C003
CST00328 | P001 | A033 | 2025-10-10 | C003 | Other | Other cost for External Brickwork (F8-F10) | 36397.95 | 34668.56 | C003
CST00329 | P001 | A034 | 2025-06-27 | C004 | Material | Material cost for Internal Plastering (G-F5) | 34380.12 | 33881.21 | C004
CST00330 | P001 | A034 | 2025-06-27 | C004 | Labour | Labour cost for Internal Plastering (G-F5) (Idle Labour) | 20628.07 | 18998.06 | C004
CST00331 | P001 | A034 | 2025-06-27 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 10314.04 | 10496.17 | C004
CST00332 | P001 | A034 | 2025-06-27 | C004 | Other | Other cost for Internal Plastering (G-F5) | 3438.01 | 3308.7 | C004
CST00333 | P001 | A034 | 2025-07-04 | C004 | Material | Material cost for Internal Plastering (G-F5) | 63898.67 | 67396.06 | C004
CST00334 | P001 | A034 | 2025-07-04 | C004 | Labour | Labour cost for Internal Plastering (G-F5) (Idle Labour) | 38339.2 | 35172.49 | C004
CST00335 | P001 | A034 | 2025-07-04 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 19169.6 | 16796.12 | C004
CST00336 | P001 | A034 | 2025-07-04 | C004 | Other | Other cost for Internal Plastering (G-F5) | 6389.87 | 6537.67 | C004
CST00337 | P001 | A034 | 2025-07-11 | C004 | Material | Material cost for Internal Plastering (G-F5) | 97246.23 | 102153.08 | C004
CST00338 | P001 | A034 | 2025-07-11 | C004 | Labour | Labour cost for Internal Plastering (G-F5) (Idle Labour) | 58347.74 | 53575.39 | C004
CST00339 | P001 | A034 | 2025-07-11 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 29173.87 | 29398.64 | C004
CST00340 | P001 | A034 | 2025-07-11 | C004 | Other | Other cost for Internal Plastering (G-F5) | 9724.62 | 9124.57 | C004
CST00341 | P001 | A034 | 2025-07-18 | C004 | Material | Material cost for Internal Plastering (G-F5) | 99732.16 | 88413.86 | C004
CST00342 | P001 | A034 | 2025-07-18 | C004 | Labour | Labour cost for Internal Plastering (G-F5) (Idle Labour) | 59839.3 | 62353.25 | C004
CST00343 | P001 | A034 | 2025-07-18 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 29919.65 | 28707.53 | C004
CST00344 | P001 | A034 | 2025-07-18 | C004 | Other | Other cost for Internal Plastering (G-F5) | 9973.22 | 9734.86 | C004
CST00345 | P001 | A034 | 2025-07-25 | C004 | Material | Material cost for Internal Plastering (G-F5) | 91156.23 | 92463.46 | C004
CST00346 | P001 | A034 | 2025-07-25 | C004 | Labour | Labour cost for Internal Plastering (G-F5) (Idle Labour) | 54693.74 | 53467.71 | C004
CST00347 | P001 | A034 | 2025-07-25 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 27346.87 | 26672.58 | C004
CST00348 | P001 | A034 | 2025-07-25 | C004 | Other | Other cost for Internal Plastering (G-F5) | 9115.62 | 9615.61 | C004
CST00349 | P001 | A034 | 2025-08-01 | C004 | Material | Material cost for Internal Plastering (G-F5) | 176086.57 | 182066.53 | C004
CST00350 | P001 | A034 | 2025-08-01 | C004 | Labour | Labour cost for Internal Plastering (G-F5) | 105651.94 | 93074.91 | C004
CST00351 | P001 | A034 | 2025-08-01 | C004 | Equipment | Equipment cost for Internal Plastering (G-F5) | 52825.97 | 50777.15 | C004
CST00352 | P001 | A034 | 2025-08-01 | C004 | Other | Other cost for Internal Plastering (G-F5) | 17608.66 | 16075.45 | C004
CST00353 | P001 | A035 | 2025-10-10 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 27632.55 | 22766.13 | C004
CST00354 | P001 | A035 | 2025-10-10 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) | 16579.53 | 13935.06 | C004
CST00355 | P001 | A035 | 2025-10-10 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 8289.77 | 7746.57 | C004
CST00356 | P001 | A035 | 2025-10-10 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 2763.26 | 2589.71 | C004
CST00357 | P001 | A035 | 2025-10-17 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 106078.37 | 98029.95 | C004
CST00358 | P001 | A035 | 2025-10-17 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) | 63647.02 | 56792.77 | C004
CST00359 | P001 | A035 | 2025-10-17 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 31823.51 | 26837.47 | C004
CST00360 | P001 | A035 | 2025-10-17 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 10607.84 | 10481.14 | C004
CST00361 | P001 | A035 | 2025-10-24 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 80037.97 | 75588.39 | C004
CST00362 | P001 | A035 | 2025-10-24 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) (Idle Labour) | 48022.78 | 47970.7 | C004
CST00363 | P001 | A035 | 2025-10-24 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 24011.39 | 20373.81 | C004
CST00364 | P001 | A035 | 2025-10-24 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 8003.8 | 7324.93 | C004
CST00365 | P001 | A035 | 2025-10-31 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 62254.91 | 55993.43 | C004
CST00366 | P001 | A035 | 2025-10-31 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) (Idle Labour) | 37352.94 | 35560.56 | C004
CST00367 | P001 | A035 | 2025-10-31 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 18676.47 | 17945.82 | C004
CST00368 | P001 | A035 | 2025-10-31 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 6225.49 | 5469.6 | C004
CST00369 | P001 | A035 | 2025-11-07 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 181778.98 | 167528.12 | C004
CST00370 | P001 | A035 | 2025-11-07 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) | 109067.39 | 107377.36 | C004
CST00371 | P001 | A035 | 2025-11-07 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 54533.69 | 49145.06 | C004
CST00372 | P001 | A035 | 2025-11-07 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 18177.9 | 15018.49 | C004
CST00373 | P001 | A035 | 2025-11-14 | C004 | Material | Material cost for Internal Plastering (F6-F10) | 42217.23 | 37062.12 | C004
CST00374 | P001 | A035 | 2025-11-14 | C004 | Labour | Labour cost for Internal Plastering (F6-F10) | 25330.34 | 24363.33 | C004
CST00375 | P001 | A035 | 2025-11-14 | C004 | Equipment | Equipment cost for Internal Plastering (F6-F10) | 12665.17 | 10509.2 | C004
CST00376 | P001 | A035 | 2025-11-14 | C004 | Other | Other cost for Internal Plastering (F6-F10) | 4221.72 | 4107.26 | C004
CST00377 | P001 | A036 | 2025-06-27 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 8906.13 | 12064.38 | C006
CST00378 | P001 | A036 | 2025-06-27 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 5343.68 | 7227.3 | C006
CST00379 | P001 | A036 | 2025-06-27 | C006 | Equipment | Equipment cost for Electrical Rough-in | 2671.84 | 3332.28 | C006
CST00380 | P001 | A036 | 2025-06-27 | C006 | Other | Other cost for Electrical Rough-in | 890.61 | 1061.88 | C006
CST00381 | P001 | A036 | 2025-07-04 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 19415.6 | 24905.19 | C006
CST00382 | P001 | A036 | 2025-07-04 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 11649.36 | 13976.19 | C006
CST00383 | P001 | A036 | 2025-07-04 | C006 | Equipment | Equipment cost for Electrical Rough-in | 5824.68 | 7099.12 | C006
CST00384 | P001 | A036 | 2025-07-04 | C006 | Other | Other cost for Electrical Rough-in | 1941.56 | 2552.1 | C006
CST00385 | P001 | A036 | 2025-07-11 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 32324.15 | 40701.48 | C006
CST00386 | P001 | A036 | 2025-07-11 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 19394.49 | 24822.77 | C006
CST00387 | P001 | A036 | 2025-07-11 | C006 | Equipment | Equipment cost for Electrical Rough-in | 9697.24 | 11886.34 | C006
CST00388 | P001 | A036 | 2025-07-11 | C006 | Other | Other cost for Electrical Rough-in | 3232.41 | 4309.5 | C006
CST00389 | P001 | A036 | 2025-07-18 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 28399.43 | 33809.84 | C006
CST00390 | P001 | A036 | 2025-07-18 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 17039.66 | 22582.62 | C006
CST00391 | P001 | A036 | 2025-07-18 | C006 | Equipment | Equipment cost for Electrical Rough-in | 8519.83 | 10813.76 | C006
CST00392 | P001 | A036 | 2025-07-18 | C006 | Other | Other cost for Electrical Rough-in | 2839.94 | 3938.59 | C006
CST00393 | P001 | A036 | 2025-07-25 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 42095.22 | 51777.17 | C006
CST00394 | P001 | A036 | 2025-07-25 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 25257.13 | 33792.89 | C006
CST00395 | P001 | A036 | 2025-07-25 | C006 | Equipment | Equipment cost for Electrical Rough-in | 12628.57 | 15758.1 | C006
CST00396 | P001 | A036 | 2025-07-25 | C006 | Other | Other cost for Electrical Rough-in | 4209.52 | 4826.05 | C006
CST00397 | P001 | A036 | 2025-08-01 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 36383.42 | 50271.21 | C006
CST00398 | P001 | A036 | 2025-08-01 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 21830.05 | 29055.53 | C006
CST00399 | P001 | A036 | 2025-08-01 | C006 | Equipment | Equipment cost for Electrical Rough-in | 10915.02 | 14173.48 | C006
CST00400 | P001 | A036 | 2025-08-01 | C006 | Other | Other cost for Electrical Rough-in | 3638.34 | 4993.64 | C006
CST00401 | P001 | A036 | 2025-08-08 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 22702.8 | 28007.77 | C006
CST00402 | P001 | A036 | 2025-08-08 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 13621.68 | 15872.59 | C006
CST00403 | P001 | A036 | 2025-08-08 | C006 | Equipment | Equipment cost for Electrical Rough-in | 6810.84 | 7743.13 | C006
CST00404 | P001 | A036 | 2025-08-08 | C006 | Other | Other cost for Electrical Rough-in | 2270.28 | 2990.26 | C006
CST00405 | P001 | A036 | 2025-08-15 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 18098.95 | 24044.13 | C006
CST00406 | P001 | A036 | 2025-08-15 | C006 | Labour | Labour cost for Electrical Rough-in (Idle Labour) | 10859.37 | 13528.88 | C006
CST00407 | P001 | A036 | 2025-08-15 | C006 | Equipment | Equipment cost for Electrical Rough-in | 5429.69 | 6706.13 | C006
CST00408 | P001 | A036 | 2025-08-15 | C006 | Other | Other cost for Electrical Rough-in | 1809.9 | 2356.67 | C006
CST00409 | P001 | A036 | 2025-08-22 | C006 | Material | Material cost for Electrical Rough-in (Price Hike) | 91674.3 | 116925.54 | C006
CST00410 | P001 | A036 | 2025-08-22 | C006 | Labour | Labour cost for Electrical Rough-in | 55004.58 | 64162.23 | C006
CST00411 | P001 | A036 | 2025-08-22 | C006 | Equipment | Equipment cost for Electrical Rough-in | 27502.29 | 31260.88 | C006
CST00412 | P001 | A036 | 2025-08-22 | C006 | Other | Other cost for Electrical Rough-in | 9167.43 | 11788.74 | C006
CST00413 | P001 | A037 | 2025-06-27 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 8379.63 | 9846.59 | C007
CST00414 | P001 | A037 | 2025-06-27 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 5027.78 | 6389.88 | C007
CST00415 | P001 | A037 | 2025-06-27 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 2513.89 | 3428.21 | C007
CST00416 | P001 | A037 | 2025-06-27 | C007 | Other | Other cost for Plumbing Rough-in | 837.96 | 1018.14 | C007
CST00417 | P001 | A037 | 2025-07-04 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 28161.03 | 36214.62 | C007
CST00418 | P001 | A037 | 2025-07-04 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 16896.62 | 20189.58 | C007
CST00419 | P001 | A037 | 2025-07-04 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 8448.31 | 10269.79 | C007
CST00420 | P001 | A037 | 2025-07-04 | C007 | Other | Other cost for Plumbing Rough-in | 2816.1 | 3648.75 | C007
CST00421 | P001 | A037 | 2025-07-11 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 27412.68 | 34551.3 | C007
CST00422 | P001 | A037 | 2025-07-11 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 16447.61 | 19597.75 | C007
CST00423 | P001 | A037 | 2025-07-11 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 8223.8 | 11080.71 | C007
CST00424 | P001 | A037 | 2025-07-11 | C007 | Other | Other cost for Plumbing Rough-in | 2741.27 | 3138.22 | C007
CST00425 | P001 | A037 | 2025-07-18 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 42858.21 | 57961.01 | C007
CST00426 | P001 | A037 | 2025-07-18 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 25714.93 | 32494.9 | C007
CST00427 | P001 | A037 | 2025-07-18 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 12857.46 | 16221.32 | C007
CST00428 | P001 | A037 | 2025-07-18 | C007 | Other | Other cost for Plumbing Rough-in | 4285.82 | 5895.19 | C007
CST00429 | P001 | A037 | 2025-07-25 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 26057.53 | 30889.48 | C007
CST00430 | P001 | A037 | 2025-07-25 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 15634.52 | 21369.62 | C007
CST00431 | P001 | A037 | 2025-07-25 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 7817.26 | 10719.72 | C007
CST00432 | P001 | A037 | 2025-07-25 | C007 | Other | Other cost for Plumbing Rough-in | 2605.75 | 3379.2 | C007
CST00433 | P001 | A037 | 2025-08-01 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 49428.94 | 65427.2 | C007
CST00434 | P001 | A037 | 2025-08-01 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 29657.37 | 36263.82 | C007
CST00435 | P001 | A037 | 2025-08-01 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 14828.68 | 20097.18 | C007
CST00436 | P001 | A037 | 2025-08-01 | C007 | Other | Other cost for Plumbing Rough-in | 4942.89 | 6654.12 | C007
CST00437 | P001 | A037 | 2025-08-08 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 58850.99 | 70123.67 | C007
CST00438 | P001 | A037 | 2025-08-08 | C007 | Labour | Labour cost for Plumbing Rough-in (Idle Labour) | 35310.59 | 44556.57 | C007
CST00439 | P001 | A037 | 2025-08-08 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 17655.3 | 20641.97 | C007
CST00440 | P001 | A037 | 2025-08-08 | C007 | Other | Other cost for Plumbing Rough-in | 5885.1 | 7587.04 | C007
CST00441 | P001 | A037 | 2025-08-15 | C007 | Material | Material cost for Plumbing Rough-in (Price Hike) | 58850.99 | 73344.67 | C007
CST00442 | P001 | A037 | 2025-08-15 | C007 | Labour | Labour cost for Plumbing Rough-in | 35310.59 | 45085.31 | C007
CST00443 | P001 | A037 | 2025-08-15 | C007 | Equipment | Equipment cost for Plumbing Rough-in | 17655.3 | 22090.52 | C007
CST00444 | P001 | A037 | 2025-08-15 | C007 | Other | Other cost for Plumbing Rough-in | 5885.1 | 6829.31 | C007
CST00445 | P001 | A038 | 2025-08-08 | C008 | Material | Material cost for Floor Tiling (G-F5) | 68919.69 | 70115.24 | C008
CST00446 | P001 | A038 | 2025-08-08 | C008 | Labour | Labour cost for Floor Tiling (G-F5) (Idle Labour) | 41351.81 | 39803.71 | C008
CST00447 | P001 | A038 | 2025-08-08 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 20675.91 | 19692.9 | C008
CST00448 | P001 | A038 | 2025-08-08 | C008 | Other | Other cost for Floor Tiling (G-F5) | 6891.97 | 7510.83 | C008
CST00449 | P001 | A038 | 2025-08-15 | C008 | Material | Material cost for Floor Tiling (G-F5) | 203871.65 | 210940.41 | C008
CST00450 | P001 | A038 | 2025-08-15 | C008 | Labour | Labour cost for Floor Tiling (G-F5) (Idle Labour) | 122322.99 | 112942.41 | C008
CST00451 | P001 | A038 | 2025-08-15 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 61161.5 | 65231.01 | C008
CST00452 | P001 | A038 | 2025-08-15 | C008 | Other | Other cost for Floor Tiling (G-F5) | 20387.17 | 21502.88 | C008
CST00453 | P001 | A038 | 2025-08-22 | C008 | Material | Material cost for Floor Tiling (G-F5) | 236924.9 | 239807.85 | C008
CST00454 | P001 | A038 | 2025-08-22 | C008 | Labour | Labour cost for Floor Tiling (G-F5) (Idle Labour) | 142154.94 | 147867.84 | C008
CST00455 | P001 | A038 | 2025-08-22 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 71077.47 | 68694.05 | C008
CST00456 | P001 | A038 | 2025-08-22 | C008 | Other | Other cost for Floor Tiling (G-F5) | 23692.49 | 23651.54 | C008
CST00457 | P001 | A038 | 2025-08-29 | C008 | Material | Material cost for Floor Tiling (G-F5) | 305240.96 | 327598.84 | C008
CST00458 | P001 | A038 | 2025-08-29 | C008 | Labour | Labour cost for Floor Tiling (G-F5) (Idle Labour) | 183144.58 | 171890.4 | C008
CST00459 | P001 | A038 | 2025-08-29 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 91572.29 | 96539.67 | C008
CST00460 | P001 | A038 | 2025-08-29 | C008 | Other | Other cost for Floor Tiling (G-F5) | 30524.1 | 33692.97 | C008
CST00461 | P001 | A038 | 2025-09-05 | C008 | Material | Material cost for Floor Tiling (G-F5) | 222419.38 | 204843.43 | C008
CST00462 | P001 | A038 | 2025-09-05 | C008 | Labour | Labour cost for Floor Tiling (G-F5) (Idle Labour) | 133451.63 | 140558.61 | C008
CST00463 | P001 | A038 | 2025-09-05 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 66725.81 | 70732.25 | C008
CST00464 | P001 | A038 | 2025-09-05 | C008 | Other | Other cost for Floor Tiling (G-F5) | 22241.94 | 21887.36 | C008
CST00465 | P001 | A038 | 2025-09-12 | C008 | Material | Material cost for Floor Tiling (G-F5) | 762623.41 | 811176.35 | C008
CST00466 | P001 | A038 | 2025-09-12 | C008 | Labour | Labour cost for Floor Tiling (G-F5) | 457574.05 | 489537.67 | C008
CST00467 | P001 | A038 | 2025-09-12 | C008 | Equipment | Equipment cost for Floor Tiling (G-F5) | 228787.02 | 250342.12 | C008
CST00468 | P001 | A038 | 2025-09-12 | C008 | Other | Other cost for Floor Tiling (G-F5) | 76262.34 | 80397.51 | C008
CST00469 | P001 | A039 | 2025-11-21 | C008 | Material | Material cost for Floor Tiling (F6-F10) | 405392.7 | 410028.46 | C008
CST00470 | P001 | A039 | 2025-11-21 | C008 | Labour | Labour cost for Floor Tiling (F6-F10) (Idle Labour) | 243235.62 | 262824.19 | C008
CST00471 | P001 | A039 | 2025-11-21 | C008 | Equipment | Equipment cost for Floor Tiling (F6-F10) | 121617.81 | 128383.93 | C008
CST00472 | P001 | A039 | 2025-11-21 | C008 | Other | Other cost for Floor Tiling (F6-F10) | 40539.27 | 41347.27 | C008
CST00473 | P001 | A039 | 2025-11-28 | C008 | Material | Material cost for Floor Tiling (F6-F10) | 490655.58 | 472478.06 | C008
CST00474 | P001 | A039 | 2025-11-28 | C008 | Labour | Labour cost for Floor Tiling (F6-F10) (Idle Labour) | 294393.35 | 285941.09 | C008
CST00475 | P001 | A039 | 2025-11-28 | C008 | Equipment | Equipment cost for Floor Tiling (F6-F10) | 147196.67 | 148547.17 | C008
CST00476 | P001 | A039 | 2025-11-28 | C008 | Other | Other cost for Floor Tiling (F6-F10) | 49065.56 | 48850.42 | C008
CST00477 | P001 | A039 | 2025-12-05 | C008 | Material | Material cost for Floor Tiling (F6-F10) | 306604.74 | 280881.27 | C008
CST00478 | P001 | A039 | 2025-12-05 | C008 | Labour | Labour cost for Floor Tiling (F6-F10) (Idle Labour) | 183962.85 | 182993.58 | C008
CST00479 | P001 | A039 | 2025-12-05 | C008 | Equipment | Equipment cost for Floor Tiling (F6-F10) | 91981.42 | 86831.99 | C008
CST00480 | P001 | A039 | 2025-12-05 | C008 | Other | Other cost for Floor Tiling (F6-F10) | 30660.47 | 30648.69 | C008
CST00481 | P001 | A039 | 2025-12-12 | C008 | Material | Material cost for Floor Tiling (F6-F10) | 597346.98 | 534514.81 | C008
CST00482 | P001 | A039 | 2025-12-12 | C008 | Labour | Labour cost for Floor Tiling (F6-F10) | 358408.19 | 379197.68 | C008
CST00483 | P001 | A039 | 2025-12-12 | C008 | Equipment | Equipment cost for Floor Tiling (F6-F10) | 179204.09 | 168836.13 | C008
CST00484 | P001 | A039 | 2025-12-12 | C008 | Other | Other cost for Floor Tiling (F6-F10) | 59734.7 | 54438.63 | C008
CST00485 | P001 | A040 | 2025-09-05 | C004 | Material | Material cost for Internal Painting | 41446.63 | 41904.33 | C004
CST00486 | P001 | A040 | 2025-09-05 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 24867.98 | 25840.89 | C004
CST00487 | P001 | A040 | 2025-09-05 | C004 | Equipment | Equipment cost for Internal Painting | 12433.99 | 12596.65 | C004
CST00488 | P001 | A040 | 2025-09-05 | C004 | Other | Other cost for Internal Painting | 4144.66 | 4613.55 | C004
CST00489 | P001 | A040 | 2025-09-12 | C004 | Material | Material cost for Internal Painting | 71016.48 | 70061.45 | C004
CST00490 | P001 | A040 | 2025-09-12 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 42609.89 | 46362.29 | C004
CST00491 | P001 | A040 | 2025-09-12 | C004 | Equipment | Equipment cost for Internal Painting | 21304.94 | 20264.22 | C004
CST00492 | P001 | A040 | 2025-09-12 | C004 | Other | Other cost for Internal Painting | 7101.65 | 6863.83 | C004
CST00493 | P001 | A040 | 2025-09-19 | C004 | Material | Material cost for Internal Painting | 123440.19 | 117633.51 | C004
CST00494 | P001 | A040 | 2025-09-19 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 74064.12 | 79657.62 | C004
CST00495 | P001 | A040 | 2025-09-19 | C004 | Equipment | Equipment cost for Internal Painting | 37032.06 | 39366.68 | C004
CST00496 | P001 | A040 | 2025-09-19 | C004 | Other | Other cost for Internal Painting | 12344.02 | 12457.03 | C004
CST00497 | P001 | A040 | 2025-09-26 | C004 | Material | Material cost for Internal Painting | 72278.74 | 76924.18 | C004
CST00498 | P001 | A040 | 2025-09-26 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 43367.24 | 41887.86 | C004
CST00499 | P001 | A040 | 2025-09-26 | C004 | Equipment | Equipment cost for Internal Painting | 21683.62 | 21386.32 | C004
CST00500 | P001 | A040 | 2025-09-26 | C004 | Other | Other cost for Internal Painting | 7227.87 | 7417.99 | C004
CST00501 | P001 | A040 | 2025-10-03 | C004 | Material | Material cost for Internal Painting | 160045.72 | 174348.39 | C004
CST00502 | P001 | A040 | 2025-10-03 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 96027.43 | 100172.39 | C004
CST00503 | P001 | A040 | 2025-10-03 | C004 | Equipment | Equipment cost for Internal Painting | 48013.72 | 52892.13 | C004
CST00504 | P001 | A040 | 2025-10-03 | C004 | Other | Other cost for Internal Painting | 16004.57 | 15984.9 | C004
CST00505 | P001 | A040 | 2025-10-10 | C004 | Material | Material cost for Internal Painting | 117943.99 | 109619.53 | C004
CST00506 | P001 | A040 | 2025-10-10 | C004 | Labour | Labour cost for Internal Painting (Idle Labour) | 70766.39 | 67018.86 | C004
CST00507 | P001 | A040 | 2025-10-10 | C004 | Equipment | Equipment cost for Internal Painting | 35383.2 | 33050.61 | C004
CST00508 | P001 | A040 | 2025-10-10 | C004 | Other | Other cost for Internal Painting | 11794.4 | 10923.01 | C004
CST00509 | P001 | A040 | 2025-10-17 | C004 | Material | Material cost for Internal Painting | 178828.26 | 180255.18 | C004
CST00510 | P001 | A040 | 2025-10-17 | C004 | Labour | Labour cost for Internal Painting | 107296.96 | 116943.17 | C004
CST00511 | P001 | A040 | 2025-10-17 | C004 | Equipment | Equipment cost for Internal Painting | 53648.48 | 59167.89 | C004
CST00512 | P001 | A040 | 2025-10-17 | C004 | Other | Other cost for Internal Painting | 17882.83 | 18320.74 | C004
CST00513 | P001 | A041 | 2025-11-14 | C004 | Material | Material cost for External Painting | 42526.82 | 37079.67 | C004
CST00514 | P001 | A041 | 2025-11-14 | C004 | Labour | Labour cost for External Painting | 25516.09 | 22823.36 | C004
CST00515 | P001 | A041 | 2025-11-14 | C004 | Equipment | Equipment cost for External Painting | 12758.05 | 10353.28 | C004
CST00516 | P001 | A041 | 2025-11-14 | C004 | Other | Other cost for External Painting | 4252.68 | 4150.58 | C004
CST00517 | P001 | A041 | 2025-11-21 | C004 | Material | Material cost for External Painting | 115717.32 | 109657.38 | C004
CST00518 | P001 | A041 | 2025-11-21 | C004 | Labour | Labour cost for External Painting (Idle Labour) | 69430.39 | 67611.79 | C004
CST00519 | P001 | A041 | 2025-11-21 | C004 | Equipment | Equipment cost for External Painting | 34715.2 | 33166.14 | C004
CST00520 | P001 | A041 | 2025-11-21 | C004 | Other | Other cost for External Painting | 11571.73 | 10799.31 | C004
CST00521 | P001 | A041 | 2025-11-28 | C004 | Material | Material cost for External Painting | 142327.92 | 115497.58 | C004
CST00522 | P001 | A041 | 2025-11-28 | C004 | Labour | Labour cost for External Painting (Idle Labour) | 85396.75 | 70558.91 | C004
CST00523 | P001 | A041 | 2025-11-28 | C004 | Equipment | Equipment cost for External Painting | 42698.38 | 34699.39 | C004
CST00524 | P001 | A041 | 2025-11-28 | C004 | Other | Other cost for External Painting | 14232.79 | 12085.16 | C004
CST00525 | P001 | A041 | 2025-12-05 | C004 | Material | Material cost for External Painting | 185745.88 | 154534.23 | C004
CST00526 | P001 | A041 | 2025-12-05 | C004 | Labour | Labour cost for External Painting | 111447.53 | 105683.55 | C004
CST00527 | P001 | A041 | 2025-12-05 | C004 | Equipment | Equipment cost for External Painting | 55723.76 | 47634.14 | C004
CST00528 | P001 | A041 | 2025-12-05 | C004 | Other | Other cost for External Painting | 18574.59 | 17624.22 | C004
CST00529 | P001 | A041 | 2025-12-12 | C004 | Material | Material cost for External Painting | 118682.06 | 116926.1 | C004
CST00530 | P001 | A041 | 2025-12-12 | C004 | Labour | Labour cost for External Painting | 71209.24 | 60704.95 | C004
CST00531 | P001 | A041 | 2025-12-12 | C004 | Equipment | Equipment cost for External Painting | 35604.62 | 31622.7 | C004
CST00532 | P001 | A041 | 2025-12-12 | C004 | Other | Other cost for External Painting | 11868.21 | 9645.58 | C004
CST00533 | P001 | A042 | 2025-08-01 | C009 | Material | Material cost for Doors & Windows Installation | 8525.24 | 8200.88 | C009
CST00534 | P001 | A042 | 2025-08-01 | C009 | Labour | Labour cost for Doors & Windows Installation | 5115.14 | 4301.55 | C009
CST00535 | P001 | A042 | 2025-08-01 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 2557.57 | 2200.45 | C009
CST00536 | P001 | A042 | 2025-08-01 | C009 | Other | Other cost for Doors & Windows Installation | 852.52 | 849.57 | C009
CST00537 | P001 | A042 | 2025-08-08 | C009 | Material | Material cost for Doors & Windows Installation | 60745.7 | 53268.67 | C009
CST00538 | P001 | A042 | 2025-08-08 | C009 | Labour | Labour cost for Doors & Windows Installation (Idle Labour) | 36447.42 | 32920.06 | C009
CST00539 | P001 | A042 | 2025-08-08 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 18223.71 | 17782.78 | C009
CST00540 | P001 | A042 | 2025-08-08 | C009 | Other | Other cost for Doors & Windows Installation | 6074.57 | 5630.55 | C009
CST00541 | P001 | A042 | 2025-08-15 | C009 | Material | Material cost for Doors & Windows Installation | 86512.81 | 78598.68 | C009
CST00542 | P001 | A042 | 2025-08-15 | C009 | Labour | Labour cost for Doors & Windows Installation (Idle Labour) | 51907.68 | 47668.01 | C009
CST00543 | P001 | A042 | 2025-08-15 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 25953.84 | 24124.51 | C009
CST00544 | P001 | A042 | 2025-08-15 | C009 | Other | Other cost for Doors & Windows Installation | 8651.28 | 7584.72 | C009
CST00545 | P001 | A042 | 2025-08-22 | C009 | Material | Material cost for Doors & Windows Installation | 105355.49 | 97494.11 | C009
CST00546 | P001 | A042 | 2025-08-22 | C009 | Labour | Labour cost for Doors & Windows Installation (Idle Labour) | 63213.29 | 52276.95 | C009
CST00547 | P001 | A042 | 2025-08-22 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 31606.65 | 27124.68 | C009
CST00548 | P001 | A042 | 2025-08-22 | C009 | Other | Other cost for Doors & Windows Installation | 10535.55 | 9993.7 | C009
CST00549 | P001 | A042 | 2025-08-29 | C009 | Material | Material cost for Doors & Windows Installation | 69636.16 | 64031.42 | C009
CST00550 | P001 | A042 | 2025-08-29 | C009 | Labour | Labour cost for Doors & Windows Installation (Idle Labour) | 41781.7 | 41306.89 | C009
CST00551 | P001 | A042 | 2025-08-29 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 20890.85 | 18669.88 | C009
CST00552 | P001 | A042 | 2025-08-29 | C009 | Other | Other cost for Doors & Windows Installation | 6963.62 | 6163.94 | C009
CST00553 | P001 | A042 | 2025-09-05 | C009 | Material | Material cost for Doors & Windows Installation | 93914.38 | 89619.5 | C009
CST00554 | P001 | A042 | 2025-09-05 | C009 | Labour | Labour cost for Doors & Windows Installation (Idle Labour) | 56348.63 | 50350.17 | C009
CST00555 | P001 | A042 | 2025-09-05 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 28174.31 | 23588.98 | C009
CST00556 | P001 | A042 | 2025-09-05 | C009 | Other | Other cost for Doors & Windows Installation | 9391.44 | 8773.17 | C009
CST00557 | P001 | A042 | 2025-09-12 | C009 | Material | Material cost for Doors & Windows Installation | 250310.24 | 224930.35 | C009
CST00558 | P001 | A042 | 2025-09-12 | C009 | Labour | Labour cost for Doors & Windows Installation | 150186.14 | 132482.17 | C009
CST00559 | P001 | A042 | 2025-09-12 | C009 | Equipment | Equipment cost for Doors & Windows Installation | 75093.07 | 65733.67 | C009
CST00560 | P001 | A042 | 2025-09-12 | C009 | Other | Other cost for Doors & Windows Installation | 25031.02 | 24988.74 | C009
CST00561 | P001 | A043 | 2025-10-17 | C006 | Material | Material cost for MEP Fixtures & Testing | 107469.32 | 123676.52 | C006
CST00562 | P001 | A043 | 2025-10-17 | C006 | Labour | Labour cost for MEP Fixtures & Testing | 64481.59 | 64864.06 | C006
CST00563 | P001 | A043 | 2025-10-17 | C006 | Equipment | Equipment cost for MEP Fixtures & Testing | 32240.79 | 32421.85 | C006
CST00564 | P001 | A043 | 2025-10-17 | C006 | Other | Other cost for MEP Fixtures & Testing | 10746.93 | 10630.67 | C006
CST00565 | P001 | A043 | 2025-10-24 | C006 | Material | Material cost for MEP Fixtures & Testing | 210092.73 | 209716.91 | C006
CST00566 | P001 | A043 | 2025-10-24 | C006 | Labour | Labour cost for MEP Fixtures & Testing (Idle Labour) | 126055.64 | 142325.08 | C006
CST00567 | P001 | A043 | 2025-10-24 | C006 | Equipment | Equipment cost for MEP Fixtures & Testing | 63027.82 | 62715.29 | C006
CST00568 | P001 | A043 | 2025-10-24 | C006 | Other | Other cost for MEP Fixtures & Testing | 21009.27 | 20933.21 | C006
CST00569 | P001 | A043 | 2025-10-31 | C006 | Material | Material cost for MEP Fixtures & Testing | 249888.16 | 273825.26 | C006
CST00570 | P001 | A043 | 2025-10-31 | C006 | Labour | Labour cost for MEP Fixtures & Testing (Idle Labour) | 149932.9 | 159442.25 | C006
CST00571 | P001 | A043 | 2025-10-31 | C006 | Equipment | Equipment cost for MEP Fixtures & Testing | 74966.45 | 71903.26 | C006
CST00572 | P001 | A043 | 2025-10-31 | C006 | Other | Other cost for MEP Fixtures & Testing | 24988.82 | 23849.68 | C006
CST00573 | P001 | A043 | 2025-11-07 | C006 | Material | Material cost for MEP Fixtures & Testing | 182549.79 | 184588.26 | C006
CST00574 | P001 | A043 | 2025-11-07 | C006 | Labour | Labour cost for MEP Fixtures & Testing | 109529.87 | 119264.21 | C006
CST00575 | P001 | A043 | 2025-11-07 | C006 | Equipment | Equipment cost for MEP Fixtures & Testing | 54764.94 | 53384.44 | C006
CST00576 | P001 | A043 | 2025-11-07 | C006 | Other | Other cost for MEP Fixtures & Testing | 18254.98 | 19785.08 | C006
CST00577 | P001 | A044 | 2025-11-14 | C001 | Material | Material cost for Final Cleaning & Handover | 25538.21 | 21608.05 | C001
CST00578 | P001 | A044 | 2025-11-14 | C001 | Labour | Labour cost for Final Cleaning & Handover (Idle Labour) | 15322.92 | 14152.05 | C001
CST00579 | P001 | A044 | 2025-11-14 | C001 | Equipment | Equipment cost for Final Cleaning & Handover | 7661.46 | 6976.11 | C001
CST00580 | P001 | A044 | 2025-11-14 | C001 | Other | Other cost for Final Cleaning & Handover | 2553.82 | 2402.01 | C001
CST00581 | P001 | A044 | 2025-11-21 | C001 | Material | Material cost for Final Cleaning & Handover | 40033.01 | 33541.31 | C001
CST00582 | P001 | A044 | 2025-11-21 | C001 | Labour | Labour cost for Final Cleaning & Handover (Idle Labour) | 24019.81 | 22677.45 | C001
CST00583 | P001 | A044 | 2025-11-21 | C001 | Equipment | Equipment cost for Final Cleaning & Handover | 12009.9 | 10794.55 | C001
CST00584 | P001 | A044 | 2025-11-21 | C001 | Other | Other cost for Final Cleaning & Handover | 4003.3 | 3543.2 | C001
CST00585 | P001 | A044 | 2025-11-28 | C001 | Material | Material cost for Final Cleaning & Handover | 17711.7 | 16999.9 | C001
CST00586 | P001 | A044 | 2025-11-28 | C001 | Labour | Labour cost for Final Cleaning & Handover (Idle Labour) | 10627.02 | 10384.3 | C001
CST00587 | P001 | A044 | 2025-11-28 | C001 | Equipment | Equipment cost for Final Cleaning & Handover | 5313.51 | 4473.97 | C001
CST00588 | P001 | A044 | 2025-11-28 | C001 | Other | Other cost for Final Cleaning & Handover | 1771.17 | 1472.62 | C001
CST00589 | P001 | A044 | 2025-12-05 | C001 | Material | Material cost for Final Cleaning & Handover | 16717.08 | 16761.09 | C001
CST00590 | P001 | A044 | 2025-12-05 | C001 | Labour | Labour cost for Final Cleaning & Handover | 10030.25 | 9512.41 | C001
CST00591 | P001 | A044 | 2025-12-05 | C001 | Equipment | Equipment cost for Final Cleaning & Handover | 5015.12 | 4731.66 | C001
CST00592 | P001 | A044 | 2025-12-05 | C001 | Other | Other cost for Final Cleaning & Handover | 1671.71 | 1488.22 | C001

## Labour
Labour_ID | Project_ID | Activity_ID | Date | Contractor_ID | Labour_Type | Number_of_Workers | Working_Hours | Man_Hours | Overtime_Hours | Productivity_Quantity | Productivity_Unit | Productivity_Rate
LAB00001 | P001 | A001 | 2025-01-03 | C001 | Semi-skilled | 23 | 8 | 184 | 0 | 0.09 | LS | 0.0005
LAB00002 | P001 | A001 | 2024-12-31 | C001 | Unskilled | 23 | 8 | 184 | 0 | 0.07 | LS | 0.0004
LAB00003 | P001 | A001 | 2025-01-08 | C001 | Semi-skilled | 21 | 8 | 168 | 0 | 0.22 | LS | 0.0013
LAB00004 | P001 | A001 | 2025-01-06 | C001 | Skilled | 17 | 8 | 136 | 0 | 0.24 | LS | 0.0018
LAB00005 | P001 | A002 | 2025-01-08 | C001 | Semi-skilled | 15 | 8 | 120 | 0 | 260.24 | m2 | 2.1687
LAB00006 | P001 | A002 | 2025-01-13 | C001 | Semi-skilled | 21 | 8 | 168 | 0 | 451.21 | m2 | 2.6858
LAB00007 | P001 | A002 | 2025-01-16 | C001 | Semi-skilled | 5 | 8 | 40 | 0 | 368.38 | m2 | 9.2096
LAB00008 | P001 | A002 | 2025-01-16 | C001 | Skilled | 20 | 8 | 160 | 0 | 506.89 | m2 | 3.168
LAB00009 | P001 | A003 | 2025-01-23 | C001 | Semi-skilled | 6 | 8 | 48 | 0 | 220.83 | m3 | 4.6006
LAB00010 | P001 | A003 | 2025-01-21 | C001 | Skilled | 24 | 8 | 192 | 0 | 226.78 | m3 | 1.1812
LAB00011 | P001 | A003 | 2025-01-31 | C001 | Unskilled | 11 | 8 | 88 | 0 | 497.22 | m3 | 5.6503
LAB00012 | P001 | A003 | 2025-02-03 | C001 | Semi-skilled | 16 | 8 | 144 | 16 | 288.11 | m3 | 2.2508
LAB00013 | P001 | A003 | 2025-02-06 | C001 | Skilled | 12 | 8 | 96 | 0 | 292.08 | m3 | 3.0425
LAB00014 | P001 | A003 | 2025-02-13 | C001 | Unskilled | 7 | 8 | 56 | 0 | 156.81 | m3 | 2.8002
LAB00015 | P001 | A004 | 2025-01-30 | C002 | Unskilled | 24 | 8 | 192 | 0 | 29.64 | m3 | 0.1544
LAB00016 | P001 | A004 | 2025-02-05 | C002 | Unskilled | 23 | 8 | 207 | 23 | 18.07 | m3 | 0.0982
LAB00017 | P001 | A005 | 2025-02-04 | C002 | Semi-skilled | 16 | 8 | 128 | 0 | 19.95 | m3 | 0.1559
LAB00018 | P001 | A005 | 2025-02-14 | C002 | Unskilled | 10 | 8 | 80 | 0 | 72.43 | m3 | 0.9054
LAB00019 | P001 | A005 | 2025-02-14 | C002 | Skilled | 16 | 8 | 128 | 0 | 75 | m3 | 0.5859
LAB00020 | P001 | A005 | 2025-02-19 | C002 | Unskilled | 23 | 8 | 184 | 0 | 33.66 | m3 | 0.1829
LAB00021 | P001 | A006 | 2025-02-19 | C005 | Skilled | 16 | 8 | 160 | 32 | 253.71 | m2 | 1.9821
LAB00022 | P001 | A006 | 2025-02-20 | C005 | Skilled | 25 | 8 | 200 | 0 | 235.67 | m2 | 1.1784
LAB00023 | P001 | A006 | 2025-02-27 | C005 | Unskilled | 16 | 8 | 128 | 0 | 179.58 | m2 | 1.403
LAB00024 | P001 | A006 | 2025-02-25 | C005 | Unskilled | 7 | 8 | 56 | 0 | 144.37 | m2 | 2.5781
LAB00025 | P001 | A006 | 2025-02-26 | C005 | Unskilled | 18 | 8 | 180 | 36 | 124.84 | m2 | 0.867
LAB00026 | P001 | A007 | 2025-02-26 | C001 | Skilled | 12 | 8 | 96 | 0 | 37.67 | m3 | 0.3924
LAB00027 | P001 | A007 | 2025-02-26 | C001 | Skilled | 13 | 8 | 104 | 0 | 37.87 | m3 | 0.3641
LAB00028 | P001 | A007 | 2025-02-24 | C001 | Unskilled | 25 | 8 | 200 | 0 | 32.45 | m3 | 0.1623
LAB00029 | P001 | A007 | 2025-03-03 | C001 | Semi-skilled | 25 | 8 | 225 | 25 | 149.72 | m3 | 0.7486
LAB00030 | P001 | A007 | 2025-03-12 | C001 | Unskilled | 11 | 8 | 88 | 0 | 99.46 | m3 | 1.1302
LAB00031 | P001 | A007 | 2025-03-10 | C001 | Unskilled | 16 | 8 | 128 | 0 | 128.08 | m3 | 1.0006
LAB00032 | P001 | A007 | 2025-03-17 | C001 | Semi-skilled | 15 | 8 | 120 | 0 | 38.12 | m3 | 0.3177
LAB00033 | P001 | A007 | 2025-03-18 | C001 | Unskilled | 20 | 8 | 180 | 20 | 35.72 | m3 | 0.2232
LAB00034 | P001 | A007 | 2025-03-21 | C001 | Skilled | 19 | 8 | 152 | 0 | 45.6 | m3 | 0.3
LAB00035 | P001 | A008 | 2025-03-11 | C002 | Unskilled | 22 | 8 | 176 | 0 | 29.77 | m3 | 0.1692
LAB00036 | P001 | A008 | 2025-03-14 | C002 | Skilled | 13 | 8 | 130 | 26 | 33.44 | m3 | 0.3216
LAB00037 | P001 | A008 | 2025-03-19 | C002 | Unskilled | 9 | 8 | 72 | 0 | 8.86 | m3 | 0.1231
LAB00038 | P001 | A008 | 2025-03-19 | C002 | Unskilled | 15 | 8 | 120 | 0 | 10.54 | m3 | 0.0878
LAB00039 | P001 | A009 | 2025-03-18 | C002 | Skilled | 10 | 8 | 80 | 0 | 18.6 | m3 | 0.2325
LAB00040 | P001 | A009 | 2025-03-21 | C002 | Skilled | 12 | 8 | 96 | 0 | 20.15 | m3 | 0.2099
LAB00041 | P001 | A009 | 2025-03-27 | C002 | Semi-skilled | 20 | 8 | 160 | 0 | 2.7 | m3 | 0.0169
LAB00042 | P001 | A009 | 2025-03-26 | C002 | Unskilled | 22 | 8 | 176 | 0 | 2.74 | m3 | 0.0156
LAB00043 | P001 | A009 | 2025-03-24 | C002 | Semi-skilled | 20 | 8 | 160 | 0 | 2.62 | m3 | 0.0164
LAB00044 | P001 | A010 | 2025-03-28 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 17.08 | m3 | 0.1525
LAB00045 | P001 | A010 | 2025-04-04 | C002 | Unskilled | 20 | 8 | 160 | 0 | 50.49 | m3 | 0.3156
LAB00046 | P001 | A010 | 2025-04-01 | C002 | Semi-skilled | 10 | 8 | 80 | 0 | 53.48 | m3 | 0.6685
LAB00047 | P001 | A010 | 2025-04-02 | C002 | Semi-skilled | 25 | 8 | 200 | 0 | 54.01 | m3 | 0.27
LAB00048 | P001 | A011 | 2025-04-02 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 6.85 | m3 | 0.0612
LAB00049 | P001 | A011 | 2025-04-08 | C002 | Semi-skilled | 11 | 8 | 88 | 0 | 13.56 | m3 | 0.1541
LAB00050 | P001 | A011 | 2025-04-11 | C002 | Skilled | 21 | 8 | 168 | 0 | 11.4 | m3 | 0.0678
LAB00051 | P001 | A011 | 2025-04-11 | C002 | Semi-skilled | 9 | 8 | 72 | 0 | 13.94 | m3 | 0.1936
LAB00052 | P001 | A012 | 2025-04-08 | C002 | Unskilled | 24 | 8 | 192 | 0 | 8.77 | m3 | 0.0457
LAB00053 | P001 | A012 | 2025-04-11 | C002 | Unskilled | 11 | 8 | 110 | 22 | 8.94 | m3 | 0.1016
LAB00054 | P001 | A012 | 2025-04-14 | C002 | Skilled | 19 | 8 | 152 | 0 | 50.13 | m3 | 0.3298
LAB00055 | P001 | A013 | 2025-04-21 | C002 | Skilled | 19 | 8 | 171 | 19 | 3.2 | m3 | 0.021
LAB00056 | P001 | A013 | 2025-04-21 | C002 | Semi-skilled | 25 | 8 | 200 | 0 | 2.93 | m3 | 0.0147
LAB00057 | P001 | A013 | 2025-05-02 | C002 | Skilled | 6 | 8 | 54 | 6 | 5.21 | m3 | 0.1085
LAB00058 | P001 | A013 | 2025-05-05 | C002 | Unskilled | 12 | 8 | 120 | 24 | 5.04 | m3 | 0.0525
LAB00059 | P001 | A013 | 2025-05-05 | C002 | Skilled | 15 | 8 | 120 | 0 | 5.62 | m3 | 0.0469
LAB00060 | P001 | A013 | 2025-05-13 | C002 | Unskilled | 19 | 8 | 190 | 38 | 6.53 | m3 | 0.043
LAB00061 | P001 | A014 | 2025-04-29 | C002 | Skilled | 11 | 8 | 110 | 22 | 34.42 | m3 | 0.3911
LAB00062 | P001 | A014 | 2025-05-05 | C002 | Skilled | 11 | 8 | 88 | 0 | 18.69 | m3 | 0.2124
LAB00063 | P001 | A014 | 2025-05-05 | C002 | Unskilled | 9 | 8 | 72 | 0 | 19.77 | m3 | 0.2746
LAB00064 | P001 | A015 | 2025-05-09 | C002 | Unskilled | 6 | 8 | 48 | 0 | 5.14 | m3 | 0.1071
LAB00065 | P001 | A015 | 2025-05-08 | C002 | Skilled | 6 | 8 | 54 | 6 | 3.87 | m3 | 0.0807
LAB00066 | P001 | A015 | 2025-05-07 | C002 | Skilled | 9 | 8 | 72 | 0 | 4.54 | m3 | 0.063
LAB00067 | P001 | A015 | 2025-05-16 | C002 | Semi-skilled | 13 | 8 | 117 | 13 | 17.3 | m3 | 0.1663
LAB00068 | P001 | A015 | 2025-05-15 | C002 | Semi-skilled | 17 | 8 | 136 | 0 | 13.88 | m3 | 0.1021
LAB00069 | P001 | A015 | 2025-05-16 | C002 | Skilled | 7 | 8 | 56 | 0 | 17.69 | m3 | 0.3159
LAB00070 | P001 | A016 | 2025-05-13 | C002 | Skilled | 11 | 8 | 88 | 0 | 23.36 | m3 | 0.2655
LAB00071 | P001 | A016 | 2025-05-23 | C002 | Unskilled | 24 | 8 | 192 | 0 | 43.02 | m3 | 0.2241
LAB00072 | P001 | A016 | 2025-05-21 | C002 | Unskilled | 13 | 8 | 117 | 13 | 38.64 | m3 | 0.3715
LAB00073 | P001 | A016 | 2025-05-20 | C002 | Skilled | 17 | 8 | 136 | 0 | 41.57 | m3 | 0.3057
LAB00074 | P001 | A017 | 2025-05-20 | C002 | Skilled | 24 | 8 | 192 | 0 | 1.24 | m3 | 0.0065
LAB00075 | P001 | A017 | 2025-05-29 | C002 | Semi-skilled | 24 | 8 | 192 | 0 | 18.35 | m3 | 0.0956
LAB00076 | P001 | A017 | 2025-05-27 | C002 | Semi-skilled | 5 | 8 | 45 | 5 | 21.22 | m3 | 0.5304
LAB00077 | P001 | A018 | 2025-06-05 | C002 | Semi-skilled | 5 | 8 | 45 | 5 | 24.98 | m3 | 0.6246
LAB00078 | P001 | A018 | 2025-06-03 | C002 | Unskilled | 14 | 8 | 112 | 0 | 23.93 | m3 | 0.2137
LAB00079 | P001 | A018 | 2025-06-04 | C002 | Unskilled | 20 | 8 | 160 | 0 | 19.55 | m3 | 0.1222
LAB00080 | P001 | A018 | 2025-06-12 | C002 | Unskilled | 24 | 8 | 192 | 0 | 32.34 | m3 | 0.1684
LAB00081 | P001 | A018 | 2025-06-09 | C002 | Unskilled | 16 | 8 | 128 | 0 | 40.53 | m3 | 0.3166
LAB00082 | P001 | A018 | 2025-06-10 | C002 | Skilled | 25 | 8 | 200 | 0 | 42.7 | m3 | 0.2135
LAB00083 | P001 | A019 | 2025-06-11 | C002 | Skilled | 8 | 8 | 64 | 0 | 6.49 | m3 | 0.1014
LAB00084 | P001 | A019 | 2025-06-13 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 6.53 | m3 | 0.0583
LAB00085 | P001 | A019 | 2025-06-17 | C002 | Semi-skilled | 5 | 8 | 40 | 0 | 13.7 | m3 | 0.3425
LAB00086 | P001 | A019 | 2025-06-20 | C002 | Unskilled | 5 | 8 | 40 | 0 | 12.74 | m3 | 0.3186
LAB00087 | P001 | A020 | 2025-06-18 | C002 | Skilled | 24 | 8 | 192 | 0 | 8.29 | m3 | 0.0432
LAB00088 | P001 | A020 | 2025-06-19 | C002 | Unskilled | 12 | 8 | 96 | 0 | 6.77 | m3 | 0.0705
LAB00089 | P001 | A020 | 2025-06-24 | C002 | Semi-skilled | 22 | 8 | 176 | 0 | 52.14 | m3 | 0.2963
LAB00090 | P001 | A020 | 2025-06-27 | C002 | Skilled | 19 | 8 | 152 | 0 | 43.53 | m3 | 0.2864
LAB00091 | P001 | A021 | 2025-06-27 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 2.83 | m3 | 0.0186
LAB00092 | P001 | A021 | 2025-07-02 | C002 | Unskilled | 15 | 8 | 135 | 15 | 16.05 | m3 | 0.1338
LAB00093 | P001 | A022 | 2025-07-09 | C002 | Semi-skilled | 17 | 8 | 136 | 0 | 20.64 | m3 | 0.1517
LAB00094 | P001 | A022 | 2025-07-15 | C002 | Skilled | 15 | 8 | 120 | 0 | 30.57 | m3 | 0.2548
LAB00095 | P001 | A022 | 2025-07-18 | C002 | Semi-skilled | 8 | 8 | 64 | 0 | 36.48 | m3 | 0.57
LAB00096 | P001 | A023 | 2025-07-15 | C002 | Skilled | 9 | 8 | 72 | 0 | 15.52 | m3 | 0.2155
LAB00097 | P001 | A023 | 2025-07-21 | C002 | Unskilled | 9 | 8 | 72 | 0 | 4.72 | m3 | 0.0655
LAB00098 | P001 | A023 | 2025-07-24 | C002 | Semi-skilled | 10 | 8 | 80 | 0 | 5.01 | m3 | 0.0626
LAB00099 | P001 | A023 | 2025-07-25 | C002 | Skilled | 24 | 8 | 192 | 0 | 5.26 | m3 | 0.0274
LAB00100 | P001 | A024 | 2025-07-22 | C002 | Unskilled | 12 | 8 | 96 | 0 | 13.55 | m3 | 0.1411
LAB00101 | P001 | A024 | 2025-08-01 | C002 | Semi-skilled | 5 | 8 | 40 | 0 | 35.88 | m3 | 0.8969
LAB00102 | P001 | A025 | 2025-07-31 | C002 | Skilled | 24 | 8 | 192 | 0 | 4.96 | m3 | 0.0259
LAB00103 | P001 | A025 | 2025-07-29 | C002 | Semi-skilled | 5 | 8 | 50 | 10 | 3.74 | m3 | 0.0936
LAB00104 | P001 | A025 | 2025-07-30 | C002 | Skilled | 21 | 8 | 168 | 0 | 5.25 | m3 | 0.0313
LAB00105 | P001 | A025 | 2025-08-08 | C002 | Unskilled | 10 | 8 | 80 | 0 | 13.84 | m3 | 0.173
LAB00106 | P001 | A025 | 2025-08-08 | C002 | Skilled | 8 | 8 | 64 | 0 | 15.4 | m3 | 0.2406
LAB00107 | P001 | A025 | 2025-08-07 | C002 | Skilled | 12 | 8 | 96 | 0 | 14.51 | m3 | 0.1512
LAB00108 | P001 | A026 | 2025-08-06 | C002 | Skilled | 15 | 8 | 120 | 0 | 5.33 | m3 | 0.0444
LAB00109 | P001 | A026 | 2025-08-04 | C002 | Skilled | 14 | 8 | 112 | 0 | 5 | m3 | 0.0446
LAB00110 | P001 | A026 | 2025-08-14 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 55.23 | m3 | 0.4931
LAB00111 | P001 | A026 | 2025-08-15 | C002 | Skilled | 20 | 8 | 160 | 0 | 59.2 | m3 | 0.37
LAB00112 | P001 | A027 | 2025-08-22 | C002 | Skilled | 15 | 8 | 120 | 0 | 18.18 | m3 | 0.1515
LAB00113 | P001 | A027 | 2025-08-22 | C002 | Skilled | 9 | 8 | 90 | 18 | 16.87 | m3 | 0.2343
LAB00114 | P001 | A027 | 2025-08-18 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 19.25 | m3 | 0.1267
LAB00115 | P001 | A028 | 2025-08-29 | C002 | Skilled | 22 | 8 | 176 | 0 | 14.33 | m3 | 0.0814
LAB00116 | P001 | A028 | 2025-08-28 | C002 | Skilled | 8 | 8 | 64 | 0 | 19.37 | m3 | 0.3026
LAB00117 | P001 | A028 | 2025-09-04 | C002 | Unskilled | 8 | 8 | 64 | 0 | 42.22 | m3 | 0.6597
LAB00118 | P001 | A028 | 2025-09-02 | C002 | Unskilled | 18 | 8 | 162 | 18 | 42.83 | m3 | 0.2974
LAB00119 | P001 | A029 | 2025-09-01 | C002 | Semi-skilled | 5 | 8 | 50 | 10 | 4.99 | m3 | 0.1248
LAB00120 | P001 | A029 | 2025-09-03 | C002 | Skilled | 16 | 8 | 160 | 32 | 4.91 | m3 | 0.0384
LAB00121 | P001 | A029 | 2025-09-03 | C002 | Skilled | 5 | 8 | 40 | 0 | 4.7 | m3 | 0.1174
LAB00122 | P001 | A029 | 2025-09-08 | C002 | Skilled | 15 | 8 | 150 | 30 | 13.88 | m3 | 0.1157
LAB00123 | P001 | A029 | 2025-09-11 | C002 | Semi-skilled | 16 | 8 | 160 | 32 | 12.6 | m3 | 0.0985
LAB00124 | P001 | A029 | 2025-09-12 | C002 | Skilled | 22 | 8 | 176 | 0 | 14.65 | m3 | 0.0833
LAB00125 | P001 | A030 | 2025-09-17 | C002 | Skilled | 17 | 8 | 136 | 0 | 8.99 | m3 | 0.0661
LAB00126 | P001 | A030 | 2025-09-16 | C002 | Unskilled | 10 | 8 | 90 | 10 | 10.74 | m3 | 0.1342
LAB00127 | P001 | A030 | 2025-09-15 | C002 | Semi-skilled | 15 | 8 | 120 | 0 | 11.42 | m3 | 0.0951
LAB00128 | P001 | A030 | 2025-09-22 | C002 | Skilled | 15 | 8 | 150 | 30 | 22.38 | m3 | 0.1865
LAB00129 | P001 | A030 | 2025-09-25 | C002 | Semi-skilled | 20 | 8 | 160 | 0 | 27.66 | m3 | 0.1729
LAB00130 | P001 | A030 | 2025-09-26 | C002 | Unskilled | 15 | 8 | 120 | 0 | 29.08 | m3 | 0.2423
LAB00131 | P001 | A030 | 2025-10-02 | C002 | Semi-skilled | 23 | 8 | 184 | 0 | 27.08 | m3 | 0.1472
LAB00132 | P001 | A030 | 2025-10-01 | C002 | Semi-skilled | 7 | 8 | 56 | 0 | 23.13 | m3 | 0.413
LAB00133 | P001 | A031 | 2025-05-29 | C003 | Skilled | 22 | 8 | 176 | 0 | 14.86 | m2 | 0.0844
LAB00134 | P001 | A031 | 2025-05-27 | C003 | Skilled | 6 | 8 | 48 | 0 | 16.61 | m2 | 0.3459
LAB00135 | P001 | A031 | 2025-05-28 | C003 | Unskilled | 6 | 8 | 48 | 0 | 15.81 | m2 | 0.3294
LAB00136 | P001 | A031 | 2025-06-03 | C003 | Semi-skilled | 16 | 8 | 128 | 0 | 70.45 | m2 | 0.5504
LAB00137 | P001 | A031 | 2025-06-06 | C003 | Skilled | 13 | 8 | 104 | 0 | 78.16 | m2 | 0.7516
LAB00138 | P001 | A031 | 2025-06-10 | C003 | Unskilled | 23 | 8 | 207 | 23 | 104.69 | m2 | 0.569
LAB00139 | P001 | A031 | 2025-06-09 | C003 | Unskilled | 6 | 8 | 48 | 0 | 132.09 | m2 | 2.7518
LAB00140 | P001 | A031 | 2025-06-20 | C003 | Skilled | 9 | 8 | 81 | 9 | 117.8 | m2 | 1.6361
LAB00141 | P001 | A031 | 2025-06-18 | C003 | Unskilled | 17 | 8 | 136 | 0 | 129.59 | m2 | 0.9529
LAB00142 | P001 | A031 | 2025-06-16 | C003 | Unskilled | 19 | 8 | 152 | 0 | 141.5 | m2 | 0.9309
LAB00143 | P001 | A031 | 2025-06-23 | C003 | Unskilled | 6 | 8 | 48 | 0 | 135.86 | m2 | 2.8304
LAB00144 | P001 | A031 | 2025-06-25 | C003 | Unskilled | 17 | 8 | 136 | 0 | 163.37 | m2 | 1.2013
LAB00145 | P001 | A031 | 2025-07-02 | C003 | Semi-skilled | 9 | 8 | 72 | 0 | 199.86 | m2 | 2.7758
LAB00146 | P001 | A032 | 2025-07-30 | C003 | Unskilled | 6 | 8 | 48 | 0 | 12.1 | m2 | 0.252
LAB00147 | P001 | A032 | 2025-08-06 | C003 | Unskilled | 16 | 8 | 128 | 0 | 87.34 | m2 | 0.6823
LAB00148 | P001 | A032 | 2025-08-07 | C003 | Unskilled | 7 | 8 | 56 | 0 | 73.46 | m2 | 1.3117
LAB00149 | P001 | A032 | 2025-08-07 | C003 | Semi-skilled | 11 | 8 | 110 | 22 | 68.49 | m2 | 0.7783
LAB00150 | P001 | A032 | 2025-08-11 | C003 | Unskilled | 13 | 8 | 104 | 0 | 125.61 | m2 | 1.2078
LAB00151 | P001 | A032 | 2025-08-13 | C003 | Unskilled | 17 | 8 | 136 | 0 | 109.53 | m2 | 0.8054
LAB00152 | P001 | A032 | 2025-08-20 | C003 | Semi-skilled | 5 | 8 | 40 | 0 | 121.28 | m2 | 3.0319
LAB00153 | P001 | A032 | 2025-08-27 | C003 | Unskilled | 10 | 8 | 80 | 0 | 335.88 | m2 | 4.1984
LAB00154 | P001 | A032 | 2025-08-27 | C003 | Unskilled | 22 | 8 | 176 | 0 | 400.6 | m2 | 2.2761
LAB00155 | P001 | A032 | 2025-08-27 | C003 | Semi-skilled | 7 | 8 | 56 | 0 | 302.24 | m2 | 5.3971
LAB00156 | P001 | A033 | 2025-09-18 | C003 | Skilled | 23 | 8 | 207 | 23 | 9.53 | m2 | 0.0518
LAB00157 | P001 | A033 | 2025-09-17 | C003 | Unskilled | 20 | 8 | 160 | 0 | 13.28 | m2 | 0.083
LAB00158 | P001 | A033 | 2025-09-26 | C003 | Skilled | 17 | 8 | 136 | 0 | 78.48 | m2 | 0.577
LAB00159 | P001 | A033 | 2025-09-26 | C003 | Semi-skilled | 22 | 8 | 176 | 0 | 75.17 | m2 | 0.4271
LAB00160 | P001 | A033 | 2025-09-29 | C003 | Unskilled | 14 | 8 | 126 | 14 | 135.53 | m2 | 1.2101
LAB00161 | P001 | A033 | 2025-10-08 | C003 | Unskilled | 25 | 8 | 225 | 25 | 328.47 | m2 | 1.6424
LAB00162 | P001 | A033 | 2025-10-10 | C003 | Unskilled | 24 | 8 | 192 | 0 | 341.96 | m2 | 1.781
LAB00163 | P001 | A033 | 2025-10-07 | C003 | Semi-skilled | 5 | 8 | 40 | 0 | 241.6 | m2 | 6.04
LAB00164 | P001 | A034 | 2025-06-25 | C004 | Unskilled | 11 | 8 | 110 | 22 | 109.03 | m2 | 1.239
LAB00165 | P001 | A034 | 2025-06-24 | C004 | Skilled | 18 | 8 | 144 | 0 | 74.79 | m2 | 0.5194
LAB00166 | P001 | A034 | 2025-06-27 | C004 | Skilled | 20 | 8 | 160 | 0 | 73.44 | m2 | 0.459
LAB00167 | P001 | A034 | 2025-07-01 | C004 | Unskilled | 14 | 8 | 112 | 0 | 182.44 | m2 | 1.629
LAB00168 | P001 | A034 | 2025-07-08 | C004 | Semi-skilled | 10 | 8 | 80 | 0 | 248.98 | m2 | 3.1122
LAB00169 | P001 | A034 | 2025-07-08 | C004 | Unskilled | 17 | 8 | 136 | 0 | 257.07 | m2 | 1.8902
LAB00170 | P001 | A034 | 2025-07-14 | C004 | Skilled | 10 | 8 | 80 | 0 | 295.65 | m2 | 3.6956
LAB00171 | P001 | A034 | 2025-07-15 | C004 | Semi-skilled | 9 | 8 | 72 | 0 | 264.69 | m2 | 3.6762
LAB00172 | P001 | A034 | 2025-07-21 | C004 | Skilled | 15 | 8 | 120 | 0 | 261.39 | m2 | 2.1782
LAB00173 | P001 | A034 | 2025-07-23 | C004 | Unskilled | 18 | 8 | 144 | 0 | 218.64 | m2 | 1.5183
LAB00174 | P001 | A034 | 2025-07-21 | C004 | Unskilled | 25 | 8 | 200 | 0 | 276.05 | m2 | 1.3802
LAB00175 | P001 | A034 | 2025-07-29 | C004 | Semi-skilled | 6 | 8 | 48 | 0 | 479.05 | m2 | 9.9802
LAB00176 | P001 | A034 | 2025-07-28 | C004 | Semi-skilled | 12 | 8 | 96 | 0 | 459.08 | m2 | 4.7821
LAB00177 | P001 | A035 | 2025-10-07 | C004 | Semi-skilled | 21 | 8 | 168 | 0 | 78.24 | m2 | 0.4657
LAB00178 | P001 | A035 | 2025-10-08 | C004 | Unskilled | 16 | 8 | 128 | 0 | 83.84 | m2 | 0.655
LAB00179 | P001 | A035 | 2025-10-17 | C004 | Semi-skilled | 9 | 8 | 90 | 18 | 307.95 | m2 | 4.277
LAB00180 | P001 | A035 | 2025-10-14 | C004 | Skilled | 24 | 8 | 192 | 0 | 239.96 | m2 | 1.2498
LAB00181 | P001 | A035 | 2025-10-20 | C004 | Semi-skilled | 6 | 8 | 48 | 0 | 207.7 | m2 | 4.327
LAB00182 | P001 | A035 | 2025-10-23 | C004 | Unskilled | 21 | 8 | 168 | 0 | 229.81 | m2 | 1.3679
LAB00183 | P001 | A035 | 2025-10-20 | C004 | Semi-skilled | 9 | 8 | 72 | 0 | 226.88 | m2 | 3.1512
LAB00184 | P001 | A035 | 2025-10-27 | C004 | Unskilled | 22 | 8 | 220 | 44 | 181.74 | m2 | 1.0326
LAB00185 | P001 | A035 | 2025-10-29 | C004 | Unskilled | 11 | 8 | 88 | 0 | 174.26 | m2 | 1.9802
LAB00186 | P001 | A035 | 2025-10-30 | C004 | Unskilled | 16 | 8 | 128 | 0 | 197.98 | m2 | 1.5467
LAB00187 | P001 | A035 | 2025-11-07 | C004 | Skilled | 5 | 8 | 40 | 0 | 398.08 | m2 | 9.9521
LAB00188 | P001 | A035 | 2025-11-13 | C004 | Unskilled | 24 | 8 | 240 | 48 | 115.37 | m2 | 0.6009
LAB00189 | P001 | A036 | 2025-06-23 | C006 | Skilled | 25 | 8 | 200 | 0 | 51.23 | m | 0.2561
LAB00190 | P001 | A036 | 2025-06-27 | C006 | Skilled | 11 | 8 | 88 | 0 | 43.09 | m | 0.4897
LAB00191 | P001 | A036 | 2025-06-24 | C006 | Semi-skilled | 10 | 8 | 80 | 0 | 47.05 | m | 0.5881
LAB00192 | P001 | A036 | 2025-07-04 | C006 | Unskilled | 6 | 8 | 48 | 0 | 100.21 | m | 2.0877
LAB00193 | P001 | A036 | 2025-07-11 | C006 | Unskilled | 21 | 8 | 168 | 0 | 156.87 | m | 0.9338
LAB00194 | P001 | A036 | 2025-07-11 | C006 | Semi-skilled | 10 | 8 | 80 | 0 | 182.24 | m | 2.278
LAB00195 | P001 | A036 | 2025-07-17 | C006 | Unskilled | 5 | 8 | 40 | 0 | 148.06 | m | 3.7014
LAB00196 | P001 | A036 | 2025-07-16 | C006 | Semi-skilled | 24 | 8 | 192 | 0 | 186.74 | m | 0.9726
LAB00197 | P001 | A036 | 2025-07-16 | C006 | Skilled | 8 | 8 | 64 | 0 | 160.31 | m | 2.5049
LAB00198 | P001 | A036 | 2025-07-25 | C006 | Skilled | 11 | 8 | 88 | 0 | 194.79 | m | 2.2136
LAB00199 | P001 | A036 | 2025-07-24 | C006 | Unskilled | 22 | 8 | 176 | 0 | 245.74 | m | 1.3962
LAB00200 | P001 | A036 | 2025-07-25 | C006 | Skilled | 25 | 8 | 250 | 50 | 226.77 | m | 1.1339
LAB00201 | P001 | A036 | 2025-08-01 | C006 | Skilled | 9 | 8 | 72 | 0 | 219.66 | m | 3.0509
LAB00202 | P001 | A036 | 2025-07-28 | C006 | Skilled | 7 | 8 | 56 | 0 | 225.92 | m | 4.0342
LAB00203 | P001 | A036 | 2025-07-29 | C006 | Unskilled | 23 | 8 | 207 | 23 | 194.66 | m | 1.0579
LAB00204 | P001 | A036 | 2025-08-06 | C006 | Unskilled | 23 | 8 | 184 | 0 | 143.7 | m | 0.781
LAB00205 | P001 | A036 | 2025-08-12 | C006 | Unskilled | 10 | 8 | 80 | 0 | 85.93 | m | 1.0741
LAB00206 | P001 | A036 | 2025-08-13 | C006 | Skilled | 14 | 8 | 112 | 0 | 92.43 | m | 0.8252
LAB00207 | P001 | A036 | 2025-08-20 | C006 | Skilled | 22 | 8 | 198 | 22 | 450.23 | m | 2.5581
LAB00208 | P001 | A036 | 2025-08-21 | C006 | Skilled | 18 | 8 | 180 | 36 | 436.46 | m | 3.031
LAB00209 | P001 | A036 | 2025-08-18 | C006 | Skilled | 24 | 8 | 192 | 0 | 430.79 | m | 2.2437
LAB00210 | P001 | A037 | 2025-06-27 | C007 | Skilled | 25 | 8 | 200 | 0 | 25.53 | m | 0.1277
LAB00211 | P001 | A037 | 2025-06-25 | C007 | Unskilled | 15 | 8 | 120 | 0 | 26.01 | m | 0.2168
LAB00212 | P001 | A037 | 2025-06-25 | C007 | Semi-skilled | 23 | 8 | 184 | 0 | 28.68 | m | 0.1559
LAB00213 | P001 | A037 | 2025-07-02 | C007 | Semi-skilled | 20 | 8 | 160 | 0 | 88.57 | m | 0.5535
LAB00214 | P001 | A037 | 2025-07-04 | C007 | Semi-skilled | 22 | 8 | 176 | 0 | 99.34 | m | 0.5644
LAB00215 | P001 | A037 | 2025-07-07 | C007 | Unskilled | 5 | 8 | 50 | 10 | 74.24 | m | 1.856
LAB00216 | P001 | A037 | 2025-07-14 | C007 | Unskilled | 25 | 8 | 225 | 25 | 136.72 | m | 0.6836
LAB00217 | P001 | A037 | 2025-07-18 | C007 | Semi-skilled | 14 | 8 | 112 | 0 | 142.92 | m | 1.2761
LAB00218 | P001 | A037 | 2025-07-21 | C007 | Unskilled | 9 | 8 | 72 | 0 | 75.71 | m | 1.0515
LAB00219 | P001 | A037 | 2025-07-25 | C007 | Skilled | 9 | 8 | 81 | 9 | 102.12 | m | 1.4183
LAB00220 | P001 | A037 | 2025-07-24 | C007 | Skilled | 20 | 8 | 160 | 0 | 78.67 | m | 0.4917
LAB00221 | P001 | A037 | 2025-07-28 | C007 | Unskilled | 25 | 8 | 200 | 0 | 178.19 | m | 0.891
LAB00222 | P001 | A037 | 2025-08-04 | C007 | Semi-skilled | 23 | 8 | 184 | 0 | 222.49 | m | 1.2092
LAB00223 | P001 | A037 | 2025-08-06 | C007 | Semi-skilled | 17 | 8 | 136 | 0 | 197.45 | m | 1.4519
LAB00224 | P001 | A037 | 2025-08-14 | C007 | Skilled | 12 | 8 | 96 | 0 | 207.43 | m | 2.1607
LAB00225 | P001 | A038 | 2025-08-07 | C008 | Skilled | 12 | 8 | 96 | 0 | 39.41 | m2 | 0.4106
LAB00226 | P001 | A038 | 2025-08-12 | C008 | Semi-skilled | 7 | 8 | 56 | 0 | 118.09 | m2 | 2.1087
LAB00227 | P001 | A038 | 2025-08-14 | C008 | Unskilled | 10 | 8 | 80 | 0 | 109.22 | m2 | 1.3652
LAB00228 | P001 | A038 | 2025-08-18 | C008 | Unskilled | 5 | 8 | 40 | 0 | 150.56 | m2 | 3.7639
LAB00229 | P001 | A038 | 2025-08-25 | C008 | Semi-skilled | 5 | 8 | 50 | 10 | 179.7 | m2 | 4.4925
LAB00230 | P001 | A038 | 2025-08-28 | C008 | Semi-skilled | 16 | 8 | 160 | 32 | 171.6 | m2 | 1.3406
LAB00231 | P001 | A038 | 2025-08-25 | C008 | Skilled | 17 | 8 | 136 | 0 | 190.24 | m2 | 1.3988
LAB00232 | P001 | A038 | 2025-09-03 | C008 | Semi-skilled | 8 | 8 | 64 | 0 | 131.06 | m2 | 2.0478
LAB00233 | P001 | A038 | 2025-09-03 | C008 | Unskilled | 22 | 8 | 176 | 0 | 116.93 | m2 | 0.6643
LAB00234 | P001 | A038 | 2025-09-11 | C008 | Skilled | 12 | 8 | 96 | 0 | 457.46 | m2 | 4.7652
LAB00235 | P001 | A038 | 2025-09-08 | C008 | Unskilled | 11 | 8 | 88 | 0 | 472.16 | m2 | 5.3655
LAB00236 | P001 | A038 | 2025-09-12 | C008 | Skilled | 6 | 8 | 48 | 0 | 502.41 | m2 | 10.4669
LAB00237 | P001 | A039 | 2025-11-17 | C008 | Semi-skilled | 5 | 8 | 40 | 0 | 239.35 | m2 | 5.9838
LAB00238 | P001 | A039 | 2025-11-17 | C008 | Unskilled | 11 | 8 | 88 | 0 | 234.18 | m2 | 2.6612
LAB00239 | P001 | A039 | 2025-11-24 | C008 | Unskilled | 7 | 8 | 70 | 14 | 249.09 | m2 | 4.448
LAB00240 | P001 | A039 | 2025-11-27 | C008 | Unskilled | 16 | 8 | 128 | 0 | 306.99 | m2 | 2.3983
LAB00241 | P001 | A039 | 2025-11-28 | C008 | Semi-skilled | 11 | 8 | 88 | 0 | 262.11 | m2 | 2.9786
LAB00242 | P001 | A039 | 2025-12-01 | C008 | Semi-skilled | 13 | 8 | 104 | 0 | 202.09 | m2 | 1.9432
LAB00243 | P001 | A039 | 2025-12-01 | C008 | Skilled | 12 | 8 | 108 | 12 | 182.71 | m2 | 1.9032
LAB00244 | P001 | A039 | 2025-12-04 | C008 | Unskilled | 20 | 8 | 160 | 0 | 140.87 | m2 | 0.8804
LAB00245 | P001 | A039 | 2025-12-09 | C008 | Semi-skilled | 15 | 8 | 120 | 0 | 389.12 | m2 | 3.2427
LAB00246 | P001 | A039 | 2025-12-11 | C008 | Unskilled | 16 | 8 | 128 | 0 | 341.64 | m2 | 2.6691
LAB00247 | P001 | A039 | 2025-12-11 | C008 | Semi-skilled | 11 | 8 | 88 | 0 | 291.99 | m2 | 3.3181
LAB00248 | P001 | A040 | 2025-09-01 | C004 | Semi-skilled | 13 | 8 | 104 | 0 | 183.25 | m2 | 1.762
LAB00249 | P001 | A040 | 2025-09-05 | C004 | Unskilled | 17 | 8 | 136 | 0 | 158.21 | m2 | 1.1633
LAB00250 | P001 | A040 | 2025-09-01 | C004 | Semi-skilled | 18 | 8 | 144 | 0 | 156.01 | m2 | 1.0834
LAB00251 | P001 | A040 | 2025-09-09 | C004 | Semi-skilled | 20 | 8 | 180 | 20 | 248.92 | m2 | 1.5557
LAB00252 | P001 | A040 | 2025-09-10 | C004 | Semi-skilled | 11 | 8 | 88 | 0 | 289.56 | m2 | 3.2904
LAB00253 | P001 | A040 | 2025-09-15 | C004 | Unskilled | 10 | 8 | 80 | 0 | 390.34 | m2 | 4.8793
LAB00254 | P001 | A040 | 2025-09-22 | C004 | Skilled | 16 | 8 | 128 | 0 | 227.14 | m2 | 1.7745
LAB00255 | P001 | A040 | 2025-09-25 | C004 | Semi-skilled | 23 | 8 | 184 | 0 | 283.67 | m2 | 1.5417
LAB00256 | P001 | A040 | 2025-10-03 | C004 | Skilled | 23 | 8 | 184 | 0 | 689.28 | m2 | 3.7461
LAB00257 | P001 | A040 | 2025-10-01 | C004 | Unskilled | 15 | 8 | 120 | 0 | 549.34 | m2 | 4.5779
LAB00258 | P001 | A040 | 2025-09-30 | C004 | Semi-skilled | 13 | 8 | 104 | 0 | 567.97 | m2 | 5.4613
LAB00259 | P001 | A040 | 2025-10-06 | C004 | Skilled | 22 | 8 | 176 | 0 | 484.17 | m2 | 2.751
LAB00260 | P001 | A040 | 2025-10-07 | C004 | Semi-skilled | 8 | 8 | 64 | 0 | 376.6 | m2 | 5.8843
LAB00261 | P001 | A040 | 2025-10-13 | C004 | Semi-skilled | 22 | 8 | 176 | 0 | 688.18 | m2 | 3.9101
LAB00262 | P001 | A041 | 2025-11-12 | C004 | Unskilled | 14 | 8 | 112 | 0 | 125.28 | m2 | 1.1186
LAB00263 | P001 | A041 | 2025-11-11 | C004 | Unskilled | 12 | 8 | 120 | 24 | 122.36 | m2 | 1.2745
LAB00264 | P001 | A041 | 2025-11-21 | C004 | Skilled | 25 | 8 | 225 | 25 | 338.44 | m2 | 1.6922
LAB00265 | P001 | A041 | 2025-11-17 | C004 | Semi-skilled | 9 | 8 | 72 | 0 | 369.86 | m2 | 5.1369
LAB00266 | P001 | A041 | 2025-11-25 | C004 | Unskilled | 14 | 8 | 126 | 14 | 517.2 | m2 | 4.6179
LAB00267 | P001 | A041 | 2025-11-27 | C004 | Skilled | 6 | 8 | 48 | 0 | 490.56 | m2 | 10.2201
LAB00268 | P001 | A041 | 2025-12-05 | C004 | Unskilled | 12 | 8 | 96 | 0 | 495.14 | m2 | 5.1577
LAB00269 | P001 | A041 | 2025-12-03 | C004 | Semi-skilled | 11 | 8 | 88 | 0 | 603.72 | m2 | 6.8604
LAB00270 | P001 | A041 | 2025-12-12 | C004 | Skilled | 23 | 8 | 184 | 0 | 401.24 | m2 | 2.1806
LAB00271 | P001 | A041 | 2025-12-11 | C004 | Semi-skilled | 23 | 8 | 207 | 23 | 386.75 | m2 | 2.1019
LAB00272 | P001 | A042 | 2025-08-01 | C009 | Unskilled | 16 | 8 | 144 | 16 | 1.38 | Nos | 0.0108
LAB00273 | P001 | A042 | 2025-08-01 | C009 | Semi-skilled | 17 | 8 | 136 | 0 | 1.08 | Nos | 0.0079
LAB00274 | P001 | A042 | 2025-07-29 | C009 | Skilled | 19 | 8 | 152 | 0 | 1.28 | Nos | 0.0085
LAB00275 | P001 | A042 | 2025-08-06 | C009 | Semi-skilled | 10 | 8 | 80 | 0 | 7.76 | Nos | 0.097
LAB00276 | P001 | A042 | 2025-08-04 | C009 | Semi-skilled | 22 | 8 | 176 | 0 | 7.2 | Nos | 0.0409
LAB00277 | P001 | A042 | 2025-08-04 | C009 | Skilled | 10 | 8 | 100 | 20 | 10.28 | Nos | 0.1285
LAB00278 | P001 | A042 | 2025-08-15 | C009 | Skilled | 15 | 8 | 120 | 0 | 12.94 | Nos | 0.1078
LAB00279 | P001 | A042 | 2025-08-15 | C009 | Semi-skilled | 9 | 8 | 72 | 0 | 10.41 | Nos | 0.1446
LAB00280 | P001 | A042 | 2025-08-12 | C009 | Unskilled | 11 | 8 | 88 | 0 | 13.18 | Nos | 0.1498
LAB00281 | P001 | A042 | 2025-08-22 | C009 | Semi-skilled | 11 | 8 | 88 | 0 | 18.28 | Nos | 0.2078
LAB00282 | P001 | A042 | 2025-08-29 | C009 | Semi-skilled | 6 | 8 | 54 | 6 | 10.44 | Nos | 0.2174
LAB00283 | P001 | A042 | 2025-08-28 | C009 | Unskilled | 7 | 8 | 70 | 14 | 8.65 | Nos | 0.1545
LAB00284 | P001 | A042 | 2025-08-28 | C009 | Unskilled | 17 | 8 | 136 | 0 | 10.42 | Nos | 0.0767
LAB00285 | P001 | A042 | 2025-09-04 | C009 | Skilled | 19 | 8 | 171 | 19 | 16.04 | Nos | 0.1056
LAB00286 | P001 | A042 | 2025-09-04 | C009 | Unskilled | 22 | 8 | 176 | 0 | 13.01 | Nos | 0.0739
LAB00287 | P001 | A042 | 2025-09-10 | C009 | Unskilled | 16 | 8 | 128 | 0 | 39.06 | Nos | 0.3052
LAB00288 | P001 | A042 | 2025-09-08 | C009 | Unskilled | 12 | 8 | 96 | 0 | 32.84 | Nos | 0.3421
LAB00289 | P001 | A043 | 2025-10-13 | C006 | Unskilled | 5 | 8 | 50 | 10 | 0.05 | LS | 0.0013
LAB00290 | P001 | A043 | 2025-10-17 | C006 | Skilled | 22 | 8 | 176 | 0 | 0.05 | LS | 0.0003
LAB00291 | P001 | A043 | 2025-10-23 | C006 | Unskilled | 7 | 8 | 56 | 0 | 0.1 | LS | 0.0017
LAB00292 | P001 | A043 | 2025-10-20 | C006 | Skilled | 7 | 8 | 63 | 7 | 0.08 | LS | 0.0014
LAB00293 | P001 | A043 | 2025-10-31 | C006 | Skilled | 16 | 8 | 144 | 16 | 0.11 | LS | 0.0008
LAB00294 | P001 | A043 | 2025-10-28 | C006 | Skilled | 25 | 8 | 200 | 0 | 0.12 | LS | 0.0006
LAB00295 | P001 | A043 | 2025-11-06 | C006 | Semi-skilled | 19 | 8 | 190 | 38 | 0.08 | LS | 0.0005
LAB00296 | P001 | A043 | 2025-11-07 | C006 | Semi-skilled | 14 | 8 | 112 | 0 | 0.07 | LS | 0.0006
LAB00297 | P001 | A044 | 2025-11-13 | C001 | Skilled | 22 | 8 | 176 | 0 | 0.09 | LS | 0.0005
LAB00298 | P001 | A044 | 2025-11-19 | C001 | Skilled | 16 | 8 | 128 | 0 | 0.11 | LS | 0.0008
LAB00299 | P001 | A044 | 2025-11-18 | C001 | Unskilled | 16 | 8 | 128 | 0 | 0.16 | LS | 0.0012
LAB00300 | P001 | A044 | 2025-11-28 | C001 | Semi-skilled | 9 | 8 | 81 | 9 | 0.05 | LS | 0.0007
LAB00301 | P001 | A044 | 2025-11-24 | C001 | Skilled | 19 | 8 | 152 | 0 | 0.06 | LS | 0.0004
LAB00302 | P001 | A044 | 2025-11-24 | C001 | Semi-skilled | 11 | 8 | 88 | 0 | 0.06 | LS | 0.0007
LAB00303 | P001 | A044 | 2025-12-03 | C001 | Skilled | 21 | 8 | 168 | 0 | 0.05 | LS | 0.0003
LAB00304 | P001 | A044 | 2025-12-05 | C001 | Skilled | 24 | 8 | 192 | 0 | 0.05 | LS | 0.0003
LAB00305 | P001 | A044 | 2025-12-03 | C001 | Skilled | 17 | 8 | 136 | 0 | 0.06 | LS | 0.0004

## Materials
Material_ID | Project_ID | Activity_ID | Date | Material_Name | Material_Category | Unit | Planned_Quantity | Actual_Quantity | Unit_Cost_INR | Total_Cost_INR | Supplier | Wastage_Quantity | Wastage_Percentage
MAT00001 | P001 | A004 | 2025-01-31 | Material for PCC | Foundation | m3 | 43.24 | 44.55 | 1800 | 80195.48 | Kolkata Builders Supply | 1.21 | 280%
MAT00002 | P001 | A004 | 2025-02-04 | Material for PCC | Foundation | m3 | 31.76 | 33.37 | 1800 | 60072.23 | Kolkata Builders Supply | 0.61 | 188%
MAT00003 | P001 | A004 | 2025-02-06 | Material for PCC | Foundation | m3 | 31.76 | 34.42 | 1800 | 61955.9 | Kolkata Builders Supply | 1.13 | 339%
MAT00004 | P001 | A005 | 2025-02-04 | Material for RCC works | Foundation | m3 | 31.18 | 33.79 | 3400 | 114883.21 | Kolkata Builders Supply | 1.14 | 348%
MAT00005 | P001 | A005 | 2025-02-05 | Material for RCC works | Foundation | m3 | 31.18 | 32.3 | 3400 | 109806.6 | Kolkata Builders Supply | 1.53 | 499%
MAT00006 | P001 | A005 | 2025-02-13 | Material for RCC works | Foundation | m3 | 115.5 | 119.63 | 3400 | 406727.03 | Kolkata Builders Supply | 5.7 | 501%
MAT00007 | P001 | A005 | 2025-02-11 | Material for RCC works | Foundation | m3 | 115.5 | 122.8 | 3400 | 417523.41 | Kolkata Builders Supply | 2.07 | 171%
MAT00008 | P001 | A005 | 2025-02-20 | Material for RCC works | Foundation | m3 | 53.32 | 52.8 | 3400 | 179526.75 | Kolkata Builders Supply | 0.81 | 157%
MAT00009 | P001 | A005 | 2025-02-21 | Material for RCC works | Foundation | m3 | 53.32 | 54.88 | 3400 | 186599.06 | Kolkata Builders Supply | 1.56 | 293%
MAT00010 | P001 | A008 | 2025-03-12 | Material for RCC works | Foundation | m3 | 46.79 | 48.59 | 3600 | 174933.3 | Kolkata Builders Supply | 2.3 | 497%
MAT00011 | P001 | A008 | 2025-03-18 | Material for RCC works | Foundation | m3 | 13.21 | 13.69 | 3600 | 49293.44 | Kolkata Builders Supply | 0.47 | 355%
MAT00012 | P001 | A008 | 2025-03-21 | Material for RCC works | Foundation | m3 | 13.21 | 13.83 | 3600 | 49775.89 | Kolkata Builders Supply | 0.34 | 250%
MAT00013 | P001 | A009 | 2025-03-18 | Material for Columns | Structural works | m3 | 25.63 | 26.27 | 4800 | 126076.75 | Kolkata Builders Supply | 0.79 | 309%
MAT00014 | P001 | A009 | 2025-03-26 | Material for Columns | Structural works | m3 | 4.37 | 4.83 | 4800 | 23202.89 | Kolkata Builders Supply | 0.27 | 591%
MAT00015 | P001 | A010 | 2025-03-27 | Material for Slabs | Structural works | m3 | 21.67 | 23.05 | 4400 | 101405.74 | Kolkata Builders Supply | 1.04 | 474%
MAT00016 | P001 | A010 | 2025-03-26 | Material for Slabs | Structural works | m3 | 21.67 | 21.8 | 4400 | 95908.15 | Kolkata Builders Supply | 0.78 | 369%
MAT00017 | P001 | A010 | 2025-04-03 | Material for Slabs | Structural works | m3 | 68.33 | 72.15 | 4400 | 317461.64 | Kolkata Builders Supply | 1.03 | 145%
MAT00018 | P001 | A011 | 2025-04-01 | Material for Columns | Structural works | m3 | 12.2 | 13.27 | 4800 | 63688.62 | Kolkata Builders Supply | 0.48 | 372%
MAT00019 | P001 | A011 | 2025-04-01 | Material for Columns | Structural works | m3 | 12.2 | 12.88 | 4800 | 61838.29 | Kolkata Builders Supply | 0.21 | 167%
MAT00020 | P001 | A011 | 2025-04-09 | Material for Columns | Structural works | m3 | 17.8 | 18.16 | 4800 | 87164.21 | Kolkata Builders Supply | 0.83 | 477%
MAT00021 | P001 | A011 | 2025-04-11 | Material for Columns | Structural works | m3 | 17.8 | 18.26 | 4800 | 87629.62 | Kolkata Builders Supply | 0.81 | 461%
MAT00022 | P001 | A012 | 2025-04-11 | Material for Slabs | Structural works | m3 | 12.17 | 12.55 | 4400 | 55228.29 | Kolkata Builders Supply | 0.34 | 281%
MAT00023 | P001 | A012 | 2025-04-10 | Material for Slabs | Structural works | m3 | 12.17 | 12.08 | 4400 | 53135.61 | Kolkata Builders Supply | 0.44 | 374%
MAT00024 | P001 | A012 | 2025-04-18 | Material for Slabs | Structural works | m3 | 77.83 | 81.18 | 4400 | 357198.66 | Kolkata Builders Supply | 2.01 | 254%
MAT00025 | P001 | A012 | 2025-04-17 | Material for Slabs | Structural works | m3 | 77.83 | 80.93 | 4400 | 356090.72 | Kolkata Builders Supply | 3.91 | 508%
MAT00026 | P001 | A013 | 2025-04-25 | Material for Columns | Structural works | m3 | 5.04 | 5.27 | 4800 | 25285.08 | Kolkata Builders Supply | 0.11 | 211%
MAT00027 | P001 | A013 | 2025-04-29 | Material for Columns | Structural works | m3 | 7.47 | 7.43 | 4800 | 35658.52 | Kolkata Builders Supply | 0.28 | 397%
MAT00028 | P001 | A013 | 2025-05-08 | Material for Columns | Structural works | m3 | 7.33 | 7.28 | 4800 | 34935.49 | Kolkata Builders Supply | 0.09 | 130%
MAT00029 | P001 | A013 | 2025-05-06 | Material for Columns | Structural works | m3 | 7.33 | 7.66 | 4800 | 36748.24 | Kolkata Builders Supply | 0.23 | 314%
MAT00030 | P001 | A013 | 2025-05-14 | Material for Columns | Structural works | m3 | 10.16 | 10.27 | 4800 | 49306.94 | Kolkata Builders Supply | 0.23 | 227%
MAT00031 | P001 | A014 | 2025-04-30 | Material for Slabs | Structural works | m3 | 60.96 | 61.66 | 4400 | 271292.59 | Kolkata Builders Supply | 1.33 | 220%
MAT00032 | P001 | A014 | 2025-05-08 | Material for Slabs | Structural works | m3 | 29.04 | 29.01 | 4400 | 127628.4 | Kolkata Builders Supply | 0.56 | 198%
MAT00033 | P001 | A014 | 2025-05-06 | Material for Slabs | Structural works | m3 | 29.04 | 30.17 | 4400 | 132752.86 | Kolkata Builders Supply | 1.48 | 517%
MAT00034 | P001 | A015 | 2025-05-06 | Material for Columns | Structural works | m3 | 6.79 | 6.98 | 4800 | 33480.11 | Kolkata Builders Supply | 0.07 | 108%
MAT00035 | P001 | A015 | 2025-05-07 | Material for Columns | Structural works | m3 | 6.79 | 6.7 | 4800 | 32143 | Kolkata Builders Supply | 0.24 | 365%
MAT00036 | P001 | A015 | 2025-05-16 | Material for Columns | Structural works | m3 | 23.21 | 23.79 | 4800 | 114193.34 | Kolkata Builders Supply | 0.86 | 376%
MAT00037 | P001 | A015 | 2025-05-16 | Material for Columns | Structural works | m3 | 23.21 | 24.59 | 4800 | 118017.28 | Kolkata Builders Supply | 1.06 | 451%
MAT00038 | P001 | A016 | 2025-05-13 | Material for Slabs | Structural works | m3 | 31.83 | 31.43 | 4400 | 138296.32 | Kolkata Builders Supply | 0.68 | 220%
MAT00039 | P001 | A016 | 2025-05-13 | Material for Slabs | Structural works | m3 | 31.83 | 33.59 | 4400 | 147799.93 | Kolkata Builders Supply | 1.2 | 370%
MAT00040 | P001 | A016 | 2025-05-23 | Material for Slabs | Structural works | m3 | 58.17 | 62.64 | 4400 | 275619.71 | Kolkata Builders Supply | 2.74 | 457%
MAT00041 | P001 | A016 | 2025-05-22 | Material for Slabs | Structural works | m3 | 58.17 | 58.47 | 4400 | 257268.28 | Kolkata Builders Supply | 1.65 | 290%
MAT00042 | P001 | A017 | 2025-05-22 | Material for Columns | Structural works | m3 | 2 | 2.08 | 4800 | 9997.32 | Kolkata Builders Supply | 0.1 | 490%
MAT00043 | P001 | A017 | 2025-05-20 | Material for Columns | Structural works | m3 | 2 | 2.05 | 4800 | 9861.68 | Kolkata Builders Supply | 0.04 | 185%
MAT00044 | P001 | A017 | 2025-05-29 | Material for Columns | Structural works | m3 | 28 | 28.93 | 4800 | 138876.05 | Kolkata Builders Supply | 1.4 | 508%
MAT00045 | P001 | A017 | 2025-05-29 | Material for Columns | Structural works | m3 | 28 | 28.54 | 4800 | 136993.88 | Kolkata Builders Supply | 1.1 | 402%
MAT00046 | P001 | A018 | 2025-06-06 | Material for Slabs | Structural works | m3 | 31.83 | 34.13 | 4400 | 150154.17 | Kolkata Builders Supply | 1.61 | 495%
MAT00047 | P001 | A018 | 2025-06-12 | Material for Slabs | Structural works | m3 | 58.17 | 57.01 | 4400 | 250846.67 | Kolkata Builders Supply | 1.18 | 211%
MAT00048 | P001 | A019 | 2025-06-12 | Material for Columns | Structural works | m3 | 9.03 | 9.35 | 4800 | 44899.56 | Kolkata Builders Supply | 0.17 | 182%
MAT00049 | P001 | A019 | 2025-06-18 | Material for Columns | Structural works | m3 | 20.97 | 22.4 | 4800 | 107506.7 | Kolkata Builders Supply | 0.8 | 368%
MAT00050 | P001 | A020 | 2025-06-17 | Material for Slabs | Structural works | m3 | 11.63 | 11.73 | 4400 | 51600.85 | Kolkata Builders Supply | 0.19 | 169%
MAT00051 | P001 | A020 | 2025-06-19 | Material for Slabs | Structural works | m3 | 11.63 | 11.93 | 4400 | 52511.22 | Kolkata Builders Supply | 0.4 | 343%
MAT00052 | P001 | A020 | 2025-06-25 | Material for Slabs | Structural works | m3 | 78.37 | 76.3 | 4400 | 335706.43 | Kolkata Builders Supply | 1.59 | 212%
MAT00053 | P001 | A020 | 2025-06-24 | Material for Slabs | Structural works | m3 | 78.37 | 78.26 | 4400 | 344354.1 | Kolkata Builders Supply | 2.49 | 329%
MAT00054 | P001 | A021 | 2025-06-25 | Material for Columns | Structural works | m3 | 3.71 | 3.9 | 4800 | 18696.38 | Kolkata Builders Supply | 0.08 | 218%
MAT00055 | P001 | A021 | 2025-07-01 | Material for Columns | Structural works | m3 | 26.29 | 26.54 | 4800 | 127371.84 | Kolkata Builders Supply | 1.2 | 475%
MAT00056 | P001 | A022 | 2025-07-11 | Material for Slabs | Structural works | m3 | 33.97 | 33.72 | 4400 | 148358.64 | Kolkata Builders Supply | 0.34 | 101%
MAT00057 | P001 | A022 | 2025-07-09 | Material for Slabs | Structural works | m3 | 33.97 | 35.9 | 4400 | 157938.3 | Kolkata Builders Supply | 1.14 | 329%
MAT00058 | P001 | A022 | 2025-07-16 | Material for Slabs | Structural works | m3 | 56.03 | 62.07 | 4400 | 273122.19 | Kolkata Builders Supply | 3.26 | 555%
MAT00059 | P001 | A023 | 2025-07-15 | Material for Columns | Structural works | m3 | 23.1 | 24.75 | 4800 | 118786.7 | Kolkata Builders Supply | 1.2 | 509%
MAT00060 | P001 | A023 | 2025-07-22 | Material for Columns | Structural works | m3 | 6.9 | 7.36 | 4800 | 35307.81 | Kolkata Builders Supply | 0.28 | 395%
MAT00061 | P001 | A024 | 2025-07-23 | Material for Slabs | Structural works | m3 | 24.04 | 25.53 | 4400 | 112337.12 | Kolkata Builders Supply | 1.42 | 589%
MAT00062 | P001 | A024 | 2025-07-29 | Material for Slabs | Structural works | m3 | 65.96 | 69.15 | 4400 | 304243.79 | Kolkata Builders Supply | 2.34 | 351%
MAT00063 | P001 | A024 | 2025-07-31 | Material for Slabs | Structural works | m3 | 65.96 | 67.42 | 4400 | 296663.83 | Kolkata Builders Supply | 1.97 | 301%
MAT00064 | P001 | A025 | 2025-07-30 | Material for Columns | Structural works | m3 | 6.98 | 7.05 | 4800 | 33844.14 | Kolkata Builders Supply | 0.33 | 491%
MAT00065 | P001 | A025 | 2025-08-01 | Material for Columns | Structural works | m3 | 6.98 | 7.26 | 4800 | 34837.69 | Kolkata Builders Supply | 0.11 | 159%
MAT00066 | P001 | A025 | 2025-08-05 | Material for Columns | Structural works | m3 | 23.02 | 24.43 | 4800 | 117258.8 | Kolkata Builders Supply | 1.29 | 557%
MAT00067 | P001 | A026 | 2025-08-07 | Material for Slabs | Structural works | m3 | 8.14 | 8.5 | 4400 | 37404.95 | Kolkata Builders Supply | 0.47 | 586%
MAT00068 | P001 | A026 | 2025-08-07 | Material for Slabs | Structural works | m3 | 8.14 | 8.64 | 4400 | 38006.27 | Kolkata Builders Supply | 0.31 | 373%
MAT00069 | P001 | A026 | 2025-08-13 | Material for Slabs | Structural works | m3 | 81.86 | 88.18 | 4400 | 387981.42 | Kolkata Builders Supply | 3.06 | 360%
MAT00070 | P001 | A027 | 2025-08-22 | Material for Columns | Structural works | m3 | 30 | 30.85 | 4800 | 148060.74 | Kolkata Builders Supply | 0.99 | 332%
MAT00071 | P001 | A028 | 2025-08-29 | Material for Slabs | Structural works | m3 | 25.66 | 27.25 | 4400 | 119905.44 | Kolkata Builders Supply | 0.76 | 286%
MAT00072 | P001 | A028 | 2025-09-04 | Material for Slabs | Structural works | m3 | 64.34 | 63.52 | 4400 | 279500.23 | Kolkata Builders Supply | 1.29 | 207%
MAT00073 | P001 | A028 | 2025-09-04 | Material for Slabs | Structural works | m3 | 64.34 | 64.92 | 4400 | 285652.76 | Kolkata Builders Supply | 2.03 | 323%
MAT00074 | P001 | A029 | 2025-09-04 | Material for Columns | Structural works | m3 | 7.94 | 8.34 | 4800 | 40047.66 | Kolkata Builders Supply | 0.38 | 483%
MAT00075 | P001 | A029 | 2025-09-04 | Material for Columns | Structural works | m3 | 7.94 | 8.44 | 4800 | 40492.86 | Kolkata Builders Supply | 0.12 | 150%
MAT00076 | P001 | A029 | 2025-09-09 | Material for Columns | Structural works | m3 | 22.06 | 22.53 | 4800 | 108164.36 | Kolkata Builders Supply | 0.25 | 110%
MAT00077 | P001 | A030 | 2025-09-16 | Material for Slabs | Structural works | m3 | 14.42 | 15.4 | 4400 | 67779.6 | Kolkata Builders Supply | 0.74 | 507%
MAT00078 | P001 | A030 | 2025-09-25 | Material for Slabs | Structural works | m3 | 37.79 | 38.46 | 4400 | 169230.95 | Kolkata Builders Supply | 0.87 | 233%
MAT00079 | P001 | A030 | 2025-09-26 | Material for Slabs | Structural works | m3 | 37.79 | 39.58 | 4400 | 174148.24 | Kolkata Builders Supply | 1.06 | 275%
MAT00080 | P001 | A030 | 2025-09-30 | Material for Slabs | Structural works | m3 | 37.79 | 36.85 | 4400 | 162137.46 | Kolkata Builders Supply | 0.67 | 185%
MAT00081 | P001 | A031 | 2025-05-28 | Material for External | Masonry | m2 | 24.42 | 25.16 | 340 | 8553.43 | Kolkata Builders Supply | 1.47 | 620%
MAT00082 | P001 | A031 | 2025-05-27 | Material for External | Masonry | m2 | 24.42 | 27.07 | 340 | 9205.25 | Kolkata Builders Supply | 1.49 | 581%
MAT00083 | P001 | A031 | 2025-06-05 | Material for External | Masonry | m2 | 129.2 | 134.74 | 340 | 45810.46 | Kolkata Builders Supply | 10.89 | 879%
MAT00084 | P001 | A031 | 2025-06-12 | Material for External | Masonry | m2 | 170.77 | 174.49 | 340 | 59326.89 | Kolkata Builders Supply | 10.2 | 621%
MAT00085 | P001 | A031 | 2025-06-20 | Material for External | Masonry | m2 | 190.42 | 199.46 | 340 | 67815.56 | Kolkata Builders Supply | 16.41 | 897%
MAT00086 | P001 | A031 | 2025-06-18 | Material for External | Masonry | m2 | 190.42 | 209.84 | 340 | 71347.22 | Kolkata Builders Supply | 11.33 | 571%
MAT00087 | P001 | A031 | 2025-06-25 | Material for External | Masonry | m2 | 212.02 | 216.39 | 340 | 73573.36 | Kolkata Builders Supply | 13.93 | 688%
MAT00088 | P001 | A031 | 2025-07-01 | Material for External | Masonry | m2 | 273.16 | 298.36 | 340 | 101443.33 | Kolkata Builders Supply | 22.34 | 809%
MAT00089 | P001 | A031 | 2025-07-04 | Material for External | Masonry | m2 | 273.16 | 310.71 | 340 | 105641.01 | Kolkata Builders Supply | 30.97 | 1107%
MAT00090 | P001 | A032 | 2025-08-01 | Material for External | Masonry | m2 | 18.47 | 19.59 | 340 | 6660.72 | Kolkata Builders Supply | 1.54 | 854%
MAT00091 | P001 | A032 | 2025-08-08 | Material for External | Masonry | m2 | 115.42 | 129.18 | 340 | 43920.29 | Kolkata Builders Supply | 13.6 | 1177%
MAT00092 | P001 | A032 | 2025-08-08 | Material for External | Masonry | m2 | 115.42 | 122.27 | 340 | 41573.1 | Kolkata Builders Supply | 7.15 | 621%
MAT00093 | P001 | A032 | 2025-08-13 | Material for External | Masonry | m2 | 204.62 | 211.41 | 340 | 71880.26 | Kolkata Builders Supply | 10.92 | 545%
MAT00094 | P001 | A032 | 2025-08-13 | Material for External | Masonry | m2 | 204.62 | 221.66 | 340 | 75364.37 | Kolkata Builders Supply | 14.17 | 683%
MAT00095 | P001 | A032 | 2025-08-21 | Material for External | Masonry | m2 | 151.73 | 164.97 | 340 | 56089.06 | Kolkata Builders Supply | 14.94 | 996%
MAT00096 | P001 | A032 | 2025-08-19 | Material for External | Masonry | m2 | 151.73 | 163.99 | 340 | 55755.89 | Kolkata Builders Supply | 14.64 | 980%
MAT00097 | P001 | A032 | 2025-08-29 | Material for External | Masonry | m2 | 509.77 | 544.73 | 340 | 185207.5 | Kolkata Builders Supply | 41.5 | 825%
MAT00098 | P001 | A032 | 2025-08-29 | Material for External | Masonry | m2 | 509.77 | 554.45 | 340 | 188511.52 | Kolkata Builders Supply | 46.18 | 909%
MAT00099 | P001 | A033 | 2025-09-18 | Material for External | Masonry | m2 | 16.68 | 17.49 | 340 | 5946.42 | Kolkata Builders Supply | 1.64 | 1033%
MAT00100 | P001 | A033 | 2025-09-25 | Material for External | Masonry | m2 | 118.79 | 124.52 | 340 | 42337.83 | Kolkata Builders Supply | 11.46 | 1014%
MAT00101 | P001 | A033 | 2025-09-30 | Material for External | Masonry | m2 | 186.32 | 196.07 | 340 | 66664.41 | Kolkata Builders Supply | 10.99 | 594%
MAT00102 | P001 | A033 | 2025-09-30 | Material for External | Masonry | m2 | 186.32 | 205.07 | 340 | 69725.12 | Kolkata Builders Supply | 21.38 | 1164%
MAT00103 | P001 | A033 | 2025-10-10 | Material for External | Masonry | m2 | 428.21 | 456.36 | 340 | 155162.15 | Kolkata Builders Supply | 26.12 | 607%
MAT00104 | P001 | A034 | 2025-06-27 | Material for Internal | Plastering | m2 | 137.52 | 134.62 | 100 | 13462.01 | Kolkata Builders Supply | 1.92 | 145%
MAT00105 | P001 | A034 | 2025-06-25 | Material for Internal | Plastering | m2 | 137.52 | 142.71 | 100 | 14271.29 | Kolkata Builders Supply | 2.12 | 151%
MAT00106 | P001 | A034 | 2025-07-04 | Material for Internal | Plastering | m2 | 255.59 | 256.99 | 100 | 25699.27 | Kolkata Builders Supply | 11.75 | 479%
MAT00107 | P001 | A034 | 2025-07-11 | Material for Internal | Plastering | m2 | 388.98 | 390.69 | 100 | 39068.88 | Kolkata Builders Supply | 16.76 | 448%
MAT00108 | P001 | A034 | 2025-07-18 | Material for Internal | Plastering | m2 | 398.93 | 397.82 | 100 | 39781.79 | Kolkata Builders Supply | 16.31 | 427%
MAT00109 | P001 | A034 | 2025-07-22 | Material for Internal | Plastering | m2 | 364.62 | 366.49 | 100 | 36648.93 | Kolkata Builders Supply | 19.67 | 567%
MAT00110 | P001 | A034 | 2025-08-01 | Material for Internal | Plastering | m2 | 704.35 | 753.06 | 100 | 75306.31 | Kolkata Builders Supply | 23.6 | 324%
MAT00111 | P001 | A035 | 2025-10-07 | Material for Internal | Plastering | m2 | 110.53 | 116.11 | 100 | 11610.54 | Kolkata Builders Supply | 3.18 | 282%
MAT00112 | P001 | A035 | 2025-10-09 | Material for Internal | Plastering | m2 | 110.53 | 111.36 | 100 | 11136.11 | Kolkata Builders Supply | 5.1 | 480%
MAT00113 | P001 | A035 | 2025-10-15 | Material for Internal | Plastering | m2 | 424.31 | 446.64 | 100 | 44664.01 | Kolkata Builders Supply | 8.56 | 195%
MAT00114 | P001 | A035 | 2025-10-17 | Material for Internal | Plastering | m2 | 424.31 | 420.2 | 100 | 42019.55 | Kolkata Builders Supply | 12.53 | 307%
MAT00115 | P001 | A035 | 2025-10-23 | Material for Internal | Plastering | m2 | 320.15 | 330.39 | 100 | 33039.26 | Kolkata Builders Supply | 12.84 | 404%
MAT00116 | P001 | A035 | 2025-10-22 | Material for Internal | Plastering | m2 | 320.15 | 331.11 | 100 | 33110.81 | Kolkata Builders Supply | 18.2 | 582%
MAT00117 | P001 | A035 | 2025-10-28 | Material for Internal | Plastering | m2 | 249.02 | 266.47 | 100 | 26647.21 | Kolkata Builders Supply | 12.21 | 480%
MAT00118 | P001 | A035 | 2025-10-28 | Material for Internal | Plastering | m2 | 249.02 | 265.43 | 100 | 26542.69 | Kolkata Builders Supply | 14.35 | 571%
MAT00119 | P001 | A035 | 2025-11-05 | Material for Internal | Plastering | m2 | 727.12 | 758.76 | 100 | 75875.76 | Kolkata Builders Supply | 13.45 | 180%
MAT00120 | P001 | A035 | 2025-11-07 | Material for Internal | Plastering | m2 | 727.12 | 753.28 | 100 | 75327.62 | Kolkata Builders Supply | 12.83 | 173%
MAT00121 | P001 | A035 | 2025-11-12 | Material for Internal | Plastering | m2 | 168.87 | 172.53 | 100 | 17253.06 | Kolkata Builders Supply | 8.09 | 492%
MAT00122 | P001 | A035 | 2025-11-11 | Material for Internal | Plastering | m2 | 168.87 | 174.25 | 100 | 17425.26 | Kolkata Builders Supply | 2.13 | 123%
MAT00123 | P001 | A038 | 2025-08-07 | Material for Tiles | Flooring | m2 | 57.43 | 60.71 | 480 | 29142.02 | Kolkata Builders Supply | 1.04 | 173%
MAT00124 | P001 | A038 | 2025-08-14 | Material for Tiles | Flooring | m2 | 169.89 | 178.1 | 480 | 85487.4 | Kolkata Builders Supply | 6.11 | 355%
MAT00125 | P001 | A038 | 2025-08-21 | Material for Tiles | Flooring | m2 | 197.44 | 212.1 | 480 | 101805.87 | Kolkata Builders Supply | 8.21 | 403%
MAT00126 | P001 | A038 | 2025-08-22 | Material for Tiles | Flooring | m2 | 197.44 | 204.98 | 480 | 98392.64 | Kolkata Builders Supply | 8.02 | 407%
MAT00127 | P001 | A038 | 2025-08-28 | Material for Tiles | Flooring | m2 | 254.37 | 253.35 | 480 | 121608.71 | Kolkata Builders Supply | 8.3 | 339%
MAT00128 | P001 | A038 | 2025-08-26 | Material for Tiles | Flooring | m2 | 254.37 | 268.56 | 480 | 128907.09 | Kolkata Builders Supply | 3.76 | 142%
MAT00129 | P001 | A038 | 2025-09-02 | Material for Tiles | Flooring | m2 | 185.35 | 195.9 | 480 | 94033.61 | Kolkata Builders Supply | 5.83 | 307%
MAT00130 | P001 | A038 | 2025-09-02 | Material for Tiles | Flooring | m2 | 185.35 | 186.2 | 480 | 89377.65 | Kolkata Builders Supply | 6.81 | 380%
MAT00131 | P001 | A038 | 2025-09-12 | Material for Tiles | Flooring | m2 | 635.52 | 659.08 | 480 | 316356.26 | Kolkata Builders Supply | 25.36 | 400%
MAT00132 | P001 | A039 | 2025-11-19 | Material for Tiles | Flooring | m2 | 337.83 | 356.65 | 480 | 171193.06 | Kolkata Builders Supply | 14.93 | 437%
MAT00133 | P001 | A039 | 2025-11-28 | Material for Tiles | Flooring | m2 | 408.88 | 411.29 | 480 | 197419.08 | Kolkata Builders Supply | 6.21 | 153%
MAT00134 | P001 | A039 | 2025-12-03 | Material for Tiles | Flooring | m2 | 255.5 | 271.23 | 480 | 130191.31 | Kolkata Builders Supply | 8.06 | 306%
MAT00135 | P001 | A039 | 2025-12-10 | Material for Tiles | Flooring | m2 | 497.79 | 509.37 | 480 | 244498.06 | Kolkata Builders Supply | 25.06 | 517%
MAT00136 | P001 | A040 | 2025-09-02 | Material for Internal | Painting | m2 | 230.26 | 250.2 | 72 | 18014.26 | Kolkata Builders Supply | 11.64 | 488%
MAT00137 | P001 | A040 | 2025-09-02 | Material for Internal | Painting | m2 | 230.26 | 252.07 | 72 | 18148.7 | Kolkata Builders Supply | 10.83 | 449%
MAT00138 | P001 | A040 | 2025-09-11 | Material for Internal | Painting | m2 | 394.54 | 407.73 | 72 | 29356.89 | Kolkata Builders Supply | 15.14 | 386%
MAT00139 | P001 | A040 | 2025-09-11 | Material for Internal | Painting | m2 | 394.54 | 425.67 | 72 | 30648.05 | Kolkata Builders Supply | 18.74 | 460%
MAT00140 | P001 | A040 | 2025-09-19 | Material for Internal | Painting | m2 | 685.78 | 722.98 | 72 | 52054.65 | Kolkata Builders Supply | 17.63 | 250%
MAT00141 | P001 | A040 | 2025-09-19 | Material for Internal | Painting | m2 | 685.78 | 709.04 | 72 | 51050.67 | Kolkata Builders Supply | 30.23 | 445%
MAT00142 | P001 | A040 | 2025-09-23 | Material for Internal | Painting | m2 | 401.55 | 408.54 | 72 | 29414.84 | Kolkata Builders Supply | 14.01 | 355%
MAT00143 | P001 | A040 | 2025-09-24 | Material for Internal | Painting | m2 | 401.55 | 429.32 | 72 | 30910.69 | Kolkata Builders Supply | 12.12 | 291%
MAT00144 | P001 | A040 | 2025-10-03 | Material for Internal | Painting | m2 | 889.14 | 898.41 | 72 | 64685.88 | Kolkata Builders Supply | 16.92 | 192%
MAT00145 | P001 | A040 | 2025-10-01 | Material for Internal | Painting | m2 | 889.14 | 874.4 | 72 | 62956.9 | Kolkata Builders Supply | 18.6 | 217%
MAT00146 | P001 | A040 | 2025-10-09 | Material for Internal | Painting | m2 | 655.24 | 654.15 | 72 | 47099.13 | Kolkata Builders Supply | 15.46 | 242%
MAT00147 | P001 | A040 | 2025-10-16 | Material for Internal | Painting | m2 | 993.49 | 1069.36 | 72 | 76994.05 | Kolkata Builders Supply | 35.25 | 341%
MAT00148 | P001 | A040 | 2025-10-15 | Material for Internal | Painting | m2 | 993.49 | 1056.62 | 72 | 76076.52 | Kolkata Builders Supply | 32.86 | 321%
MAT00149 | P001 | A041 | 2025-11-11 | Material for External | Painting | m2 | 193.3 | 194.74 | 88 | 17137.42 | Kolkata Builders Supply | 3.47 | 182%
MAT00150 | P001 | A041 | 2025-11-14 | Material for External | Painting | m2 | 193.3 | 203.85 | 88 | 17938.88 | Kolkata Builders Supply | 4.2 | 210%
MAT00151 | P001 | A041 | 2025-11-19 | Material for External | Painting | m2 | 525.99 | 555.1 | 88 | 48848.48 | Kolkata Builders Supply | 18.56 | 346%
MAT00152 | P001 | A041 | 2025-11-21 | Material for External | Painting | m2 | 525.99 | 506.96 | 88 | 44612.33 | Kolkata Builders Supply | 6.25 | 125%
MAT00153 | P001 | A041 | 2025-11-25 | Material for External | Painting | m2 | 646.95 | 673.8 | 88 | 59294.3 | Kolkata Builders Supply | 9.02 | 136%
MAT00154 | P001 | A041 | 2025-11-26 | Material for External | Painting | m2 | 646.95 | 660.66 | 88 | 58138.17 | Kolkata Builders Supply | 34.31 | 548%
MAT00155 | P001 | A041 | 2025-12-05 | Material for External | Painting | m2 | 844.3 | 865.56 | 88 | 76169.34 | Kolkata Builders Supply | 10.36 | 121%
MAT00156 | P001 | A041 | 2025-12-10 | Material for External | Painting | m2 | 539.46 | 544.31 | 88 | 47899.55 | Kolkata Builders Supply | 18.4 | 350%

## Quality
Inspection_ID | Project_ID | Activity_ID | Date | Contractor_ID | Inspection_Type | Test_or_Check | Result | Defect_Type | Defect_Severity | Rework_Required | Rework_Cost_INR | Remarks
Q0001 | P001 | A001 | 2025-01-03 | C001 | Mobilization Inspection | Visual & Measurement | Fail | Crack | Medium | Yes | 12703 | Rework ordered
Q0002 | P001 | A003 | 2025-01-31 | C001 | Excavation Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0003 | P001 | A003 | 2025-02-07 | C001 | Excavation Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0004 | P001 | A003 | 2025-02-14 | C001 | Excavation Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0005 | P001 | A004 | 2025-02-07 | C002 | PCC Inspection | Visual & Measurement | Conditional Pass | Alignment | High | No | 7524 | Approved
Q0006 | P001 | A006 | 2025-02-28 | C005 | Foundation Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0007 | P001 | A007 | 2025-03-07 | C001 | Filling Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0008 | P001 | A007 | 2025-03-14 | C001 | Filling Inspection | Visual & Measurement | Fail | Surface Finish | High | Yes | 7850 | Rework ordered
Q0009 | P001 | A013 | 2025-05-09 | C002 | Columns Inspection | Visual & Measurement | Conditional Pass | Surface Finish | Low | No | 13360 | Approved
Q0010 | P001 | A013 | 2025-05-16 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0011 | P001 | A015 | 2025-05-16 | C002 | Columns Inspection | Visual & Measurement | Conditional Pass | Honeycombing | High | No | 10286 | Approved
Q0012 | P001 | A017 | 2025-05-23 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0013 | P001 | A018 | 2025-06-13 | C002 | Slabs Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0014 | P001 | A022 | 2025-07-18 | C002 | Slabs Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0015 | P001 | A023 | 2025-07-25 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0016 | P001 | A024 | 2025-08-01 | C002 | Slabs Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0017 | P001 | A025 | 2025-08-08 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0018 | P001 | A029 | 2025-09-05 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0019 | P001 | A029 | 2025-09-12 | C002 | Columns Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0020 | P001 | A031 | 2025-06-27 | C003 | External Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0021 | P001 | A032 | 2025-08-08 | C003 | External Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0022 | P001 | A032 | 2025-08-15 | C003 | External Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0023 | P001 | A033 | 2025-10-03 | C003 | External Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0024 | P001 | A033 | 2025-10-10 | C003 | External Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0025 | P001 | A034 | 2025-07-04 | C004 | Internal Inspection | Visual & Measurement | Fail | Honeycombing | Medium | Yes | 6857 | Rework ordered
Q0026 | P001 | A035 | 2025-10-10 | C004 | Internal Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0027 | P001 | A036 | 2025-07-11 | C006 | Electrical Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0028 | P001 | A036 | 2025-08-08 | C006 | Electrical Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0029 | P001 | A037 | 2025-06-27 | C007 | Plumbing Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0030 | P001 | A037 | 2025-08-15 | C007 | Plumbing Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0031 | P001 | A038 | 2025-08-08 | C008 | Tiles Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0032 | P001 | A038 | 2025-08-29 | C008 | Tiles Inspection | Visual & Measurement | Fail | Crack | High | Yes | 9561 | Rework ordered
Q0033 | P001 | A038 | 2025-09-05 | C008 | Tiles Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0034 | P001 | A038 | 2025-09-12 | C008 | Tiles Inspection | Visual & Measurement | Conditional Pass | Crack | High | No | 7296 | Approved
Q0035 | P001 | A039 | 2025-11-21 | C008 | Tiles Inspection | Visual & Measurement | Fail | Honeycombing | Low | Yes | 5520 | Rework ordered
Q0036 | P001 | A039 | 2025-12-12 | C008 | Tiles Inspection | Visual & Measurement | Fail | Crack | High | Yes | 11869 | Rework ordered
Q0037 | P001 | A040 | 2025-09-05 | C004 | Internal Inspection | Visual & Measurement | Fail | Honeycombing | Medium | Yes | 10519 | Rework ordered
Q0038 | P001 | A040 | 2025-09-19 | C004 | Internal Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0039 | P001 | A040 | 2025-10-10 | C004 | Internal Inspection | Visual & Measurement | Conditional Pass | Alignment | Medium | No | 8801 | Approved
Q0040 | P001 | A041 | 2025-11-21 | C004 | External Inspection | Visual & Measurement | Fail | Alignment | Low | Yes | 12717 | Rework ordered
Q0041 | P001 | A041 | 2025-12-05 | C004 | External Inspection | Visual & Measurement | Conditional Pass | Crack | High | No | 4568 | Approved
Q0042 | P001 | A042 | 2025-08-08 | C009 | Installation Inspection | Visual & Measurement | Fail | Workmanship | Medium | Yes | 4110 | Rework ordered
Q0043 | P001 | A042 | 2025-09-12 | C009 | Installation Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0044 | P001 | A043 | 2025-10-31 | C006 | Electrical Inspection | Visual & Measurement | Fail | Workmanship | High | Yes | 3450 | Rework ordered
Q0045 | P001 | A044 | 2025-11-14 | C001 | Cleaning Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved
Q0046 | P001 | A044 | 2025-11-21 | C001 | Cleaning Inspection | Visual & Measurement | Fail | Honeycombing | Low | Yes | 12228 | Rework ordered
Q0047 | P001 | A044 | 2025-12-05 | C001 | Cleaning Inspection | Visual & Measurement | Pass | None | None | No | 0 | Approved

## Equipment
Equipment_ID | Project_ID | Activity_ID | Date | Equipment_Name | Equipment_Type | Operating_Hours | Downtime_Hours | Fuel_Consumption_Litres | Rental_Cost_INR | Maintenance_Cost_INR | Equipment_Status
EQ0001 | P001 | A002 | 2025-01-10 | Tower Crane - 01 | Tower Crane | 5 | 0 | 45 | 8220 | 0 | Operational
EQ0002 | P001 | A002 | 2025-01-15 | Transit Mixer - 01 | Transit Mixer | 10 | 0 | 130 | 22100 | 0 | Operational
EQ0003 | P001 | A003 | 2025-01-23 | Vibrator - 01 | Vibrator | 5 | 0 | 40 | 6265 | 0 | Operational
EQ0004 | P001 | A003 | 2025-01-31 | Tower Crane - 01 | Tower Crane | 10 | 0 | 130 | 22430 | 0 | Operational
EQ0005 | P001 | A003 | 2025-02-05 | Transit Mixer - 01 | Transit Mixer | 4 | 0 | 40 | 8480 | 0 | Operational
EQ0006 | P001 | A003 | 2025-02-13 | Vibrator - 01 | Vibrator | 8 | 0 | 64 | 8928 | 0 | Operational
EQ0007 | P001 | A004 | 2025-01-29 | Tower Crane - 01 | Tower Crane | 10 | 0 | 110 | 12640 | 0 | Operational
EQ0008 | P001 | A004 | 2025-02-06 | Concrete Mixer - 01 | Concrete Mixer | 4 | 0 | 20 | 4400 | 0 | Operational
EQ0009 | P001 | A005 | 2025-02-06 | Excavator - 01 | Excavator | 9 | 0 | 126 | 19656 | 0 | Operational
EQ0010 | P001 | A005 | 2025-02-13 | Excavator - 01 | Excavator | 5 | 3 | 50 | 6420 | 14667 | Breakdown
EQ0011 | P001 | A005 | 2025-02-20 | Transit Mixer - 01 | Transit Mixer | 10 | 0 | 80 | 17530 | 0 | Operational
EQ0012 | P001 | A007 | 2025-02-28 | Concrete Mixer - 01 | Concrete Mixer | 8 | 0 | 56 | 14792 | 0 | Operational
EQ0013 | P001 | A007 | 2025-03-05 | Vibrator - 01 | Vibrator | 9 | 3 | 81 | 16326 | 14754 | Breakdown
EQ0014 | P001 | A007 | 2025-03-14 | Excavator - 01 | Excavator | 6 | 0 | 54 | 8520 | 0 | Operational
EQ0015 | P001 | A007 | 2025-03-19 | Transit Mixer - 01 | Transit Mixer | 7 | 0 | 105 | 10241 | 0 | Operational
EQ0016 | P001 | A008 | 2025-03-14 | Vibrator - 01 | Vibrator | 6 | 0 | 84 | 9252 | 0 | Operational
EQ0017 | P001 | A008 | 2025-03-20 | Transit Mixer - 01 | Transit Mixer | 6 | 0 | 84 | 6780 | 0 | Operational
EQ0018 | P001 | A009 | 2025-03-19 | Concrete Mixer - 01 | Concrete Mixer | 7 | 0 | 84 | 16009 | 0 | Operational
EQ0019 | P001 | A009 | 2025-03-27 | Concrete Mixer - 01 | Concrete Mixer | 9 | 0 | 108 | 10926 | 0 | Operational
EQ0020 | P001 | A010 | 2025-03-26 | Concrete Mixer - 01 | Concrete Mixer | 4 | 0 | 32 | 3984 | 0 | Operational
EQ0021 | P001 | A010 | 2025-04-04 | Vibrator - 01 | Vibrator | 9 | 0 | 63 | 12195 | 0 | Operational
EQ0022 | P001 | A011 | 2025-04-03 | Transit Mixer - 01 | Transit Mixer | 5 | 0 | 35 | 9985 | 0 | Operational
EQ0023 | P001 | A011 | 2025-04-11 | Transit Mixer - 01 | Transit Mixer | 9 | 0 | 45 | 16803 | 0 | Operational
EQ0024 | P001 | A012 | 2025-04-10 | Vibrator - 01 | Vibrator | 8 | 0 | 104 | 11232 | 0 | Operational
EQ0025 | P001 | A012 | 2025-04-16 | Vibrator - 01 | Vibrator | 4 | 2 | 24 | 6432 | 2492 | Breakdown
EQ0026 | P001 | A013 | 2025-04-23 | Excavator - 01 | Excavator | 6 | 0 | 78 | 8208 | 0 | Operational
EQ0027 | P001 | A013 | 2025-05-02 | Vibrator - 01 | Vibrator | 9 | 0 | 72 | 18144 | 0 | Operational
EQ0028 | P001 | A013 | 2025-05-07 | Excavator - 01 | Excavator | 6 | 0 | 66 | 12654 | 0 | Operational
EQ0029 | P001 | A013 | 2025-05-16 | Excavator - 01 | Excavator | 7 | 0 | 91 | 13881 | 0 | Operational
EQ0030 | P001 | A014 | 2025-04-30 | Transit Mixer - 01 | Transit Mixer | 7 | 0 | 70 | 7917 | 0 | Operational
EQ0031 | P001 | A014 | 2025-05-08 | Vibrator - 01 | Vibrator | 9 | 0 | 81 | 18567 | 0 | Operational
EQ0032 | P001 | A015 | 2025-05-07 | Vibrator - 01 | Vibrator | 6 | 3 | 66 | 12906 | 14547 | Breakdown
EQ0033 | P001 | A015 | 2025-05-15 | Tower Crane - 01 | Tower Crane | 10 | 0 | 140 | 22570 | 0 | Operational
EQ0034 | P001 | A016 | 2025-05-14 | Concrete Mixer - 01 | Concrete Mixer | 10 | 0 | 60 | 15250 | 0 | Operational
EQ0035 | P001 | A016 | 2025-05-23 | Tower Crane - 01 | Tower Crane | 6 | 0 | 30 | 14586 | 0 | Operational
EQ0036 | P001 | A017 | 2025-05-22 | Concrete Mixer - 01 | Concrete Mixer | 5 | 0 | 60 | 3990 | 0 | Operational
EQ0037 | P001 | A017 | 2025-05-29 | Tower Crane - 01 | Tower Crane | 6 | 0 | 60 | 6576 | 0 | Operational
EQ0038 | P001 | A018 | 2025-06-05 | Tower Crane - 01 | Tower Crane | 8 | 0 | 104 | 12296 | 0 | Operational
EQ0039 | P001 | A018 | 2025-06-11 | Tower Crane - 01 | Tower Crane | 6 | 0 | 84 | 11484 | 0 | Operational
EQ0040 | P001 | A019 | 2025-06-12 | Vibrator - 01 | Vibrator | 5 | 0 | 65 | 6865 | 0 | Operational
EQ0041 | P001 | A019 | 2025-06-19 | Transit Mixer - 01 | Transit Mixer | 5 | 0 | 75 | 11330 | 0 | Operational
EQ0042 | P001 | A020 | 2025-06-20 | Vibrator - 01 | Vibrator | 5 | 0 | 35 | 5720 | 0 | Operational
EQ0043 | P001 | A020 | 2025-06-27 | Vibrator - 01 | Vibrator | 8 | 0 | 72 | 16696 | 0 | Operational
EQ0044 | P001 | A021 | 2025-06-25 | Vibrator - 01 | Vibrator | 9 | 0 | 63 | 18963 | 0 | Operational
EQ0045 | P001 | A021 | 2025-07-04 | Excavator - 01 | Excavator | 6 | 0 | 42 | 6066 | 0 | Operational
EQ0046 | P001 | A022 | 2025-07-11 | Excavator - 01 | Excavator | 10 | 0 | 110 | 21890 | 0 | Operational
EQ0047 | P001 | A022 | 2025-07-17 | Concrete Mixer - 01 | Concrete Mixer | 10 | 0 | 60 | 18400 | 0 | Operational
EQ0048 | P001 | A023 | 2025-07-18 | Concrete Mixer - 01 | Concrete Mixer | 7 | 2 | 42 | 4977 | 4566 | Breakdown
EQ0049 | P001 | A023 | 2025-07-25 | Transit Mixer - 01 | Transit Mixer | 7 | 0 | 56 | 7469 | 0 | Operational
EQ0050 | P001 | A024 | 2025-07-23 | Transit Mixer - 01 | Transit Mixer | 5 | 0 | 55 | 6240 | 0 | Operational
EQ0051 | P001 | A024 | 2025-07-30 | Transit Mixer - 01 | Transit Mixer | 4 | 0 | 32 | 9980 | 0 | Operational
EQ0052 | P001 | A025 | 2025-07-30 | Transit Mixer - 01 | Transit Mixer | 10 | 0 | 60 | 10380 | 0 | Operational
EQ0053 | P001 | A025 | 2025-08-06 | Concrete Mixer - 01 | Concrete Mixer | 6 | 0 | 60 | 6330 | 0 | Operational
EQ0054 | P001 | A026 | 2025-08-08 | Concrete Mixer - 01 | Concrete Mixer | 4 | 0 | 32 | 6436 | 0 | Operational
EQ0055 | P001 | A026 | 2025-08-13 | Tower Crane - 01 | Tower Crane | 9 | 1 | 63 | 16245 | 4358 | Breakdown
EQ0056 | P001 | A027 | 2025-08-21 | Excavator - 01 | Excavator | 5 | 0 | 70 | 2910 | 0 | Operational
EQ0057 | P001 | A028 | 2025-08-29 | Vibrator - 01 | Vibrator | 8 | 0 | 40 | 5056 | 0 | Operational
EQ0058 | P001 | A028 | 2025-09-05 | Excavator - 01 | Excavator | 8 | 0 | 120 | 8832 | 0 | Operational
EQ0059 | P001 | A029 | 2025-09-03 | Transit Mixer - 01 | Transit Mixer | 8 | 0 | 40 | 16512 | 0 | Operational
EQ0060 | P001 | A029 | 2025-09-12 | Excavator - 01 | Excavator | 6 | 0 | 42 | 7182 | 0 | Operational
EQ0061 | P001 | A030 | 2025-09-19 | Transit Mixer - 01 | Transit Mixer | 9 | 0 | 63 | 17928 | 0 | Operational
EQ0062 | P001 | A030 | 2025-09-24 | Excavator - 01 | Excavator | 4 | 0 | 44 | 9936 | 0 | Operational
EQ0063 | P001 | A030 | 2025-10-02 | Concrete Mixer - 01 | Concrete Mixer | 9 | 1 | 126 | 15804 | 4658 | Breakdown

## Weather
Weather_ID | Date | Location | Temperature_C | Rainfall_mm | Humidity_Percentage | Weather_Condition | Working_Days_Lost | Weather_Impact
W20250101 | 2025-01-01 | Kolkata | 25 | 40 | 43 | Light Rain | 0 | Low
W20250102 | 2025-01-02 | Kolkata | 18 | 0 | 47 | Cloudy | 0 | None
W20250103 | 2025-01-03 | Kolkata | 26 | 0 | 57 | Clear | 0 | None
W20250104 | 2025-01-04 | Kolkata | 15 | 0 | 42 | Clear | 0 | None
W20250105 | 2025-01-05 | Kolkata | 15 | 0 | 57 | Clear | 0 | None
W20250106 | 2025-01-06 | Kolkata | 23 | 0 | 53 | Clear | 0 | None
W20250107 | 2025-01-07 | Kolkata | 27 | 0 | 40 | Cloudy | 0 | None
W20250108 | 2025-01-08 | Kolkata | 21 | 0 | 50 | Cloudy | 0 | None
W20250109 | 2025-01-09 | Kolkata | 27 | 0 | 50 | Clear | 0 | None
W20250110 | 2025-01-10 | Kolkata | 20 | 0 | 51 | Clear | 0 | None
W20250111 | 2025-01-11 | Kolkata | 26 | 0 | 54 | Clear | 0 | None
W20250112 | 2025-01-12 | Kolkata | 21 | 0 | 42 | Clear | 0 | None
W20250113 | 2025-01-13 | Kolkata | 24 | 0 | 51 | Clear | 0 | None
W20250114 | 2025-01-14 | Kolkata | 15 | 0 | 61 | Cloudy | 0 | None
W20250115 | 2025-01-15 | Kolkata | 16 | 0 | 47 | Clear | 0 | None
W20250116 | 2025-01-16 | Kolkata | 22 | 0 | 60 | Cloudy | 0 | None
W20250117 | 2025-01-17 | Kolkata | 20 | 0 | 46 | Clear | 0 | None
W20250118 | 2025-01-18 | Kolkata | 25 | 0 | 60 | Clear | 0 | None
W20250119 | 2025-01-19 | Kolkata | 23 | 0 | 63 | Clear | 0 | None
W20250120 | 2025-01-20 | Kolkata | 19 | 0 | 60 | Cloudy | 0 | None
W20250121 | 2025-01-21 | Kolkata | 20 | 0 | 64 | Cloudy | 0 | None
W20250122 | 2025-01-22 | Kolkata | 15 | 0 | 65 | Cloudy | 0 | None
W20250123 | 2025-01-23 | Kolkata | 18 | 0 | 58 | Clear | 0 | None
W20250124 | 2025-01-24 | Kolkata | 25 | 0 | 55 | Clear | 0 | None
W20250125 | 2025-01-25 | Kolkata | 22 | 0 | 44 | Cloudy | 0 | None
W20250126 | 2025-01-26 | Kolkata | 23 | 0 | 57 | Clear | 0 | None
W20250127 | 2025-01-27 | Kolkata | 24 | 0 | 52 | Clear | 0 | None
W20250128 | 2025-01-28 | Kolkata | 17 | 0 | 56 | Clear | 0 | None
W20250129 | 2025-01-29 | Kolkata | 28 | 0 | 43 | Cloudy | 0 | None
W20250130 | 2025-01-30 | Kolkata | 25 | 0 | 53 | Clear | 0 | None
W20250131 | 2025-01-31 | Kolkata | 24 | 0 | 54 | Clear | 0 | None
W20250201 | 2025-02-01 | Kolkata | 28 | 0 | 40 | Cloudy | 0 | None
W20250202 | 2025-02-02 | Kolkata | 23 | 0 | 64 | Clear | 0 | None
W20250203 | 2025-02-03 | Kolkata | 16 | 0 | 49 | Clear | 0 | None
W20250204 | 2025-02-04 | Kolkata | 26 | 0 | 63 | Clear | 0 | None
W20250205 | 2025-02-05 | Kolkata | 17 | 0 | 56 | Clear | 0 | None
W20250206 | 2025-02-06 | Kolkata | 19 | 0 | 60 | Cloudy | 0 | None
W20250207 | 2025-02-07 | Kolkata | 20 | 0 | 64 | Clear | 0 | None
W20250208 | 2025-02-08 | Kolkata | 23 | 0 | 40 | Clear | 0 | None
W20250209 | 2025-02-09 | Kolkata | 16 | 0 | 51 | Clear | 0 | None
W20250210 | 2025-02-10 | Kolkata | 19 | 0 | 47 | Clear | 0 | None
W20250211 | 2025-02-11 | Kolkata | 16 | 0 | 42 | Clear | 0 | None
W20250212 | 2025-02-12 | Kolkata | 27 | 0 | 57 | Cloudy | 0 | None
W20250213 | 2025-02-13 | Kolkata | 22 | 0 | 57 | Clear | 0 | None
W20250214 | 2025-02-14 | Kolkata | 24 | 0 | 53 | Clear | 0 | None
W20250215 | 2025-02-15 | Kolkata | 27 | 0 | 63 | Clear | 0 | None
W20250216 | 2025-02-16 | Kolkata | 21 | 0 | 61 | Clear | 0 | None
W20250217 | 2025-02-17 | Kolkata | 23 | 0 | 54 | Cloudy | 0 | None
W20250218 | 2025-02-18 | Kolkata | 20 | 0 | 40 | Cloudy | 0 | None
W20250219 | 2025-02-19 | Kolkata | 18 | 0 | 40 | Clear | 0 | None
W20250220 | 2025-02-20 | Kolkata | 18 | 0 | 42 | Clear | 0 | None
W20250221 | 2025-02-21 | Kolkata | 16 | 0 | 56 | Clear | 0 | None
W20250222 | 2025-02-22 | Kolkata | 18 | 0 | 57 | Clear | 0 | None
W20250223 | 2025-02-23 | Kolkata | 24 | 0 | 58 | Clear | 0 | None
W20250224 | 2025-02-24 | Kolkata | 27 | 0 | 53 | Cloudy | 0 | None
W20250225 | 2025-02-25 | Kolkata | 21 | 0 | 51 | Clear | 0 | None
W20250226 | 2025-02-26 | Kolkata | 26 | 0 | 41 | Clear | 0 | None
W20250227 | 2025-02-27 | Kolkata | 16 | 0 | 41 | Clear | 0 | None
W20250228 | 2025-02-28 | Kolkata | 28 | 0 | 43 | Cloudy | 0 | None
W20250301 | 2025-03-01 | Kolkata | 22 | 0 | 44 | Cloudy | 0 | None
W20250302 | 2025-03-02 | Kolkata | 18 | 0 | 42 | Clear | 0 | None
W20250303 | 2025-03-03 | Kolkata | 23 | 0 | 43 | Clear | 0 | None
W20250304 | 2025-03-04 | Kolkata | 28 | 0 | 40 | Clear | 0 | None
W20250305 | 2025-03-05 | Kolkata | 28 | 0 | 47 | Clear | 0 | None
W20250306 | 2025-03-06 | Kolkata | 18 | 0 | 52 | Cloudy | 0 | None
W20250307 | 2025-03-07 | Kolkata | 15 | 0 | 52 | Clear | 0 | None
W20250308 | 2025-03-08 | Kolkata | 22 | 0 | 49 | Clear | 0 | None
W20250309 | 2025-03-09 | Kolkata | 27 | 0 | 57 | Clear | 0 | None
W20250310 | 2025-03-10 | Kolkata | 18 | 0 | 49 | Cloudy | 0 | None
W20250311 | 2025-03-11 | Kolkata | 26 | 0 | 57 | Clear | 0 | None
W20250312 | 2025-03-12 | Kolkata | 15 | 0 | 58 | Clear | 0 | None
W20250313 | 2025-03-13 | Kolkata | 23 | 0 | 45 | Clear | 0 | None
W20250314 | 2025-03-14 | Kolkata | 28 | 0 | 45 | Cloudy | 0 | None
W20250315 | 2025-03-15 | Kolkata | 28 | 0 | 47 | Clear | 0 | None
W20250316 | 2025-03-16 | Kolkata | 24 | 0 | 47 | Cloudy | 0 | None
W20250317 | 2025-03-17 | Kolkata | 16 | 0 | 53 | Clear | 0 | None
W20250318 | 2025-03-18 | Kolkata | 20 | 0 | 48 | Clear | 0 | None
W20250319 | 2025-03-19 | Kolkata | 18 | 0 | 48 | Clear | 0 | None
W20250320 | 2025-03-20 | Kolkata | 19 | 0 | 54 | Clear | 0 | None
W20250321 | 2025-03-21 | Kolkata | 16 | 0 | 40 | Clear | 0 | None
W20250322 | 2025-03-22 | Kolkata | 16 | 0 | 42 | Clear | 0 | None
W20250323 | 2025-03-23 | Kolkata | 17 | 0 | 51 | Clear | 0 | None
W20250324 | 2025-03-24 | Kolkata | 20 | 0 | 49 | Clear | 0 | None
W20250325 | 2025-03-25 | Kolkata | 26 | 0 | 49 | Clear | 0 | None
W20250326 | 2025-03-26 | Kolkata | 25 | 75 | 56 | Heavy Rain | 1 | High
W20250327 | 2025-03-27 | Kolkata | 19 | 0 | 61 | Clear | 0 | None
W20250328 | 2025-03-28 | Kolkata | 19 | 0 | 43 | Clear | 0 | None
W20250329 | 2025-03-29 | Kolkata | 17 | 0 | 48 | Cloudy | 0 | None
W20250330 | 2025-03-30 | Kolkata | 20 | 0 | 46 | Clear | 0 | None
W20250331 | 2025-03-31 | Kolkata | 23 | 0 | 55 | Clear | 0 | None
W20250401 | 2025-04-01 | Kolkata | 34 | 0 | 62 | Clear | 0 | None
W20250402 | 2025-04-02 | Kolkata | 34 | 0 | 60 | Cloudy | 0 | None
W20250403 | 2025-04-03 | Kolkata | 38 | 0 | 65 | Clear | 0 | None
W20250404 | 2025-04-04 | Kolkata | 40 | 14 | 77 | Hot/Humid | 0 | Low
W20250405 | 2025-04-05 | Kolkata | 36 | 52 | 77 | Heavy Rain | 1 | High
W20250406 | 2025-04-06 | Kolkata | 42 | 0 | 64 | Hot/Humid | 0 | None
W20250407 | 2025-04-07 | Kolkata | 39 | 0 | 61 | Hot/Humid | 0 | None
W20250408 | 2025-04-08 | Kolkata | 37 | 0 | 63 | Clear | 0 | None
W20250409 | 2025-04-09 | Kolkata | 40 | 0 | 79 | Hot/Humid | 0 | None
W20250410 | 2025-04-10 | Kolkata | 37 | 0 | 65 | Clear | 0 | None
W20250411 | 2025-04-11 | Kolkata | 40 | 0 | 60 | Hot/Humid | 0 | None
W20250412 | 2025-04-12 | Kolkata | 40 | 0 | 67 | Hot/Humid | 0 | None
W20250413 | 2025-04-13 | Kolkata | 35 | 0 | 72 | Clear | 0 | None
W20250414 | 2025-04-14 | Kolkata | 37 | 0 | 66 | Clear | 0 | None
W20250415 | 2025-04-15 | Kolkata | 38 | 0 | 67 | Clear | 0 | None
W20250416 | 2025-04-16 | Kolkata | 40 | 0 | 70 | Hot/Humid | 0 | None
W20250417 | 2025-04-17 | Kolkata | 38 | 0 | 71 | Clear | 0 | None
W20250418 | 2025-04-18 | Kolkata | 42 | 0 | 70 | Hot/Humid | 0 | None
W20250419 | 2025-04-19 | Kolkata | 38 | 0 | 65 | Clear | 0 | None
W20250420 | 2025-04-20 | Kolkata | 34 | 0 | 63 | Clear | 0 | None
W20250421 | 2025-04-21 | Kolkata | 39 | 0 | 73 | Hot/Humid | 0 | None
W20250422 | 2025-04-22 | Kolkata | 40 | 0 | 78 | Hot/Humid | 0 | None
W20250423 | 2025-04-23 | Kolkata | 40 | 0 | 60 | Hot/Humid | 0 | None
W20250424 | 2025-04-24 | Kolkata | 37 | 0 | 71 | Clear | 0 | None
W20250425 | 2025-04-25 | Kolkata | 39 | 0 | 79 | Hot/Humid | 0 | None
W20250426 | 2025-04-26 | Kolkata | 38 | 0 | 76 | Clear | 0 | None
W20250427 | 2025-04-27 | Kolkata | 40 | 0 | 69 | Hot/Humid | 0 | None
W20250428 | 2025-04-28 | Kolkata | 40 | 0 | 65 | Hot/Humid | 0 | None
W20250429 | 2025-04-29 | Kolkata | 42 | 0 | 60 | Hot/Humid | 0 | None
W20250430 | 2025-04-30 | Kolkata | 39 | 0 | 74 | Hot/Humid | 0 | None
W20250501 | 2025-05-01 | Kolkata | 42 | 0 | 75 | Hot/Humid | 0 | None
W20250502 | 2025-05-02 | Kolkata | 36 | 0 | 62 | Clear | 0 | None
W20250503 | 2025-05-03 | Kolkata | 39 | 0 | 62 | Hot/Humid | 0 | None
W20250504 | 2025-05-04 | Kolkata | 38 | 0 | 67 | Cloudy | 0 | None
W20250505 | 2025-05-05 | Kolkata | 34 | 0 | 67 | Clear | 0 | None
W20250506 | 2025-05-06 | Kolkata | 35 | 0 | 74 | Clear | 0 | None
W20250507 | 2025-05-07 | Kolkata | 37 | 0 | 72 | Cloudy | 0 | None
W20250508 | 2025-05-08 | Kolkata | 34 | 0 | 63 | Cloudy | 0 | None
W20250509 | 2025-05-09 | Kolkata | 42 | 36 | 74 | Hot/Humid | 0 | Low
W20250510 | 2025-05-10 | Kolkata | 35 | 0 | 74 | Clear | 0 | None
W20250511 | 2025-05-11 | Kolkata | 42 | 0 | 77 | Hot/Humid | 0 | None
W20250512 | 2025-05-12 | Kolkata | 41 | 0 | 79 | Hot/Humid | 0 | None
W20250513 | 2025-05-13 | Kolkata | 40 | 0 | 77 | Hot/Humid | 0 | None
W20250514 | 2025-05-14 | Kolkata | 41 | 0 | 74 | Hot/Humid | 0 | None
W20250515 | 2025-05-15 | Kolkata | 38 | 0 | 76 | Cloudy | 0 | None
W20250516 | 2025-05-16 | Kolkata | 41 | 0 | 62 | Hot/Humid | 0 | None
W20250517 | 2025-05-17 | Kolkata | 39 | 0 | 70 | Hot/Humid | 0 | None
W20250518 | 2025-05-18 | Kolkata | 36 | 0 | 67 | Cloudy | 0 | None
W20250519 | 2025-05-19 | Kolkata | 37 | 0 | 62 | Clear | 0 | None
W20250520 | 2025-05-20 | Kolkata | 41 | 58 | 73 | Hot/Humid | 1 | High
W20250521 | 2025-05-21 | Kolkata | 40 | 0 | 78 | Hot/Humid | 0 | None
W20250522 | 2025-05-22 | Kolkata | 40 | 50 | 75 | Hot/Humid | 1 | High
W20250523 | 2025-05-23 | Kolkata | 38 | 0 | 72 | Clear | 0 | None
W20250524 | 2025-05-24 | Kolkata | 40 | 0 | 77 | Hot/Humid | 0 | None
W20250525 | 2025-05-25 | Kolkata | 37 | 0 | 75 | Clear | 0 | None
W20250526 | 2025-05-26 | Kolkata | 34 | 0 | 72 | Clear | 0 | None
W20250527 | 2025-05-27 | Kolkata | 40 | 0 | 65 | Hot/Humid | 0 | None
W20250528 | 2025-05-28 | Kolkata | 42 | 0 | 60 | Hot/Humid | 0 | None
W20250529 | 2025-05-29 | Kolkata | 34 | 0 | 62 | Cloudy | 0 | None
W20250530 | 2025-05-30 | Kolkata | 41 | 53 | 65 | Hot/Humid | 1 | High
W20250531 | 2025-05-31 | Kolkata | 39 | 0 | 66 | Hot/Humid | 0 | None
W20250601 | 2025-06-01 | Kolkata | 34 | 0 | 83 | Clear | 0 | None
W20250602 | 2025-06-02 | Kolkata | 32 | 74 | 77 | Heavy Rain | 1 | High
W20250603 | 2025-06-03 | Kolkata | 28 | 13 | 86 | Light Rain | 0 | Low
W20250604 | 2025-06-04 | Kolkata | 28 | 0 | 75 | Cloudy | 0 | None
W20250605 | 2025-06-05 | Kolkata | 28 | 21 | 94 | Light Rain | 0 | Low
W20250606 | 2025-06-06 | Kolkata | 35 | 32 | 78 | Light Rain | 0 | Low
W20250607 | 2025-06-07 | Kolkata | 35 | 0 | 83 | Cloudy | 0 | None
W20250608 | 2025-06-08 | Kolkata | 29 | 0 | 80 | Cloudy | 0 | None
W20250609 | 2025-06-09 | Kolkata | 28 | 53 | 84 | Heavy Rain | 1 | High
W20250610 | 2025-06-10 | Kolkata | 34 | 36 | 81 | Light Rain | 0 | Low
W20250611 | 2025-06-11 | Kolkata | 29 | 0 | 84 | Clear | 0 | None
W20250612 | 2025-06-12 | Kolkata | 29 | 0 | 93 | Clear | 0 | None
W20250613 | 2025-06-13 | Kolkata | 34 | 48 | 86 | Heavy Rain | 1 | High
W20250614 | 2025-06-14 | Kolkata | 28 | 0 | 88 | Cloudy | 0 | None
W20250615 | 2025-06-15 | Kolkata | 33 | 0 | 95 | Clear | 0 | None
W20250616 | 2025-06-16 | Kolkata | 30 | 71 | 88 | Heavy Rain | 1 | High
W20250617 | 2025-06-17 | Kolkata | 32 | 0 | 94 | Clear | 0 | None
W20250618 | 2025-06-18 | Kolkata | 35 | 80 | 89 | Heavy Rain | 1 | High
W20250619 | 2025-06-19 | Kolkata | 32 | 0 | 85 | Clear | 0 | None
W20250620 | 2025-06-20 | Kolkata | 29 | 0 | 83 | Cloudy | 0 | None
W20250621 | 2025-06-21 | Kolkata | 35 | 0 | 93 | Clear | 0 | None
W20250622 | 2025-06-22 | Kolkata | 28 | 0 | 90 | Cloudy | 0 | None
W20250623 | 2025-06-23 | Kolkata | 31 | 0 | 86 | Clear | 0 | None
W20250624 | 2025-06-24 | Kolkata | 32 | 29 | 92 | Light Rain | 0 | Low
W20250625 | 2025-06-25 | Kolkata | 29 | 0 | 82 | Clear | 0 | None
W20250626 | 2025-06-26 | Kolkata | 31 | 0 | 90 | Clear | 0 | None
W20250627 | 2025-06-27 | Kolkata | 28 | 56 | 77 | Heavy Rain | 1 | High
W20250628 | 2025-06-28 | Kolkata | 31 | 0 | 84 | Clear | 0 | None
W20250629 | 2025-06-29 | Kolkata | 33 | 0 | 88 | Clear | 0 | None
W20250630 | 2025-06-30 | Kolkata | 33 | 37 | 89 | Light Rain | 0 | Low
W20250701 | 2025-07-01 | Kolkata | 31 | 0 | 78 | Clear | 0 | None
W20250702 | 2025-07-02 | Kolkata | 30 | 66 | 81 | Heavy Rain | 1 | High
W20250703 | 2025-07-03 | Kolkata | 32 | 0 | 93 | Clear | 0 | None
W20250704 | 2025-07-04 | Kolkata | 32 | 0 | 78 | Cloudy | 0 | None
W20250705 | 2025-07-05 | Kolkata | 33 | 73 | 80 | Heavy Rain | 1 | High
W20250706 | 2025-07-06 | Kolkata | 30 | 11 | 83 | Light Rain | 0 | Low
W20250707 | 2025-07-07 | Kolkata | 32 | 0 | 79 | Clear | 0 | None
W20250708 | 2025-07-08 | Kolkata | 29 | 65 | 75 | Heavy Rain | 1 | High
W20250709 | 2025-07-09 | Kolkata | 35 | 11 | 89 | Light Rain | 0 | Low
W20250710 | 2025-07-10 | Kolkata | 32 | 13 | 90 | Light Rain | 0 | Low
W20250711 | 2025-07-11 | Kolkata | 34 | 11 | 90 | Light Rain | 0 | Low
W20250712 | 2025-07-12 | Kolkata | 30 | 0 | 79 | Clear | 0 | None
W20250713 | 2025-07-13 | Kolkata | 29 | 58 | 82 | Heavy Rain | 1 | High
W20250714 | 2025-07-14 | Kolkata | 31 | 61 | 91 | Heavy Rain | 1 | High
W20250715 | 2025-07-15 | Kolkata | 32 | 0 | 93 | Clear | 0 | None
W20250716 | 2025-07-16 | Kolkata | 28 | 0 | 94 | Cloudy | 0 | None
W20250717 | 2025-07-17 | Kolkata | 31 | 15 | 95 | Light Rain | 0 | Low
W20250718 | 2025-07-18 | Kolkata | 30 | 14 | 82 | Light Rain | 0 | Low
W20250719 | 2025-07-19 | Kolkata | 30 | 65 | 75 | Heavy Rain | 1 | High
W20250720 | 2025-07-20 | Kolkata | 32 | 41 | 76 | Heavy Rain | 1 | High
W20250721 | 2025-07-21 | Kolkata | 35 | 0 | 77 | Clear | 0 | None
W20250722 | 2025-07-22 | Kolkata | 31 | 33 | 88 | Light Rain | 0 | Low
W20250723 | 2025-07-23 | Kolkata | 30 | 0 | 83 | Cloudy | 0 | None
W20250724 | 2025-07-24 | Kolkata | 30 | 77 | 84 | Heavy Rain | 1 | High
W20250725 | 2025-07-25 | Kolkata | 32 | 43 | 89 | Heavy Rain | 1 | High
W20250726 | 2025-07-26 | Kolkata | 34 | 68 | 83 | Heavy Rain | 1 | High
W20250727 | 2025-07-27 | Kolkata | 35 | 60 | 77 | Heavy Rain | 1 | High
W20250728 | 2025-07-28 | Kolkata | 33 | 16 | 94 | Light Rain | 0 | Low
W20250729 | 2025-07-29 | Kolkata | 31 | 7 | 93 | Light Rain | 0 | Low
W20250730 | 2025-07-30 | Kolkata | 32 | 27 | 93 | Light Rain | 0 | Low
W20250731 | 2025-07-31 | Kolkata | 35 | 0 | 91 | Clear | 0 | None
W20250801 | 2025-08-01 | Kolkata | 30 | 67 | 93 | Heavy Rain | 1 | High
W20250802 | 2025-08-02 | Kolkata | 29 | 47 | 90 | Heavy Rain | 1 | High
W20250803 | 2025-08-03 | Kolkata | 33 | 0 | 78 | Clear | 0 | None
W20250804 | 2025-08-04 | Kolkata | 35 | 0 | 84 | Clear | 0 | None
W20250805 | 2025-08-05 | Kolkata | 28 | 37 | 89 | Light Rain | 0 | Low
W20250806 | 2025-08-06 | Kolkata | 33 | 0 | 78 | Clear | 0 | None
W20250807 | 2025-08-07 | Kolkata | 28 | 11 | 92 | Light Rain | 0 | Low
W20250808 | 2025-08-08 | Kolkata | 31 | 68 | 91 | Heavy Rain | 1 | High
W20250809 | 2025-08-09 | Kolkata | 35 | 75 | 76 | Heavy Rain | 1 | High
W20250810 | 2025-08-10 | Kolkata | 30 | 67 | 84 | Heavy Rain | 1 | High
W20250811 | 2025-08-11 | Kolkata | 29 | 0 | 75 | Clear | 0 | None
W20250812 | 2025-08-12 | Kolkata | 31 | 6 | 80 | Light Rain | 0 | Low
W20250813 | 2025-08-13 | Kolkata | 34 | 19 | 77 | Light Rain | 0 | Low
W20250814 | 2025-08-14 | Kolkata | 35 | 0 | 78 | Cloudy | 0 | None
W20250815 | 2025-08-15 | Kolkata | 32 | 0 | 91 | Clear | 0 | None
W20250816 | 2025-08-16 | Kolkata | 35 | 75 | 90 | Heavy Rain | 1 | High
W20250817 | 2025-08-17 | Kolkata | 30 | 70 | 87 | Heavy Rain | 1 | High
W20250818 | 2025-08-18 | Kolkata | 30 | 58 | 77 | Heavy Rain | 1 | High
W20250819 | 2025-08-19 | Kolkata | 33 | 5 | 91 | Light Rain | 0 | Low
W20250820 | 2025-08-20 | Kolkata | 32 | 0 | 84 | Clear | 0 | None
W20250821 | 2025-08-21 | Kolkata | 35 | 66 | 79 | Heavy Rain | 1 | High
W20250822 | 2025-08-22 | Kolkata | 33 | 74 | 85 | Heavy Rain | 1 | High
W20250823 | 2025-08-23 | Kolkata | 34 | 0 | 89 | Clear | 0 | None
W20250824 | 2025-08-24 | Kolkata | 31 | 57 | 93 | Heavy Rain | 1 | High
W20250825 | 2025-08-25 | Kolkata | 28 | 0 | 85 | Clear | 0 | None
W20250826 | 2025-08-26 | Kolkata | 34 | 0 | 87 | Clear | 0 | None
W20250827 | 2025-08-27 | Kolkata | 30 | 0 | 90 | Cloudy | 0 | None
W20250828 | 2025-08-28 | Kolkata | 33 | 0 | 78 | Clear | 0 | None
W20250829 | 2025-08-29 | Kolkata | 35 | 0 | 75 | Clear | 0 | None
W20250830 | 2025-08-30 | Kolkata | 30 | 38 | 77 | Light Rain | 0 | Low
W20250831 | 2025-08-31 | Kolkata | 33 | 0 | 94 | Clear | 0 | None
W20250901 | 2025-09-01 | Kolkata | 33 | 45 | 92 | Heavy Rain | 1 | High
W20250902 | 2025-09-02 | Kolkata | 35 | 13 | 92 | Light Rain | 0 | Low
W20250903 | 2025-09-03 | Kolkata | 31 | 0 | 95 | Cloudy | 0 | None
W20250904 | 2025-09-04 | Kolkata | 31 | 17 | 77 | Light Rain | 0 | Low
W20250905 | 2025-09-05 | Kolkata | 29 | 43 | 89 | Heavy Rain | 1 | High
W20250906 | 2025-09-06 | Kolkata | 28 | 12 | 76 | Light Rain | 0 | Low
W20250907 | 2025-09-07 | Kolkata | 32 | 23 | 86 | Light Rain | 0 | Low
W20250908 | 2025-09-08 | Kolkata | 31 | 28 | 91 | Light Rain | 0 | Low
W20250909 | 2025-09-09 | Kolkata | 30 | 53 | 80 | Heavy Rain | 1 | High
W20250910 | 2025-09-10 | Kolkata | 31 | 0 | 90 | Cloudy | 0 | None
W20250911 | 2025-09-11 | Kolkata | 35 | 37 | 95 | Light Rain | 0 | Low
W20250912 | 2025-09-12 | Kolkata | 28 | 0 | 89 | Clear | 0 | None
W20250913 | 2025-09-13 | Kolkata | 30 | 49 | 77 | Heavy Rain | 1 | High
W20250914 | 2025-09-14 | Kolkata | 32 | 0 | 95 | Clear | 0 | None
W20250915 | 2025-09-15 | Kolkata | 35 | 54 | 84 | Heavy Rain | 1 | High
W20250916 | 2025-09-16 | Kolkata | 35 | 78 | 78 | Heavy Rain | 1 | High
W20250917 | 2025-09-17 | Kolkata | 33 | 42 | 93 | Heavy Rain | 1 | High
W20250918 | 2025-09-18 | Kolkata | 28 | 77 | 87 | Heavy Rain | 1 | High
W20250919 | 2025-09-19 | Kolkata | 28 | 0 | 94 | Clear | 0 | None
W20250920 | 2025-09-20 | Kolkata | 32 | 0 | 82 | Clear | 0 | None
W20250921 | 2025-09-21 | Kolkata | 31 | 22 | 94 | Light Rain | 0 | Low
W20250922 | 2025-09-22 | Kolkata | 29 | 0 | 95 | Clear | 0 | None
W20250923 | 2025-09-23 | Kolkata | 35 | 21 | 76 | Light Rain | 0 | Low
W20250924 | 2025-09-24 | Kolkata | 29 | 58 | 84 | Heavy Rain | 1 | High
W20250925 | 2025-09-25 | Kolkata | 30 | 74 | 81 | Heavy Rain | 1 | High
W20250926 | 2025-09-26 | Kolkata | 33 | 39 | 91 | Light Rain | 0 | Low
W20250927 | 2025-09-27 | Kolkata | 30 | 0 | 83 | Clear | 0 | None
W20250928 | 2025-09-28 | Kolkata | 32 | 0 | 85 | Clear | 0 | None
W20250929 | 2025-09-29 | Kolkata | 29 | 0 | 79 | Cloudy | 0 | None
W20250930 | 2025-09-30 | Kolkata | 34 | 55 | 92 | Heavy Rain | 1 | High
W20251001 | 2025-10-01 | Kolkata | 15 | 0 | 48 | Clear | 0 | None
W20251002 | 2025-10-02 | Kolkata | 25 | 0 | 63 | Clear | 0 | None
W20251003 | 2025-10-03 | Kolkata | 28 | 0 | 60 | Cloudy | 0 | None
W20251004 | 2025-10-04 | Kolkata | 18 | 76 | 55 | Heavy Rain | 1 | High
W20251005 | 2025-10-05 | Kolkata | 20 | 0 | 59 | Cloudy | 0 | None
W20251006 | 2025-10-06 | Kolkata | 28 | 0 | 54 | Clear | 0 | None
W20251007 | 2025-10-07 | Kolkata | 21 | 0 | 43 | Clear | 0 | None
W20251008 | 2025-10-08 | Kolkata | 19 | 0 | 55 | Cloudy | 0 | None
W20251009 | 2025-10-09 | Kolkata | 23 | 0 | 44 | Clear | 0 | None
W20251010 | 2025-10-10 | Kolkata | 26 | 0 | 62 | Clear | 0 | None
W20251011 | 2025-10-11 | Kolkata | 26 | 0 | 63 | Clear | 0 | None
W20251012 | 2025-10-12 | Kolkata | 16 | 0 | 55 | Clear | 0 | None
W20251013 | 2025-10-13 | Kolkata | 19 | 0 | 41 | Cloudy | 0 | None
W20251014 | 2025-10-14 | Kolkata | 22 | 0 | 47 | Cloudy | 0 | None
W20251015 | 2025-10-15 | Kolkata | 25 | 0 | 51 | Clear | 0 | None
W20251016 | 2025-10-16 | Kolkata | 20 | 0 | 41 | Cloudy | 0 | None
W20251017 | 2025-10-17 | Kolkata | 16 | 0 | 54 | Cloudy | 0 | None
W20251018 | 2025-10-18 | Kolkata | 25 | 0 | 59 | Cloudy | 0 | None
W20251019 | 2025-10-19 | Kolkata | 20 | 0 | 47 | Clear | 0 | None
W20251020 | 2025-10-20 | Kolkata | 18 | 0 | 42 | Clear | 0 | None
W20251021 | 2025-10-21 | Kolkata | 24 | 0 | 46 | Cloudy | 0 | None
W20251022 | 2025-10-22 | Kolkata | 27 | 0 | 44 | Clear | 0 | None
W20251023 | 2025-10-23 | Kolkata | 19 | 0 | 44 | Clear | 0 | None
W20251024 | 2025-10-24 | Kolkata | 27 | 0 | 45 | Clear | 0 | None
W20251025 | 2025-10-25 | Kolkata | 17 | 0 | 40 | Clear | 0 | None
W20251026 | 2025-10-26 | Kolkata | 24 | 38 | 50 | Light Rain | 0 | Low
W20251027 | 2025-10-27 | Kolkata | 15 | 0 | 44 | Clear | 0 | None
W20251028 | 2025-10-28 | Kolkata | 26 | 0 | 42 | Clear | 0 | None
W20251029 | 2025-10-29 | Kolkata | 23 | 0 | 58 | Clear | 0 | None
W20251030 | 2025-10-30 | Kolkata | 24 | 0 | 41 | Clear | 0 | None
W20251031 | 2025-10-31 | Kolkata | 25 | 0 | 56 | Clear | 0 | None
W20251101 | 2025-11-01 | Kolkata | 15 | 0 | 41 | Clear | 0 | None
W20251102 | 2025-11-02 | Kolkata | 21 | 0 | 61 | Clear | 0 | None
W20251103 | 2025-11-03 | Kolkata | 22 | 0 | 42 | Clear | 0 | None
W20251104 | 2025-11-04 | Kolkata | 17 | 0 | 42 | Clear | 0 | None
W20251105 | 2025-11-05 | Kolkata | 24 | 0 | 57 | Clear | 0 | None
W20251106 | 2025-11-06 | Kolkata | 24 | 0 | 56 | Clear | 0 | None
W20251107 | 2025-11-07 | Kolkata | 21 | 0 | 43 | Cloudy | 0 | None
W20251108 | 2025-11-08 | Kolkata | 25 | 0 | 60 | Clear | 0 | None
W20251109 | 2025-11-09 | Kolkata | 28 | 0 | 46 | Clear | 0 | None
W20251110 | 2025-11-10 | Kolkata | 21 | 0 | 50 | Clear | 0 | None
W20251111 | 2025-11-11 | Kolkata | 26 | 0 | 43 | Clear | 0 | None
W20251112 | 2025-11-12 | Kolkata | 19 | 0 | 51 | Clear | 0 | None
W20251113 | 2025-11-13 | Kolkata | 22 | 0 | 42 | Cloudy | 0 | None
W20251114 | 2025-11-14 | Kolkata | 21 | 0 | 43 | Clear | 0 | None
W20251115 | 2025-11-15 | Kolkata | 17 | 0 | 57 | Clear | 0 | None
W20251116 | 2025-11-16 | Kolkata | 23 | 0 | 50 | Clear | 0 | None
W20251117 | 2025-11-17 | Kolkata | 28 | 0 | 61 | Clear | 0 | None
W20251118 | 2025-11-18 | Kolkata | 26 | 0 | 41 | Clear | 0 | None
W20251119 | 2025-11-19 | Kolkata | 20 | 0 | 43 | Cloudy | 0 | None
W20251120 | 2025-11-20 | Kolkata | 25 | 0 | 55 | Cloudy | 0 | None
W20251121 | 2025-11-21 | Kolkata | 28 | 0 | 57 | Clear | 0 | None
W20251122 | 2025-11-22 | Kolkata | 24 | 0 | 47 | Clear | 0 | None
W20251123 | 2025-11-23 | Kolkata | 27 | 0 | 59 | Clear | 0 | None
W20251124 | 2025-11-24 | Kolkata | 15 | 0 | 59 | Clear | 0 | None
W20251125 | 2025-11-25 | Kolkata | 19 | 0 | 40 | Clear | 0 | None
W20251126 | 2025-11-26 | Kolkata | 19 | 0 | 50 | Cloudy | 0 | None
W20251127 | 2025-11-27 | Kolkata | 17 | 0 | 58 | Cloudy | 0 | None
W20251128 | 2025-11-28 | Kolkata | 26 | 0 | 60 | Cloudy | 0 | None
W20251129 | 2025-11-29 | Kolkata | 23 | 0 | 46 | Clear | 0 | None
W20251130 | 2025-11-30 | Kolkata | 17 | 0 | 51 | Clear | 0 | None
W20251201 | 2025-12-01 | Kolkata | 24 | 0 | 59 | Cloudy | 0 | None
W20251202 | 2025-12-02 | Kolkata | 17 | 0 | 64 | Clear | 0 | None
W20251203 | 2025-12-03 | Kolkata | 19 | 0 | 54 | Clear | 0 | None
W20251204 | 2025-12-04 | Kolkata | 22 | 0 | 53 | Clear | 0 | None
W20251205 | 2025-12-05 | Kolkata | 16 | 0 | 51 | Cloudy | 0 | None
W20251206 | 2025-12-06 | Kolkata | 25 | 0 | 58 | Clear | 0 | None
W20251207 | 2025-12-07 | Kolkata | 15 | 0 | 47 | Clear | 0 | None
W20251208 | 2025-12-08 | Kolkata | 15 | 0 | 46 | Cloudy | 0 | None
W20251209 | 2025-12-09 | Kolkata | 17 | 0 | 64 | Clear | 0 | None
W20251210 | 2025-12-10 | Kolkata | 15 | 0 | 55 | Cloudy | 0 | None
W20251211 | 2025-12-11 | Kolkata | 21 | 0 | 57 | Clear | 0 | None
W20251212 | 2025-12-12 | Kolkata | 28 | 0 | 61 | Cloudy | 0 | None
W20251213 | 2025-12-13 | Kolkata | 28 | 7 | 63 | Light Rain | 0 | Low
W20251214 | 2025-12-14 | Kolkata | 22 | 0 | 42 | Clear | 0 | None
W20251215 | 2025-12-15 | Kolkata | 24 | 0 | 52 | Clear | 0 | None
W20251216 | 2025-12-16 | Kolkata | 16 | 46 | 52 | Heavy Rain | 1 | High
W20251217 | 2025-12-17 | Kolkata | 17 | 0 | 65 | Clear | 0 | None
W20251218 | 2025-12-18 | Kolkata | 26 | 0 | 51 | Clear | 0 | None
W20251219 | 2025-12-19 | Kolkata | 18 | 0 | 53 | Clear | 0 | None
W20251220 | 2025-12-20 | Kolkata | 21 | 0 | 49 | Cloudy | 0 | None
W20251221 | 2025-12-21 | Kolkata | 27 | 0 | 45 | Clear | 0 | None
W20251222 | 2025-12-22 | Kolkata | 23 | 0 | 56 | Clear | 0 | None
W20251223 | 2025-12-23 | Kolkata | 20 | 0 | 63 | Clear | 0 | None
W20251224 | 2025-12-24 | Kolkata | 17 | 0 | 47 | Cloudy | 0 | None
W20251225 | 2025-12-25 | Kolkata | 17 | 0 | 59 | Clear | 0 | None
W20251226 | 2025-12-26 | Kolkata | 16 | 0 | 45 | Clear | 0 | None
W20251227 | 2025-12-27 | Kolkata | 22 | 0 | 64 | Clear | 0 | None
W20251228 | 2025-12-28 | Kolkata | 25 | 0 | 58 | Clear | 0 | None
W20251229 | 2025-12-29 | Kolkata | 20 | 0 | 60 | Clear | 0 | None
W20251230 | 2025-12-30 | Kolkata | 22 | 0 | 54 | Clear | 0 | None
W20251231 | 2025-12-31 | Kolkata | 24 | 0 | 41 | Cloudy | 0 | None

## Calendar
Date | Year | Month | Month_Number | Quarter | Week_Number | Day | Day_Name | Is_Weekend | Is_Working_Day
2025-01-01 | 2025 | January | 1 | 1 | 1 | 1 | Wednesday | FALSE | TRUE
2025-01-02 | 2025 | January | 1 | 1 | 1 | 2 | Thursday | FALSE | TRUE
2025-01-03 | 2025 | January | 1 | 1 | 1 | 3 | Friday | FALSE | TRUE
2025-01-04 | 2025 | January | 1 | 1 | 1 | 4 | Saturday | TRUE | FALSE
2025-01-05 | 2025 | January | 1 | 1 | 1 | 5 | Sunday | TRUE | FALSE
2025-01-06 | 2025 | January | 1 | 1 | 2 | 6 | Monday | FALSE | TRUE
2025-01-07 | 2025 | January | 1 | 1 | 2 | 7 | Tuesday | FALSE | TRUE
2025-01-08 | 2025 | January | 1 | 1 | 2 | 8 | Wednesday | FALSE | TRUE
2025-01-09 | 2025 | January | 1 | 1 | 2 | 9 | Thursday | FALSE | TRUE
2025-01-10 | 2025 | January | 1 | 1 | 2 | 10 | Friday | FALSE | TRUE
2025-01-11 | 2025 | January | 1 | 1 | 2 | 11 | Saturday | TRUE | FALSE
2025-01-12 | 2025 | January | 1 | 1 | 2 | 12 | Sunday | TRUE | FALSE
2025-01-13 | 2025 | January | 1 | 1 | 3 | 13 | Monday | FALSE | TRUE
2025-01-14 | 2025 | January | 1 | 1 | 3 | 14 | Tuesday | FALSE | TRUE
2025-01-15 | 2025 | January | 1 | 1 | 3 | 15 | Wednesday | FALSE | TRUE
2025-01-16 | 2025 | January | 1 | 1 | 3 | 16 | Thursday | FALSE | TRUE
2025-01-17 | 2025 | January | 1 | 1 | 3 | 17 | Friday | FALSE | TRUE
2025-01-18 | 2025 | January | 1 | 1 | 3 | 18 | Saturday | TRUE | FALSE
2025-01-19 | 2025 | January | 1 | 1 | 3 | 19 | Sunday | TRUE | FALSE
2025-01-20 | 2025 | January | 1 | 1 | 4 | 20 | Monday | FALSE | TRUE
2025-01-21 | 2025 | January | 1 | 1 | 4 | 21 | Tuesday | FALSE | TRUE
2025-01-22 | 2025 | January | 1 | 1 | 4 | 22 | Wednesday | FALSE | TRUE
2025-01-23 | 2025 | January | 1 | 1 | 4 | 23 | Thursday | FALSE | TRUE
2025-01-24 | 2025 | January | 1 | 1 | 4 | 24 | Friday | FALSE | TRUE
2025-01-25 | 2025 | January | 1 | 1 | 4 | 25 | Saturday | TRUE | FALSE
2025-01-26 | 2025 | January | 1 | 1 | 4 | 26 | Sunday | TRUE | FALSE
2025-01-27 | 2025 | January | 1 | 1 | 5 | 27 | Monday | FALSE | TRUE
2025-01-28 | 2025 | January | 1 | 1 | 5 | 28 | Tuesday | FALSE | TRUE
2025-01-29 | 2025 | January | 1 | 1 | 5 | 29 | Wednesday | FALSE | TRUE
2025-01-30 | 2025 | January | 1 | 1 | 5 | 30 | Thursday | FALSE | TRUE
2025-01-31 | 2025 | January | 1 | 1 | 5 | 31 | Friday | FALSE | TRUE
2025-02-01 | 2025 | February | 2 | 1 | 5 | 1 | Saturday | TRUE | FALSE
2025-02-02 | 2025 | February | 2 | 1 | 5 | 2 | Sunday | TRUE | FALSE
2025-02-03 | 2025 | February | 2 | 1 | 6 | 3 | Monday | FALSE | TRUE
2025-02-04 | 2025 | February | 2 | 1 | 6 | 4 | Tuesday | FALSE | TRUE
2025-02-05 | 2025 | February | 2 | 1 | 6 | 5 | Wednesday | FALSE | TRUE
2025-02-06 | 2025 | February | 2 | 1 | 6 | 6 | Thursday | FALSE | TRUE
2025-02-07 | 2025 | February | 2 | 1 | 6 | 7 | Friday | FALSE | TRUE
2025-02-08 | 2025 | February | 2 | 1 | 6 | 8 | Saturday | TRUE | FALSE
2025-02-09 | 2025 | February | 2 | 1 | 6 | 9 | Sunday | TRUE | FALSE
2025-02-10 | 2025 | February | 2 | 1 | 7 | 10 | Monday | FALSE | TRUE
2025-02-11 | 2025 | February | 2 | 1 | 7 | 11 | Tuesday | FALSE | TRUE
2025-02-12 | 2025 | February | 2 | 1 | 7 | 12 | Wednesday | FALSE | TRUE
2025-02-13 | 2025 | February | 2 | 1 | 7 | 13 | Thursday | FALSE | TRUE
2025-02-14 | 2025 | February | 2 | 1 | 7 | 14 | Friday | FALSE | TRUE
2025-02-15 | 2025 | February | 2 | 1 | 7 | 15 | Saturday | TRUE | FALSE
2025-02-16 | 2025 | February | 2 | 1 | 7 | 16 | Sunday | TRUE | FALSE
2025-02-17 | 2025 | February | 2 | 1 | 8 | 17 | Monday | FALSE | TRUE
2025-02-18 | 2025 | February | 2 | 1 | 8 | 18 | Tuesday | FALSE | TRUE
2025-02-19 | 2025 | February | 2 | 1 | 8 | 19 | Wednesday | FALSE | TRUE
2025-02-20 | 2025 | February | 2 | 1 | 8 | 20 | Thursday | FALSE | TRUE
2025-02-21 | 2025 | February | 2 | 1 | 8 | 21 | Friday | FALSE | TRUE
2025-02-22 | 2025 | February | 2 | 1 | 8 | 22 | Saturday | TRUE | FALSE
2025-02-23 | 2025 | February | 2 | 1 | 8 | 23 | Sunday | TRUE | FALSE
2025-02-24 | 2025 | February | 2 | 1 | 9 | 24 | Monday | FALSE | TRUE
2025-02-25 | 2025 | February | 2 | 1 | 9 | 25 | Tuesday | FALSE | TRUE
2025-02-26 | 2025 | February | 2 | 1 | 9 | 26 | Wednesday | FALSE | TRUE
2025-02-27 | 2025 | February | 2 | 1 | 9 | 27 | Thursday | FALSE | TRUE
2025-02-28 | 2025 | February | 2 | 1 | 9 | 28 | Friday | FALSE | TRUE
2025-03-01 | 2025 | March | 3 | 1 | 9 | 1 | Saturday | TRUE | FALSE
2025-03-02 | 2025 | March | 3 | 1 | 9 | 2 | Sunday | TRUE | FALSE
2025-03-03 | 2025 | March | 3 | 1 | 10 | 3 | Monday | FALSE | TRUE
2025-03-04 | 2025 | March | 3 | 1 | 10 | 4 | Tuesday | FALSE | TRUE
2025-03-05 | 2025 | March | 3 | 1 | 10 | 5 | Wednesday | FALSE | TRUE
2025-03-06 | 2025 | March | 3 | 1 | 10 | 6 | Thursday | FALSE | TRUE
2025-03-07 | 2025 | March | 3 | 1 | 10 | 7 | Friday | FALSE | TRUE
2025-03-08 | 2025 | March | 3 | 1 | 10 | 8 | Saturday | TRUE | FALSE
2025-03-09 | 2025 | March | 3 | 1 | 10 | 9 | Sunday | TRUE | FALSE
2025-03-10 | 2025 | March | 3 | 1 | 11 | 10 | Monday | FALSE | TRUE
2025-03-11 | 2025 | March | 3 | 1 | 11 | 11 | Tuesday | FALSE | TRUE
2025-03-12 | 2025 | March | 3 | 1 | 11 | 12 | Wednesday | FALSE | TRUE
2025-03-13 | 2025 | March | 3 | 1 | 11 | 13 | Thursday | FALSE | TRUE
2025-03-14 | 2025 | March | 3 | 1 | 11 | 14 | Friday | FALSE | TRUE
2025-03-15 | 2025 | March | 3 | 1 | 11 | 15 | Saturday | TRUE | FALSE
2025-03-16 | 2025 | March | 3 | 1 | 11 | 16 | Sunday | TRUE | FALSE
2025-03-17 | 2025 | March | 3 | 1 | 12 | 17 | Monday | FALSE | TRUE
2025-03-18 | 2025 | March | 3 | 1 | 12 | 18 | Tuesday | FALSE | TRUE
2025-03-19 | 2025 | March | 3 | 1 | 12 | 19 | Wednesday | FALSE | TRUE
2025-03-20 | 2025 | March | 3 | 1 | 12 | 20 | Thursday | FALSE | TRUE
2025-03-21 | 2025 | March | 3 | 1 | 12 | 21 | Friday | FALSE | TRUE
2025-03-22 | 2025 | March | 3 | 1 | 12 | 22 | Saturday | TRUE | FALSE
2025-03-23 | 2025 | March | 3 | 1 | 12 | 23 | Sunday | TRUE | FALSE
2025-03-24 | 2025 | March | 3 | 1 | 13 | 24 | Monday | FALSE | TRUE
2025-03-25 | 2025 | March | 3 | 1 | 13 | 25 | Tuesday | FALSE | TRUE
2025-03-26 | 2025 | March | 3 | 1 | 13 | 26 | Wednesday | FALSE | TRUE
2025-03-27 | 2025 | March | 3 | 1 | 13 | 27 | Thursday | FALSE | TRUE
2025-03-28 | 2025 | March | 3 | 1 | 13 | 28 | Friday | FALSE | TRUE
2025-03-29 | 2025 | March | 3 | 1 | 13 | 29 | Saturday | TRUE | FALSE
2025-03-30 | 2025 | March | 3 | 1 | 13 | 30 | Sunday | TRUE | FALSE
2025-03-31 | 2025 | March | 3 | 1 | 14 | 31 | Monday | FALSE | TRUE
2025-04-01 | 2025 | April | 4 | 2 | 14 | 1 | Tuesday | FALSE | TRUE
2025-04-02 | 2025 | April | 4 | 2 | 14 | 2 | Wednesday | FALSE | TRUE
2025-04-03 | 2025 | April | 4 | 2 | 14 | 3 | Thursday | FALSE | TRUE
2025-04-04 | 2025 | April | 4 | 2 | 14 | 4 | Friday | FALSE | TRUE
2025-04-05 | 2025 | April | 4 | 2 | 14 | 5 | Saturday | TRUE | FALSE
2025-04-06 | 2025 | April | 4 | 2 | 14 | 6 | Sunday | TRUE | FALSE
2025-04-07 | 2025 | April | 4 | 2 | 15 | 7 | Monday | FALSE | TRUE
2025-04-08 | 2025 | April | 4 | 2 | 15 | 8 | Tuesday | FALSE | TRUE
2025-04-09 | 2025 | April | 4 | 2 | 15 | 9 | Wednesday | FALSE | TRUE
2025-04-10 | 2025 | April | 4 | 2 | 15 | 10 | Thursday | FALSE | TRUE
2025-04-11 | 2025 | April | 4 | 2 | 15 | 11 | Friday | FALSE | TRUE
2025-04-12 | 2025 | April | 4 | 2 | 15 | 12 | Saturday | TRUE | FALSE
2025-04-13 | 2025 | April | 4 | 2 | 15 | 13 | Sunday | TRUE | FALSE
2025-04-14 | 2025 | April | 4 | 2 | 16 | 14 | Monday | FALSE | TRUE
2025-04-15 | 2025 | April | 4 | 2 | 16 | 15 | Tuesday | FALSE | TRUE
2025-04-16 | 2025 | April | 4 | 2 | 16 | 16 | Wednesday | FALSE | TRUE
2025-04-17 | 2025 | April | 4 | 2 | 16 | 17 | Thursday | FALSE | TRUE
2025-04-18 | 2025 | April | 4 | 2 | 16 | 18 | Friday | FALSE | TRUE
2025-04-19 | 2025 | April | 4 | 2 | 16 | 19 | Saturday | TRUE | FALSE
2025-04-20 | 2025 | April | 4 | 2 | 16 | 20 | Sunday | TRUE | FALSE
2025-04-21 | 2025 | April | 4 | 2 | 17 | 21 | Monday | FALSE | TRUE
2025-04-22 | 2025 | April | 4 | 2 | 17 | 22 | Tuesday | FALSE | TRUE
2025-04-23 | 2025 | April | 4 | 2 | 17 | 23 | Wednesday | FALSE | TRUE
2025-04-24 | 2025 | April | 4 | 2 | 17 | 24 | Thursday | FALSE | TRUE
2025-04-25 | 2025 | April | 4 | 2 | 17 | 25 | Friday | FALSE | TRUE
2025-04-26 | 2025 | April | 4 | 2 | 17 | 26 | Saturday | TRUE | FALSE
2025-04-27 | 2025 | April | 4 | 2 | 17 | 27 | Sunday | TRUE | FALSE
2025-04-28 | 2025 | April | 4 | 2 | 18 | 28 | Monday | FALSE | TRUE
2025-04-29 | 2025 | April | 4 | 2 | 18 | 29 | Tuesday | FALSE | TRUE
2025-04-30 | 2025 | April | 4 | 2 | 18 | 30 | Wednesday | FALSE | TRUE
2025-05-01 | 2025 | May | 5 | 2 | 18 | 1 | Thursday | FALSE | TRUE
2025-05-02 | 2025 | May | 5 | 2 | 18 | 2 | Friday | FALSE | TRUE
2025-05-03 | 2025 | May | 5 | 2 | 18 | 3 | Saturday | TRUE | FALSE
2025-05-04 | 2025 | May | 5 | 2 | 18 | 4 | Sunday | TRUE | FALSE
2025-05-05 | 2025 | May | 5 | 2 | 19 | 5 | Monday | FALSE | TRUE
2025-05-06 | 2025 | May | 5 | 2 | 19 | 6 | Tuesday | FALSE | TRUE
2025-05-07 | 2025 | May | 5 | 2 | 19 | 7 | Wednesday | FALSE | TRUE
2025-05-08 | 2025 | May | 5 | 2 | 19 | 8 | Thursday | FALSE | TRUE
2025-05-09 | 2025 | May | 5 | 2 | 19 | 9 | Friday | FALSE | TRUE
2025-05-10 | 2025 | May | 5 | 2 | 19 | 10 | Saturday | TRUE | FALSE
2025-05-11 | 2025 | May | 5 | 2 | 19 | 11 | Sunday | TRUE | FALSE
2025-05-12 | 2025 | May | 5 | 2 | 20 | 12 | Monday | FALSE | TRUE
2025-05-13 | 2025 | May | 5 | 2 | 20 | 13 | Tuesday | FALSE | TRUE
2025-05-14 | 2025 | May | 5 | 2 | 20 | 14 | Wednesday | FALSE | TRUE
2025-05-15 | 2025 | May | 5 | 2 | 20 | 15 | Thursday | FALSE | TRUE
2025-05-16 | 2025 | May | 5 | 2 | 20 | 16 | Friday | FALSE | TRUE
2025-05-17 | 2025 | May | 5 | 2 | 20 | 17 | Saturday | TRUE | FALSE
2025-05-18 | 2025 | May | 5 | 2 | 20 | 18 | Sunday | TRUE | FALSE
2025-05-19 | 2025 | May | 5 | 2 | 21 | 19 | Monday | FALSE | TRUE
2025-05-20 | 2025 | May | 5 | 2 | 21 | 20 | Tuesday | FALSE | TRUE
2025-05-21 | 2025 | May | 5 | 2 | 21 | 21 | Wednesday | FALSE | TRUE
2025-05-22 | 2025 | May | 5 | 2 | 21 | 22 | Thursday | FALSE | TRUE
2025-05-23 | 2025 | May | 5 | 2 | 21 | 23 | Friday | FALSE | TRUE
2025-05-24 | 2025 | May | 5 | 2 | 21 | 24 | Saturday | TRUE | FALSE
2025-05-25 | 2025 | May | 5 | 2 | 21 | 25 | Sunday | TRUE | FALSE
2025-05-26 | 2025 | May | 5 | 2 | 22 | 26 | Monday | FALSE | TRUE
2025-05-27 | 2025 | May | 5 | 2 | 22 | 27 | Tuesday | FALSE | TRUE
2025-05-28 | 2025 | May | 5 | 2 | 22 | 28 | Wednesday | FALSE | TRUE
2025-05-29 | 2025 | May | 5 | 2 | 22 | 29 | Thursday | FALSE | TRUE
2025-05-30 | 2025 | May | 5 | 2 | 22 | 30 | Friday | FALSE | TRUE
2025-05-31 | 2025 | May | 5 | 2 | 22 | 31 | Saturday | TRUE | FALSE
2025-06-01 | 2025 | June | 6 | 2 | 22 | 1 | Sunday | TRUE | FALSE
2025-06-02 | 2025 | June | 6 | 2 | 23 | 2 | Monday | FALSE | TRUE
2025-06-03 | 2025 | June | 6 | 2 | 23 | 3 | Tuesday | FALSE | TRUE
2025-06-04 | 2025 | June | 6 | 2 | 23 | 4 | Wednesday | FALSE | TRUE
2025-06-05 | 2025 | June | 6 | 2 | 23 | 5 | Thursday | FALSE | TRUE
2025-06-06 | 2025 | June | 6 | 2 | 23 | 6 | Friday | FALSE | TRUE
2025-06-07 | 2025 | June | 6 | 2 | 23 | 7 | Saturday | TRUE | FALSE
2025-06-08 | 2025 | June | 6 | 2 | 23 | 8 | Sunday | TRUE | FALSE
2025-06-09 | 2025 | June | 6 | 2 | 24 | 9 | Monday | FALSE | TRUE
2025-06-10 | 2025 | June | 6 | 2 | 24 | 10 | Tuesday | FALSE | TRUE
2025-06-11 | 2025 | June | 6 | 2 | 24 | 11 | Wednesday | FALSE | TRUE
2025-06-12 | 2025 | June | 6 | 2 | 24 | 12 | Thursday | FALSE | TRUE
2025-06-13 | 2025 | June | 6 | 2 | 24 | 13 | Friday | FALSE | TRUE
2025-06-14 | 2025 | June | 6 | 2 | 24 | 14 | Saturday | TRUE | FALSE
2025-06-15 | 2025 | June | 6 | 2 | 24 | 15 | Sunday | TRUE | FALSE
2025-06-16 | 2025 | June | 6 | 2 | 25 | 16 | Monday | FALSE | TRUE
2025-06-17 | 2025 | June | 6 | 2 | 25 | 17 | Tuesday | FALSE | TRUE
2025-06-18 | 2025 | June | 6 | 2 | 25 | 18 | Wednesday | FALSE | TRUE
2025-06-19 | 2025 | June | 6 | 2 | 25 | 19 | Thursday | FALSE | TRUE
2025-06-20 | 2025 | June | 6 | 2 | 25 | 20 | Friday | FALSE | TRUE
2025-06-21 | 2025 | June | 6 | 2 | 25 | 21 | Saturday | TRUE | FALSE
2025-06-22 | 2025 | June | 6 | 2 | 25 | 22 | Sunday | TRUE | FALSE
2025-06-23 | 2025 | June | 6 | 2 | 26 | 23 | Monday | FALSE | TRUE
2025-06-24 | 2025 | June | 6 | 2 | 26 | 24 | Tuesday | FALSE | TRUE
2025-06-25 | 2025 | June | 6 | 2 | 26 | 25 | Wednesday | FALSE | TRUE
2025-06-26 | 2025 | June | 6 | 2 | 26 | 26 | Thursday | FALSE | TRUE
2025-06-27 | 2025 | June | 6 | 2 | 26 | 27 | Friday | FALSE | TRUE
2025-06-28 | 2025 | June | 6 | 2 | 26 | 28 | Saturday | TRUE | FALSE
2025-06-29 | 2025 | June | 6 | 2 | 26 | 29 | Sunday | TRUE | FALSE
2025-06-30 | 2025 | June | 6 | 2 | 27 | 30 | Monday | FALSE | TRUE
2025-07-01 | 2025 | July | 7 | 3 | 27 | 1 | Tuesday | FALSE | TRUE
2025-07-02 | 2025 | July | 7 | 3 | 27 | 2 | Wednesday | FALSE | TRUE
2025-07-03 | 2025 | July | 7 | 3 | 27 | 3 | Thursday | FALSE | TRUE
2025-07-04 | 2025 | July | 7 | 3 | 27 | 4 | Friday | FALSE | TRUE
2025-07-05 | 2025 | July | 7 | 3 | 27 | 5 | Saturday | TRUE | FALSE
2025-07-06 | 2025 | July | 7 | 3 | 27 | 6 | Sunday | TRUE | FALSE
2025-07-07 | 2025 | July | 7 | 3 | 28 | 7 | Monday | FALSE | TRUE
2025-07-08 | 2025 | July | 7 | 3 | 28 | 8 | Tuesday | FALSE | TRUE
2025-07-09 | 2025 | July | 7 | 3 | 28 | 9 | Wednesday | FALSE | TRUE
2025-07-10 | 2025 | July | 7 | 3 | 28 | 10 | Thursday | FALSE | TRUE
2025-07-11 | 2025 | July | 7 | 3 | 28 | 11 | Friday | FALSE | TRUE
2025-07-12 | 2025 | July | 7 | 3 | 28 | 12 | Saturday | TRUE | FALSE
2025-07-13 | 2025 | July | 7 | 3 | 28 | 13 | Sunday | TRUE | FALSE
2025-07-14 | 2025 | July | 7 | 3 | 29 | 14 | Monday | FALSE | TRUE
2025-07-15 | 2025 | July | 7 | 3 | 29 | 15 | Tuesday | FALSE | TRUE
2025-07-16 | 2025 | July | 7 | 3 | 29 | 16 | Wednesday | FALSE | TRUE
2025-07-17 | 2025 | July | 7 | 3 | 29 | 17 | Thursday | FALSE | TRUE
2025-07-18 | 2025 | July | 7 | 3 | 29 | 18 | Friday | FALSE | TRUE
2025-07-19 | 2025 | July | 7 | 3 | 29 | 19 | Saturday | TRUE | FALSE
2025-07-20 | 2025 | July | 7 | 3 | 29 | 20 | Sunday | TRUE | FALSE
2025-07-21 | 2025 | July | 7 | 3 | 30 | 21 | Monday | FALSE | TRUE
2025-07-22 | 2025 | July | 7 | 3 | 30 | 22 | Tuesday | FALSE | TRUE
2025-07-23 | 2025 | July | 7 | 3 | 30 | 23 | Wednesday | FALSE | TRUE
2025-07-24 | 2025 | July | 7 | 3 | 30 | 24 | Thursday | FALSE | TRUE
2025-07-25 | 2025 | July | 7 | 3 | 30 | 25 | Friday | FALSE | TRUE
2025-07-26 | 2025 | July | 7 | 3 | 30 | 26 | Saturday | TRUE | FALSE
2025-07-27 | 2025 | July | 7 | 3 | 30 | 27 | Sunday | TRUE | FALSE
2025-07-28 | 2025 | July | 7 | 3 | 31 | 28 | Monday | FALSE | TRUE
2025-07-29 | 2025 | July | 7 | 3 | 31 | 29 | Tuesday | FALSE | TRUE
2025-07-30 | 2025 | July | 7 | 3 | 31 | 30 | Wednesday | FALSE | TRUE
2025-07-31 | 2025 | July | 7 | 3 | 31 | 31 | Thursday | FALSE | TRUE
2025-08-01 | 2025 | August | 8 | 3 | 31 | 1 | Friday | FALSE | TRUE
2025-08-02 | 2025 | August | 8 | 3 | 31 | 2 | Saturday | TRUE | FALSE
2025-08-03 | 2025 | August | 8 | 3 | 31 | 3 | Sunday | TRUE | FALSE
2025-08-04 | 2025 | August | 8 | 3 | 32 | 4 | Monday | FALSE | TRUE
2025-08-05 | 2025 | August | 8 | 3 | 32 | 5 | Tuesday | FALSE | TRUE
2025-08-06 | 2025 | August | 8 | 3 | 32 | 6 | Wednesday | FALSE | TRUE
2025-08-07 | 2025 | August | 8 | 3 | 32 | 7 | Thursday | FALSE | TRUE
2025-08-08 | 2025 | August | 8 | 3 | 32 | 8 | Friday | FALSE | TRUE
2025-08-09 | 2025 | August | 8 | 3 | 32 | 9 | Saturday | TRUE | FALSE
2025-08-10 | 2025 | August | 8 | 3 | 32 | 10 | Sunday | TRUE | FALSE
2025-08-11 | 2025 | August | 8 | 3 | 33 | 11 | Monday | FALSE | TRUE
2025-08-12 | 2025 | August | 8 | 3 | 33 | 12 | Tuesday | FALSE | TRUE
2025-08-13 | 2025 | August | 8 | 3 | 33 | 13 | Wednesday | FALSE | TRUE
2025-08-14 | 2025 | August | 8 | 3 | 33 | 14 | Thursday | FALSE | TRUE
2025-08-15 | 2025 | August | 8 | 3 | 33 | 15 | Friday | FALSE | TRUE
2025-08-16 | 2025 | August | 8 | 3 | 33 | 16 | Saturday | TRUE | FALSE
2025-08-17 | 2025 | August | 8 | 3 | 33 | 17 | Sunday | TRUE | FALSE
2025-08-18 | 2025 | August | 8 | 3 | 34 | 18 | Monday | FALSE | TRUE
2025-08-19 | 2025 | August | 8 | 3 | 34 | 19 | Tuesday | FALSE | TRUE
2025-08-20 | 2025 | August | 8 | 3 | 34 | 20 | Wednesday | FALSE | TRUE
2025-08-21 | 2025 | August | 8 | 3 | 34 | 21 | Thursday | FALSE | TRUE
2025-08-22 | 2025 | August | 8 | 3 | 34 | 22 | Friday | FALSE | TRUE
2025-08-23 | 2025 | August | 8 | 3 | 34 | 23 | Saturday | TRUE | FALSE
2025-08-24 | 2025 | August | 8 | 3 | 34 | 24 | Sunday | TRUE | FALSE
2025-08-25 | 2025 | August | 8 | 3 | 35 | 25 | Monday | FALSE | TRUE
2025-08-26 | 2025 | August | 8 | 3 | 35 | 26 | Tuesday | FALSE | TRUE
2025-08-27 | 2025 | August | 8 | 3 | 35 | 27 | Wednesday | FALSE | TRUE
2025-08-28 | 2025 | August | 8 | 3 | 35 | 28 | Thursday | FALSE | TRUE
2025-08-29 | 2025 | August | 8 | 3 | 35 | 29 | Friday | FALSE | TRUE
2025-08-30 | 2025 | August | 8 | 3 | 35 | 30 | Saturday | TRUE | FALSE
2025-08-31 | 2025 | August | 8 | 3 | 35 | 31 | Sunday | TRUE | FALSE
2025-09-01 | 2025 | September | 9 | 3 | 36 | 1 | Monday | FALSE | TRUE
2025-09-02 | 2025 | September | 9 | 3 | 36 | 2 | Tuesday | FALSE | TRUE
2025-09-03 | 2025 | September | 9 | 3 | 36 | 3 | Wednesday | FALSE | TRUE
2025-09-04 | 2025 | September | 9 | 3 | 36 | 4 | Thursday | FALSE | TRUE
2025-09-05 | 2025 | September | 9 | 3 | 36 | 5 | Friday | FALSE | TRUE
2025-09-06 | 2025 | September | 9 | 3 | 36 | 6 | Saturday | TRUE | FALSE
2025-09-07 | 2025 | September | 9 | 3 | 36 | 7 | Sunday | TRUE | FALSE
2025-09-08 | 2025 | September | 9 | 3 | 37 | 8 | Monday | FALSE | TRUE
2025-09-09 | 2025 | September | 9 | 3 | 37 | 9 | Tuesday | FALSE | TRUE
2025-09-10 | 2025 | September | 9 | 3 | 37 | 10 | Wednesday | FALSE | TRUE
2025-09-11 | 2025 | September | 9 | 3 | 37 | 11 | Thursday | FALSE | TRUE
2025-09-12 | 2025 | September | 9 | 3 | 37 | 12 | Friday | FALSE | TRUE
2025-09-13 | 2025 | September | 9 | 3 | 37 | 13 | Saturday | TRUE | FALSE
2025-09-14 | 2025 | September | 9 | 3 | 37 | 14 | Sunday | TRUE | FALSE
2025-09-15 | 2025 | September | 9 | 3 | 38 | 15 | Monday | FALSE | TRUE
2025-09-16 | 2025 | September | 9 | 3 | 38 | 16 | Tuesday | FALSE | TRUE
2025-09-17 | 2025 | September | 9 | 3 | 38 | 17 | Wednesday | FALSE | TRUE
2025-09-18 | 2025 | September | 9 | 3 | 38 | 18 | Thursday | FALSE | TRUE
2025-09-19 | 2025 | September | 9 | 3 | 38 | 19 | Friday | FALSE | TRUE
2025-09-20 | 2025 | September | 9 | 3 | 38 | 20 | Saturday | TRUE | FALSE
2025-09-21 | 2025 | September | 9 | 3 | 38 | 21 | Sunday | TRUE | FALSE
2025-09-22 | 2025 | September | 9 | 3 | 39 | 22 | Monday | FALSE | TRUE
2025-09-23 | 2025 | September | 9 | 3 | 39 | 23 | Tuesday | FALSE | TRUE
2025-09-24 | 2025 | September | 9 | 3 | 39 | 24 | Wednesday | FALSE | TRUE
2025-09-25 | 2025 | September | 9 | 3 | 39 | 25 | Thursday | FALSE | TRUE
2025-09-26 | 2025 | September | 9 | 3 | 39 | 26 | Friday | FALSE | TRUE
2025-09-27 | 2025 | September | 9 | 3 | 39 | 27 | Saturday | TRUE | FALSE
2025-09-28 | 2025 | September | 9 | 3 | 39 | 28 | Sunday | TRUE | FALSE
2025-09-29 | 2025 | September | 9 | 3 | 40 | 29 | Monday | FALSE | TRUE
2025-09-30 | 2025 | September | 9 | 3 | 40 | 30 | Tuesday | FALSE | TRUE
2025-10-01 | 2025 | October | 10 | 4 | 40 | 1 | Wednesday | FALSE | TRUE
2025-10-02 | 2025 | October | 10 | 4 | 40 | 2 | Thursday | FALSE | TRUE
2025-10-03 | 2025 | October | 10 | 4 | 40 | 3 | Friday | FALSE | TRUE
2025-10-04 | 2025 | October | 10 | 4 | 40 | 4 | Saturday | TRUE | FALSE
2025-10-05 | 2025 | October | 10 | 4 | 40 | 5 | Sunday | TRUE | FALSE
2025-10-06 | 2025 | October | 10 | 4 | 41 | 6 | Monday | FALSE | TRUE
2025-10-07 | 2025 | October | 10 | 4 | 41 | 7 | Tuesday | FALSE | TRUE
2025-10-08 | 2025 | October | 10 | 4 | 41 | 8 | Wednesday | FALSE | TRUE
2025-10-09 | 2025 | October | 10 | 4 | 41 | 9 | Thursday | FALSE | TRUE
2025-10-10 | 2025 | October | 10 | 4 | 41 | 10 | Friday | FALSE | TRUE
2025-10-11 | 2025 | October | 10 | 4 | 41 | 11 | Saturday | TRUE | FALSE
2025-10-12 | 2025 | October | 10 | 4 | 41 | 12 | Sunday | TRUE | FALSE
2025-10-13 | 2025 | October | 10 | 4 | 42 | 13 | Monday | FALSE | TRUE
2025-10-14 | 2025 | October | 10 | 4 | 42 | 14 | Tuesday | FALSE | TRUE
2025-10-15 | 2025 | October | 10 | 4 | 42 | 15 | Wednesday | FALSE | TRUE
2025-10-16 | 2025 | October | 10 | 4 | 42 | 16 | Thursday | FALSE | TRUE
2025-10-17 | 2025 | October | 10 | 4 | 42 | 17 | Friday | FALSE | TRUE
2025-10-18 | 2025 | October | 10 | 4 | 42 | 18 | Saturday | TRUE | FALSE
2025-10-19 | 2025 | October | 10 | 4 | 42 | 19 | Sunday | TRUE | FALSE
2025-10-20 | 2025 | October | 10 | 4 | 43 | 20 | Monday | FALSE | TRUE
2025-10-21 | 2025 | October | 10 | 4 | 43 | 21 | Tuesday | FALSE | TRUE
2025-10-22 | 2025 | October | 10 | 4 | 43 | 22 | Wednesday | FALSE | TRUE
2025-10-23 | 2025 | October | 10 | 4 | 43 | 23 | Thursday | FALSE | TRUE
2025-10-24 | 2025 | October | 10 | 4 | 43 | 24 | Friday | FALSE | TRUE
2025-10-25 | 2025 | October | 10 | 4 | 43 | 25 | Saturday | TRUE | FALSE
2025-10-26 | 2025 | October | 10 | 4 | 43 | 26 | Sunday | TRUE | FALSE
2025-10-27 | 2025 | October | 10 | 4 | 44 | 27 | Monday | FALSE | TRUE
2025-10-28 | 2025 | October | 10 | 4 | 44 | 28 | Tuesday | FALSE | TRUE
2025-10-29 | 2025 | October | 10 | 4 | 44 | 29 | Wednesday | FALSE | TRUE
2025-10-30 | 2025 | October | 10 | 4 | 44 | 30 | Thursday | FALSE | TRUE
2025-10-31 | 2025 | October | 10 | 4 | 44 | 31 | Friday | FALSE | TRUE
2025-11-01 | 2025 | November | 11 | 4 | 44 | 1 | Saturday | TRUE | FALSE
2025-11-02 | 2025 | November | 11 | 4 | 44 | 2 | Sunday | TRUE | FALSE
2025-11-03 | 2025 | November | 11 | 4 | 45 | 3 | Monday | FALSE | TRUE
2025-11-04 | 2025 | November | 11 | 4 | 45 | 4 | Tuesday | FALSE | TRUE
2025-11-05 | 2025 | November | 11 | 4 | 45 | 5 | Wednesday | FALSE | TRUE
2025-11-06 | 2025 | November | 11 | 4 | 45 | 6 | Thursday | FALSE | TRUE
2025-11-07 | 2025 | November | 11 | 4 | 45 | 7 | Friday | FALSE | TRUE
2025-11-08 | 2025 | November | 11 | 4 | 45 | 8 | Saturday | TRUE | FALSE
2025-11-09 | 2025 | November | 11 | 4 | 45 | 9 | Sunday | TRUE | FALSE
2025-11-10 | 2025 | November | 11 | 4 | 46 | 10 | Monday | FALSE | TRUE
2025-11-11 | 2025 | November | 11 | 4 | 46 | 11 | Tuesday | FALSE | TRUE
2025-11-12 | 2025 | November | 11 | 4 | 46 | 12 | Wednesday | FALSE | TRUE
2025-11-13 | 2025 | November | 11 | 4 | 46 | 13 | Thursday | FALSE | TRUE
2025-11-14 | 2025 | November | 11 | 4 | 46 | 14 | Friday | FALSE | TRUE
2025-11-15 | 2025 | November | 11 | 4 | 46 | 15 | Saturday | TRUE | FALSE
2025-11-16 | 2025 | November | 11 | 4 | 46 | 16 | Sunday | TRUE | FALSE
2025-11-17 | 2025 | November | 11 | 4 | 47 | 17 | Monday | FALSE | TRUE
2025-11-18 | 2025 | November | 11 | 4 | 47 | 18 | Tuesday | FALSE | TRUE
2025-11-19 | 2025 | November | 11 | 4 | 47 | 19 | Wednesday | FALSE | TRUE
2025-11-20 | 2025 | November | 11 | 4 | 47 | 20 | Thursday | FALSE | TRUE
2025-11-21 | 2025 | November | 11 | 4 | 47 | 21 | Friday | FALSE | TRUE
2025-11-22 | 2025 | November | 11 | 4 | 47 | 22 | Saturday | TRUE | FALSE
2025-11-23 | 2025 | November | 11 | 4 | 47 | 23 | Sunday | TRUE | FALSE
2025-11-24 | 2025 | November | 11 | 4 | 48 | 24 | Monday | FALSE | TRUE
2025-11-25 | 2025 | November | 11 | 4 | 48 | 25 | Tuesday | FALSE | TRUE
2025-11-26 | 2025 | November | 11 | 4 | 48 | 26 | Wednesday | FALSE | TRUE
2025-11-27 | 2025 | November | 11 | 4 | 48 | 27 | Thursday | FALSE | TRUE
2025-11-28 | 2025 | November | 11 | 4 | 48 | 28 | Friday | FALSE | TRUE
2025-11-29 | 2025 | November | 11 | 4 | 48 | 29 | Saturday | TRUE | FALSE
2025-11-30 | 2025 | November | 11 | 4 | 48 | 30 | Sunday | TRUE | FALSE
2025-12-01 | 2025 | December | 12 | 4 | 49 | 1 | Monday | FALSE | TRUE
2025-12-02 | 2025 | December | 12 | 4 | 49 | 2 | Tuesday | FALSE | TRUE
2025-12-03 | 2025 | December | 12 | 4 | 49 | 3 | Wednesday | FALSE | TRUE
2025-12-04 | 2025 | December | 12 | 4 | 49 | 4 | Thursday | FALSE | TRUE
2025-12-05 | 2025 | December | 12 | 4 | 49 | 5 | Friday | FALSE | TRUE
2025-12-06 | 2025 | December | 12 | 4 | 49 | 6 | Saturday | TRUE | FALSE
2025-12-07 | 2025 | December | 12 | 4 | 49 | 7 | Sunday | TRUE | FALSE
2025-12-08 | 2025 | December | 12 | 4 | 50 | 8 | Monday | FALSE | TRUE
2025-12-09 | 2025 | December | 12 | 4 | 50 | 9 | Tuesday | FALSE | TRUE
2025-12-10 | 2025 | December | 12 | 4 | 50 | 10 | Wednesday | FALSE | TRUE
2025-12-11 | 2025 | December | 12 | 4 | 50 | 11 | Thursday | FALSE | TRUE
2025-12-12 | 2025 | December | 12 | 4 | 50 | 12 | Friday | FALSE | TRUE
2025-12-13 | 2025 | December | 12 | 4 | 50 | 13 | Saturday | TRUE | FALSE
2025-12-14 | 2025 | December | 12 | 4 | 50 | 14 | Sunday | TRUE | FALSE
2025-12-15 | 2025 | December | 12 | 4 | 51 | 15 | Monday | FALSE | TRUE
2025-12-16 | 2025 | December | 12 | 4 | 51 | 16 | Tuesday | FALSE | TRUE
2025-12-17 | 2025 | December | 12 | 4 | 51 | 17 | Wednesday | FALSE | TRUE
2025-12-18 | 2025 | December | 12 | 4 | 51 | 18 | Thursday | FALSE | TRUE
2025-12-19 | 2025 | December | 12 | 4 | 51 | 19 | Friday | FALSE | TRUE
2025-12-20 | 2025 | December | 12 | 4 | 51 | 20 | Saturday | TRUE | FALSE
2025-12-21 | 2025 | December | 12 | 4 | 51 | 21 | Sunday | TRUE | FALSE
2025-12-22 | 2025 | December | 12 | 4 | 52 | 22 | Monday | FALSE | TRUE
2025-12-23 | 2025 | December | 12 | 4 | 52 | 23 | Tuesday | FALSE | TRUE
2025-12-24 | 2025 | December | 12 | 4 | 52 | 24 | Wednesday | FALSE | TRUE
2025-12-25 | 2025 | December | 12 | 4 | 52 | 25 | Thursday | FALSE | TRUE
2025-12-26 | 2025 | December | 12 | 4 | 52 | 26 | Friday | FALSE | TRUE
2025-12-27 | 2025 | December | 12 | 4 | 52 | 27 | Saturday | TRUE | FALSE
2025-12-28 | 2025 | December | 12 | 4 | 52 | 28 | Sunday | TRUE | FALSE
2025-12-29 | 2025 | December | 12 | 4 | 1 | 29 | Monday | FALSE | TRUE
2025-12-30 | 2025 | December | 12 | 4 | 1 | 30 | Tuesday | FALSE | TRUE
2025-12-31 | 2025 | December | 12 | 4 | 1 | 31 | Wednesday | FALSE | TRUE