## Projects
Project_ID | Project_Name | Project_Type | Location | Client | Main_Contractor | Consultant | Building_Type | Total_Floors | Total_Built_Up_Area_sqft | Start_Date | Planned_End_Date | Total_Budget_INR | Project_Status
P001 | Green Heights Residential Tower | Residential | Kolkata | XYZ Developers | ABC Construction Pvt Ltd | Urban Structural Consultants | G+10 | 11 | 85000 | 2026-01-01 | 2026-12-31 | 85000000 | In Progress

## Contractors
Contractor_ID | Contractor_Name | Specialization | Contact_Person | Contractor_Type | Activities_Handled
C001 | ABC Civil Works | Civil Works | Project Manager | Main Contractor | All Civil Works
C002 | Prime RCC Contractors | RCC Works | Site Manager | Subcontractor | RCC Structure
C003 | Eastern Masonry Works | Masonry | Site Supervisor | Subcontractor | Brickwork and Blockwork
C004 | FinishPro Interiors | Finishing | Project Supervisor | Subcontractor | Plastering and Flooring
C005 | ColorCraft Solutions | Painting | Site Supervisor | Subcontractor | Painting
C006 | AquaFlow Services | Plumbing | MEP Manager | Subcontractor | Plumbing and Sanitary
C007 | Spark Electricals | Electrical | MEP Manager | Subcontractor | Electrical Works
C008 | SafeSeal Waterproofing | Waterproofing | Site Supervisor | Subcontractor | Waterproofing
C009 | BuildPlant Equipment | Equipment | Equipment Manager | Equipment Vendor | Construction Equipment

## Activities
Activity_ID | Project_ID | WBS_Code | Activity_Name | Category | Subcategory | Unit | Planned_Quantity | Unit_Rate_INR | Budget_Cost_INR | Planned_Start_Date | Planned_End_Date | Duration_Days | Predecessor_ID | Contractor_ID
A001 | P001 | 01.01 | Site Mobilization | Preliminaries | Mobilization | lot | 1 | 450000 | 450000 | 2026-01-01 | 2026-01-10 | 30 |  | C001
A002 | P001 | 01.02 | Site Clearance | Preliminaries | Site Preparation | m² | 5000 | 35 | 175000 | 2026-01-01 | 2026-01-10 | 10 | A001 | C001
A003 | P001 | 01.03 | Temporary Facilities | Preliminaries | Site Setup | lot | 1 | 300000 | 300000 | 2026-01-05 | 2026-01-24 | 20 | A002 | C001
A004 | P001 | 01.04 | Setting Out | Preliminaries | Survey | lot | 1 | 150000 | 150000 | 2026-01-08 | 2026-01-14 | 7 | A003 | C001
A005 | P001 | 02.01 | Excavation | Earthwork | Excavation | m³ | 3500 | 450 | 1575000 | 2026-01-12 | 2026-02-10 | 30 | A004 | C001
A006 | P001 | 02.02 | Earth Filling | Earthwork | Filling | m³ | 1800 | 550 | 990000 | 2026-02-01 | 2026-02-20 | 20 | A005 | C001
A007 | P001 | 02.03 | Compaction | Earthwork | Compaction | m³ | 1800 | 180 | 324000 | 2026-02-06 | 2026-02-20 | 15 | A006 | C001
A008 | P001 | 02.04 | Disposal of Excavated Soil | Earthwork | Disposal | m³ | 1700 | 320 | 544000 | 2026-01-20 | 2026-02-06 | 18 | A007 | C001
A009 | P001 | 03.01 | PCC for Foundations | Foundation | PCC | m³ | 450 | 6500 | 2925000 | 2026-02-15 | 2026-03-04 | 18 | A008 | C002
A010 | P001 | 03.02 | Footing Reinforcement | Foundation | Reinforcement | tonne | 85 | 72000 | 6120000 | 2026-02-20 | 2026-03-16 | 25 | A009 | C002
A011 | P001 | 03.03 | Footing RCC | Foundation | RCC | m³ | 650 | 8500 | 5525000 | 2026-03-01 | 2026-03-30 | 30 | A010 | C002
A012 | P001 | 03.04 | Foundation Columns | Foundation | RCC Columns | m³ | 220 | 9000 | 1980000 | 2026-03-15 | 2026-04-05 | 22 | A011 | C002
A013 | P001 | 03.05 | Plinth Beam | Foundation | RCC Beam | m³ | 180 | 9000 | 1620000 | 2026-03-25 | 2026-04-13 | 20 | A012 | C002
A014 | P001 | 03.06 | Damp Proof Course | Foundation | DPC | m | 850 | 180 | 153000 | 2026-04-10 | 2026-04-19 | 10 | A013 | C001
A015 | P001 | 04.01 | Ground Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-04-01 | 2026-04-18 | 18 | A014 | C002
A016 | P001 | 04.02 | First Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-04-20 | 2026-05-07 | 18 | A015 | C002
A017 | P001 | 04.03 | Second Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-05-09 | 2026-05-26 | 18 | A016 | C002
A018 | P001 | 04.04 | Third Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-05-28 | 2026-06-14 | 18 | A017 | C002
A019 | P001 | 04.05 | Fourth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-06-16 | 2026-07-03 | 18 | A018 | C002
A020 | P001 | 04.06 | Fifth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-07-05 | 2026-07-22 | 18 | A019 | C002
A021 | P001 | 04.07 | Sixth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-07-24 | 2026-08-10 | 18 | A020 | C002
A022 | P001 | 04.08 | Seventh Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-08-12 | 2026-08-29 | 18 | A021 | C002
A023 | P001 | 04.09 | Eighth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-08-31 | 2026-09-17 | 18 | A022 | C002
A024 | P001 | 04.10 | Ninth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-09-19 | 2026-10-06 | 18 | A023 | C002
A025 | P001 | 04.11 | Tenth Floor Columns | Structure | Columns | m³ | 90 | 9000 | 810000 | 2026-10-08 | 2026-10-25 | 18 | A024 | C002
A026 | P001 | 05.01 | Ground Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-04-12 | 2026-05-01 | 20 | A025 | C002
A027 | P001 | 05.02 | First Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-05-03 | 2026-05-22 | 20 | A026 | C002
A028 | P001 | 05.03 | Second Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-05-24 | 2026-06-12 | 20 | A027 | C002
A029 | P001 | 05.04 | Third Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-06-14 | 2026-07-03 | 20 | A028 | C002
A030 | P001 | 05.05 | Fourth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-07-05 | 2026-07-24 | 20 | A029 | C002
A031 | P001 | 05.06 | Fifth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-07-26 | 2026-08-14 | 20 | A030 | C002
A032 | P001 | 05.07 | Sixth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-08-16 | 2026-09-04 | 20 | A031 | C002
A033 | P001 | 05.08 | Seventh Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-09-06 | 2026-09-25 | 20 | A032 | C002
A034 | P001 | 05.09 | Eighth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-09-27 | 2026-10-16 | 20 | A033 | C002
A035 | P001 | 05.10 | Ninth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-10-18 | 2026-11-06 | 20 | A034 | C002
A036 | P001 | 05.11 | Tenth Floor Beams | Structure | Beams | m³ | 105 | 9000 | 945000 | 2026-11-08 | 2026-11-27 | 20 | A035 | C002
A037 | P001 | 06.01 | Ground Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-04-25 | 2026-05-16 | 22 | A036 | C002
A038 | P001 | 06.02 | First Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-05-18 | 2026-06-08 | 22 | A037 | C002
A039 | P001 | 06.03 | Second Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-06-10 | 2026-07-01 | 22 | A038 | C002
A040 | P001 | 06.04 | Third Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-07-03 | 2026-07-24 | 22 | A039 | C002
A041 | P001 | 06.05 | Fourth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-07-26 | 2026-08-16 | 22 | A040 | C002
A042 | P001 | 06.06 | Fifth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-08-18 | 2026-09-08 | 22 | A041 | C002
A043 | P001 | 06.07 | Sixth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-09-10 | 2026-10-01 | 22 | A042 | C002
A044 | P001 | 06.08 | Seventh Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-10-03 | 2026-10-24 | 22 | A043 | C002
A045 | P001 | 06.09 | Eighth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-10-26 | 2026-11-16 | 22 | A044 | C002
A046 | P001 | 06.10 | Ninth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-11-18 | 2026-12-09 | 22 | A045 | C002
A047 | P001 | 06.11 | Tenth Floor Slab | Structure | Slab | m³ | 170 | 9000 | 1530000 | 2026-12-11 | 2026-12-31 | 22 | A046 | C002
A048 | P001 | 07.01 | Staircase Construction | Structure | Staircase | m³ | 120 | 11000 | 1320000 | 2026-04-15 | 2026-05-29 | 45 | A047 | C002
A049 | P001 | 08.01 | External Brickwork | Masonry | Brickwork | m³ | 1300 | 7500 | 9750000 | 2026-06-01 | 2026-08-09 | 70 | A048 | C003
A050 | P001 | 08.02 | Internal Brickwork | Masonry | Brickwork | m³ | 900 | 7500 | 6750000 | 2026-06-15 | 2026-08-28 | 75 | A049 | C003
A051 | P001 | 08.03 | Lintels | Masonry | RCC Lintel | m³ | 80 | 9500 | 760000 | 2026-07-01 | 2026-07-30 | 30 | A050 | C003
A052 | P001 | 09.01 | Internal Plaster | Finishing | Plaster | m² | 18000 | 280 | 5040000 | 2026-08-01 | 2026-10-14 | 75 | A051 | C004
A053 | P001 | 09.02 | External Plaster | Finishing | Plaster | m² | 12000 | 320 | 3840000 | 2026-08-15 | 2026-10-18 | 65 | A052 | C004
A054 | P001 | 10.01 | Toilet Waterproofing | Waterproofing | Waterproofing | m² | 1800 | 420 | 756000 | 2026-08-20 | 2026-09-23 | 35 | A053 | C008
A055 | P001 | 10.02 | Terrace Waterproofing | Waterproofing | Waterproofing | m² | 2500 | 450 | 1125000 | 2026-11-20 | 2026-12-19 | 30 | A054 | C008
A056 | P001 | 11.01 | Floor Tiles | Finishing | Flooring | m² | 12000 | 850 | 10200000 | 2026-09-15 | 2026-12-08 | 85 | A055 | C004
A057 | P001 | 11.02 | Toilet Wall Tiles | Finishing | Tiling | m² | 5000 | 900 | 4500000 | 2026-09-25 | 2026-12-03 | 70 | A056 | C004
A058 | P001 | 11.03 | Door Installation | Finishing | Doors | no. | 220 | 8500 | 1870000 | 2026-10-15 | 2026-12-18 | 65 | A057 | C004
A059 | P001 | 11.04 | Window Installation | Finishing | Windows | m² | 2500 | 5200 | 13000000 | 2026-09-25 | 2026-12-03 | 70 | A058 | C004
A060 | P001 | 12.01 | Internal Painting | Finishing | Painting | m² | 25000 | 180 | 4500000 | 2026-10-01 | 2026-12-19 | 80 | A059 | C005
A061 | P001 | 12.02 | External Painting | Finishing | Painting | m² | 14000 | 210 | 2940000 | 2026-10-15 | 2026-12-18 | 65 | A060 | C005
A062 | P001 | 13.01 | Plumbing Works | MEP | Plumbing | m | 6500 | 520 | 3380000 | 2026-08-15 | 2026-11-22 | 100 | A061 | C006
A063 | P001 | 13.02 | Sanitary Fixtures | MEP | Sanitary | no. | 220 | 6500 | 1430000 | 2026-10-20 | 2026-12-23 | 65 | A062 | C006
A064 | P001 | 13.03 | Electrical Wiring | MEP | Electrical | m | 18000 | 190 | 3420000 | 2026-08-20 | 2026-11-28 | 100 | A063 | C007
A065 | P001 | 13.04 | Electrical Fixtures | MEP | Electrical | no. | 950 | 1800 | 1710000 | 2026-10-25 | 2026-12-23 | 60 | A064 | C007
A066 | P001 | 14.01 | External Drainage | External Works | Drainage | m | 900 | 1200 | 1080000 | 2026-10-15 | 2026-12-08 | 55 | A065 | C001
A067 | P001 | 14.02 | Paving Works | External Works | Paving | m² | 4500 | 750 | 3375000 | 2026-11-01 | 2026-12-25 | 55 | A066 | C001
A068 | P001 | 14.03 | Final Cleaning | External Works | Cleaning | m² | 85000 | 12 | 1020000 | 2026-12-01 | 2026-12-25 | 25 | A067 | C001

## Progress
Progress_ID | Project_ID | Activity_ID | Date | Planned_Quantity_To_Date | Actual_Quantity_To_Date | Planned_Percentage | Actual_Percentage | Quantity_Completed_This_Period | Status | Delay_Days
PR00001 | P001 | A001 | 2026-01-04 | 0.3 | 0.30647 | 30 | 30.6468 | 0.30647 | In Progress | 0
PR00002 | P001 | A001 | 2026-01-11 | 1 | 1 | 100 | 100 | 0.69353 | Completed | 0
PR00003 | P001 | A001 | 2026-01-18 | 1 | 0.99601 | 100 | 99.6012 | 0 | In Progress | 0
PR00004 | P001 | A001 | 2026-01-25 | 1 | 0.97059 | 100 | 97.0595 | 0 | In Progress | 0
PR00005 | P001 | A001 | 2026-02-01 | 1 | 0.97114 | 100 | 97.1143 | 0.00054863 | In Progress | 0
PR00006 | P001 | A001 | 2026-02-08 | 1 | 1 | 100 | 100 | 0.028857 | Completed | 0
PR00007 | P001 | A001 | 2026-02-15 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00008 | P001 | A001 | 2026-02-22 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00009 | P001 | A001 | 2026-03-01 | 1 | 0.97671 | 100 | 97.6707 | 0 | In Progress | 0
PR00010 | P001 | A001 | 2026-03-08 | 1 | 1 | 100 | 100 | 0.023293 | Completed | 0
PR00011 | P001 | A001 | 2026-03-15 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00012 | P001 | A001 | 2026-03-22 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00013 | P001 | A001 | 2026-03-29 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00014 | P001 | A001 | 2026-04-05 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00015 | P001 | A001 | 2026-04-12 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00016 | P001 | A001 | 2026-04-19 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00017 | P001 | A001 | 2026-04-26 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00018 | P001 | A001 | 2026-05-03 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00019 | P001 | A001 | 2026-05-10 | 1 | 0.949 | 100 | 94.9 | 0 | Delayed | 0
PR00020 | P001 | A001 | 2026-05-17 | 1 | 0.98881 | 100 | 98.8812 | 0.039812 | In Progress | 0
PR00021 | P001 | A001 | 2026-05-24 | 1 | 0.98354 | 100 | 98.3537 | 0 | In Progress | 0
PR00022 | P001 | A001 | 2026-05-31 | 1 | 0.97764 | 100 | 97.7639 | 0 | In Progress | 0
PR00023 | P001 | A001 | 2026-06-07 | 1 | 0.99037 | 100 | 99.037 | 0.012731 | In Progress | 0
PR00024 | P001 | A001 | 2026-06-14 | 1 | 1 | 100 | 100 | 0.00963 | Completed | 0
PR00025 | P001 | A001 | 2026-06-21 | 1 | 0.9697 | 100 | 96.9696 | 0 | In Progress | 0
PR00026 | P001 | A001 | 2026-06-28 | 1 | 1 | 100 | 100 | 0.030304 | Completed | 0
PR00027 | P001 | A001 | 2026-07-05 | 1 | 0.9411 | 100 | 94.11 | 0 | Delayed | 0
PR00028 | P001 | A001 | 2026-07-12 | 1 | 0.98828 | 100 | 98.8279 | 0.047179 | In Progress | 0
PR00029 | P001 | A001 | 2026-07-19 | 1 | 1 | 100 | 100 | 0.011721 | Completed | 0
PR00030 | P001 | A001 | 2026-07-26 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00031 | P001 | A001 | 2026-08-02 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00032 | P001 | A001 | 2026-08-09 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00033 | P001 | A001 | 2026-08-16 | 1 | 0.98779 | 100 | 98.7795 | 0 | In Progress | 0
PR00034 | P001 | A001 | 2026-08-23 | 1 | 0.98382 | 100 | 98.3818 | 0 | In Progress | 0
PR00035 | P001 | A001 | 2026-08-30 | 1 | 1 | 100 | 100 | 0.016182 | Completed | 0
PR00036 | P001 | A001 | 2026-09-06 | 1 | 0.9933 | 100 | 99.3304 | 0 | In Progress | 0
PR00037 | P001 | A001 | 2026-09-13 | 1 | 0.95535 | 100 | 95.5351 | 0 | In Progress | 0
PR00038 | P001 | A001 | 2026-09-20 | 1 | 0.96033 | 100 | 96.0335 | 0.004984 | In Progress | 0
PR00039 | P001 | A001 | 2026-09-27 | 1 | 0.96782 | 100 | 96.7819 | 0.0074842 | In Progress | 0
PR00040 | P001 | A001 | 2026-10-04 | 1 | 1 | 100 | 100 | 0.032181 | Completed | 0
PR00041 | P001 | A001 | 2026-10-11 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00042 | P001 | A001 | 2026-10-18 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00043 | P001 | A001 | 2026-10-25 | 1 | 0.98505 | 100 | 98.5046 | 0 | In Progress | 0
PR00044 | P001 | A001 | 2026-11-01 | 1 | 1 | 100 | 100 | 0.014954 | Completed | 0
PR00045 | P001 | A001 | 2026-11-08 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00046 | P001 | A001 | 2026-11-15 | 1 | 0.98917 | 100 | 98.9173 | 0 | In Progress | 0
PR00047 | P001 | A001 | 2026-11-22 | 1 | 1 | 100 | 100 | 0.010827 | Completed | 0
PR00048 | P001 | A001 | 2026-11-29 | 1 | 0.97683 | 100 | 97.6833 | 0 | In Progress | 0
PR00049 | P001 | A001 | 2026-12-06 | 1 | 0.98729 | 100 | 98.7293 | 0.010461 | In Progress | 0
PR00050 | P001 | A001 | 2026-12-13 | 1 | 0.98664 | 100 | 98.6639 | 0 | In Progress | 0
PR00051 | P001 | A001 | 2026-12-20 | 1 | 0.95815 | 100 | 95.8146 | 0 | In Progress | 0
PR00052 | P001 | A001 | 2026-12-27 | 1 | 1 | 100 | 100 | 0.041854 | Completed | 0
PR00053 | P001 | A002 | 2026-01-04 | 1500 | 1355.3564 | 30 | 27.1071 | 1355.3564 | In Progress | 8
PR00054 | P001 | A002 | 2026-01-11 | 5000 | 4602.1865 | 100 | 92.0437 | 3246.8301 | Delayed | 8
PR00055 | P001 | A002 | 2026-01-18 | 5000 | 4684.1307 | 100 | 93.6826 | 81.9442 | Delayed | 8
PR00056 | P001 | A002 | 2026-01-25 | 5000 | 4678.143 | 100 | 93.5629 | 0 | Delayed | 8
PR00057 | P001 | A002 | 2026-02-01 | 5000 | 4716.4424 | 100 | 94.3288 | 38.2994 | Delayed | 8
PR00058 | P001 | A002 | 2026-02-08 | 5000 | 4582.765 | 100 | 91.6553 | 0 | Delayed | 8
PR00059 | P001 | A002 | 2026-02-15 | 5000 | 4525.9228 | 100 | 90.5185 | 0 | Delayed | 8
PR00060 | P001 | A002 | 2026-02-22 | 5000 | 4586.0493 | 100 | 91.721 | 60.1265 | Delayed | 8
PR00061 | P001 | A002 | 2026-03-01 | 5000 | 4304.7165 | 100 | 86.0943 | 0 | Delayed | 8
PR00062 | P001 | A002 | 2026-03-08 | 5000 | 4346.7553 | 100 | 86.9351 | 42.0388 | Delayed | 8
PR00063 | P001 | A002 | 2026-03-15 | 5000 | 4368.5276 | 100 | 87.3706 | 21.7723 | Delayed | 8
PR00064 | P001 | A002 | 2026-03-22 | 5000 | 4425.4818 | 100 | 88.5096 | 56.9542 | Delayed | 8
PR00065 | P001 | A002 | 2026-03-29 | 5000 | 4669.9605 | 100 | 93.3992 | 244.4787 | Delayed | 8
PR00066 | P001 | A002 | 2026-04-05 | 5000 | 4441.5412 | 100 | 88.8308 | 0 | Delayed | 8
PR00067 | P001 | A002 | 2026-04-12 | 5000 | 4533.8216 | 100 | 90.6764 | 92.2804 | Delayed | 8
PR00068 | P001 | A002 | 2026-04-19 | 5000 | 4827.365 | 100 | 96.5473 | 293.5434 | In Progress | 8
PR00069 | P001 | A002 | 2026-04-26 | 5000 | 4537.6538 | 100 | 90.7531 | 0 | Delayed | 8
PR00070 | P001 | A002 | 2026-05-03 | 5000 | 4729.0652 | 100 | 94.5813 | 191.4114 | Delayed | 8
PR00071 | P001 | A002 | 2026-05-10 | 5000 | 4436.6169 | 100 | 88.7323 | 0 | Delayed | 8
PR00072 | P001 | A002 | 2026-05-17 | 5000 | 4564.0484 | 100 | 91.281 | 127.4315 | Delayed | 8
PR00073 | P001 | A002 | 2026-05-24 | 5000 | 4433.7461 | 100 | 88.6749 | 0 | Delayed | 8
PR00074 | P001 | A002 | 2026-05-31 | 5000 | 4540.6692 | 100 | 90.8134 | 106.9231 | Delayed | 8
PR00075 | P001 | A002 | 2026-06-07 | 5000 | 4747.0539 | 100 | 94.9411 | 206.3847 | Delayed | 8
PR00076 | P001 | A002 | 2026-06-14 | 5000 | 4297.7189 | 100 | 85.9544 | 0 | Delayed | 8
PR00077 | P001 | A002 | 2026-06-21 | 5000 | 4676.0241 | 100 | 93.5205 | 378.3052 | Delayed | 8
PR00078 | P001 | A002 | 2026-06-28 | 5000 | 4641.6037 | 100 | 92.8321 | 0 | Delayed | 8
PR00079 | P001 | A002 | 2026-07-05 | 5000 | 4496.0238 | 100 | 89.9205 | 0 | Delayed | 8
PR00080 | P001 | A002 | 2026-07-12 | 5000 | 4346.9399 | 100 | 86.9388 | 0 | Delayed | 8
PR00081 | P001 | A002 | 2026-07-19 | 5000 | 4612.6227 | 100 | 92.2525 | 265.6828 | Delayed | 8
PR00082 | P001 | A002 | 2026-07-26 | 5000 | 4507.3388 | 100 | 90.1468 | 0 | Delayed | 8
PR00083 | P001 | A002 | 2026-08-02 | 5000 | 4640.7183 | 100 | 92.8144 | 133.3796 | Delayed | 8
PR00084 | P001 | A002 | 2026-08-09 | 5000 | 4603.8241 | 100 | 92.0765 | 0 | Delayed | 8
PR00085 | P001 | A002 | 2026-08-16 | 5000 | 4880.3113 | 100 | 97.6062 | 276.4872 | In Progress | 8
PR00086 | P001 | A002 | 2026-08-23 | 5000 | 4558.1128 | 100 | 91.1623 | 0 | Delayed | 8
PR00087 | P001 | A002 | 2026-08-30 | 5000 | 4420.8879 | 100 | 88.4178 | 0 | Delayed | 8
PR00088 | P001 | A002 | 2026-09-06 | 5000 | 4631.3732 | 100 | 92.6275 | 210.4853 | Delayed | 8
PR00089 | P001 | A002 | 2026-09-13 | 5000 | 4638.4994 | 100 | 92.77 | 7.1262 | Delayed | 8
PR00090 | P001 | A002 | 2026-09-20 | 5000 | 4837.8578 | 100 | 96.7572 | 199.3584 | In Progress | 8
PR00091 | P001 | A002 | 2026-09-27 | 5000 | 4746.1445 | 100 | 94.9229 | 0 | Delayed | 8
PR00092 | P001 | A002 | 2026-10-04 | 5000 | 4662.4524 | 100 | 93.249 | 0 | Delayed | 8
PR00093 | P001 | A002 | 2026-10-11 | 5000 | 4856.078 | 100 | 97.1216 | 193.6256 | In Progress | 8
PR00094 | P001 | A002 | 2026-10-18 | 5000 | 4391.9665 | 100 | 87.8393 | 0 | Delayed | 8
PR00095 | P001 | A002 | 2026-10-25 | 5000 | 4488.0435 | 100 | 89.7609 | 96.077 | Delayed | 8
PR00096 | P001 | A002 | 2026-11-01 | 5000 | 4437.8492 | 100 | 88.757 | 0 | Delayed | 8
PR00097 | P001 | A002 | 2026-11-08 | 5000 | 4531.7833 | 100 | 90.6357 | 93.9341 | Delayed | 8
PR00098 | P001 | A002 | 2026-11-15 | 5000 | 4359.0799 | 100 | 87.1816 | 0 | Delayed | 8
PR00099 | P001 | A002 | 2026-11-22 | 5000 | 4711.1514 | 100 | 94.223 | 352.0715 | Delayed | 8
PR00100 | P001 | A002 | 2026-11-29 | 5000 | 4561.111 | 100 | 91.2222 | 0 | Delayed | 8
PR00101 | P001 | A002 | 2026-12-06 | 5000 | 4342.6089 | 100 | 86.8522 | 0 | Delayed | 8
PR00102 | P001 | A002 | 2026-12-13 | 5000 | 4422.2737 | 100 | 88.4455 | 79.6648 | Delayed | 8
PR00103 | P001 | A002 | 2026-12-20 | 5000 | 4654.8649 | 100 | 93.0973 | 232.5913 | Delayed | 8
PR00104 | P001 | A002 | 2026-12-27 | 5000 | 4746.6721 | 100 | 94.9334 | 91.8072 | Delayed | 8
PR00105 | P001 | A003 | 2026-01-11 | 0.3 | 0.30597 | 30 | 30.5966 | 0.30597 | In Progress | 5
PR00106 | P001 | A003 | 2026-01-18 | 0.65 | 0.68379 | 65 | 68.379 | 0.37782 | In Progress | 5
PR00107 | P001 | A003 | 2026-01-25 | 1 | 0.9645 | 100 | 96.4504 | 0.28071 | In Progress | 5
PR00108 | P001 | A003 | 2026-02-01 | 1 | 0.91537 | 100 | 91.5366 | 0 | Delayed | 5
PR00109 | P001 | A003 | 2026-02-08 | 1 | 0.87538 | 100 | 87.5378 | 0 | Delayed | 5
PR00110 | P001 | A003 | 2026-02-15 | 1 | 0.95937 | 100 | 95.937 | 0.083992 | In Progress | 5
PR00111 | P001 | A003 | 2026-02-22 | 1 | 0.92155 | 100 | 92.1547 | 0 | Delayed | 5
PR00112 | P001 | A003 | 2026-03-01 | 1 | 0.93546 | 100 | 93.5462 | 0.013915 | Delayed | 5
PR00113 | P001 | A003 | 2026-03-08 | 1 | 0.92858 | 100 | 92.8577 | 0 | Delayed | 5
PR00114 | P001 | A003 | 2026-03-15 | 1 | 0.94507 | 100 | 94.5072 | 0.016496 | Delayed | 5
PR00115 | P001 | A003 | 2026-03-22 | 1 | 0.98731 | 100 | 98.7309 | 0.042237 | In Progress | 5
PR00116 | P001 | A003 | 2026-03-29 | 1 | 0.9555 | 100 | 95.5497 | 0 | In Progress | 5
PR00117 | P001 | A003 | 2026-04-05 | 1 | 0.94445 | 100 | 94.4448 | 0 | Delayed | 5
PR00118 | P001 | A003 | 2026-04-12 | 1 | 0.91375 | 100 | 91.3752 | 0 | Delayed | 5
PR00119 | P001 | A003 | 2026-04-19 | 1 | 0.89139 | 100 | 89.1386 | 0 | Delayed | 5
PR00120 | P001 | A003 | 2026-04-26 | 1 | 0.93298 | 100 | 93.2979 | 0.041593 | Delayed | 5
PR00121 | P001 | A003 | 2026-05-03 | 1 | 0.94812 | 100 | 94.8118 | 0.015138 | Delayed | 5
PR00122 | P001 | A003 | 2026-05-10 | 1 | 1 | 100 | 100 | 0.051882 | Completed | 5
PR00123 | P001 | A003 | 2026-05-17 | 1 | 0.95456 | 100 | 95.456 | 0 | In Progress | 5
PR00124 | P001 | A003 | 2026-05-24 | 1 | 0.9844 | 100 | 98.4396 | 0.029836 | In Progress | 5
PR00125 | P001 | A003 | 2026-05-31 | 1 | 0.93252 | 100 | 93.2525 | 0 | Delayed | 5
PR00126 | P001 | A003 | 2026-06-07 | 1 | 0.90853 | 100 | 90.8527 | 0 | Delayed | 5
PR00127 | P001 | A003 | 2026-06-14 | 1 | 0.91622 | 100 | 91.6221 | 0.0076939 | Delayed | 5
PR00128 | P001 | A003 | 2026-06-21 | 1 | 0.92462 | 100 | 92.4617 | 0.0083962 | Delayed | 5
PR00129 | P001 | A003 | 2026-06-28 | 1 | 1 | 100 | 100 | 0.075383 | Completed | 5
PR00130 | P001 | A003 | 2026-07-05 | 1 | 0.92125 | 100 | 92.1251 | 0 | Delayed | 5
PR00131 | P001 | A003 | 2026-07-12 | 1 | 0.97935 | 100 | 97.9347 | 0.058096 | In Progress | 5
PR00132 | P001 | A003 | 2026-07-19 | 1 | 0.9184 | 100 | 91.8398 | 0 | Delayed | 5
PR00133 | P001 | A003 | 2026-07-26 | 1 | 0.98261 | 100 | 98.2605 | 0.064208 | In Progress | 5
PR00134 | P001 | A003 | 2026-08-02 | 1 | 0.96347 | 100 | 96.3473 | 0 | In Progress | 5
PR00135 | P001 | A003 | 2026-08-09 | 1 | 0.94452 | 100 | 94.4518 | 0 | Delayed | 5
PR00136 | P001 | A003 | 2026-08-16 | 1 | 0.94857 | 100 | 94.8573 | 0.0040556 | Delayed | 5
PR00137 | P001 | A003 | 2026-08-23 | 1 | 0.92708 | 100 | 92.7082 | 0 | Delayed | 5
PR00138 | P001 | A003 | 2026-08-30 | 1 | 0.96561 | 100 | 96.5613 | 0.03853 | In Progress | 5
PR00139 | P001 | A003 | 2026-09-06 | 1 | 0.93408 | 100 | 93.4076 | 0 | Delayed | 5
PR00140 | P001 | A003 | 2026-09-13 | 1 | 0.9071 | 100 | 90.7104 | 0 | Delayed | 5
PR00141 | P001 | A003 | 2026-09-20 | 1 | 0.90527 | 100 | 90.5272 | 0 | Delayed | 5
PR00142 | P001 | A003 | 2026-09-27 | 1 | 0.95604 | 100 | 95.6041 | 0.050768 | In Progress | 5
PR00143 | P001 | A003 | 2026-10-04 | 1 | 1 | 100 | 100 | 0.043959 | Completed | 5
PR00144 | P001 | A003 | 2026-10-11 | 1 | 0.9556 | 100 | 95.56 | 0 | In Progress | 5
PR00145 | P001 | A003 | 2026-10-18 | 1 | 0.94585 | 100 | 94.5848 | 0 | Delayed | 5
PR00146 | P001 | A003 | 2026-10-25 | 1 | 0.96 | 100 | 96.0004 | 0.014156 | In Progress | 5
PR00147 | P001 | A003 | 2026-11-01 | 1 | 0.99571 | 100 | 99.571 | 0.035706 | In Progress | 5
PR00148 | P001 | A003 | 2026-11-08 | 1 | 0.95768 | 100 | 95.7678 | 0 | In Progress | 5
PR00149 | P001 | A003 | 2026-11-15 | 1 | 0.93562 | 100 | 93.5618 | 0 | Delayed | 5
PR00150 | P001 | A003 | 2026-11-22 | 1 | 0.98872 | 100 | 98.872 | 0.053103 | In Progress | 5
PR00151 | P001 | A003 | 2026-11-29 | 1 | 0.96501 | 100 | 96.5006 | 0 | In Progress | 5
PR00152 | P001 | A003 | 2026-12-06 | 1 | 1 | 100 | 100 | 0.034994 | Completed | 5
PR00153 | P001 | A003 | 2026-12-13 | 1 | 0.95641 | 100 | 95.6413 | 0 | In Progress | 5
PR00154 | P001 | A003 | 2026-12-20 | 1 | 0.90714 | 100 | 90.7144 | 0 | Delayed | 5
PR00155 | P001 | A003 | 2026-12-27 | 1 | 0.90211 | 100 | 90.2114 | 0 | Delayed | 5
PR00156 | P001 | A004 | 2026-01-11 | 0.42857 | 0.45334 | 42.8571 | 45.3335 | 0.45334 | In Progress | 0
PR00157 | P001 | A004 | 2026-01-18 | 1 | 1 | 100 | 100 | 0.54666 | Completed | 0
PR00158 | P001 | A004 | 2026-01-25 | 1 | 0.99372 | 100 | 99.3717 | 0 | In Progress | 0
PR00159 | P001 | A004 | 2026-02-01 | 1 | 0.98659 | 100 | 98.6588 | 0 | In Progress | 0
PR00160 | P001 | A004 | 2026-02-08 | 1 | 1 | 100 | 100 | 0.013412 | Completed | 0
PR00161 | P001 | A004 | 2026-02-15 | 1 | 0.96125 | 100 | 96.1253 | 0 | In Progress | 0
PR00162 | P001 | A004 | 2026-02-22 | 1 | 0.96868 | 100 | 96.8685 | 0.0074312 | In Progress | 0
PR00163 | P001 | A004 | 2026-03-01 | 1 | 1 | 100 | 100 | 0.031315 | Completed | 0
PR00164 | P001 | A004 | 2026-03-08 | 1 | 0.98619 | 100 | 98.6189 | 0 | In Progress | 0
PR00165 | P001 | A004 | 2026-03-15 | 1 | 0.99982 | 100 | 99.9821 | 0.013632 | Completed | 0
PR00166 | P001 | A004 | 2026-03-22 | 1 | 0.99428 | 100 | 99.4279 | 0 | In Progress | 0
PR00167 | P001 | A004 | 2026-03-29 | 1 | 1 | 100 | 100 | 0.0057205 | Completed | 0
PR00168 | P001 | A004 | 2026-04-05 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00169 | P001 | A004 | 2026-04-12 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00170 | P001 | A004 | 2026-04-19 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00171 | P001 | A004 | 2026-04-26 | 1 | 0.92824 | 100 | 92.8244 | 0 | Delayed | 0
PR00172 | P001 | A004 | 2026-05-03 | 1 | 0.99829 | 100 | 99.8295 | 0.070051 | In Progress | 0
PR00173 | P001 | A004 | 2026-05-10 | 1 | 0.97049 | 100 | 97.0487 | 0 | In Progress | 0
PR00174 | P001 | A004 | 2026-05-17 | 1 | 0.95734 | 100 | 95.7342 | 0 | In Progress | 0
PR00175 | P001 | A004 | 2026-05-24 | 1 | 0.96926 | 100 | 96.9265 | 0.011923 | In Progress | 0
PR00176 | P001 | A004 | 2026-05-31 | 1 | 0.98831 | 100 | 98.8306 | 0.019041 | In Progress | 0
PR00177 | P001 | A004 | 2026-06-07 | 1 | 1 | 100 | 100 | 0.011694 | Completed | 0
PR00178 | P001 | A004 | 2026-06-14 | 1 | 0.95358 | 100 | 95.3576 | 0 | In Progress | 0
PR00179 | P001 | A004 | 2026-06-21 | 1 | 1 | 100 | 100 | 0.046424 | Completed | 0
PR00180 | P001 | A004 | 2026-06-28 | 1 | 0.98305 | 100 | 98.3054 | 0 | In Progress | 0
PR00181 | P001 | A004 | 2026-07-05 | 1 | 0.98853 | 100 | 98.8531 | 0.0054774 | In Progress | 0
PR00182 | P001 | A004 | 2026-07-12 | 1 | 1 | 100 | 100 | 0.011469 | Completed | 0
PR00183 | P001 | A004 | 2026-07-19 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00184 | P001 | A004 | 2026-07-26 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00185 | P001 | A004 | 2026-08-02 | 1 | 0.99459 | 100 | 99.4592 | 0 | In Progress | 0
PR00186 | P001 | A004 | 2026-08-09 | 1 | 0.97564 | 100 | 97.5642 | 0 | In Progress | 0
PR00187 | P001 | A004 | 2026-08-16 | 1 | 0.99216 | 100 | 99.2165 | 0.016523 | In Progress | 0
PR00188 | P001 | A004 | 2026-08-23 | 1 | 1 | 100 | 100 | 0.0078351 | Completed | 0
PR00189 | P001 | A004 | 2026-08-30 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00190 | P001 | A004 | 2026-09-06 | 1 | 0.96205 | 100 | 96.2046 | 0 | In Progress | 0
PR00191 | P001 | A004 | 2026-09-13 | 1 | 1 | 100 | 100 | 0.037954 | Completed | 0
PR00192 | P001 | A004 | 2026-09-20 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00193 | P001 | A004 | 2026-09-27 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00194 | P001 | A004 | 2026-10-04 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00195 | P001 | A004 | 2026-10-11 | 1 | 0.97014 | 100 | 97.0136 | 0 | In Progress | 0
PR00196 | P001 | A004 | 2026-10-18 | 1 | 0.98994 | 100 | 98.9942 | 0.019805 | In Progress | 0
PR00197 | P001 | A004 | 2026-10-25 | 1 | 0.94878 | 100 | 94.878 | 0 | Delayed | 0
PR00198 | P001 | A004 | 2026-11-01 | 1 | 0.97933 | 100 | 97.9325 | 0.030546 | In Progress | 0
PR00199 | P001 | A004 | 2026-11-08 | 1 | 1 | 100 | 100 | 0.020675 | Completed | 0
PR00200 | P001 | A004 | 2026-11-15 | 1 | 1 | 100 | 100 | 0 | Completed | 0
PR00201 | P001 | A004 | 2026-11-22 | 1 | 0.97448 | 100 | 97.4482 | 0 | In Progress | 0
PR00202 | P001 | A004 | 2026-11-29 | 1 | 0.9771 | 100 | 97.7105 | 0.0026228 | In Progress | 0
PR00203 | P001 | A004 | 2026-12-06 | 1 | 0.92484 | 100 | 92.4845 | 0 | Delayed | 0
PR00204 | P001 | A004 | 2026-12-13 | 1 | 0.99431 | 100 | 99.4307 | 0.069462 | In Progress | 0
PR00205 | P001 | A004 | 2026-12-20 | 1 | 0.96282 | 100 | 96.2815 | 0 | In Progress | 0
PR00206 | P001 | A004 | 2026-12-27 | 1 | 0.98147 | 100 | 98.147 | 0.018654 | In Progress | 0
PR00207 | P001 | A005 | 2026-01-18 | 700 | 678.5169 | 20 | 19.3862 | 678.5169 | In Progress | 0
PR00208 | P001 | A005 | 2026-01-25 | 1516.6667 | 1511.6629 | 43.3333 | 43.1904 | 833.146 | In Progress | 0
PR00209 | P001 | A005 | 2026-02-01 | 2333.3333 | 2189.7855 | 66.6667 | 62.5653 | 678.1226 | In Progress | 0
PR00210 | P001 | A005 | 2026-02-08 | 3150 | 2988.2583 | 90 | 85.3788 | 798.4727 | In Progress | 0
PR00211 | P001 | A005 | 2026-02-15 | 3500 | 3500 | 100 | 100 | 511.7417 | Completed | 0
PR00212 | P001 | A005 | 2026-02-22 | 3500 | 3342.2907 | 100 | 95.494 | 0 | In Progress | 0
PR00213 | P001 | A005 | 2026-03-01 | 3500 | 3190.6438 | 100 | 91.1613 | 0 | Delayed | 0
PR00214 | P001 | A005 | 2026-03-08 | 3500 | 3325 | 100 | 95 | 134.3562 | In Progress | 0
PR00215 | P001 | A005 | 2026-03-15 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00216 | P001 | A005 | 2026-03-22 | 3500 | 3181.4831 | 100 | 90.8995 | 0 | Delayed | 0
PR00217 | P001 | A005 | 2026-03-29 | 3500 | 3279.8895 | 100 | 93.7111 | 98.4064 | Delayed | 0
PR00218 | P001 | A005 | 2026-04-05 | 3500 | 3325 | 100 | 95 | 45.1105 | In Progress | 0
PR00219 | P001 | A005 | 2026-04-12 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00220 | P001 | A005 | 2026-04-19 | 3500 | 3204.11 | 100 | 91.546 | 0 | Delayed | 0
PR00221 | P001 | A005 | 2026-04-26 | 3500 | 3294.9535 | 100 | 94.1415 | 90.8435 | Delayed | 0
PR00222 | P001 | A005 | 2026-05-03 | 3500 | 3500 | 100 | 100 | 205.0465 | Completed | 0
PR00223 | P001 | A005 | 2026-05-10 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00224 | P001 | A005 | 2026-05-17 | 3500 | 3453.9209 | 100 | 98.6835 | 0 | In Progress | 0
PR00225 | P001 | A005 | 2026-05-24 | 3500 | 3483.6067 | 100 | 99.5316 | 29.6858 | In Progress | 0
PR00226 | P001 | A005 | 2026-05-31 | 3500 | 3331.5753 | 100 | 95.1879 | 0 | In Progress | 0
PR00227 | P001 | A005 | 2026-06-07 | 3500 | 3470.8237 | 100 | 99.1664 | 139.2485 | In Progress | 0
PR00228 | P001 | A005 | 2026-06-14 | 3500 | 3467.3675 | 100 | 99.0676 | 0 | In Progress | 0
PR00229 | P001 | A005 | 2026-06-21 | 3500 | 3500 | 100 | 100 | 32.6325 | Completed | 0
PR00230 | P001 | A005 | 2026-06-28 | 3500 | 3431.9724 | 100 | 98.0564 | 0 | In Progress | 0
PR00231 | P001 | A005 | 2026-07-05 | 3500 | 3500 | 100 | 100 | 68.0276 | Completed | 0
PR00232 | P001 | A005 | 2026-07-12 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00233 | P001 | A005 | 2026-07-19 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00234 | P001 | A005 | 2026-07-26 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00235 | P001 | A005 | 2026-08-02 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00236 | P001 | A005 | 2026-08-09 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00237 | P001 | A005 | 2026-08-16 | 3500 | 3236.6091 | 100 | 92.4745 | 0 | Delayed | 0
PR00238 | P001 | A005 | 2026-08-23 | 3500 | 3325 | 100 | 95 | 88.3909 | In Progress | 0
PR00239 | P001 | A005 | 2026-08-30 | 3500 | 3313.0824 | 100 | 94.6595 | 0 | Delayed | 0
PR00240 | P001 | A005 | 2026-09-06 | 3500 | 3325 | 100 | 95 | 11.9176 | In Progress | 0
PR00241 | P001 | A005 | 2026-09-13 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00242 | P001 | A005 | 2026-09-20 | 3500 | 3325 | 100 | 95 | 0 | In Progress | 0
PR00243 | P001 | A005 | 2026-09-27 | 3500 | 3231.5255 | 100 | 92.3293 | 0 | Delayed | 0
PR00244 | P001 | A005 | 2026-10-04 | 3500 | 3363.7296 | 100 | 96.1066 | 132.2041 | In Progress | 0
PR00245 | P001 | A005 | 2026-10-11 | 3500 | 3500 | 100 | 100 | 136.2704 | Completed | 0
PR00246 | P001 | A005 | 2026-10-18 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00247 | P001 | A005 | 2026-10-25 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00248 | P001 | A005 | 2026-11-01 | 3500 | 3286.2882 | 100 | 93.8939 | 0 | Delayed | 0
PR00249 | P001 | A005 | 2026-11-08 | 3500 | 3500 | 100 | 100 | 213.7118 | Completed | 0
PR00250 | P001 | A005 | 2026-11-15 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00251 | P001 | A005 | 2026-11-22 | 3500 | 3363.9722 | 100 | 96.1135 | 0 | In Progress | 0
PR00252 | P001 | A005 | 2026-11-29 | 3500 | 3442.2382 | 100 | 98.3497 | 78.266 | In Progress | 0
PR00253 | P001 | A005 | 2026-12-06 | 3500 | 3500 | 100 | 100 | 57.7618 | Completed | 0
PR00254 | P001 | A005 | 2026-12-13 | 3500 | 3500 | 100 | 100 | 0 | Completed | 0
PR00255 | P001 | A005 | 2026-12-20 | 3500 | 3464.209 | 100 | 98.9774 | 0 | In Progress | 0
PR00256 | P001 | A005 | 2026-12-27 | 3500 | 3487.3227 | 100 | 99.6378 | 23.1137 | In Progress | 0
PR00257 | P001 | A006 | 2026-02-01 | 0 | 0 | 0 | 0 | 0 | Not Started | 8
PR00258 | P001 | A006 | 2026-02-08 | 630 | 582.964 | 35 | 32.3869 | 582.964 | In Progress | 8
PR00259 | P001 | A006 | 2026-02-15 | 1260 | 1224.0928 | 70 | 68.0052 | 641.1288 | In Progress | 8
PR00260 | P001 | A006 | 2026-02-22 | 1800 | 1494.3005 | 100 | 83.0167 | 270.2077 | Delayed | 8
PR00261 | P001 | A006 | 2026-03-01 | 1800 | 1641.0784 | 100 | 91.171 | 146.7779 | Delayed | 8
PR00262 | P001 | A006 | 2026-03-08 | 1800 | 1667.1203 | 100 | 92.6178 | 26.0418 | Delayed | 8
PR00263 | P001 | A006 | 2026-03-15 | 1800 | 1674.6476 | 100 | 93.036 | 7.5273 | Delayed | 8
PR00264 | P001 | A006 | 2026-03-22 | 1800 | 1632.5694 | 100 | 90.6983 | 0 | Delayed | 8
PR00265 | P001 | A006 | 2026-03-29 | 1800 | 1545.3265 | 100 | 85.8515 | 0 | Delayed | 8
PR00266 | P001 | A006 | 2026-04-05 | 1800 | 1676.6637 | 100 | 93.148 | 131.3372 | Delayed | 8
PR00267 | P001 | A006 | 2026-04-12 | 1800 | 1764.8231 | 100 | 98.0457 | 88.1593 | In Progress | 8
PR00268 | P001 | A006 | 2026-04-19 | 1800 | 1559.3667 | 100 | 86.6315 | 0 | Delayed | 8
PR00269 | P001 | A006 | 2026-04-26 | 1800 | 1710.4212 | 100 | 95.0234 | 151.0544 | In Progress | 8
PR00270 | P001 | A006 | 2026-05-03 | 1800 | 1635.3029 | 100 | 90.8502 | 0 | Delayed | 8
PR00271 | P001 | A006 | 2026-05-10 | 1800 | 1652.1366 | 100 | 91.7854 | 16.8337 | Delayed | 8
PR00272 | P001 | A006 | 2026-05-17 | 1800 | 1589.6674 | 100 | 88.3149 | 0 | Delayed | 8
PR00273 | P001 | A006 | 2026-05-24 | 1800 | 1634.9293 | 100 | 90.8294 | 45.2619 | Delayed | 8
PR00274 | P001 | A006 | 2026-05-31 | 1800 | 1737.9028 | 100 | 96.5502 | 102.9735 | In Progress | 8
PR00275 | P001 | A006 | 2026-06-07 | 1800 | 1692.7073 | 100 | 94.0393 | 0 | Delayed | 8
PR00276 | P001 | A006 | 2026-06-14 | 1800 | 1765.1356 | 100 | 98.0631 | 72.4284 | In Progress | 8
PR00277 | P001 | A006 | 2026-06-21 | 1800 | 1730.1769 | 100 | 96.1209 | 0 | In Progress | 8
PR00278 | P001 | A006 | 2026-06-28 | 1800 | 1683.6625 | 100 | 93.5368 | 0 | Delayed | 8
PR00279 | P001 | A006 | 2026-07-05 | 1800 | 1765.8679 | 100 | 98.1038 | 82.2054 | In Progress | 8
PR00280 | P001 | A006 | 2026-07-12 | 1800 | 1683.6566 | 100 | 93.5365 | 0 | Delayed | 8
PR00281 | P001 | A006 | 2026-07-19 | 1800 | 1708.1633 | 100 | 94.898 | 24.5067 | Delayed | 8
PR00282 | P001 | A006 | 2026-07-26 | 1800 | 1637.316 | 100 | 90.962 | 0 | Delayed | 8
PR00283 | P001 | A006 | 2026-08-02 | 1800 | 1660.1924 | 100 | 92.2329 | 22.8764 | Delayed | 8
PR00284 | P001 | A006 | 2026-08-09 | 1800 | 1612.0623 | 100 | 89.559 | 0 | Delayed | 8
PR00285 | P001 | A006 | 2026-08-16 | 1800 | 1718.3438 | 100 | 95.4635 | 106.2815 | In Progress | 8
PR00286 | P001 | A006 | 2026-08-23 | 1800 | 1581.7669 | 100 | 87.8759 | 0 | Delayed | 8
PR00287 | P001 | A006 | 2026-08-30 | 1800 | 1705.2881 | 100 | 94.7382 | 123.5212 | Delayed | 8
PR00288 | P001 | A006 | 2026-09-06 | 1800 | 1643.989 | 100 | 91.3327 | 0 | Delayed | 8
PR00289 | P001 | A006 | 2026-09-13 | 1800 | 1729.7886 | 100 | 96.0994 | 85.7996 | In Progress | 8
PR00290 | P001 | A006 | 2026-09-20 | 1800 | 1703.3047 | 100 | 94.628 | 0 | Delayed | 8
PR00291 | P001 | A006 | 2026-09-27 | 1800 | 1770.7007 | 100 | 98.3723 | 67.396 | In Progress | 8
PR00292 | P001 | A006 | 2026-10-04 | 1800 | 1702.0388 | 100 | 94.5577 | 0 | Delayed | 8
PR00293 | P001 | A006 | 2026-10-11 | 1800 | 1556.9615 | 100 | 86.4979 | 0 | Delayed | 8
PR00294 | P001 | A006 | 2026-10-18 | 1800 | 1651.782 | 100 | 91.7657 | 94.8205 | Delayed | 8
PR00295 | P001 | A006 | 2026-10-25 | 1800 | 1582.1635 | 100 | 87.898 | 0 | Delayed | 8
PR00296 | P001 | A006 | 2026-11-01 | 1800 | 1623.3484 | 100 | 90.186 | 41.1848 | Delayed | 8
PR00297 | P001 | A006 | 2026-11-08 | 1800 | 1751.2074 | 100 | 97.2893 | 127.859 | In Progress | 8
PR00298 | P001 | A006 | 2026-11-15 | 1800 | 1696.1646 | 100 | 94.2314 | 0 | Delayed | 8
PR00299 | P001 | A006 | 2026-11-22 | 1800 | 1611.9674 | 100 | 89.5537 | 0 | Delayed | 8
PR00300 | P001 | A006 | 2026-11-29 | 1800 | 1592.1358 | 100 | 88.452 | 0 | Delayed | 8
PR00301 | P001 | A006 | 2026-12-06 | 1800 | 1658.0653 | 100 | 92.1147 | 65.9295 | Delayed | 8
PR00302 | P001 | A006 | 2026-12-13 | 1800 | 1579.3567 | 100 | 87.742 | 0 | Delayed | 8
PR00303 | P001 | A006 | 2026-12-20 | 1800 | 1613.7182 | 100 | 89.651 | 34.3615 | Delayed | 8
PR00304 | P001 | A006 | 2026-12-27 | 1800 | 1675.6566 | 100 | 93.092 | 61.9384 | Delayed | 8
PR00305 | P001 | A007 | 2026-02-08 | 240 | 249.7046 | 13.3333 | 13.8725 | 249.7046 | In Progress | 0
PR00306 | P001 | A007 | 2026-02-15 | 1080 | 1103.0112 | 60 | 61.2784 | 853.3066 | In Progress | 0
PR00307 | P001 | A007 | 2026-02-22 | 1800 | 1655.6488 | 100 | 91.9805 | 552.6376 | Delayed | 0
PR00308 | P001 | A007 | 2026-03-01 | 1800 | 1800 | 100 | 100 | 144.3512 | Completed | 0
PR00309 | P001 | A007 | 2026-03-08 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00310 | P001 | A007 | 2026-03-15 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00311 | P001 | A007 | 2026-03-22 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00312 | P001 | A007 | 2026-03-29 | 1800 | 1670.016 | 100 | 92.7787 | 0 | Delayed | 0
PR00313 | P001 | A007 | 2026-04-05 | 1800 | 1762.7605 | 100 | 97.9311 | 92.7445 | In Progress | 0
PR00314 | P001 | A007 | 2026-04-12 | 1800 | 1800 | 100 | 100 | 37.2395 | Completed | 0
PR00315 | P001 | A007 | 2026-04-19 | 1800 | 1700.3596 | 100 | 94.4644 | 0 | Delayed | 0
PR00316 | P001 | A007 | 2026-04-26 | 1800 | 1800 | 100 | 100 | 99.6404 | Completed | 0
PR00317 | P001 | A007 | 2026-05-03 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00318 | P001 | A007 | 2026-05-10 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00319 | P001 | A007 | 2026-05-17 | 1800 | 1764.0305 | 100 | 98.0017 | 0 | In Progress | 0
PR00320 | P001 | A007 | 2026-05-24 | 1800 | 1800 | 100 | 100 | 35.9695 | Completed | 0
PR00321 | P001 | A007 | 2026-05-31 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00322 | P001 | A007 | 2026-06-07 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00323 | P001 | A007 | 2026-06-14 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00324 | P001 | A007 | 2026-06-21 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00325 | P001 | A007 | 2026-06-28 | 1800 | 1745.6092 | 100 | 96.9783 | 0 | In Progress | 0
PR00326 | P001 | A007 | 2026-07-05 | 1800 | 1790.7057 | 100 | 99.4836 | 45.0964 | In Progress | 0
PR00327 | P001 | A007 | 2026-07-12 | 1800 | 1790.3911 | 100 | 99.4662 | 0 | In Progress | 0
PR00328 | P001 | A007 | 2026-07-19 | 1800 | 1800 | 100 | 100 | 9.6089 | Completed | 0
PR00329 | P001 | A007 | 2026-07-26 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00330 | P001 | A007 | 2026-08-02 | 1800 | 1733.3122 | 100 | 96.2951 | 0 | In Progress | 0
PR00331 | P001 | A007 | 2026-08-09 | 1800 | 1792.1244 | 100 | 99.5625 | 58.8122 | In Progress | 0
PR00332 | P001 | A007 | 2026-08-16 | 1800 | 1800 | 100 | 100 | 7.8756 | Completed | 0
PR00333 | P001 | A007 | 2026-08-23 | 1800 | 1753.1539 | 100 | 97.3974 | 0 | In Progress | 0
PR00334 | P001 | A007 | 2026-08-30 | 1800 | 1748.1982 | 100 | 97.1221 | 0 | In Progress | 0
PR00335 | P001 | A007 | 2026-09-06 | 1800 | 1800 | 100 | 100 | 51.8018 | Completed | 0
PR00336 | P001 | A007 | 2026-09-13 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00337 | P001 | A007 | 2026-09-20 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00338 | P001 | A007 | 2026-09-27 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00339 | P001 | A007 | 2026-10-04 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00340 | P001 | A007 | 2026-10-11 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00341 | P001 | A007 | 2026-10-18 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00342 | P001 | A007 | 2026-10-25 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00343 | P001 | A007 | 2026-11-01 | 1800 | 1787.0748 | 100 | 99.2819 | 0 | In Progress | 0
PR00344 | P001 | A007 | 2026-11-08 | 1800 | 1673.7781 | 100 | 92.9877 | 0 | Delayed | 0
PR00345 | P001 | A007 | 2026-11-15 | 1800 | 1800 | 100 | 100 | 126.2219 | Completed | 0
PR00346 | P001 | A007 | 2026-11-22 | 1800 | 1771.1649 | 100 | 98.3981 | 0 | In Progress | 0
PR00347 | P001 | A007 | 2026-11-29 | 1800 | 1800 | 100 | 100 | 28.8351 | Completed | 0
PR00348 | P001 | A007 | 2026-12-06 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR00349 | P001 | A007 | 2026-12-13 | 1800 | 1699.0576 | 100 | 94.3921 | 0 | Delayed | 0
PR00350 | P001 | A007 | 2026-12-20 | 1800 | 1721.1462 | 100 | 95.6192 | 22.0886 | In Progress | 0
PR00351 | P001 | A007 | 2026-12-27 | 1800 | 1699.1195 | 100 | 94.3955 | 0 | Delayed | 0
PR00352 | P001 | A008 | 2026-01-25 | 472.2222 | 435.4858 | 27.7778 | 25.6168 | 435.4858 | In Progress | 5
PR00353 | P001 | A008 | 2026-02-01 | 1133.3333 | 1094.1056 | 66.6667 | 64.3592 | 658.6198 | In Progress | 5
PR00354 | P001 | A008 | 2026-02-08 | 1700 | 1646.1892 | 100 | 96.8347 | 552.0836 | In Progress | 5
PR00355 | P001 | A008 | 2026-02-15 | 1700 | 1631.4383 | 100 | 95.967 | 0 | In Progress | 5
PR00356 | P001 | A008 | 2026-02-22 | 1700 | 1530.9404 | 100 | 90.0553 | 0 | Delayed | 5
PR00357 | P001 | A008 | 2026-03-01 | 1700 | 1477.5488 | 100 | 86.9146 | 0 | Delayed | 5
PR00358 | P001 | A008 | 2026-03-08 | 1700 | 1618.234 | 100 | 95.1902 | 140.6852 | In Progress | 5
PR00359 | P001 | A008 | 2026-03-15 | 1700 | 1586.9293 | 100 | 93.3488 | 0 | Delayed | 5
PR00360 | P001 | A008 | 2026-03-22 | 1700 | 1642.3335 | 100 | 96.6079 | 55.4041 | In Progress | 5
PR00361 | P001 | A008 | 2026-03-29 | 1700 | 1656.7662 | 100 | 97.4568 | 14.4328 | In Progress | 5
PR00362 | P001 | A008 | 2026-04-05 | 1700 | 1623.2254 | 100 | 95.4838 | 0 | In Progress | 5
PR00363 | P001 | A008 | 2026-04-12 | 1700 | 1660.2279 | 100 | 97.6605 | 37.0026 | In Progress | 5
PR00364 | P001 | A008 | 2026-04-19 | 1700 | 1628.6381 | 100 | 95.8022 | 0 | In Progress | 5
PR00365 | P001 | A008 | 2026-04-26 | 1700 | 1646.5388 | 100 | 96.8552 | 17.9008 | In Progress | 5
PR00366 | P001 | A008 | 2026-05-03 | 1700 | 1573.0719 | 100 | 92.5336 | 0 | Delayed | 5
PR00367 | P001 | A008 | 2026-05-10 | 1700 | 1604.3131 | 100 | 94.3714 | 31.2412 | Delayed | 5
PR00368 | P001 | A008 | 2026-05-17 | 1700 | 1626.7082 | 100 | 95.6887 | 22.3951 | In Progress | 5
PR00369 | P001 | A008 | 2026-05-24 | 1700 | 1663.8214 | 100 | 97.8718 | 37.1133 | In Progress | 5
PR00370 | P001 | A008 | 2026-05-31 | 1700 | 1591.5724 | 100 | 93.6219 | 0 | Delayed | 5
PR00371 | P001 | A008 | 2026-06-07 | 1700 | 1646.0095 | 100 | 96.8241 | 54.4371 | In Progress | 5
PR00372 | P001 | A008 | 2026-06-14 | 1700 | 1599.1826 | 100 | 94.0696 | 0 | Delayed | 5
PR00373 | P001 | A008 | 2026-06-21 | 1700 | 1608.0062 | 100 | 94.5886 | 8.8236 | Delayed | 5
PR00374 | P001 | A008 | 2026-06-28 | 1700 | 1664.3564 | 100 | 97.9033 | 56.3501 | In Progress | 5
PR00375 | P001 | A008 | 2026-07-05 | 1700 | 1496.4129 | 100 | 88.0243 | 0 | Delayed | 5
PR00376 | P001 | A008 | 2026-07-12 | 1700 | 1537.8599 | 100 | 90.4623 | 41.447 | Delayed | 5
PR00377 | P001 | A008 | 2026-07-19 | 1700 | 1526.81 | 100 | 89.8124 | 0 | Delayed | 5
PR00378 | P001 | A008 | 2026-07-26 | 1700 | 1476.1498 | 100 | 86.8323 | 0 | Delayed | 5
PR00379 | P001 | A008 | 2026-08-02 | 1700 | 1574.6433 | 100 | 92.6261 | 98.4934 | Delayed | 5
PR00380 | P001 | A008 | 2026-08-09 | 1700 | 1659.5913 | 100 | 97.623 | 84.9481 | In Progress | 5
PR00381 | P001 | A008 | 2026-08-16 | 1700 | 1598.0494 | 100 | 94.0029 | 0 | Delayed | 5
PR00382 | P001 | A008 | 2026-08-23 | 1700 | 1626.7685 | 100 | 95.6923 | 28.7191 | In Progress | 5
PR00383 | P001 | A008 | 2026-08-30 | 1700 | 1679.8084 | 100 | 98.8123 | 53.0399 | In Progress | 5
PR00384 | P001 | A008 | 2026-09-06 | 1700 | 1693.9973 | 100 | 99.6469 | 14.1889 | In Progress | 5
PR00385 | P001 | A008 | 2026-09-13 | 1700 | 1610.8863 | 100 | 94.758 | 0 | Delayed | 5
PR00386 | P001 | A008 | 2026-09-20 | 1700 | 1695.5384 | 100 | 99.7376 | 84.6521 | In Progress | 5
PR00387 | P001 | A008 | 2026-09-27 | 1700 | 1620.4815 | 100 | 95.3224 | 0 | In Progress | 5
PR00388 | P001 | A008 | 2026-10-04 | 1700 | 1565.1748 | 100 | 92.0691 | 0 | Delayed | 5
PR00389 | P001 | A008 | 2026-10-11 | 1700 | 1579.6332 | 100 | 92.9196 | 14.4584 | Delayed | 5
PR00390 | P001 | A008 | 2026-10-18 | 1700 | 1526.9081 | 100 | 89.8181 | 0 | Delayed | 5
PR00391 | P001 | A008 | 2026-10-25 | 1700 | 1562.156 | 100 | 91.8915 | 35.248 | Delayed | 5
PR00392 | P001 | A008 | 2026-11-01 | 1700 | 1593.698 | 100 | 93.7469 | 31.542 | Delayed | 5
PR00393 | P001 | A008 | 2026-11-08 | 1700 | 1662.8133 | 100 | 97.8125 | 69.1153 | In Progress | 5
PR00394 | P001 | A008 | 2026-11-15 | 1700 | 1700 | 100 | 100 | 37.1867 | Completed | 5
PR00395 | P001 | A008 | 2026-11-22 | 1700 | 1532.7602 | 100 | 90.1624 | 0 | Delayed | 5
PR00396 | P001 | A008 | 2026-11-29 | 1700 | 1638.3732 | 100 | 96.3749 | 105.613 | In Progress | 5
PR00397 | P001 | A008 | 2026-12-06 | 1700 | 1553.0876 | 100 | 91.3581 | 0 | Delayed | 5
PR00398 | P001 | A008 | 2026-12-13 | 1700 | 1643.2445 | 100 | 96.6614 | 90.1568 | In Progress | 5
PR00399 | P001 | A008 | 2026-12-20 | 1700 | 1607.2003 | 100 | 94.5412 | 0 | Delayed | 5
PR00400 | P001 | A008 | 2026-12-27 | 1700 | 1506.0611 | 100 | 88.5918 | 0 | Delayed | 5
PR00401 | P001 | A009 | 2026-02-15 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR00402 | P001 | A009 | 2026-02-22 | 175 | 171.2944 | 38.8889 | 38.0654 | 171.2944 | In Progress | 0
PR00403 | P001 | A009 | 2026-03-01 | 350 | 343.4597 | 77.7778 | 76.3244 | 172.1654 | In Progress | 0
PR00404 | P001 | A009 | 2026-03-08 | 450 | 433.1514 | 100 | 96.2559 | 89.6917 | In Progress | 0
PR00405 | P001 | A009 | 2026-03-15 | 450 | 439.695 | 100 | 97.71 | 6.5436 | In Progress | 0
PR00406 | P001 | A009 | 2026-03-22 | 450 | 450 | 100 | 100 | 10.305 | Completed | 0
PR00407 | P001 | A009 | 2026-03-29 | 450 | 447.0194 | 100 | 99.3376 | 0 | In Progress | 0
PR00408 | P001 | A009 | 2026-04-05 | 450 | 450 | 100 | 100 | 2.9806 | Completed | 0
PR00409 | P001 | A009 | 2026-04-12 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00410 | P001 | A009 | 2026-04-19 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00411 | P001 | A009 | 2026-04-26 | 450 | 444.6011 | 100 | 98.8002 | 0 | In Progress | 0
PR00412 | P001 | A009 | 2026-05-03 | 450 | 426.7395 | 100 | 94.831 | 0 | Delayed | 0
PR00413 | P001 | A009 | 2026-05-10 | 450 | 450 | 100 | 100 | 23.2605 | Completed | 0
PR00414 | P001 | A009 | 2026-05-17 | 450 | 444.7791 | 100 | 98.8398 | 0 | In Progress | 0
PR00415 | P001 | A009 | 2026-05-24 | 450 | 450 | 100 | 100 | 5.2209 | Completed | 0
PR00416 | P001 | A009 | 2026-05-31 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00417 | P001 | A009 | 2026-06-07 | 450 | 447.9346 | 100 | 99.541 | 0 | In Progress | 0
PR00418 | P001 | A009 | 2026-06-14 | 450 | 450 | 100 | 100 | 2.0654 | Completed | 0
PR00419 | P001 | A009 | 2026-06-21 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00420 | P001 | A009 | 2026-06-28 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00421 | P001 | A009 | 2026-07-05 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00422 | P001 | A009 | 2026-07-12 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00423 | P001 | A009 | 2026-07-19 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00424 | P001 | A009 | 2026-07-26 | 450 | 436.6808 | 100 | 97.0402 | 0 | In Progress | 0
PR00425 | P001 | A009 | 2026-08-02 | 450 | 450 | 100 | 100 | 13.3192 | Completed | 0
PR00426 | P001 | A009 | 2026-08-09 | 450 | 449.5927 | 100 | 99.9095 | 0 | Completed | 0
PR00427 | P001 | A009 | 2026-08-16 | 450 | 450 | 100 | 100 | 0.40734 | Completed | 0
PR00428 | P001 | A009 | 2026-08-23 | 450 | 436.8744 | 100 | 97.0832 | 0 | In Progress | 0
PR00429 | P001 | A009 | 2026-08-30 | 450 | 424.9643 | 100 | 94.4365 | 0 | Delayed | 0
PR00430 | P001 | A009 | 2026-09-06 | 450 | 417.3505 | 100 | 92.7446 | 0 | Delayed | 0
PR00431 | P001 | A009 | 2026-09-13 | 450 | 432.4012 | 100 | 96.0892 | 15.0507 | In Progress | 0
PR00432 | P001 | A009 | 2026-09-20 | 450 | 442.7759 | 100 | 98.3946 | 10.3747 | In Progress | 0
PR00433 | P001 | A009 | 2026-09-27 | 450 | 445.3822 | 100 | 98.9738 | 2.6064 | In Progress | 0
PR00434 | P001 | A009 | 2026-10-04 | 450 | 450 | 100 | 100 | 4.6178 | Completed | 0
PR00435 | P001 | A009 | 2026-10-11 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00436 | P001 | A009 | 2026-10-18 | 450 | 434.8471 | 100 | 96.6327 | 0 | In Progress | 0
PR00437 | P001 | A009 | 2026-10-25 | 450 | 450 | 100 | 100 | 15.1529 | Completed | 0
PR00438 | P001 | A009 | 2026-11-01 | 450 | 443.5885 | 100 | 98.5752 | 0 | In Progress | 0
PR00439 | P001 | A009 | 2026-11-08 | 450 | 445.5213 | 100 | 99.0047 | 1.9328 | In Progress | 0
PR00440 | P001 | A009 | 2026-11-15 | 450 | 450 | 100 | 100 | 4.4787 | Completed | 0
PR00441 | P001 | A009 | 2026-11-22 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00442 | P001 | A009 | 2026-11-29 | 450 | 444.6567 | 100 | 98.8126 | 0 | In Progress | 0
PR00443 | P001 | A009 | 2026-12-06 | 450 | 450 | 100 | 100 | 5.3433 | Completed | 0
PR00444 | P001 | A009 | 2026-12-13 | 450 | 432.0145 | 100 | 96.0032 | 0 | In Progress | 0
PR00445 | P001 | A009 | 2026-12-20 | 450 | 450 | 100 | 100 | 17.9855 | Completed | 0
PR00446 | P001 | A009 | 2026-12-27 | 450 | 450 | 100 | 100 | 0 | Completed | 0
PR00447 | P001 | A010 | 2026-02-22 | 6.8 | 6.8531 | 8 | 8.0625 | 6.8531 | In Progress | 0
PR00448 | P001 | A010 | 2026-03-01 | 30.6 | 32.135 | 36 | 37.8059 | 25.2819 | In Progress | 0
PR00449 | P001 | A010 | 2026-03-08 | 54.4 | 54.5743 | 64 | 64.205 | 22.4393 | In Progress | 0
PR00450 | P001 | A010 | 2026-03-15 | 78.2 | 79.7896 | 92 | 93.8701 | 25.2153 | In Progress | 0
PR00451 | P001 | A010 | 2026-03-22 | 85 | 84.8311 | 100 | 99.8013 | 5.0415 | In Progress | 0
PR00452 | P001 | A010 | 2026-03-29 | 85 | 84.493 | 100 | 99.4036 | 0 | In Progress | 0
PR00453 | P001 | A010 | 2026-04-05 | 85 | 82.681 | 100 | 97.2718 | 0 | In Progress | 0
PR00454 | P001 | A010 | 2026-04-12 | 85 | 85 | 100 | 100 | 2.319 | Completed | 0
PR00455 | P001 | A010 | 2026-04-19 | 85 | 82.4667 | 100 | 97.0196 | 0 | In Progress | 0
PR00456 | P001 | A010 | 2026-04-26 | 85 | 85 | 100 | 100 | 2.5333 | Completed | 0
PR00457 | P001 | A010 | 2026-05-03 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00458 | P001 | A010 | 2026-05-10 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00459 | P001 | A010 | 2026-05-17 | 85 | 84.1484 | 100 | 98.9981 | 0 | In Progress | 0
PR00460 | P001 | A010 | 2026-05-24 | 85 | 85 | 100 | 100 | 0.85159 | Completed | 0
PR00461 | P001 | A010 | 2026-05-31 | 85 | 84.0817 | 100 | 98.9196 | 0 | In Progress | 0
PR00462 | P001 | A010 | 2026-06-07 | 85 | 85 | 100 | 100 | 0.9183 | Completed | 0
PR00463 | P001 | A010 | 2026-06-14 | 85 | 79.5516 | 100 | 93.5901 | 0 | Delayed | 0
PR00464 | P001 | A010 | 2026-06-21 | 85 | 84.0016 | 100 | 98.8254 | 4.45 | In Progress | 0
PR00465 | P001 | A010 | 2026-06-28 | 85 | 79.0773 | 100 | 93.0322 | 0 | Delayed | 0
PR00466 | P001 | A010 | 2026-07-05 | 85 | 80.5522 | 100 | 94.7673 | 1.4749 | Delayed | 0
PR00467 | P001 | A010 | 2026-07-12 | 85 | 85 | 100 | 100 | 4.4478 | Completed | 0
PR00468 | P001 | A010 | 2026-07-19 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00469 | P001 | A010 | 2026-07-26 | 85 | 82.8595 | 100 | 97.4818 | 0 | In Progress | 0
PR00470 | P001 | A010 | 2026-08-02 | 85 | 80.5301 | 100 | 94.7412 | 0 | Delayed | 0
PR00471 | P001 | A010 | 2026-08-09 | 85 | 76.1805 | 100 | 89.6241 | 0 | Delayed | 0
PR00472 | P001 | A010 | 2026-08-16 | 85 | 83.3831 | 100 | 98.0978 | 7.2026 | In Progress | 0
PR00473 | P001 | A010 | 2026-08-23 | 85 | 85 | 100 | 100 | 1.6169 | Completed | 0
PR00474 | P001 | A010 | 2026-08-30 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00475 | P001 | A010 | 2026-09-06 | 85 | 83.3353 | 100 | 98.0415 | 0 | In Progress | 0
PR00476 | P001 | A010 | 2026-09-13 | 85 | 85 | 100 | 100 | 1.6647 | Completed | 0
PR00477 | P001 | A010 | 2026-09-20 | 85 | 80.3561 | 100 | 94.5366 | 0 | Delayed | 0
PR00478 | P001 | A010 | 2026-09-27 | 85 | 84.1155 | 100 | 98.9594 | 3.7593 | In Progress | 0
PR00479 | P001 | A010 | 2026-10-04 | 85 | 85 | 100 | 100 | 0.88454 | Completed | 0
PR00480 | P001 | A010 | 2026-10-11 | 85 | 84.7439 | 100 | 99.6986 | 0 | In Progress | 0
PR00481 | P001 | A010 | 2026-10-18 | 85 | 85 | 100 | 100 | 0.25615 | Completed | 0
PR00482 | P001 | A010 | 2026-10-25 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00483 | P001 | A010 | 2026-11-01 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00484 | P001 | A010 | 2026-11-08 | 85 | 82.9521 | 100 | 97.5907 | 0 | In Progress | 0
PR00485 | P001 | A010 | 2026-11-15 | 85 | 85 | 100 | 100 | 2.0479 | Completed | 0
PR00486 | P001 | A010 | 2026-11-22 | 85 | 85 | 100 | 100 | 0 | Completed | 0
PR00487 | P001 | A010 | 2026-11-29 | 85 | 82.1138 | 100 | 96.6045 | 0 | In Progress | 0
PR00488 | P001 | A010 | 2026-12-06 | 85 | 82.3591 | 100 | 96.8931 | 0.2453 | In Progress | 0
PR00489 | P001 | A010 | 2026-12-13 | 85 | 85 | 100 | 100 | 2.6409 | Completed | 0
PR00490 | P001 | A010 | 2026-12-20 | 85 | 84.4308 | 100 | 99.3303 | 0 | In Progress | 0
PR00491 | P001 | A010 | 2026-12-27 | 85 | 85 | 100 | 100 | 0.56925 | Completed | 0
PR00492 | P001 | A011 | 2026-03-01 | 0 | 0 | 0 | 0 | 0 | Not Started | 3
PR00493 | P001 | A011 | 2026-03-08 | 151.6667 | 154.8405 | 23.3333 | 23.8216 | 154.8405 | In Progress | 3
PR00494 | P001 | A011 | 2026-03-15 | 303.3333 | 295.6293 | 46.6667 | 45.4814 | 140.7887 | In Progress | 3
PR00495 | P001 | A011 | 2026-03-22 | 455 | 445.4623 | 70 | 68.5327 | 149.833 | In Progress | 3
PR00496 | P001 | A011 | 2026-03-29 | 606.6667 | 621.6908 | 93.3333 | 95.6447 | 176.2286 | In Progress | 3
PR00497 | P001 | A011 | 2026-04-05 | 650 | 622.2697 | 100 | 95.7338 | 0.57888 | In Progress | 3
PR00498 | P001 | A011 | 2026-04-12 | 650 | 609.0895 | 100 | 93.7061 | 0 | Delayed | 3
PR00499 | P001 | A011 | 2026-04-19 | 650 | 620.2952 | 100 | 95.43 | 11.2057 | In Progress | 3
PR00500 | P001 | A011 | 2026-04-26 | 650 | 640.7906 | 100 | 98.5832 | 20.4954 | In Progress | 3
PR00501 | P001 | A011 | 2026-05-03 | 650 | 594.879 | 100 | 91.5198 | 0 | Delayed | 3
PR00502 | P001 | A011 | 2026-05-10 | 650 | 645.0025 | 100 | 99.2311 | 50.1235 | In Progress | 3
PR00503 | P001 | A011 | 2026-05-17 | 650 | 618.243 | 100 | 95.1143 | 0 | In Progress | 3
PR00504 | P001 | A011 | 2026-05-24 | 650 | 650 | 100 | 100 | 31.757 | Completed | 3
PR00505 | P001 | A011 | 2026-05-31 | 650 | 576.0306 | 100 | 88.6201 | 0 | Delayed | 3
PR00506 | P001 | A011 | 2026-06-07 | 650 | 612.6056 | 100 | 94.247 | 36.5751 | Delayed | 3
PR00507 | P001 | A011 | 2026-06-14 | 650 | 592.1328 | 100 | 91.0974 | 0 | Delayed | 3
PR00508 | P001 | A011 | 2026-06-21 | 650 | 611.7033 | 100 | 94.1082 | 19.5704 | Delayed | 3
PR00509 | P001 | A011 | 2026-06-28 | 650 | 636.1344 | 100 | 97.8668 | 24.4311 | In Progress | 3
PR00510 | P001 | A011 | 2026-07-05 | 650 | 626.4226 | 100 | 96.3727 | 0 | In Progress | 3
PR00511 | P001 | A011 | 2026-07-12 | 650 | 624.7357 | 100 | 96.1132 | 0 | In Progress | 3
PR00512 | P001 | A011 | 2026-07-19 | 650 | 626.8785 | 100 | 96.4429 | 2.1429 | In Progress | 3
PR00513 | P001 | A011 | 2026-07-26 | 650 | 635.1271 | 100 | 97.7119 | 8.2485 | In Progress | 3
PR00514 | P001 | A011 | 2026-08-02 | 650 | 607.5558 | 100 | 93.4701 | 0 | Delayed | 3
PR00515 | P001 | A011 | 2026-08-09 | 650 | 646.5808 | 100 | 99.474 | 39.025 | In Progress | 3
PR00516 | P001 | A011 | 2026-08-16 | 650 | 645.5757 | 100 | 99.3193 | 0 | In Progress | 3
PR00517 | P001 | A011 | 2026-08-23 | 650 | 639.2596 | 100 | 98.3476 | 0 | In Progress | 3
PR00518 | P001 | A011 | 2026-08-30 | 650 | 643.1611 | 100 | 98.9479 | 3.9015 | In Progress | 3
PR00519 | P001 | A011 | 2026-09-06 | 650 | 637.2435 | 100 | 98.0375 | 0 | In Progress | 3
PR00520 | P001 | A011 | 2026-09-13 | 650 | 650 | 100 | 100 | 12.7565 | Completed | 3
PR00521 | P001 | A011 | 2026-09-20 | 650 | 628.5186 | 100 | 96.6952 | 0 | In Progress | 3
PR00522 | P001 | A011 | 2026-09-27 | 650 | 623.5139 | 100 | 95.9252 | 0 | In Progress | 3
PR00523 | P001 | A011 | 2026-10-04 | 650 | 613.3572 | 100 | 94.3627 | 0 | Delayed | 3
PR00524 | P001 | A011 | 2026-10-11 | 650 | 607.016 | 100 | 93.3871 | 0 | Delayed | 3
PR00525 | P001 | A011 | 2026-10-18 | 650 | 602.1883 | 100 | 92.6443 | 0 | Delayed | 3
PR00526 | P001 | A011 | 2026-10-25 | 650 | 610.2799 | 100 | 93.8892 | 8.0916 | Delayed | 3
PR00527 | P001 | A011 | 2026-11-01 | 650 | 628.892 | 100 | 96.7526 | 18.6122 | In Progress | 3
PR00528 | P001 | A011 | 2026-11-08 | 650 | 638.1052 | 100 | 98.17 | 9.2132 | In Progress | 3
PR00529 | P001 | A011 | 2026-11-15 | 650 | 631.6635 | 100 | 97.179 | 0 | In Progress | 3
PR00530 | P001 | A011 | 2026-11-22 | 650 | 613.0841 | 100 | 94.3206 | 0 | Delayed | 3
PR00531 | P001 | A011 | 2026-11-29 | 650 | 650 | 100 | 100 | 36.9159 | Completed | 3
PR00532 | P001 | A011 | 2026-12-06 | 650 | 647.3216 | 100 | 99.5879 | 0 | In Progress | 3
PR00533 | P001 | A011 | 2026-12-13 | 650 | 626.868 | 100 | 96.4412 | 0 | In Progress | 3
PR00534 | P001 | A011 | 2026-12-20 | 650 | 615.6462 | 100 | 94.7148 | 0 | Delayed | 3
PR00535 | P001 | A011 | 2026-12-27 | 650 | 642.9767 | 100 | 98.9195 | 27.3306 | In Progress | 3
PR00536 | P001 | A012 | 2026-03-15 | 0 | 0 | 0 | 0 | 0 | Not Started | 12
PR00537 | P001 | A012 | 2026-03-22 | 70 | 58.0521 | 31.8182 | 26.3873 | 58.0521 | Delayed | 12
PR00538 | P001 | A012 | 2026-03-29 | 140 | 122.8669 | 63.6364 | 55.8486 | 64.8148 | Delayed | 12
PR00539 | P001 | A012 | 2026-04-05 | 210 | 186.726 | 95.4545 | 84.8754 | 63.8591 | Delayed | 12
PR00540 | P001 | A012 | 2026-04-12 | 220 | 186.6724 | 100 | 84.8511 | 0 | Delayed | 12
PR00541 | P001 | A012 | 2026-04-19 | 220 | 195.0618 | 100 | 88.6645 | 8.3894 | Delayed | 12
PR00542 | P001 | A012 | 2026-04-26 | 220 | 182.3979 | 100 | 82.9081 | 0 | Delayed | 12
PR00543 | P001 | A012 | 2026-05-03 | 220 | 203.8886 | 100 | 92.6767 | 21.4908 | Delayed | 12
PR00544 | P001 | A012 | 2026-05-10 | 220 | 203.2092 | 100 | 92.3678 | 0 | Delayed | 12
PR00545 | P001 | A012 | 2026-05-17 | 220 | 191.6556 | 100 | 87.1162 | 0 | Delayed | 12
PR00546 | P001 | A012 | 2026-05-24 | 220 | 196.3986 | 100 | 89.2721 | 4.743 | Delayed | 12
PR00547 | P001 | A012 | 2026-05-31 | 220 | 175.0436 | 100 | 79.5653 | 0 | Delayed | 12
PR00548 | P001 | A012 | 2026-06-07 | 220 | 184.6961 | 100 | 83.9528 | 9.6525 | Delayed | 12
PR00549 | P001 | A012 | 2026-06-14 | 220 | 191.3379 | 100 | 86.9718 | 6.6418 | Delayed | 12
PR00550 | P001 | A012 | 2026-06-21 | 220 | 185.3446 | 100 | 84.2475 | 0 | Delayed | 12
PR00551 | P001 | A012 | 2026-06-28 | 220 | 199.1009 | 100 | 90.5004 | 13.7563 | Delayed | 12
PR00552 | P001 | A012 | 2026-07-05 | 220 | 208.9792 | 100 | 94.9905 | 9.8783 | Delayed | 12
PR00553 | P001 | A012 | 2026-07-12 | 220 | 184.5401 | 100 | 83.8818 | 0 | Delayed | 12
PR00554 | P001 | A012 | 2026-07-19 | 220 | 187.1515 | 100 | 85.0689 | 2.6115 | Delayed | 12
PR00555 | P001 | A012 | 2026-07-26 | 220 | 195.413 | 100 | 88.8241 | 8.2614 | Delayed | 12
PR00556 | P001 | A012 | 2026-08-02 | 220 | 206.0056 | 100 | 93.6389 | 10.5926 | Delayed | 12
PR00557 | P001 | A012 | 2026-08-09 | 220 | 184.1877 | 100 | 83.7217 | 0 | Delayed | 12
PR00558 | P001 | A012 | 2026-08-16 | 220 | 195.5176 | 100 | 88.8716 | 11.3299 | Delayed | 12
PR00559 | P001 | A012 | 2026-08-23 | 220 | 207.624 | 100 | 94.3745 | 12.1064 | Delayed | 12
PR00560 | P001 | A012 | 2026-08-30 | 220 | 180.8815 | 100 | 82.2188 | 0 | Delayed | 12
PR00561 | P001 | A012 | 2026-09-06 | 220 | 183.7358 | 100 | 83.5163 | 2.8543 | Delayed | 12
PR00562 | P001 | A012 | 2026-09-13 | 220 | 190.3382 | 100 | 86.5174 | 6.6025 | Delayed | 12
PR00563 | P001 | A012 | 2026-09-20 | 220 | 189.5915 | 100 | 86.1779 | 0 | Delayed | 12
PR00564 | P001 | A012 | 2026-09-27 | 220 | 199.857 | 100 | 90.8441 | 10.2656 | Delayed | 12
PR00565 | P001 | A012 | 2026-10-04 | 220 | 195.4608 | 100 | 88.8458 | 0 | Delayed | 12
PR00566 | P001 | A012 | 2026-10-11 | 220 | 179.9328 | 100 | 81.7876 | 0 | Delayed | 12
PR00567 | P001 | A012 | 2026-10-18 | 220 | 197.5687 | 100 | 89.8039 | 17.6359 | Delayed | 12
PR00568 | P001 | A012 | 2026-10-25 | 220 | 189.153 | 100 | 85.9786 | 0 | Delayed | 12
PR00569 | P001 | A012 | 2026-11-01 | 220 | 203.4132 | 100 | 92.4606 | 14.2603 | Delayed | 12
PR00570 | P001 | A012 | 2026-11-08 | 220 | 188.7676 | 100 | 85.8034 | 0 | Delayed | 12
PR00571 | P001 | A012 | 2026-11-15 | 220 | 188.6981 | 100 | 85.7718 | 0 | Delayed | 12
PR00572 | P001 | A012 | 2026-11-22 | 220 | 197.7667 | 100 | 89.894 | 9.0687 | Delayed | 12
PR00573 | P001 | A012 | 2026-11-29 | 220 | 199.4745 | 100 | 90.6702 | 1.7078 | Delayed | 12
PR00574 | P001 | A012 | 2026-12-06 | 220 | 197.0504 | 100 | 89.5683 | 0 | Delayed | 12
PR00575 | P001 | A012 | 2026-12-13 | 220 | 180.6209 | 100 | 82.1004 | 0 | Delayed | 12
PR00576 | P001 | A012 | 2026-12-20 | 220 | 197.7429 | 100 | 89.8831 | 17.122 | Delayed | 12
PR00577 | P001 | A012 | 2026-12-27 | 220 | 185.6358 | 100 | 84.3799 | 0 | Delayed | 12
PR00578 | P001 | A013 | 2026-03-29 | 36 | 34.4964 | 20 | 19.1647 | 34.4964 | In Progress | 5
PR00579 | P001 | A013 | 2026-04-05 | 99 | 89.1168 | 55 | 49.5093 | 54.6203 | Delayed | 5
PR00580 | P001 | A013 | 2026-04-12 | 162 | 156.4306 | 90 | 86.9059 | 67.3139 | In Progress | 5
PR00581 | P001 | A013 | 2026-04-19 | 180 | 165.9184 | 100 | 92.1769 | 9.4878 | Delayed | 5
PR00582 | P001 | A013 | 2026-04-26 | 180 | 162.9194 | 100 | 90.5108 | 0 | Delayed | 5
PR00583 | P001 | A013 | 2026-05-03 | 180 | 175.4971 | 100 | 97.4984 | 12.5777 | In Progress | 5
PR00584 | P001 | A013 | 2026-05-10 | 180 | 172.5224 | 100 | 95.8458 | 0 | In Progress | 5
PR00585 | P001 | A013 | 2026-05-17 | 180 | 167.1319 | 100 | 92.8511 | 0 | Delayed | 5
PR00586 | P001 | A013 | 2026-05-24 | 180 | 180 | 100 | 100 | 12.8681 | Completed | 5
PR00587 | P001 | A013 | 2026-05-31 | 180 | 168.2239 | 100 | 93.4577 | 0 | Delayed | 5
PR00588 | P001 | A013 | 2026-06-07 | 180 | 171.2023 | 100 | 95.1124 | 2.9784 | In Progress | 5
PR00589 | P001 | A013 | 2026-06-14 | 180 | 172.6942 | 100 | 95.9412 | 1.4919 | In Progress | 5
PR00590 | P001 | A013 | 2026-06-21 | 180 | 167.0961 | 100 | 92.8312 | 0 | Delayed | 5
PR00591 | P001 | A013 | 2026-06-28 | 180 | 173.9682 | 100 | 96.649 | 6.8721 | In Progress | 5
PR00592 | P001 | A013 | 2026-07-05 | 180 | 167.6393 | 100 | 93.1329 | 0 | Delayed | 5
PR00593 | P001 | A013 | 2026-07-12 | 180 | 168.4067 | 100 | 93.5593 | 0.76743 | Delayed | 5
PR00594 | P001 | A013 | 2026-07-19 | 180 | 179.5846 | 100 | 99.7692 | 11.178 | In Progress | 5
PR00595 | P001 | A013 | 2026-07-26 | 180 | 164.4443 | 100 | 91.3579 | 0 | Delayed | 5
PR00596 | P001 | A013 | 2026-08-02 | 180 | 155.7995 | 100 | 86.5553 | 0 | Delayed | 5
PR00597 | P001 | A013 | 2026-08-09 | 180 | 180 | 100 | 100 | 24.2005 | Completed | 5
PR00598 | P001 | A013 | 2026-08-16 | 180 | 180 | 100 | 100 | 0 | Completed | 5
PR00599 | P001 | A013 | 2026-08-23 | 180 | 168.4468 | 100 | 93.5816 | 0 | Delayed | 5
PR00600 | P001 | A013 | 2026-08-30 | 180 | 158.7979 | 100 | 88.2211 | 0 | Delayed | 5
PR00601 | P001 | A013 | 2026-09-06 | 180 | 169.044 | 100 | 93.9133 | 10.246 | Delayed | 5
PR00602 | P001 | A013 | 2026-09-13 | 180 | 169.1968 | 100 | 93.9982 | 0.15284 | Delayed | 5
PR00603 | P001 | A013 | 2026-09-20 | 180 | 169.8035 | 100 | 94.3353 | 0.60668 | Delayed | 5
PR00604 | P001 | A013 | 2026-09-27 | 180 | 163.9857 | 100 | 91.1031 | 0 | Delayed | 5
PR00605 | P001 | A013 | 2026-10-04 | 180 | 174.6512 | 100 | 97.0285 | 10.6656 | In Progress | 5
PR00606 | P001 | A013 | 2026-10-11 | 180 | 174.3044 | 100 | 96.8358 | 0 | In Progress | 5
PR00607 | P001 | A013 | 2026-10-18 | 180 | 161.5852 | 100 | 89.7696 | 0 | Delayed | 5
PR00608 | P001 | A013 | 2026-10-25 | 180 | 175.4049 | 100 | 97.4472 | 13.8197 | In Progress | 5
PR00609 | P001 | A013 | 2026-11-01 | 180 | 180 | 100 | 100 | 4.5951 | Completed | 5
PR00610 | P001 | A013 | 2026-11-08 | 180 | 172.0834 | 100 | 95.6019 | 0 | In Progress | 5
PR00611 | P001 | A013 | 2026-11-15 | 180 | 168.8749 | 100 | 93.8194 | 0 | Delayed | 5
PR00612 | P001 | A013 | 2026-11-22 | 180 | 170.1054 | 100 | 94.503 | 1.2305 | Delayed | 5
PR00613 | P001 | A013 | 2026-11-29 | 180 | 174.8761 | 100 | 97.1534 | 4.7707 | In Progress | 5
PR00614 | P001 | A013 | 2026-12-06 | 180 | 160.0968 | 100 | 88.9426 | 0 | Delayed | 5
PR00615 | P001 | A013 | 2026-12-13 | 180 | 172.0357 | 100 | 95.5754 | 11.9389 | In Progress | 5
PR00616 | P001 | A013 | 2026-12-20 | 180 | 168.5401 | 100 | 93.6334 | 0 | Delayed | 5
PR00617 | P001 | A013 | 2026-12-27 | 180 | 180 | 100 | 100 | 11.4599 | Completed | 5
PR00618 | P001 | A014 | 2026-04-12 | 170 | 155.3637 | 20 | 18.2781 | 155.3637 | In Progress | 8
PR00619 | P001 | A014 | 2026-04-19 | 765 | 748.4577 | 90 | 88.0538 | 593.094 | In Progress | 8
PR00620 | P001 | A014 | 2026-04-26 | 850 | 749.1637 | 100 | 88.1369 | 0.70602 | Delayed | 8
PR00621 | P001 | A014 | 2026-05-03 | 850 | 799.471 | 100 | 94.0554 | 50.3072 | Delayed | 8
PR00622 | P001 | A014 | 2026-05-10 | 850 | 791.5022 | 100 | 93.1179 | 0 | Delayed | 8
PR00623 | P001 | A014 | 2026-05-17 | 850 | 756.1458 | 100 | 88.9583 | 0 | Delayed | 8
PR00624 | P001 | A014 | 2026-05-24 | 850 | 787.2775 | 100 | 92.6209 | 31.1317 | Delayed | 8
PR00625 | P001 | A014 | 2026-05-31 | 850 | 818.0724 | 100 | 96.2438 | 30.7949 | In Progress | 8
PR00626 | P001 | A014 | 2026-06-07 | 850 | 772.3672 | 100 | 90.8667 | 0 | Delayed | 8
PR00627 | P001 | A014 | 2026-06-14 | 850 | 731.6641 | 100 | 86.0781 | 0 | Delayed | 8
PR00628 | P001 | A014 | 2026-06-21 | 850 | 781.4775 | 100 | 91.9385 | 49.8134 | Delayed | 8
PR00629 | P001 | A014 | 2026-06-28 | 850 | 755.1529 | 100 | 88.8415 | 0 | Delayed | 8
PR00630 | P001 | A014 | 2026-07-05 | 850 | 771.8154 | 100 | 90.8018 | 16.6624 | Delayed | 8
PR00631 | P001 | A014 | 2026-07-12 | 850 | 779.5728 | 100 | 91.7144 | 7.7574 | Delayed | 8
PR00632 | P001 | A014 | 2026-07-19 | 850 | 731.2568 | 100 | 86.0302 | 0 | Delayed | 8
PR00633 | P001 | A014 | 2026-07-26 | 850 | 733.9342 | 100 | 86.3452 | 2.6773 | Delayed | 8
PR00634 | P001 | A014 | 2026-08-02 | 850 | 796.3415 | 100 | 93.6872 | 62.4073 | Delayed | 8
PR00635 | P001 | A014 | 2026-08-09 | 850 | 766.4491 | 100 | 90.1705 | 0 | Delayed | 8
PR00636 | P001 | A014 | 2026-08-16 | 850 | 705.6989 | 100 | 83.0234 | 0 | Delayed | 8
PR00637 | P001 | A014 | 2026-08-23 | 850 | 805.3491 | 100 | 94.747 | 99.6503 | Delayed | 8
PR00638 | P001 | A014 | 2026-08-30 | 850 | 790.103 | 100 | 92.9533 | 0 | Delayed | 8
PR00639 | P001 | A014 | 2026-09-06 | 850 | 760.7622 | 100 | 89.5014 | 0 | Delayed | 8
PR00640 | P001 | A014 | 2026-09-13 | 850 | 742.8243 | 100 | 87.3911 | 0 | Delayed | 8
PR00641 | P001 | A014 | 2026-09-20 | 850 | 806.8653 | 100 | 94.9253 | 64.041 | Delayed | 8
PR00642 | P001 | A014 | 2026-09-27 | 850 | 792.3932 | 100 | 93.2227 | 0 | Delayed | 8
PR00643 | P001 | A014 | 2026-10-04 | 850 | 850 | 100 | 100 | 57.6068 | Completed | 8
PR00644 | P001 | A014 | 2026-10-11 | 850 | 794.5006 | 100 | 93.4707 | 0 | Delayed | 8
PR00645 | P001 | A014 | 2026-10-18 | 850 | 793.5342 | 100 | 93.357 | 0 | Delayed | 8
PR00646 | P001 | A014 | 2026-10-25 | 850 | 777.0339 | 100 | 91.4158 | 0 | Delayed | 8
PR00647 | P001 | A014 | 2026-11-01 | 850 | 806.2991 | 100 | 94.8587 | 29.2652 | Delayed | 8
PR00648 | P001 | A014 | 2026-11-08 | 850 | 800.5963 | 100 | 94.1878 | 0 | Delayed | 8
PR00649 | P001 | A014 | 2026-11-15 | 850 | 819.2388 | 100 | 96.381 | 18.6425 | In Progress | 8
PR00650 | P001 | A014 | 2026-11-22 | 850 | 766.4906 | 100 | 90.1754 | 0 | Delayed | 8
PR00651 | P001 | A014 | 2026-11-29 | 850 | 769.0466 | 100 | 90.4761 | 2.556 | Delayed | 8
PR00652 | P001 | A014 | 2026-12-06 | 850 | 767.7467 | 100 | 90.3231 | 0 | Delayed | 8
PR00653 | P001 | A014 | 2026-12-13 | 850 | 805.5264 | 100 | 94.7678 | 37.7797 | Delayed | 8
PR00654 | P001 | A014 | 2026-12-20 | 850 | 826.5766 | 100 | 97.2443 | 21.0503 | In Progress | 8
PR00655 | P001 | A014 | 2026-12-27 | 850 | 768.3495 | 100 | 90.3941 | 0 | Delayed | 8
PR00656 | P001 | A015 | 2026-04-05 | 20 | 18.7027 | 22.2222 | 20.7807 | 18.7027 | In Progress | 5
PR00657 | P001 | A015 | 2026-04-12 | 55 | 52.8546 | 61.1111 | 58.7273 | 34.1519 | In Progress | 5
PR00658 | P001 | A015 | 2026-04-19 | 90 | 84.7259 | 100 | 94.1398 | 31.8713 | Delayed | 5
PR00659 | P001 | A015 | 2026-04-26 | 90 | 88.499 | 100 | 98.3322 | 3.7731 | In Progress | 5
PR00660 | P001 | A015 | 2026-05-03 | 90 | 78.4069 | 100 | 87.1188 | 0 | Delayed | 5
PR00661 | P001 | A015 | 2026-05-10 | 90 | 82.8959 | 100 | 92.1065 | 4.489 | Delayed | 5
PR00662 | P001 | A015 | 2026-05-17 | 90 | 83.0354 | 100 | 92.2615 | 0.13951 | Delayed | 5
PR00663 | P001 | A015 | 2026-05-24 | 90 | 78.1909 | 100 | 86.8788 | 0 | Delayed | 5
PR00664 | P001 | A015 | 2026-05-31 | 90 | 82.4645 | 100 | 91.6273 | 4.2737 | Delayed | 5
PR00665 | P001 | A015 | 2026-06-07 | 90 | 82.6173 | 100 | 91.797 | 0.15272 | Delayed | 5
PR00666 | P001 | A015 | 2026-06-14 | 90 | 84.8665 | 100 | 94.2961 | 2.2493 | Delayed | 5
PR00667 | P001 | A015 | 2026-06-21 | 90 | 89.0058 | 100 | 98.8954 | 4.1393 | In Progress | 5
PR00668 | P001 | A015 | 2026-06-28 | 90 | 84.7281 | 100 | 94.1423 | 0 | Delayed | 5
PR00669 | P001 | A015 | 2026-07-05 | 90 | 82.2529 | 100 | 91.3922 | 0 | Delayed | 5
PR00670 | P001 | A015 | 2026-07-12 | 90 | 85.3206 | 100 | 94.8007 | 3.0677 | Delayed | 5
PR00671 | P001 | A015 | 2026-07-19 | 90 | 88.8049 | 100 | 98.6721 | 3.4843 | In Progress | 5
PR00672 | P001 | A015 | 2026-07-26 | 90 | 82.4257 | 100 | 91.5841 | 0 | Delayed | 5
PR00673 | P001 | A015 | 2026-08-02 | 90 | 82.6317 | 100 | 91.813 | 0.20596 | Delayed | 5
PR00674 | P001 | A015 | 2026-08-09 | 90 | 87.2594 | 100 | 96.9549 | 4.6277 | In Progress | 5
PR00675 | P001 | A015 | 2026-08-16 | 90 | 84.8022 | 100 | 94.2246 | 0 | Delayed | 5
PR00676 | P001 | A015 | 2026-08-23 | 90 | 87.5396 | 100 | 97.2662 | 2.7374 | In Progress | 5
PR00677 | P001 | A015 | 2026-08-30 | 90 | 85.457 | 100 | 94.9522 | 0 | Delayed | 5
PR00678 | P001 | A015 | 2026-09-06 | 90 | 87.7102 | 100 | 97.4558 | 2.2532 | In Progress | 5
PR00679 | P001 | A015 | 2026-09-13 | 90 | 82.2395 | 100 | 91.3772 | 0 | Delayed | 5
PR00680 | P001 | A015 | 2026-09-20 | 90 | 85.4619 | 100 | 94.9577 | 3.2224 | Delayed | 5
PR00681 | P001 | A015 | 2026-09-27 | 90 | 84.8363 | 100 | 94.2626 | 0 | Delayed | 5
PR00682 | P001 | A015 | 2026-10-04 | 90 | 81.6699 | 100 | 90.7444 | 0 | Delayed | 5
PR00683 | P001 | A015 | 2026-10-11 | 90 | 80.575 | 100 | 89.5278 | 0 | Delayed | 5
PR00684 | P001 | A015 | 2026-10-18 | 90 | 87.6601 | 100 | 97.4001 | 7.0851 | In Progress | 5
PR00685 | P001 | A015 | 2026-10-25 | 90 | 84.3945 | 100 | 93.7717 | 0 | Delayed | 5
PR00686 | P001 | A015 | 2026-11-01 | 90 | 82.2798 | 100 | 91.422 | 0 | Delayed | 5
PR00687 | P001 | A015 | 2026-11-08 | 90 | 85.197 | 100 | 94.6634 | 2.9172 | Delayed | 5
PR00688 | P001 | A015 | 2026-11-15 | 90 | 89.0533 | 100 | 98.9481 | 3.8562 | In Progress | 5
PR00689 | P001 | A015 | 2026-11-22 | 90 | 78.3157 | 100 | 87.0174 | 0 | Delayed | 5
PR00690 | P001 | A015 | 2026-11-29 | 90 | 80.7856 | 100 | 89.7618 | 2.4699 | Delayed | 5
PR00691 | P001 | A015 | 2026-12-06 | 90 | 82.5929 | 100 | 91.7699 | 1.8073 | Delayed | 5
PR00692 | P001 | A015 | 2026-12-13 | 90 | 90 | 100 | 100 | 7.4071 | Completed | 5
PR00693 | P001 | A015 | 2026-12-20 | 90 | 86.3901 | 100 | 95.9891 | 0 | In Progress | 5
PR00694 | P001 | A015 | 2026-12-27 | 90 | 87.917 | 100 | 97.6856 | 1.5269 | In Progress | 5
PR00695 | P001 | A016 | 2026-04-26 | 30 | 26.4028 | 33.3333 | 29.3365 | 26.4028 | In Progress | 8
PR00696 | P001 | A016 | 2026-05-03 | 65 | 57.2531 | 72.2222 | 63.6145 | 30.8502 | Delayed | 8
PR00697 | P001 | A016 | 2026-05-10 | 90 | 84.2106 | 100 | 93.5673 | 26.9576 | Delayed | 8
PR00698 | P001 | A016 | 2026-05-17 | 90 | 82.9836 | 100 | 92.204 | 0 | Delayed | 8
PR00699 | P001 | A016 | 2026-05-24 | 90 | 84.5285 | 100 | 93.9206 | 1.545 | Delayed | 8
PR00700 | P001 | A016 | 2026-05-31 | 90 | 82.2088 | 100 | 91.3432 | 0 | Delayed | 8
PR00701 | P001 | A016 | 2026-06-07 | 90 | 83.6762 | 100 | 92.9735 | 1.4673 | Delayed | 8
PR00702 | P001 | A016 | 2026-06-14 | 90 | 83.2981 | 100 | 92.5534 | 0 | Delayed | 8
PR00703 | P001 | A016 | 2026-06-21 | 90 | 85.25 | 100 | 94.7222 | 1.9519 | Delayed | 8
PR00704 | P001 | A016 | 2026-06-28 | 90 | 85.3421 | 100 | 94.8245 | 0.092109 | Delayed | 8
PR00705 | P001 | A016 | 2026-07-05 | 90 | 77.6974 | 100 | 86.3304 | 0 | Delayed | 8
PR00706 | P001 | A016 | 2026-07-12 | 90 | 75.7211 | 100 | 84.1346 | 0 | Delayed | 8
PR00707 | P001 | A016 | 2026-07-19 | 90 | 85.9555 | 100 | 95.5061 | 10.2344 | In Progress | 8
PR00708 | P001 | A016 | 2026-07-26 | 90 | 86.5413 | 100 | 96.157 | 0.58584 | In Progress | 8
PR00709 | P001 | A016 | 2026-08-02 | 90 | 79.585 | 100 | 88.4278 | 0 | Delayed | 8
PR00710 | P001 | A016 | 2026-08-09 | 90 | 76.9415 | 100 | 85.4906 | 0 | Delayed | 8
PR00711 | P001 | A016 | 2026-08-16 | 90 | 83.112 | 100 | 92.3466 | 6.1704 | Delayed | 8
PR00712 | P001 | A016 | 2026-08-23 | 90 | 85.7321 | 100 | 95.2579 | 2.6202 | In Progress | 8
PR00713 | P001 | A016 | 2026-08-30 | 90 | 88.4624 | 100 | 98.2916 | 2.7303 | In Progress | 8
PR00714 | P001 | A016 | 2026-09-06 | 90 | 84.4263 | 100 | 93.807 | 0 | Delayed | 8
PR00715 | P001 | A016 | 2026-09-13 | 90 | 81.6291 | 100 | 90.699 | 0 | Delayed | 8
PR00716 | P001 | A016 | 2026-09-20 | 90 | 79.9866 | 100 | 88.874 | 0 | Delayed | 8
PR00717 | P001 | A016 | 2026-09-27 | 90 | 82.8361 | 100 | 92.0401 | 2.8494 | Delayed | 8
PR00718 | P001 | A016 | 2026-10-04 | 90 | 81.8573 | 100 | 90.9526 | 0 | Delayed | 8
PR00719 | P001 | A016 | 2026-10-11 | 90 | 79.6025 | 100 | 88.4473 | 0 | Delayed | 8
PR00720 | P001 | A016 | 2026-10-18 | 90 | 89.2536 | 100 | 99.1706 | 9.651 | In Progress | 8
PR00721 | P001 | A016 | 2026-10-25 | 90 | 88.4233 | 100 | 98.2481 | 0 | In Progress | 8
PR00722 | P001 | A016 | 2026-11-01 | 90 | 86.3786 | 100 | 95.9762 | 0 | In Progress | 8
PR00723 | P001 | A016 | 2026-11-08 | 90 | 79.8993 | 100 | 88.777 | 0 | Delayed | 8
PR00724 | P001 | A016 | 2026-11-15 | 90 | 85.4933 | 100 | 94.9926 | 5.594 | Delayed | 8
PR00725 | P001 | A016 | 2026-11-22 | 90 | 84.8148 | 100 | 94.2387 | 0 | Delayed | 8
PR00726 | P001 | A016 | 2026-11-29 | 90 | 84.194 | 100 | 93.5489 | 0 | Delayed | 8
PR00727 | P001 | A016 | 2026-12-06 | 90 | 86.7364 | 100 | 96.3738 | 2.5424 | In Progress | 8
PR00728 | P001 | A016 | 2026-12-13 | 90 | 84.8014 | 100 | 94.2238 | 0 | Delayed | 8
PR00729 | P001 | A016 | 2026-12-20 | 90 | 85.131 | 100 | 94.59 | 0.32963 | Delayed | 8
PR00730 | P001 | A016 | 2026-12-27 | 90 | 84.8063 | 100 | 94.2292 | 0 | Delayed | 8
PR00731 | P001 | A017 | 2026-05-10 | 5 | 4.9096 | 5.5556 | 5.4552 | 4.9096 | In Progress | 3
PR00732 | P001 | A017 | 2026-05-17 | 40 | 36.3029 | 44.4444 | 40.3366 | 31.3933 | In Progress | 3
PR00733 | P001 | A017 | 2026-05-24 | 75 | 72.9695 | 83.3333 | 81.0772 | 36.6666 | In Progress | 3
PR00734 | P001 | A017 | 2026-05-31 | 90 | 85.548 | 100 | 95.0533 | 12.5785 | In Progress | 3
PR00735 | P001 | A017 | 2026-06-07 | 90 | 83.2685 | 100 | 92.5206 | 0 | Delayed | 3
PR00736 | P001 | A017 | 2026-06-14 | 90 | 90 | 100 | 100 | 6.7315 | Completed | 3
PR00737 | P001 | A017 | 2026-06-21 | 90 | 90 | 100 | 100 | 0 | Completed | 3
PR00738 | P001 | A017 | 2026-06-28 | 90 | 90 | 100 | 100 | 0 | Completed | 3
PR00739 | P001 | A017 | 2026-07-05 | 90 | 88.1039 | 100 | 97.8932 | 0 | In Progress | 3
PR00740 | P001 | A017 | 2026-07-12 | 90 | 90 | 100 | 100 | 1.8961 | Completed | 3
PR00741 | P001 | A017 | 2026-07-19 | 90 | 87.338 | 100 | 97.0422 | 0 | In Progress | 3
PR00742 | P001 | A017 | 2026-07-26 | 90 | 87.9388 | 100 | 97.7098 | 0.60084 | In Progress | 3
PR00743 | P001 | A017 | 2026-08-02 | 90 | 83.8556 | 100 | 93.1729 | 0 | Delayed | 3
PR00744 | P001 | A017 | 2026-08-09 | 90 | 88.5505 | 100 | 98.3895 | 4.695 | In Progress | 3
PR00745 | P001 | A017 | 2026-08-16 | 90 | 87.4902 | 100 | 97.2114 | 0 | In Progress | 3
PR00746 | P001 | A017 | 2026-08-23 | 90 | 83.1966 | 100 | 92.4407 | 0 | Delayed | 3
PR00747 | P001 | A017 | 2026-08-30 | 90 | 87.1387 | 100 | 96.8208 | 3.9421 | In Progress | 3
PR00748 | P001 | A017 | 2026-09-06 | 90 | 87.0489 | 100 | 96.7209 | 0 | In Progress | 3
PR00749 | P001 | A017 | 2026-09-13 | 90 | 90 | 100 | 100 | 2.9511 | Completed | 3
PR00750 | P001 | A017 | 2026-09-20 | 90 | 90 | 100 | 100 | 0 | Completed | 3
PR00751 | P001 | A017 | 2026-09-27 | 90 | 87.3361 | 100 | 97.0401 | 0 | In Progress | 3
PR00752 | P001 | A017 | 2026-10-04 | 90 | 88.0837 | 100 | 97.8708 | 0.74763 | In Progress | 3
PR00753 | P001 | A017 | 2026-10-11 | 90 | 87.4393 | 100 | 97.1547 | 0 | In Progress | 3
PR00754 | P001 | A017 | 2026-10-18 | 90 | 86.6608 | 100 | 96.2898 | 0 | In Progress | 3
PR00755 | P001 | A017 | 2026-10-25 | 90 | 83.8904 | 100 | 93.2115 | 0 | Delayed | 3
PR00756 | P001 | A017 | 2026-11-01 | 90 | 86.8242 | 100 | 96.4713 | 2.9338 | In Progress | 3
PR00757 | P001 | A017 | 2026-11-08 | 90 | 84.9498 | 100 | 94.3887 | 0 | Delayed | 3
PR00758 | P001 | A017 | 2026-11-15 | 90 | 83.3615 | 100 | 92.6239 | 0 | Delayed | 3
PR00759 | P001 | A017 | 2026-11-22 | 90 | 88.9103 | 100 | 98.7893 | 5.5488 | In Progress | 3
PR00760 | P001 | A017 | 2026-11-29 | 90 | 88.5325 | 100 | 98.3694 | 0 | In Progress | 3
PR00761 | P001 | A017 | 2026-12-06 | 90 | 81.6719 | 100 | 90.7465 | 0 | Delayed | 3
PR00762 | P001 | A017 | 2026-12-13 | 90 | 86.9135 | 100 | 96.5706 | 5.2417 | In Progress | 3
PR00763 | P001 | A017 | 2026-12-20 | 90 | 90 | 100 | 100 | 3.0865 | Completed | 3
PR00764 | P001 | A017 | 2026-12-27 | 90 | 90 | 100 | 100 | 0 | Completed | 3
PR00765 | P001 | A018 | 2026-05-31 | 15 | 15.5386 | 16.6667 | 17.2651 | 15.5386 | In Progress | 0
PR00766 | P001 | A018 | 2026-06-07 | 50 | 50.0681 | 55.5556 | 55.6312 | 34.5295 | In Progress | 0
PR00767 | P001 | A018 | 2026-06-14 | 85 | 82.486 | 94.4444 | 91.6511 | 32.4179 | In Progress | 0
PR00768 | P001 | A018 | 2026-06-21 | 90 | 86.5863 | 100 | 96.2071 | 4.1004 | In Progress | 0
PR00769 | P001 | A018 | 2026-06-28 | 90 | 90 | 100 | 100 | 3.4137 | Completed | 0
PR00770 | P001 | A018 | 2026-07-05 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00771 | P001 | A018 | 2026-07-12 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00772 | P001 | A018 | 2026-07-19 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00773 | P001 | A018 | 2026-07-26 | 90 | 89.5835 | 100 | 99.5372 | 0 | In Progress | 0
PR00774 | P001 | A018 | 2026-08-02 | 90 | 86.0808 | 100 | 95.6453 | 0 | In Progress | 0
PR00775 | P001 | A018 | 2026-08-09 | 90 | 88.9948 | 100 | 98.8831 | 2.9141 | In Progress | 0
PR00776 | P001 | A018 | 2026-08-16 | 90 | 90 | 100 | 100 | 1.0052 | Completed | 0
PR00777 | P001 | A018 | 2026-08-23 | 90 | 89.3634 | 100 | 99.2927 | 0 | In Progress | 0
PR00778 | P001 | A018 | 2026-08-30 | 90 | 88.1796 | 100 | 97.9774 | 0 | In Progress | 0
PR00779 | P001 | A018 | 2026-09-06 | 90 | 90 | 100 | 100 | 1.8204 | Completed | 0
PR00780 | P001 | A018 | 2026-09-13 | 90 | 88.4125 | 100 | 98.2361 | 0 | In Progress | 0
PR00781 | P001 | A018 | 2026-09-20 | 90 | 88.0216 | 100 | 97.8018 | 0 | In Progress | 0
PR00782 | P001 | A018 | 2026-09-27 | 90 | 90 | 100 | 100 | 1.9784 | Completed | 0
PR00783 | P001 | A018 | 2026-10-04 | 90 | 88.7337 | 100 | 98.593 | 0 | In Progress | 0
PR00784 | P001 | A018 | 2026-10-11 | 90 | 90 | 100 | 100 | 1.2663 | Completed | 0
PR00785 | P001 | A018 | 2026-10-18 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00786 | P001 | A018 | 2026-10-25 | 90 | 86.4108 | 100 | 96.012 | 0 | In Progress | 0
PR00787 | P001 | A018 | 2026-11-01 | 90 | 88.4841 | 100 | 98.3157 | 2.0733 | In Progress | 0
PR00788 | P001 | A018 | 2026-11-08 | 90 | 90 | 100 | 100 | 1.5159 | Completed | 0
PR00789 | P001 | A018 | 2026-11-15 | 90 | 86.3394 | 100 | 95.9327 | 0 | In Progress | 0
PR00790 | P001 | A018 | 2026-11-22 | 90 | 83.3325 | 100 | 92.5917 | 0 | Delayed | 0
PR00791 | P001 | A018 | 2026-11-29 | 90 | 84.1352 | 100 | 93.4835 | 0.80265 | Delayed | 0
PR00792 | P001 | A018 | 2026-12-06 | 90 | 90 | 100 | 100 | 5.8648 | Completed | 0
PR00793 | P001 | A018 | 2026-12-13 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00794 | P001 | A018 | 2026-12-20 | 90 | 89.6295 | 100 | 99.5884 | 0 | In Progress | 0
PR00795 | P001 | A018 | 2026-12-27 | 90 | 90 | 100 | 100 | 0.37047 | Completed | 0
PR00796 | P001 | A019 | 2026-06-21 | 25 | 20.6613 | 27.7778 | 22.957 | 20.6613 | In Progress | 8
PR00797 | P001 | A019 | 2026-06-28 | 60 | 56.0315 | 66.6667 | 62.2572 | 35.3702 | In Progress | 8
PR00798 | P001 | A019 | 2026-07-05 | 90 | 87.7185 | 100 | 97.465 | 31.6871 | In Progress | 8
PR00799 | P001 | A019 | 2026-07-12 | 90 | 79.2475 | 100 | 88.0528 | 0 | Delayed | 8
PR00800 | P001 | A019 | 2026-07-19 | 90 | 81.6036 | 100 | 90.6707 | 2.3561 | Delayed | 8
PR00801 | P001 | A019 | 2026-07-26 | 90 | 80.4284 | 100 | 89.3649 | 0 | Delayed | 8
PR00802 | P001 | A019 | 2026-08-02 | 90 | 79.9828 | 100 | 88.8698 | 0 | Delayed | 8
PR00803 | P001 | A019 | 2026-08-09 | 90 | 81.7723 | 100 | 90.8581 | 1.7895 | Delayed | 8
PR00804 | P001 | A019 | 2026-08-16 | 90 | 87.2966 | 100 | 96.9962 | 5.5243 | In Progress | 8
PR00805 | P001 | A019 | 2026-08-23 | 90 | 88.5878 | 100 | 98.4309 | 1.2912 | In Progress | 8
PR00806 | P001 | A019 | 2026-08-30 | 90 | 81.7418 | 100 | 90.8242 | 0 | Delayed | 8
PR00807 | P001 | A019 | 2026-09-06 | 90 | 88.8009 | 100 | 98.6677 | 7.0591 | In Progress | 8
PR00808 | P001 | A019 | 2026-09-13 | 90 | 82.9121 | 100 | 92.1245 | 0 | Delayed | 8
PR00809 | P001 | A019 | 2026-09-20 | 90 | 88.3241 | 100 | 98.1379 | 5.4121 | In Progress | 8
PR00810 | P001 | A019 | 2026-09-27 | 90 | 82.5061 | 100 | 91.6735 | 0 | Delayed | 8
PR00811 | P001 | A019 | 2026-10-04 | 90 | 83.2128 | 100 | 92.4587 | 0.70672 | Delayed | 8
PR00812 | P001 | A019 | 2026-10-11 | 90 | 83.9512 | 100 | 93.2792 | 0.73841 | Delayed | 8
PR00813 | P001 | A019 | 2026-10-18 | 90 | 90 | 100 | 100 | 6.0488 | Completed | 8
PR00814 | P001 | A019 | 2026-10-25 | 90 | 85.4815 | 100 | 94.9795 | 0 | Delayed | 8
PR00815 | P001 | A019 | 2026-11-01 | 90 | 80.5721 | 100 | 89.5246 | 0 | Delayed | 8
PR00816 | P001 | A019 | 2026-11-08 | 90 | 85.8523 | 100 | 95.3915 | 5.2802 | In Progress | 8
PR00817 | P001 | A019 | 2026-11-15 | 90 | 81.6602 | 100 | 90.7336 | 0 | Delayed | 8
PR00818 | P001 | A019 | 2026-11-22 | 90 | 81.2573 | 100 | 90.2859 | 0 | Delayed | 8
PR00819 | P001 | A019 | 2026-11-29 | 90 | 85.6621 | 100 | 95.1801 | 4.4048 | In Progress | 8
PR00820 | P001 | A019 | 2026-12-06 | 90 | 82.8979 | 100 | 92.1088 | 0 | Delayed | 8
PR00821 | P001 | A019 | 2026-12-13 | 90 | 83.6775 | 100 | 92.975 | 0.77959 | Delayed | 8
PR00822 | P001 | A019 | 2026-12-20 | 90 | 82.8441 | 100 | 92.0489 | 0 | Delayed | 8
PR00823 | P001 | A019 | 2026-12-27 | 90 | 83.8602 | 100 | 93.178 | 1.0162 | Delayed | 8
PR00824 | P001 | A020 | 2026-07-05 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR00825 | P001 | A020 | 2026-07-12 | 35 | 32.6272 | 38.8889 | 36.2525 | 32.6272 | In Progress | 0
PR00826 | P001 | A020 | 2026-07-19 | 70 | 71.6331 | 77.7778 | 79.5923 | 39.0059 | In Progress | 0
PR00827 | P001 | A020 | 2026-07-26 | 90 | 86.9066 | 100 | 96.5629 | 15.2735 | In Progress | 0
PR00828 | P001 | A020 | 2026-08-02 | 90 | 85.4568 | 100 | 94.952 | 0 | Delayed | 0
PR00829 | P001 | A020 | 2026-08-09 | 90 | 89.816 | 100 | 99.7956 | 4.3592 | In Progress | 0
PR00830 | P001 | A020 | 2026-08-16 | 90 | 90 | 100 | 100 | 0.184 | Completed | 0
PR00831 | P001 | A020 | 2026-08-23 | 90 | 87.8155 | 100 | 97.5727 | 0 | In Progress | 0
PR00832 | P001 | A020 | 2026-08-30 | 90 | 90 | 100 | 100 | 2.1845 | Completed | 0
PR00833 | P001 | A020 | 2026-09-06 | 90 | 85.7721 | 100 | 95.3024 | 0 | In Progress | 0
PR00834 | P001 | A020 | 2026-09-13 | 90 | 88.7181 | 100 | 98.5757 | 2.946 | In Progress | 0
PR00835 | P001 | A020 | 2026-09-20 | 90 | 88.1576 | 100 | 97.9529 | 0 | In Progress | 0
PR00836 | P001 | A020 | 2026-09-27 | 90 | 89.8533 | 100 | 99.8369 | 1.6956 | In Progress | 0
PR00837 | P001 | A020 | 2026-10-04 | 90 | 90 | 100 | 100 | 0.14675 | Completed | 0
PR00838 | P001 | A020 | 2026-10-11 | 90 | 86.8251 | 100 | 96.4724 | 0 | In Progress | 0
PR00839 | P001 | A020 | 2026-10-18 | 90 | 90 | 100 | 100 | 3.1749 | Completed | 0
PR00840 | P001 | A020 | 2026-10-25 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00841 | P001 | A020 | 2026-11-01 | 90 | 84.0404 | 100 | 93.3782 | 0 | Delayed | 0
PR00842 | P001 | A020 | 2026-11-08 | 90 | 83.8304 | 100 | 93.1449 | 0 | Delayed | 0
PR00843 | P001 | A020 | 2026-11-15 | 90 | 89.9612 | 100 | 99.9569 | 6.1308 | Completed | 0
PR00844 | P001 | A020 | 2026-11-22 | 90 | 89.304 | 100 | 99.2266 | 0 | In Progress | 0
PR00845 | P001 | A020 | 2026-11-29 | 90 | 89.6742 | 100 | 99.638 | 0.37027 | In Progress | 0
PR00846 | P001 | A020 | 2026-12-06 | 90 | 89.9119 | 100 | 99.9021 | 0.23763 | Completed | 0
PR00847 | P001 | A020 | 2026-12-13 | 90 | 90 | 100 | 100 | 0.088145 | Completed | 0
PR00848 | P001 | A020 | 2026-12-20 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00849 | P001 | A020 | 2026-12-27 | 90 | 86.5 | 100 | 96.1111 | 0 | In Progress | 0
PR00850 | P001 | A021 | 2026-07-26 | 10 | 9.2898 | 11.1111 | 10.322 | 9.2898 | In Progress | 3
PR00851 | P001 | A021 | 2026-08-02 | 45 | 41.928 | 50 | 46.5867 | 32.6382 | In Progress | 3
PR00852 | P001 | A021 | 2026-08-09 | 80 | 78.409 | 88.8889 | 87.1211 | 36.481 | In Progress | 3
PR00853 | P001 | A021 | 2026-08-16 | 90 | 90 | 100 | 100 | 11.591 | Completed | 3
PR00854 | P001 | A021 | 2026-08-23 | 90 | 85.9413 | 100 | 95.4903 | 0 | In Progress | 3
PR00855 | P001 | A021 | 2026-08-30 | 90 | 79.4196 | 100 | 88.2441 | 0 | Delayed | 3
PR00856 | P001 | A021 | 2026-09-06 | 90 | 81.9324 | 100 | 91.036 | 2.5128 | Delayed | 3
PR00857 | P001 | A021 | 2026-09-13 | 90 | 84.6759 | 100 | 94.0844 | 2.7435 | Delayed | 3
PR00858 | P001 | A021 | 2026-09-20 | 90 | 85.5432 | 100 | 95.0479 | 0.86722 | In Progress | 3
PR00859 | P001 | A021 | 2026-09-27 | 90 | 86.0136 | 100 | 95.5706 | 0.47042 | In Progress | 3
PR00860 | P001 | A021 | 2026-10-04 | 90 | 87.4215 | 100 | 97.135 | 1.408 | In Progress | 3
PR00861 | P001 | A021 | 2026-10-11 | 90 | 86.318 | 100 | 95.9089 | 0 | In Progress | 3
PR00862 | P001 | A021 | 2026-10-18 | 90 | 90 | 100 | 100 | 3.682 | Completed | 3
PR00863 | P001 | A021 | 2026-10-25 | 90 | 85.1705 | 100 | 94.6339 | 0 | Delayed | 3
PR00864 | P001 | A021 | 2026-11-01 | 90 | 84.5837 | 100 | 93.9819 | 0 | Delayed | 3
PR00865 | P001 | A021 | 2026-11-08 | 90 | 88.8085 | 100 | 98.6761 | 4.2248 | In Progress | 3
PR00866 | P001 | A021 | 2026-11-15 | 90 | 82.4627 | 100 | 91.6253 | 0 | Delayed | 3
PR00867 | P001 | A021 | 2026-11-22 | 90 | 88.5275 | 100 | 98.3639 | 6.0648 | In Progress | 3
PR00868 | P001 | A021 | 2026-11-29 | 90 | 87.623 | 100 | 97.3589 | 0 | In Progress | 3
PR00869 | P001 | A021 | 2026-12-06 | 90 | 86.8356 | 100 | 96.484 | 0 | In Progress | 3
PR00870 | P001 | A021 | 2026-12-13 | 90 | 90 | 100 | 100 | 3.1644 | Completed | 3
PR00871 | P001 | A021 | 2026-12-20 | 90 | 85.34 | 100 | 94.8223 | 0 | Delayed | 3
PR00872 | P001 | A021 | 2026-12-27 | 90 | 90 | 100 | 100 | 4.66 | Completed | 3
PR00873 | P001 | A022 | 2026-08-16 | 20 | 19.8422 | 22.2222 | 22.0469 | 19.8422 | In Progress | 0
PR00874 | P001 | A022 | 2026-08-23 | 55 | 52.5417 | 61.1111 | 58.3797 | 32.6995 | In Progress | 0
PR00875 | P001 | A022 | 2026-08-30 | 90 | 90 | 100 | 100 | 37.4583 | Completed | 0
PR00876 | P001 | A022 | 2026-09-06 | 90 | 86.6098 | 100 | 96.2331 | 0 | In Progress | 0
PR00877 | P001 | A022 | 2026-09-13 | 90 | 87.632 | 100 | 97.3689 | 1.0221 | In Progress | 0
PR00878 | P001 | A022 | 2026-09-20 | 90 | 90 | 100 | 100 | 2.368 | Completed | 0
PR00879 | P001 | A022 | 2026-09-27 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00880 | P001 | A022 | 2026-10-04 | 90 | 88.0402 | 100 | 97.8224 | 0 | In Progress | 0
PR00881 | P001 | A022 | 2026-10-11 | 90 | 90 | 100 | 100 | 1.9598 | Completed | 0
PR00882 | P001 | A022 | 2026-10-18 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00883 | P001 | A022 | 2026-10-25 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00884 | P001 | A022 | 2026-11-01 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00885 | P001 | A022 | 2026-11-08 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00886 | P001 | A022 | 2026-11-15 | 90 | 84.0755 | 100 | 93.4172 | 0 | Delayed | 0
PR00887 | P001 | A022 | 2026-11-22 | 90 | 88.9986 | 100 | 98.8873 | 4.9231 | In Progress | 0
PR00888 | P001 | A022 | 2026-11-29 | 90 | 87.2689 | 100 | 96.9655 | 0 | In Progress | 0
PR00889 | P001 | A022 | 2026-12-06 | 90 | 90 | 100 | 100 | 2.7311 | Completed | 0
PR00890 | P001 | A022 | 2026-12-13 | 90 | 88.1999 | 100 | 97.9999 | 0 | In Progress | 0
PR00891 | P001 | A022 | 2026-12-20 | 90 | 89.4766 | 100 | 99.4184 | 1.2767 | In Progress | 0
PR00892 | P001 | A022 | 2026-12-27 | 90 | 90 | 100 | 100 | 0.5234 | Completed | 0
PR00893 | P001 | A023 | 2026-09-06 | 30 | 29.8218 | 33.3333 | 33.1353 | 29.8218 | In Progress | 0
PR00894 | P001 | A023 | 2026-09-13 | 65 | 65.9414 | 72.2222 | 73.2682 | 36.1196 | In Progress | 0
PR00895 | P001 | A023 | 2026-09-20 | 90 | 89.2684 | 100 | 99.1871 | 23.327 | In Progress | 0
PR00896 | P001 | A023 | 2026-09-27 | 90 | 90 | 100 | 100 | 0.73165 | Completed | 0
PR00897 | P001 | A023 | 2026-10-04 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00898 | P001 | A023 | 2026-10-11 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00899 | P001 | A023 | 2026-10-18 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00900 | P001 | A023 | 2026-10-25 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00901 | P001 | A023 | 2026-11-01 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00902 | P001 | A023 | 2026-11-08 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00903 | P001 | A023 | 2026-11-15 | 90 | 86.3748 | 100 | 95.972 | 0 | In Progress | 0
PR00904 | P001 | A023 | 2026-11-22 | 90 | 89.7232 | 100 | 99.6924 | 3.3484 | In Progress | 0
PR00905 | P001 | A023 | 2026-11-29 | 90 | 90 | 100 | 100 | 0.27681 | Completed | 0
PR00906 | P001 | A023 | 2026-12-06 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00907 | P001 | A023 | 2026-12-13 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00908 | P001 | A023 | 2026-12-20 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00909 | P001 | A023 | 2026-12-27 | 90 | 90 | 100 | 100 | 0 | Completed | 0
PR00910 | P001 | A024 | 2026-09-20 | 5 | 4.6101 | 5.5556 | 5.1223 | 4.6101 | In Progress | 12
PR00911 | P001 | A024 | 2026-09-27 | 40 | 35.6051 | 44.4444 | 39.5612 | 30.995 | In Progress | 12
PR00912 | P001 | A024 | 2026-10-04 | 75 | 65.0663 | 83.3333 | 72.2959 | 29.4612 | Delayed | 12
PR00913 | P001 | A024 | 2026-10-11 | 90 | 80.2579 | 100 | 89.1754 | 15.1916 | Delayed | 12
PR00914 | P001 | A024 | 2026-10-18 | 90 | 69.9686 | 100 | 77.7429 | 0 | Delayed | 12
PR00915 | P001 | A024 | 2026-10-25 | 90 | 80.4061 | 100 | 89.3401 | 10.4375 | Delayed | 12
PR00916 | P001 | A024 | 2026-11-01 | 90 | 67.7075 | 100 | 75.2306 | 0 | Delayed | 12
PR00917 | P001 | A024 | 2026-11-08 | 90 | 73.7711 | 100 | 81.9679 | 6.0636 | Delayed | 12
PR00918 | P001 | A024 | 2026-11-15 | 90 | 80.6231 | 100 | 89.5812 | 6.852 | Delayed | 12
PR00919 | P001 | A024 | 2026-11-22 | 90 | 80.7042 | 100 | 89.6714 | 0.081146 | Delayed | 12
PR00920 | P001 | A024 | 2026-11-29 | 90 | 75.5383 | 100 | 83.9315 | 0 | Delayed | 12
PR00921 | P001 | A024 | 2026-12-06 | 90 | 76.9569 | 100 | 85.5076 | 1.4185 | Delayed | 12
PR00922 | P001 | A024 | 2026-12-13 | 90 | 83.5172 | 100 | 92.7969 | 6.5603 | Delayed | 12
PR00923 | P001 | A024 | 2026-12-20 | 90 | 77.6753 | 100 | 86.3059 | 0 | Delayed | 12
PR00924 | P001 | A024 | 2026-12-27 | 90 | 86.2652 | 100 | 95.8502 | 8.5899 | In Progress | 12
PR00925 | P001 | A025 | 2026-10-11 | 15 | 13.799 | 16.6667 | 15.3322 | 13.799 | In Progress | 8
PR00926 | P001 | A025 | 2026-10-18 | 50 | 46.7141 | 55.5556 | 51.9045 | 32.9151 | In Progress | 8
PR00927 | P001 | A025 | 2026-10-25 | 85 | 83.0102 | 94.4444 | 92.2336 | 36.2961 | In Progress | 8
PR00928 | P001 | A025 | 2026-11-01 | 90 | 83.2127 | 100 | 92.4586 | 0.20253 | Delayed | 8
PR00929 | P001 | A025 | 2026-11-08 | 90 | 79.6426 | 100 | 88.4918 | 0 | Delayed | 8
PR00930 | P001 | A025 | 2026-11-15 | 90 | 82.4544 | 100 | 91.616 | 2.8117 | Delayed | 8
PR00931 | P001 | A025 | 2026-11-22 | 90 | 82.6878 | 100 | 91.8754 | 0.23347 | Delayed | 8
PR00932 | P001 | A025 | 2026-11-29 | 90 | 78.5011 | 100 | 87.2234 | 0 | Delayed | 8
PR00933 | P001 | A025 | 2026-12-06 | 90 | 81.9941 | 100 | 91.1046 | 3.4931 | Delayed | 8
PR00934 | P001 | A025 | 2026-12-13 | 90 | 80.4621 | 100 | 89.4023 | 0 | Delayed | 8
PR00935 | P001 | A025 | 2026-12-20 | 90 | 85.7117 | 100 | 95.2353 | 5.2496 | In Progress | 8
PR00936 | P001 | A025 | 2026-12-27 | 90 | 82.909 | 100 | 92.1211 | 0 | Delayed | 8
PR00937 | P001 | A026 | 2026-04-12 | 0 | 0 | 0 | 0 | 0 | Not Started | 5
PR00938 | P001 | A026 | 2026-04-19 | 36.75 | 34.7759 | 35 | 33.1199 | 34.7759 | In Progress | 5
PR00939 | P001 | A026 | 2026-04-26 | 73.5 | 70.399 | 70 | 67.0466 | 35.6231 | In Progress | 5
PR00940 | P001 | A026 | 2026-05-03 | 105 | 102.0168 | 100 | 97.1588 | 31.6178 | In Progress | 5
PR00941 | P001 | A026 | 2026-05-10 | 105 | 96.0761 | 100 | 91.501 | 0 | Delayed | 5
PR00942 | P001 | A026 | 2026-05-17 | 105 | 95.9222 | 100 | 91.3544 | 0 | Delayed | 5
PR00943 | P001 | A026 | 2026-05-24 | 105 | 103.8097 | 100 | 98.8664 | 7.8875 | In Progress | 5
PR00944 | P001 | A026 | 2026-05-31 | 105 | 98.2347 | 100 | 93.5568 | 0 | Delayed | 5
PR00945 | P001 | A026 | 2026-06-07 | 105 | 94.5431 | 100 | 90.0411 | 0 | Delayed | 5
PR00946 | P001 | A026 | 2026-06-14 | 105 | 101.381 | 100 | 96.5533 | 6.8379 | In Progress | 5
PR00947 | P001 | A026 | 2026-06-21 | 105 | 101.4529 | 100 | 96.6218 | 0.071872 | In Progress | 5
PR00948 | P001 | A026 | 2026-06-28 | 105 | 94.1246 | 100 | 89.6425 | 0 | Delayed | 5
PR00949 | P001 | A026 | 2026-07-05 | 105 | 100.5933 | 100 | 95.8032 | 6.4687 | In Progress | 5
PR00950 | P001 | A026 | 2026-07-12 | 105 | 102.4533 | 100 | 97.5745 | 1.8599 | In Progress | 5
PR00951 | P001 | A026 | 2026-07-19 | 105 | 101.1259 | 100 | 96.3104 | 0 | In Progress | 5
PR00952 | P001 | A026 | 2026-07-26 | 105 | 102.0725 | 100 | 97.2119 | 0.94666 | In Progress | 5
PR00953 | P001 | A026 | 2026-08-02 | 105 | 94.5893 | 100 | 90.0851 | 0 | Delayed | 5
PR00954 | P001 | A026 | 2026-08-09 | 105 | 100.9666 | 100 | 96.1586 | 6.3773 | In Progress | 5
PR00955 | P001 | A026 | 2026-08-16 | 105 | 98.6379 | 100 | 93.9408 | 0 | Delayed | 5
PR00956 | P001 | A026 | 2026-08-23 | 105 | 97.9757 | 100 | 93.3102 | 0 | Delayed | 5
PR00957 | P001 | A026 | 2026-08-30 | 105 | 102.9493 | 100 | 98.0469 | 4.9735 | In Progress | 5
PR00958 | P001 | A026 | 2026-09-06 | 105 | 105 | 100 | 100 | 2.0507 | Completed | 5
PR00959 | P001 | A026 | 2026-09-13 | 105 | 105 | 100 | 100 | 0 | Completed | 5
PR00960 | P001 | A026 | 2026-09-20 | 105 | 104.5819 | 100 | 99.6018 | 0 | In Progress | 5
PR00961 | P001 | A026 | 2026-09-27 | 105 | 99.3467 | 100 | 94.6159 | 0 | Delayed | 5
PR00962 | P001 | A026 | 2026-10-04 | 105 | 101.0462 | 100 | 96.2345 | 1.6995 | In Progress | 5
PR00963 | P001 | A026 | 2026-10-11 | 105 | 102.5681 | 100 | 97.6839 | 1.5218 | In Progress | 5
PR00964 | P001 | A026 | 2026-10-18 | 105 | 100.1953 | 100 | 95.4241 | 0 | In Progress | 5
PR00965 | P001 | A026 | 2026-10-25 | 105 | 100.2306 | 100 | 95.4577 | 0.035229 | In Progress | 5
PR00966 | P001 | A026 | 2026-11-01 | 105 | 102.7773 | 100 | 97.8831 | 2.5467 | In Progress | 5
PR00967 | P001 | A026 | 2026-11-08 | 105 | 99.5321 | 100 | 94.7925 | 0 | Delayed | 5
PR00968 | P001 | A026 | 2026-11-15 | 105 | 97.0699 | 100 | 92.4475 | 0 | Delayed | 5
PR00969 | P001 | A026 | 2026-11-22 | 105 | 98.2268 | 100 | 93.5493 | 1.1569 | Delayed | 5
PR00970 | P001 | A026 | 2026-11-29 | 105 | 102.0796 | 100 | 97.2187 | 3.8528 | In Progress | 5
PR00971 | P001 | A026 | 2026-12-06 | 105 | 99.761 | 100 | 95.0105 | 0 | In Progress | 5
PR00972 | P001 | A026 | 2026-12-13 | 105 | 101.0003 | 100 | 96.1907 | 1.2393 | In Progress | 5
PR00973 | P001 | A026 | 2026-12-20 | 105 | 102.2125 | 100 | 97.3453 | 1.2123 | In Progress | 5
PR00974 | P001 | A026 | 2026-12-27 | 105 | 98.3725 | 100 | 93.6881 | 0 | Delayed | 5
PR00975 | P001 | A027 | 2026-05-03 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR00976 | P001 | A027 | 2026-05-10 | 36.75 | 37.2373 | 35 | 35.4641 | 37.2373 | In Progress | 0
PR00977 | P001 | A027 | 2026-05-17 | 73.5 | 70.3234 | 70 | 66.9747 | 33.0862 | In Progress | 0
PR00978 | P001 | A027 | 2026-05-24 | 105 | 105 | 100 | 100 | 34.6766 | Completed | 0
PR00979 | P001 | A027 | 2026-05-31 | 105 | 103.1598 | 100 | 98.2474 | 0 | In Progress | 0
PR00980 | P001 | A027 | 2026-06-07 | 105 | 98.9175 | 100 | 94.2072 | 0 | Delayed | 0
PR00981 | P001 | A027 | 2026-06-14 | 105 | 101.1595 | 100 | 96.3423 | 2.2419 | In Progress | 0
PR00982 | P001 | A027 | 2026-06-21 | 105 | 101.2477 | 100 | 96.4263 | 0.088195 | In Progress | 0
PR00983 | P001 | A027 | 2026-06-28 | 105 | 105 | 100 | 100 | 3.7523 | Completed | 0
PR00984 | P001 | A027 | 2026-07-05 | 105 | 103.9936 | 100 | 99.0415 | 0 | In Progress | 0
PR00985 | P001 | A027 | 2026-07-12 | 105 | 103.7621 | 100 | 98.8211 | 0 | In Progress | 0
PR00986 | P001 | A027 | 2026-07-19 | 105 | 105 | 100 | 100 | 1.2379 | Completed | 0
PR00987 | P001 | A027 | 2026-07-26 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00988 | P001 | A027 | 2026-08-02 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00989 | P001 | A027 | 2026-08-09 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00990 | P001 | A027 | 2026-08-16 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00991 | P001 | A027 | 2026-08-23 | 105 | 97.2533 | 100 | 92.6222 | 0 | Delayed | 0
PR00992 | P001 | A027 | 2026-08-30 | 105 | 103.6607 | 100 | 98.7245 | 6.4074 | In Progress | 0
PR00993 | P001 | A027 | 2026-09-06 | 105 | 96.9877 | 100 | 92.3693 | 0 | Delayed | 0
PR00994 | P001 | A027 | 2026-09-13 | 105 | 105 | 100 | 100 | 8.0123 | Completed | 0
PR00995 | P001 | A027 | 2026-09-20 | 105 | 104.983 | 100 | 99.9838 | 0 | Completed | 0
PR00996 | P001 | A027 | 2026-09-27 | 105 | 105 | 100 | 100 | 0.017026 | Completed | 0
PR00997 | P001 | A027 | 2026-10-04 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00998 | P001 | A027 | 2026-10-11 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR00999 | P001 | A027 | 2026-10-18 | 105 | 103.1612 | 100 | 98.2487 | 0 | In Progress | 0
PR01000 | P001 | A027 | 2026-10-25 | 105 | 105 | 100 | 100 | 1.8388 | Completed | 0
PR01001 | P001 | A027 | 2026-11-01 | 105 | 103.0599 | 100 | 98.1523 | 0 | In Progress | 0
PR01002 | P001 | A027 | 2026-11-08 | 105 | 104.9949 | 100 | 99.9951 | 1.935 | Completed | 0
PR01003 | P001 | A027 | 2026-11-15 | 105 | 105 | 100 | 100 | 0.005118 | Completed | 0
PR01004 | P001 | A027 | 2026-11-22 | 105 | 102.9502 | 100 | 98.0478 | 0 | In Progress | 0
PR01005 | P001 | A027 | 2026-11-29 | 105 | 105 | 100 | 100 | 2.0498 | Completed | 0
PR01006 | P001 | A027 | 2026-12-06 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01007 | P001 | A027 | 2026-12-13 | 105 | 101.4911 | 100 | 96.6582 | 0 | In Progress | 0
PR01008 | P001 | A027 | 2026-12-20 | 105 | 105 | 100 | 100 | 3.5089 | Completed | 0
PR01009 | P001 | A027 | 2026-12-27 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01010 | P001 | A028 | 2026-05-24 | 0 | 0 | 0 | 0 | 0 | Not Started | 8
PR01011 | P001 | A028 | 2026-05-31 | 36.75 | 32.8295 | 35 | 31.2662 | 32.8295 | In Progress | 8
PR01012 | P001 | A028 | 2026-06-07 | 73.5 | 65.4097 | 70 | 62.2949 | 32.5802 | Delayed | 8
PR01013 | P001 | A028 | 2026-06-14 | 105 | 94.6241 | 100 | 90.1182 | 29.2144 | Delayed | 8
PR01014 | P001 | A028 | 2026-06-21 | 105 | 98.594 | 100 | 93.8991 | 3.9699 | Delayed | 8
PR01015 | P001 | A028 | 2026-06-28 | 105 | 93.0881 | 100 | 88.6553 | 0 | Delayed | 8
PR01016 | P001 | A028 | 2026-07-05 | 105 | 98.2079 | 100 | 93.5313 | 5.1198 | Delayed | 8
PR01017 | P001 | A028 | 2026-07-12 | 105 | 92.0365 | 100 | 87.6539 | 0 | Delayed | 8
PR01018 | P001 | A028 | 2026-07-19 | 105 | 95.85 | 100 | 91.2858 | 3.8135 | Delayed | 8
PR01019 | P001 | A028 | 2026-07-26 | 105 | 97.003 | 100 | 92.3838 | 1.1529 | Delayed | 8
PR01020 | P001 | A028 | 2026-08-02 | 105 | 105 | 100 | 100 | 7.997 | Completed | 8
PR01021 | P001 | A028 | 2026-08-09 | 105 | 91.5384 | 100 | 87.1794 | 0 | Delayed | 8
PR01022 | P001 | A028 | 2026-08-16 | 105 | 102.0097 | 100 | 97.1521 | 10.4713 | In Progress | 8
PR01023 | P001 | A028 | 2026-08-23 | 105 | 97.1507 | 100 | 92.5244 | 0 | Delayed | 8
PR01024 | P001 | A028 | 2026-08-30 | 105 | 98.1111 | 100 | 93.4391 | 0.96039 | Delayed | 8
PR01025 | P001 | A028 | 2026-09-06 | 105 | 97.0349 | 100 | 92.4142 | 0 | Delayed | 8
PR01026 | P001 | A028 | 2026-09-13 | 105 | 98.2344 | 100 | 93.5565 | 1.1994 | Delayed | 8
PR01027 | P001 | A028 | 2026-09-20 | 105 | 96.0352 | 100 | 91.4621 | 0 | Delayed | 8
PR01028 | P001 | A028 | 2026-09-27 | 105 | 101.9436 | 100 | 97.0892 | 5.9084 | In Progress | 8
PR01029 | P001 | A028 | 2026-10-04 | 105 | 94.9225 | 100 | 90.4024 | 0 | Delayed | 8
PR01030 | P001 | A028 | 2026-10-11 | 105 | 100.761 | 100 | 95.9628 | 5.8385 | In Progress | 8
PR01031 | P001 | A028 | 2026-10-18 | 105 | 94.232 | 100 | 89.7447 | 0 | Delayed | 8
PR01032 | P001 | A028 | 2026-10-25 | 105 | 96.3786 | 100 | 91.7891 | 2.1466 | Delayed | 8
PR01033 | P001 | A028 | 2026-11-01 | 105 | 92.6605 | 100 | 88.2481 | 0 | Delayed | 8
PR01034 | P001 | A028 | 2026-11-08 | 105 | 98.2722 | 100 | 93.5926 | 5.6117 | Delayed | 8
PR01035 | P001 | A028 | 2026-11-15 | 105 | 101.9108 | 100 | 97.0579 | 3.6386 | In Progress | 8
PR01036 | P001 | A028 | 2026-11-22 | 105 | 96.3157 | 100 | 91.7293 | 0 | Delayed | 8
PR01037 | P001 | A028 | 2026-11-29 | 105 | 95.8764 | 100 | 91.3109 | 0 | Delayed | 8
PR01038 | P001 | A028 | 2026-12-06 | 105 | 92.5038 | 100 | 88.0988 | 0 | Delayed | 8
PR01039 | P001 | A028 | 2026-12-13 | 105 | 95.7573 | 100 | 91.1975 | 3.2536 | Delayed | 8
PR01040 | P001 | A028 | 2026-12-20 | 105 | 90.7465 | 100 | 86.4252 | 0 | Delayed | 8
PR01041 | P001 | A028 | 2026-12-27 | 105 | 93.2452 | 100 | 88.8049 | 2.4987 | Delayed | 8
PR01042 | P001 | A029 | 2026-06-14 | 0 | 0 | 0 | 0 | 0 | Not Started | 3
PR01043 | P001 | A029 | 2026-06-21 | 36.75 | 37.3441 | 35 | 35.5658 | 37.3441 | In Progress | 3
PR01044 | P001 | A029 | 2026-06-28 | 73.5 | 78.5217 | 70 | 74.7826 | 41.1776 | In Progress | 3
PR01045 | P001 | A029 | 2026-07-05 | 105 | 99.6943 | 100 | 94.947 | 21.1726 | Delayed | 3
PR01046 | P001 | A029 | 2026-07-12 | 105 | 105 | 100 | 100 | 5.3057 | Completed | 3
PR01047 | P001 | A029 | 2026-07-19 | 105 | 102.7458 | 100 | 97.8531 | 0 | In Progress | 3
PR01048 | P001 | A029 | 2026-07-26 | 105 | 101.2942 | 100 | 96.4706 | 0 | In Progress | 3
PR01049 | P001 | A029 | 2026-08-02 | 105 | 103.4398 | 100 | 98.5141 | 2.1456 | In Progress | 3
PR01050 | P001 | A029 | 2026-08-09 | 105 | 102.0775 | 100 | 97.2167 | 0 | In Progress | 3
PR01051 | P001 | A029 | 2026-08-16 | 105 | 102.2557 | 100 | 97.3864 | 0.17816 | In Progress | 3
PR01052 | P001 | A029 | 2026-08-23 | 105 | 100.3494 | 100 | 95.5708 | 0 | In Progress | 3
PR01053 | P001 | A029 | 2026-08-30 | 105 | 96.7119 | 100 | 92.1066 | 0 | Delayed | 3
PR01054 | P001 | A029 | 2026-09-06 | 105 | 96.1772 | 100 | 91.5973 | 0 | Delayed | 3
PR01055 | P001 | A029 | 2026-09-13 | 105 | 104.2507 | 100 | 99.2864 | 8.0735 | In Progress | 3
PR01056 | P001 | A029 | 2026-09-20 | 105 | 100.8331 | 100 | 96.0315 | 0 | In Progress | 3
PR01057 | P001 | A029 | 2026-09-27 | 105 | 99.6594 | 100 | 94.9137 | 0 | Delayed | 3
PR01058 | P001 | A029 | 2026-10-04 | 105 | 101.8813 | 100 | 97.0298 | 2.2219 | In Progress | 3
PR01059 | P001 | A029 | 2026-10-11 | 105 | 104.7714 | 100 | 99.7823 | 2.8901 | In Progress | 3
PR01060 | P001 | A029 | 2026-10-18 | 105 | 102.5128 | 100 | 97.6313 | 0 | In Progress | 3
PR01061 | P001 | A029 | 2026-10-25 | 105 | 99.439 | 100 | 94.7038 | 0 | Delayed | 3
PR01062 | P001 | A029 | 2026-11-01 | 105 | 105 | 100 | 100 | 5.561 | Completed | 3
PR01063 | P001 | A029 | 2026-11-08 | 105 | 105 | 100 | 100 | 0 | Completed | 3
PR01064 | P001 | A029 | 2026-11-15 | 105 | 103.6675 | 100 | 98.7309 | 0 | In Progress | 3
PR01065 | P001 | A029 | 2026-11-22 | 105 | 105 | 100 | 100 | 1.3325 | Completed | 3
PR01066 | P001 | A029 | 2026-11-29 | 105 | 105 | 100 | 100 | 0 | Completed | 3
PR01067 | P001 | A029 | 2026-12-06 | 105 | 105 | 100 | 100 | 0 | Completed | 3
PR01068 | P001 | A029 | 2026-12-13 | 105 | 104.1068 | 100 | 99.1493 | 0 | In Progress | 3
PR01069 | P001 | A029 | 2026-12-20 | 105 | 104.0489 | 100 | 99.0942 | 0 | In Progress | 3
PR01070 | P001 | A029 | 2026-12-27 | 105 | 103.7598 | 100 | 98.8188 | 0 | In Progress | 3
PR01071 | P001 | A030 | 2026-07-05 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01072 | P001 | A030 | 2026-07-12 | 36.75 | 37.6513 | 35 | 35.8584 | 37.6513 | In Progress | 0
PR01073 | P001 | A030 | 2026-07-19 | 73.5 | 70.0122 | 70 | 66.6783 | 32.3609 | In Progress | 0
PR01074 | P001 | A030 | 2026-07-26 | 105 | 102.0798 | 100 | 97.2189 | 32.0677 | In Progress | 0
PR01075 | P001 | A030 | 2026-08-02 | 105 | 105 | 100 | 100 | 2.9202 | Completed | 0
PR01076 | P001 | A030 | 2026-08-09 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01077 | P001 | A030 | 2026-08-16 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01078 | P001 | A030 | 2026-08-23 | 105 | 104.0016 | 100 | 99.0491 | 0 | In Progress | 0
PR01079 | P001 | A030 | 2026-08-30 | 105 | 100.7655 | 100 | 95.9671 | 0 | In Progress | 0
PR01080 | P001 | A030 | 2026-09-06 | 105 | 104.1164 | 100 | 99.1585 | 3.3509 | In Progress | 0
PR01081 | P001 | A030 | 2026-09-13 | 105 | 105 | 100 | 100 | 0.88361 | Completed | 0
PR01082 | P001 | A030 | 2026-09-20 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01083 | P001 | A030 | 2026-09-27 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01084 | P001 | A030 | 2026-10-04 | 105 | 103.6723 | 100 | 98.7356 | 0 | In Progress | 0
PR01085 | P001 | A030 | 2026-10-11 | 105 | 105 | 100 | 100 | 1.3277 | Completed | 0
PR01086 | P001 | A030 | 2026-10-18 | 105 | 101.3668 | 100 | 96.5398 | 0 | In Progress | 0
PR01087 | P001 | A030 | 2026-10-25 | 105 | 105 | 100 | 100 | 3.6332 | Completed | 0
PR01088 | P001 | A030 | 2026-11-01 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01089 | P001 | A030 | 2026-11-08 | 105 | 102.2444 | 100 | 97.3757 | 0 | In Progress | 0
PR01090 | P001 | A030 | 2026-11-15 | 105 | 104.1333 | 100 | 99.1746 | 1.8889 | In Progress | 0
PR01091 | P001 | A030 | 2026-11-22 | 105 | 104.3232 | 100 | 99.3554 | 0.18983 | In Progress | 0
PR01092 | P001 | A030 | 2026-11-29 | 105 | 104.0072 | 100 | 99.0545 | 0 | In Progress | 0
PR01093 | P001 | A030 | 2026-12-06 | 105 | 105 | 100 | 100 | 0.99282 | Completed | 0
PR01094 | P001 | A030 | 2026-12-13 | 105 | 104.6382 | 100 | 99.6554 | 0 | In Progress | 0
PR01095 | P001 | A030 | 2026-12-20 | 105 | 104.1037 | 100 | 99.1464 | 0 | In Progress | 0
PR01096 | P001 | A030 | 2026-12-27 | 105 | 97.2919 | 100 | 92.6589 | 0 | Delayed | 0
PR01097 | P001 | A031 | 2026-07-26 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01098 | P001 | A031 | 2026-08-02 | 36.75 | 36.4116 | 35 | 34.6777 | 36.4116 | In Progress | 0
PR01099 | P001 | A031 | 2026-08-09 | 73.5 | 71.7356 | 70 | 68.3197 | 35.324 | In Progress | 0
PR01100 | P001 | A031 | 2026-08-16 | 105 | 105 | 100 | 100 | 33.2644 | Completed | 0
PR01101 | P001 | A031 | 2026-08-23 | 105 | 104.3939 | 100 | 99.4227 | 0 | In Progress | 0
PR01102 | P001 | A031 | 2026-08-30 | 105 | 105 | 100 | 100 | 0.60615 | Completed | 0
PR01103 | P001 | A031 | 2026-09-06 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01104 | P001 | A031 | 2026-09-13 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01105 | P001 | A031 | 2026-09-20 | 105 | 104.6737 | 100 | 99.6892 | 0 | In Progress | 0
PR01106 | P001 | A031 | 2026-09-27 | 105 | 105 | 100 | 100 | 0.32633 | Completed | 0
PR01107 | P001 | A031 | 2026-10-04 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01108 | P001 | A031 | 2026-10-11 | 105 | 96.4754 | 100 | 91.8814 | 0 | Delayed | 0
PR01109 | P001 | A031 | 2026-10-18 | 105 | 97.6443 | 100 | 92.9946 | 1.1689 | Delayed | 0
PR01110 | P001 | A031 | 2026-10-25 | 105 | 103.0038 | 100 | 98.0989 | 5.3595 | In Progress | 0
PR01111 | P001 | A031 | 2026-11-01 | 105 | 105 | 100 | 100 | 1.9962 | Completed | 0
PR01112 | P001 | A031 | 2026-11-08 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01113 | P001 | A031 | 2026-11-15 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01114 | P001 | A031 | 2026-11-22 | 105 | 103.5879 | 100 | 98.6551 | 0 | In Progress | 0
PR01115 | P001 | A031 | 2026-11-29 | 105 | 105 | 100 | 100 | 1.4121 | Completed | 0
PR01116 | P001 | A031 | 2026-12-06 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01117 | P001 | A031 | 2026-12-13 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01118 | P001 | A031 | 2026-12-20 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01119 | P001 | A031 | 2026-12-27 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01120 | P001 | A032 | 2026-08-16 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01121 | P001 | A032 | 2026-08-23 | 36.75 | 37.6476 | 35 | 35.8548 | 37.6476 | In Progress | 0
PR01122 | P001 | A032 | 2026-08-30 | 73.5 | 73.7846 | 70 | 70.271 | 36.137 | In Progress | 0
PR01123 | P001 | A032 | 2026-09-06 | 105 | 105 | 100 | 100 | 31.2154 | Completed | 0
PR01124 | P001 | A032 | 2026-09-13 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01125 | P001 | A032 | 2026-09-20 | 105 | 95.993 | 100 | 91.4219 | 0 | Delayed | 0
PR01126 | P001 | A032 | 2026-09-27 | 105 | 99.79 | 100 | 95.0381 | 3.797 | In Progress | 0
PR01127 | P001 | A032 | 2026-10-04 | 105 | 100.6375 | 100 | 95.8453 | 0.84751 | In Progress | 0
PR01128 | P001 | A032 | 2026-10-11 | 105 | 103.665 | 100 | 98.7286 | 3.0275 | In Progress | 0
PR01129 | P001 | A032 | 2026-10-18 | 105 | 104.0643 | 100 | 99.1089 | 0.3993 | In Progress | 0
PR01130 | P001 | A032 | 2026-10-25 | 105 | 99.4606 | 100 | 94.7244 | 0 | Delayed | 0
PR01131 | P001 | A032 | 2026-11-01 | 105 | 101.3795 | 100 | 96.5519 | 1.919 | In Progress | 0
PR01132 | P001 | A032 | 2026-11-08 | 105 | 101.8364 | 100 | 96.9871 | 0.45686 | In Progress | 0
PR01133 | P001 | A032 | 2026-11-15 | 105 | 105 | 100 | 100 | 3.1636 | Completed | 0
PR01134 | P001 | A032 | 2026-11-22 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01135 | P001 | A032 | 2026-11-29 | 105 | 103.4868 | 100 | 98.5589 | 0 | In Progress | 0
PR01136 | P001 | A032 | 2026-12-06 | 105 | 103.6638 | 100 | 98.7275 | 0.17701 | In Progress | 0
PR01137 | P001 | A032 | 2026-12-13 | 105 | 100.7767 | 100 | 95.9778 | 0 | In Progress | 0
PR01138 | P001 | A032 | 2026-12-20 | 105 | 97.9876 | 100 | 93.3215 | 0 | Delayed | 0
PR01139 | P001 | A032 | 2026-12-27 | 105 | 104.5705 | 100 | 99.5909 | 6.5828 | In Progress | 0
PR01140 | P001 | A033 | 2026-09-06 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01141 | P001 | A033 | 2026-09-13 | 36.75 | 36.6409 | 35 | 34.8961 | 36.6409 | In Progress | 0
PR01142 | P001 | A033 | 2026-09-20 | 73.5 | 69.3835 | 70 | 66.0795 | 32.7426 | In Progress | 0
PR01143 | P001 | A033 | 2026-09-27 | 105 | 102.1997 | 100 | 97.3331 | 32.8163 | In Progress | 0
PR01144 | P001 | A033 | 2026-10-04 | 105 | 105 | 100 | 100 | 2.8003 | Completed | 0
PR01145 | P001 | A033 | 2026-10-11 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01146 | P001 | A033 | 2026-10-18 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01147 | P001 | A033 | 2026-10-25 | 105 | 100.1472 | 100 | 95.3783 | 0 | In Progress | 0
PR01148 | P001 | A033 | 2026-11-01 | 105 | 105 | 100 | 100 | 4.8528 | Completed | 0
PR01149 | P001 | A033 | 2026-11-08 | 105 | 102.0592 | 100 | 97.1993 | 0 | In Progress | 0
PR01150 | P001 | A033 | 2026-11-15 | 105 | 105 | 100 | 100 | 2.9408 | Completed | 0
PR01151 | P001 | A033 | 2026-11-22 | 105 | 104.9609 | 100 | 99.9628 | 0 | Completed | 0
PR01152 | P001 | A033 | 2026-11-29 | 105 | 99.9418 | 100 | 95.1826 | 0 | In Progress | 0
PR01153 | P001 | A033 | 2026-12-06 | 105 | 103.838 | 100 | 98.8933 | 3.8962 | In Progress | 0
PR01154 | P001 | A033 | 2026-12-13 | 105 | 105 | 100 | 100 | 1.162 | Completed | 0
PR01155 | P001 | A033 | 2026-12-20 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01156 | P001 | A033 | 2026-12-27 | 105 | 104.4819 | 100 | 99.5065 | 0 | In Progress | 0
PR01157 | P001 | A034 | 2026-09-27 | 0 | 0 | 0 | 0 | 0 | Not Started | 3
PR01158 | P001 | A034 | 2026-10-04 | 36.75 | 36.9434 | 35 | 35.1842 | 36.9434 | In Progress | 3
PR01159 | P001 | A034 | 2026-10-11 | 73.5 | 70.6348 | 70 | 67.2712 | 33.6913 | In Progress | 3
PR01160 | P001 | A034 | 2026-10-18 | 105 | 104.6067 | 100 | 99.6254 | 33.9719 | In Progress | 3
PR01161 | P001 | A034 | 2026-10-25 | 105 | 105 | 100 | 100 | 0.3933 | Completed | 3
PR01162 | P001 | A034 | 2026-11-01 | 105 | 105 | 100 | 100 | 0 | Completed | 3
PR01163 | P001 | A034 | 2026-11-08 | 105 | 97.3371 | 100 | 92.702 | 0 | Delayed | 3
PR01164 | P001 | A034 | 2026-11-15 | 105 | 98.445 | 100 | 93.7571 | 1.1079 | Delayed | 3
PR01165 | P001 | A034 | 2026-11-22 | 105 | 105 | 100 | 100 | 6.555 | Completed | 3
PR01166 | P001 | A034 | 2026-11-29 | 105 | 97.9608 | 100 | 93.296 | 0 | Delayed | 3
PR01167 | P001 | A034 | 2026-12-06 | 105 | 96.9897 | 100 | 92.3711 | 0 | Delayed | 3
PR01168 | P001 | A034 | 2026-12-13 | 105 | 100.0632 | 100 | 95.2983 | 3.0736 | In Progress | 3
PR01169 | P001 | A034 | 2026-12-20 | 105 | 103.3943 | 100 | 98.4708 | 3.3311 | In Progress | 3
PR01170 | P001 | A034 | 2026-12-27 | 105 | 101.4737 | 100 | 96.6416 | 0 | In Progress | 3
PR01171 | P001 | A035 | 2026-10-18 | 0 | 0 | 0 | 0 | 0 | Not Started | 12
PR01172 | P001 | A035 | 2026-10-25 | 36.75 | 31.4728 | 35 | 29.9741 | 31.4728 | Delayed | 12
PR01173 | P001 | A035 | 2026-11-01 | 73.5 | 62.8475 | 70 | 59.8548 | 31.3747 | Delayed | 12
PR01174 | P001 | A035 | 2026-11-08 | 105 | 89.1678 | 100 | 84.9217 | 26.3203 | Delayed | 12
PR01175 | P001 | A035 | 2026-11-15 | 105 | 100.785 | 100 | 95.9857 | 11.6172 | In Progress | 12
PR01176 | P001 | A035 | 2026-11-22 | 105 | 93.4934 | 100 | 89.0413 | 0 | Delayed | 12
PR01177 | P001 | A035 | 2026-11-29 | 105 | 95.6588 | 100 | 91.1037 | 2.1655 | Delayed | 12
PR01178 | P001 | A035 | 2026-12-06 | 105 | 90.6026 | 100 | 86.2882 | 0 | Delayed | 12
PR01179 | P001 | A035 | 2026-12-13 | 105 | 91.7166 | 100 | 87.3492 | 1.114 | Delayed | 12
PR01180 | P001 | A035 | 2026-12-20 | 105 | 89.7777 | 100 | 85.5026 | 0 | Delayed | 12
PR01181 | P001 | A035 | 2026-12-27 | 105 | 82.655 | 100 | 78.719 | 0 | Delayed | 12
PR01182 | P001 | A036 | 2026-11-08 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01183 | P001 | A036 | 2026-11-15 | 36.75 | 34.4211 | 35 | 32.782 | 34.4211 | In Progress | 0
PR01184 | P001 | A036 | 2026-11-22 | 73.5 | 67.7124 | 70 | 64.488 | 33.2913 | Delayed | 0
PR01185 | P001 | A036 | 2026-11-29 | 105 | 100.6071 | 100 | 95.8162 | 32.8946 | In Progress | 0
PR01186 | P001 | A036 | 2026-12-06 | 105 | 105 | 100 | 100 | 4.3929 | Completed | 0
PR01187 | P001 | A036 | 2026-12-13 | 105 | 104.8367 | 100 | 99.8445 | 0 | In Progress | 0
PR01188 | P001 | A036 | 2026-12-20 | 105 | 105 | 100 | 100 | 0.1633 | Completed | 0
PR01189 | P001 | A036 | 2026-12-27 | 105 | 105 | 100 | 100 | 0 | Completed | 0
PR01190 | P001 | A037 | 2026-04-26 | 7.7273 | 7.3207 | 4.5455 | 4.3063 | 7.3207 | In Progress | 8
PR01191 | P001 | A037 | 2026-05-03 | 61.8182 | 54.9235 | 36.3636 | 32.3079 | 47.6028 | In Progress | 8
PR01192 | P001 | A037 | 2026-05-10 | 115.9091 | 108.7619 | 68.1818 | 63.9776 | 53.8384 | In Progress | 8
PR01193 | P001 | A037 | 2026-05-17 | 170 | 160.7358 | 100 | 94.5505 | 51.9739 | Delayed | 8
PR01194 | P001 | A037 | 2026-05-24 | 170 | 152.9689 | 100 | 89.9817 | 0 | Delayed | 8
PR01195 | P001 | A037 | 2026-05-31 | 170 | 159.7293 | 100 | 93.9584 | 6.7603 | Delayed | 8
PR01196 | P001 | A037 | 2026-06-07 | 170 | 159.7688 | 100 | 93.9817 | 0.039552 | Delayed | 8
PR01197 | P001 | A037 | 2026-06-14 | 170 | 153.1302 | 100 | 90.0766 | 0 | Delayed | 8
PR01198 | P001 | A037 | 2026-06-21 | 170 | 149.7195 | 100 | 88.0703 | 0 | Delayed | 8
PR01199 | P001 | A037 | 2026-06-28 | 170 | 149.3544 | 100 | 87.8556 | 0 | Delayed | 8
PR01200 | P001 | A037 | 2026-07-05 | 170 | 156.9147 | 100 | 92.3028 | 7.5603 | Delayed | 8
PR01201 | P001 | A037 | 2026-07-12 | 170 | 158.3457 | 100 | 93.1445 | 1.431 | Delayed | 8
PR01202 | P001 | A037 | 2026-07-19 | 170 | 151.6845 | 100 | 89.2262 | 0 | Delayed | 8
PR01203 | P001 | A037 | 2026-07-26 | 170 | 156.5582 | 100 | 92.093 | 4.8737 | Delayed | 8
PR01204 | P001 | A037 | 2026-08-02 | 170 | 159.7947 | 100 | 93.9969 | 3.2365 | Delayed | 8
PR01205 | P001 | A037 | 2026-08-09 | 170 | 160.0782 | 100 | 94.1637 | 0.28354 | Delayed | 8
PR01206 | P001 | A037 | 2026-08-16 | 170 | 165.6337 | 100 | 97.4316 | 5.5555 | In Progress | 8
PR01207 | P001 | A037 | 2026-08-23 | 170 | 163.998 | 100 | 96.4694 | 0 | In Progress | 8
PR01208 | P001 | A037 | 2026-08-30 | 170 | 150.4423 | 100 | 88.4955 | 0 | Delayed | 8
PR01209 | P001 | A037 | 2026-09-06 | 170 | 166.4173 | 100 | 97.8926 | 15.975 | In Progress | 8
PR01210 | P001 | A037 | 2026-09-13 | 170 | 153.2407 | 100 | 90.1416 | 0 | Delayed | 8
PR01211 | P001 | A037 | 2026-09-20 | 170 | 162.617 | 100 | 95.6571 | 9.3763 | In Progress | 8
PR01212 | P001 | A037 | 2026-09-27 | 170 | 156.8045 | 100 | 92.238 | 0 | Delayed | 8
PR01213 | P001 | A037 | 2026-10-04 | 170 | 153.9477 | 100 | 90.5575 | 0 | Delayed | 8
PR01214 | P001 | A037 | 2026-10-11 | 170 | 145.6442 | 100 | 85.6731 | 0 | Delayed | 8
PR01215 | P001 | A037 | 2026-10-18 | 170 | 155.3792 | 100 | 91.3995 | 9.735 | Delayed | 8
PR01216 | P001 | A037 | 2026-10-25 | 170 | 147.1217 | 100 | 86.5422 | 0 | Delayed | 8
PR01217 | P001 | A037 | 2026-11-01 | 170 | 162.1554 | 100 | 95.3855 | 15.0338 | In Progress | 8
PR01218 | P001 | A037 | 2026-11-08 | 170 | 165.4249 | 100 | 97.3088 | 3.2695 | In Progress | 8
PR01219 | P001 | A037 | 2026-11-15 | 170 | 151.6584 | 100 | 89.2108 | 0 | Delayed | 8
PR01220 | P001 | A037 | 2026-11-22 | 170 | 158.1967 | 100 | 93.0569 | 6.5383 | Delayed | 8
PR01221 | P001 | A037 | 2026-11-29 | 170 | 152.0839 | 100 | 89.4611 | 0 | Delayed | 8
PR01222 | P001 | A037 | 2026-12-06 | 170 | 152.6605 | 100 | 89.8003 | 0.5766 | Delayed | 8
PR01223 | P001 | A037 | 2026-12-13 | 170 | 161.0082 | 100 | 94.7107 | 8.3477 | Delayed | 8
PR01224 | P001 | A037 | 2026-12-20 | 170 | 156.1707 | 100 | 91.8651 | 0 | Delayed | 8
PR01225 | P001 | A037 | 2026-12-27 | 170 | 166.7509 | 100 | 98.0888 | 10.5802 | In Progress | 8
PR01226 | P001 | A038 | 2026-05-24 | 46.3636 | 41.872 | 27.2727 | 24.6306 | 41.872 | In Progress | 8
PR01227 | P001 | A038 | 2026-05-31 | 100.4545 | 95.9318 | 59.0909 | 56.4304 | 54.0597 | In Progress | 8
PR01228 | P001 | A038 | 2026-06-07 | 154.5455 | 142.7087 | 90.9091 | 83.9463 | 46.777 | Delayed | 8
PR01229 | P001 | A038 | 2026-06-14 | 170 | 161.1349 | 100 | 94.7852 | 18.4261 | Delayed | 8
PR01230 | P001 | A038 | 2026-06-21 | 170 | 153.7394 | 100 | 90.4349 | 0 | Delayed | 8
PR01231 | P001 | A038 | 2026-06-28 | 170 | 156.1051 | 100 | 91.8265 | 2.3657 | Delayed | 8
PR01232 | P001 | A038 | 2026-07-05 | 170 | 155.7128 | 100 | 91.5958 | 0 | Delayed | 8
PR01233 | P001 | A038 | 2026-07-12 | 170 | 151.4255 | 100 | 89.0738 | 0 | Delayed | 8
PR01234 | P001 | A038 | 2026-07-19 | 170 | 160.3394 | 100 | 94.3173 | 8.9139 | Delayed | 8
PR01235 | P001 | A038 | 2026-07-26 | 170 | 160.269 | 100 | 94.2759 | 0 | Delayed | 8
PR01236 | P001 | A038 | 2026-08-02 | 170 | 159.9317 | 100 | 94.0774 | 0 | Delayed | 8
PR01237 | P001 | A038 | 2026-08-09 | 170 | 165.5449 | 100 | 97.3794 | 5.6133 | In Progress | 8
PR01238 | P001 | A038 | 2026-08-16 | 170 | 165.0236 | 100 | 97.0727 | 0 | In Progress | 8
PR01239 | P001 | A038 | 2026-08-23 | 170 | 154.1691 | 100 | 90.6877 | 0 | Delayed | 8
PR01240 | P001 | A038 | 2026-08-30 | 170 | 158.6197 | 100 | 93.3057 | 4.4506 | Delayed | 8
PR01241 | P001 | A038 | 2026-09-06 | 170 | 152.6896 | 100 | 89.8174 | 0 | Delayed | 8
PR01242 | P001 | A038 | 2026-09-13 | 170 | 156.539 | 100 | 92.0817 | 3.8494 | Delayed | 8
PR01243 | P001 | A038 | 2026-09-20 | 170 | 152.8315 | 100 | 89.9009 | 0 | Delayed | 8
PR01244 | P001 | A038 | 2026-09-27 | 170 | 166.0394 | 100 | 97.6702 | 13.2079 | In Progress | 8
PR01245 | P001 | A038 | 2026-10-04 | 170 | 158.564 | 100 | 93.2729 | 0 | Delayed | 8
PR01246 | P001 | A038 | 2026-10-11 | 170 | 155.1027 | 100 | 91.2369 | 0 | Delayed | 8
PR01247 | P001 | A038 | 2026-10-18 | 170 | 163.502 | 100 | 96.1777 | 8.3993 | In Progress | 8
PR01248 | P001 | A038 | 2026-10-25 | 170 | 143.4848 | 100 | 84.4028 | 0 | Delayed | 8
PR01249 | P001 | A038 | 2026-11-01 | 170 | 144.4161 | 100 | 84.9506 | 0.93125 | Delayed | 8
PR01250 | P001 | A038 | 2026-11-08 | 170 | 161.1352 | 100 | 94.7854 | 16.7192 | Delayed | 8
PR01251 | P001 | A038 | 2026-11-15 | 170 | 156.7598 | 100 | 92.2116 | 0 | Delayed | 8
PR01252 | P001 | A038 | 2026-11-22 | 170 | 157.8902 | 100 | 92.8766 | 1.1304 | Delayed | 8
PR01253 | P001 | A038 | 2026-11-29 | 170 | 148.5079 | 100 | 87.3576 | 0 | Delayed | 8
PR01254 | P001 | A038 | 2026-12-06 | 170 | 156.2618 | 100 | 91.9187 | 7.7538 | Delayed | 8
PR01255 | P001 | A038 | 2026-12-13 | 170 | 168.3209 | 100 | 99.0123 | 12.0591 | In Progress | 8
PR01256 | P001 | A038 | 2026-12-20 | 170 | 161.304 | 100 | 94.8847 | 0 | Delayed | 8
PR01257 | P001 | A038 | 2026-12-27 | 170 | 157.4098 | 100 | 92.594 | 0 | Delayed | 8
PR01258 | P001 | A039 | 2026-06-14 | 30.9091 | 30.4341 | 18.1818 | 17.9024 | 30.4341 | In Progress | 0
PR01259 | P001 | A039 | 2026-06-21 | 85 | 83.8261 | 50 | 49.3095 | 53.392 | In Progress | 0
PR01260 | P001 | A039 | 2026-06-28 | 139.0909 | 128.7256 | 81.8182 | 75.7209 | 44.8994 | Delayed | 0
PR01261 | P001 | A039 | 2026-07-05 | 170 | 170 | 100 | 100 | 41.2744 | Completed | 0
PR01262 | P001 | A039 | 2026-07-12 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01263 | P001 | A039 | 2026-07-19 | 170 | 160.6251 | 100 | 94.4853 | 0 | Delayed | 0
PR01264 | P001 | A039 | 2026-07-26 | 170 | 166.0646 | 100 | 97.685 | 5.4395 | In Progress | 0
PR01265 | P001 | A039 | 2026-08-02 | 170 | 163.1131 | 100 | 95.9489 | 0 | In Progress | 0
PR01266 | P001 | A039 | 2026-08-09 | 170 | 164.2562 | 100 | 96.6213 | 1.1431 | In Progress | 0
PR01267 | P001 | A039 | 2026-08-16 | 170 | 170 | 100 | 100 | 5.7438 | Completed | 0
PR01268 | P001 | A039 | 2026-08-23 | 170 | 157.5978 | 100 | 92.7046 | 0 | Delayed | 0
PR01269 | P001 | A039 | 2026-08-30 | 170 | 170 | 100 | 100 | 12.4022 | Completed | 0
PR01270 | P001 | A039 | 2026-09-06 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01271 | P001 | A039 | 2026-09-13 | 170 | 168.5059 | 100 | 99.1211 | 0 | In Progress | 0
PR01272 | P001 | A039 | 2026-09-20 | 170 | 155.2398 | 100 | 91.3175 | 0 | Delayed | 0
PR01273 | P001 | A039 | 2026-09-27 | 170 | 164.0713 | 100 | 96.5125 | 8.8315 | In Progress | 0
PR01274 | P001 | A039 | 2026-10-04 | 170 | 170 | 100 | 100 | 5.9287 | Completed | 0
PR01275 | P001 | A039 | 2026-10-11 | 170 | 153.4709 | 100 | 90.277 | 0 | Delayed | 0
PR01276 | P001 | A039 | 2026-10-18 | 170 | 167.9322 | 100 | 98.7837 | 14.4613 | In Progress | 0
PR01277 | P001 | A039 | 2026-10-25 | 170 | 162.979 | 100 | 95.87 | 0 | In Progress | 0
PR01278 | P001 | A039 | 2026-11-01 | 170 | 170 | 100 | 100 | 7.021 | Completed | 0
PR01279 | P001 | A039 | 2026-11-08 | 170 | 165.9831 | 100 | 97.6371 | 0 | In Progress | 0
PR01280 | P001 | A039 | 2026-11-15 | 170 | 170 | 100 | 100 | 4.0169 | Completed | 0
PR01281 | P001 | A039 | 2026-11-22 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01282 | P001 | A039 | 2026-11-29 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01283 | P001 | A039 | 2026-12-06 | 170 | 168.7925 | 100 | 99.2897 | 0 | In Progress | 0
PR01284 | P001 | A039 | 2026-12-13 | 170 | 170 | 100 | 100 | 1.2075 | Completed | 0
PR01285 | P001 | A039 | 2026-12-20 | 170 | 161.1639 | 100 | 94.8023 | 0 | Delayed | 0
PR01286 | P001 | A039 | 2026-12-27 | 170 | 170 | 100 | 100 | 8.8361 | Completed | 0
PR01287 | P001 | A040 | 2026-07-05 | 15.4545 | 14.2705 | 9.0909 | 8.3944 | 14.2705 | In Progress | 5
PR01288 | P001 | A040 | 2026-07-12 | 69.5455 | 64.7033 | 40.9091 | 38.0607 | 50.4328 | In Progress | 5
PR01289 | P001 | A040 | 2026-07-19 | 123.6364 | 117.3583 | 72.7273 | 69.0343 | 52.655 | In Progress | 5
PR01290 | P001 | A040 | 2026-07-26 | 170 | 152.2008 | 100 | 89.5299 | 34.8426 | Delayed | 5
PR01291 | P001 | A040 | 2026-08-02 | 170 | 162.8612 | 100 | 95.8007 | 10.6603 | In Progress | 5
PR01292 | P001 | A040 | 2026-08-09 | 170 | 167.2564 | 100 | 98.3861 | 4.3952 | In Progress | 5
PR01293 | P001 | A040 | 2026-08-16 | 170 | 163.243 | 100 | 96.0253 | 0 | In Progress | 5
PR01294 | P001 | A040 | 2026-08-23 | 170 | 152.0461 | 100 | 89.4389 | 0 | Delayed | 5
PR01295 | P001 | A040 | 2026-08-30 | 170 | 160.7633 | 100 | 94.5667 | 8.7173 | Delayed | 5
PR01296 | P001 | A040 | 2026-09-06 | 170 | 165.9151 | 100 | 97.5971 | 5.1517 | In Progress | 5
PR01297 | P001 | A040 | 2026-09-13 | 170 | 150.326 | 100 | 88.427 | 0 | Delayed | 5
PR01298 | P001 | A040 | 2026-09-20 | 170 | 155.1051 | 100 | 91.2383 | 4.7792 | Delayed | 5
PR01299 | P001 | A040 | 2026-09-27 | 170 | 166.7154 | 100 | 98.0679 | 11.6103 | In Progress | 5
PR01300 | P001 | A040 | 2026-10-04 | 170 | 163.1071 | 100 | 95.9453 | 0 | In Progress | 5
PR01301 | P001 | A040 | 2026-10-11 | 170 | 163.9512 | 100 | 96.4419 | 0.84416 | In Progress | 5
PR01302 | P001 | A040 | 2026-10-18 | 170 | 170 | 100 | 100 | 6.0488 | Completed | 5
PR01303 | P001 | A040 | 2026-10-25 | 170 | 164.2879 | 100 | 96.6399 | 0 | In Progress | 5
PR01304 | P001 | A040 | 2026-11-01 | 170 | 165.4144 | 100 | 97.3026 | 1.1265 | In Progress | 5
PR01305 | P001 | A040 | 2026-11-08 | 170 | 170 | 100 | 100 | 4.5856 | Completed | 5
PR01306 | P001 | A040 | 2026-11-15 | 170 | 160.2279 | 100 | 94.2517 | 0 | Delayed | 5
PR01307 | P001 | A040 | 2026-11-22 | 170 | 156.7526 | 100 | 92.2074 | 0 | Delayed | 5
PR01308 | P001 | A040 | 2026-11-29 | 170 | 164.0454 | 100 | 96.4973 | 7.2928 | In Progress | 5
PR01309 | P001 | A040 | 2026-12-06 | 170 | 164.112 | 100 | 96.5365 | 0.066608 | In Progress | 5
PR01310 | P001 | A040 | 2026-12-13 | 170 | 158.366 | 100 | 93.1565 | 0 | Delayed | 5
PR01311 | P001 | A040 | 2026-12-20 | 170 | 155.3572 | 100 | 91.3866 | 0 | Delayed | 5
PR01312 | P001 | A040 | 2026-12-27 | 170 | 170 | 100 | 100 | 14.6428 | Completed | 5
PR01313 | P001 | A041 | 2026-07-26 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01314 | P001 | A041 | 2026-08-02 | 54.0909 | 44.2046 | 31.8182 | 26.0027 | 44.2046 | Delayed | 0
PR01315 | P001 | A041 | 2026-08-09 | 108.1818 | 103.1499 | 63.6364 | 60.6764 | 58.9453 | In Progress | 0
PR01316 | P001 | A041 | 2026-08-16 | 162.2727 | 153.1528 | 95.4545 | 90.0899 | 50.003 | Delayed | 0
PR01317 | P001 | A041 | 2026-08-23 | 170 | 159.9954 | 100 | 94.1149 | 6.8425 | Delayed | 0
PR01318 | P001 | A041 | 2026-08-30 | 170 | 161.5 | 100 | 95 | 1.5046 | In Progress | 0
PR01319 | P001 | A041 | 2026-09-06 | 170 | 153.8133 | 100 | 90.4784 | 0 | Delayed | 0
PR01320 | P001 | A041 | 2026-09-13 | 170 | 161.5 | 100 | 95 | 7.6867 | In Progress | 0
PR01321 | P001 | A041 | 2026-09-20 | 170 | 161.5 | 100 | 95 | 0 | In Progress | 0
PR01322 | P001 | A041 | 2026-09-27 | 170 | 161.5 | 100 | 95 | 0 | In Progress | 0
PR01323 | P001 | A041 | 2026-10-04 | 170 | 167.7615 | 100 | 98.6833 | 6.2615 | In Progress | 0
PR01324 | P001 | A041 | 2026-10-11 | 170 | 166.9827 | 100 | 98.2251 | 0 | In Progress | 0
PR01325 | P001 | A041 | 2026-10-18 | 170 | 167.5585 | 100 | 98.5638 | 0.57575 | In Progress | 0
PR01326 | P001 | A041 | 2026-10-25 | 170 | 168.4889 | 100 | 99.1111 | 0.93044 | In Progress | 0
PR01327 | P001 | A041 | 2026-11-01 | 170 | 167.7521 | 100 | 98.6777 | 0 | In Progress | 0
PR01328 | P001 | A041 | 2026-11-08 | 170 | 170 | 100 | 100 | 2.2479 | Completed | 0
PR01329 | P001 | A041 | 2026-11-15 | 170 | 159.6874 | 100 | 93.9338 | 0 | Delayed | 0
PR01330 | P001 | A041 | 2026-11-22 | 170 | 170 | 100 | 100 | 10.3126 | Completed | 0
PR01331 | P001 | A041 | 2026-11-29 | 170 | 167.7409 | 100 | 98.6711 | 0 | In Progress | 0
PR01332 | P001 | A041 | 2026-12-06 | 170 | 170 | 100 | 100 | 2.2591 | Completed | 0
PR01333 | P001 | A041 | 2026-12-13 | 170 | 163.2944 | 100 | 96.0555 | 0 | In Progress | 0
PR01334 | P001 | A041 | 2026-12-20 | 170 | 170 | 100 | 100 | 6.7056 | Completed | 0
PR01335 | P001 | A041 | 2026-12-27 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01336 | P001 | A042 | 2026-08-23 | 38.6364 | 36.8431 | 22.7273 | 21.6724 | 36.8431 | In Progress | 8
PR01337 | P001 | A042 | 2026-08-30 | 92.7273 | 80.393 | 54.5455 | 47.29 | 43.5499 | Delayed | 8
PR01338 | P001 | A042 | 2026-09-06 | 146.8182 | 139.3333 | 86.3636 | 81.9608 | 58.9403 | In Progress | 8
PR01339 | P001 | A042 | 2026-09-13 | 170 | 158.8089 | 100 | 93.417 | 19.4756 | Delayed | 8
PR01340 | P001 | A042 | 2026-09-20 | 170 | 146.8486 | 100 | 86.3816 | 0 | Delayed | 8
PR01341 | P001 | A042 | 2026-09-27 | 170 | 156.2554 | 100 | 91.915 | 9.4068 | Delayed | 8
PR01342 | P001 | A042 | 2026-10-04 | 170 | 158.569 | 100 | 93.2759 | 2.3135 | Delayed | 8
PR01343 | P001 | A042 | 2026-10-11 | 170 | 159.7086 | 100 | 93.9463 | 1.1397 | Delayed | 8
PR01344 | P001 | A042 | 2026-10-18 | 170 | 157.4547 | 100 | 92.6204 | 0 | Delayed | 8
PR01345 | P001 | A042 | 2026-10-25 | 170 | 158.1328 | 100 | 93.0193 | 0.67812 | Delayed | 8
PR01346 | P001 | A042 | 2026-11-01 | 170 | 165.168 | 100 | 97.1576 | 7.0352 | In Progress | 8
PR01347 | P001 | A042 | 2026-11-08 | 170 | 163.6949 | 100 | 96.2911 | 0 | In Progress | 8
PR01348 | P001 | A042 | 2026-11-15 | 170 | 139.341 | 100 | 81.9653 | 0 | Delayed | 8
PR01349 | P001 | A042 | 2026-11-22 | 170 | 154.5112 | 100 | 90.889 | 15.1702 | Delayed | 8
PR01350 | P001 | A042 | 2026-11-29 | 170 | 155.4203 | 100 | 91.4237 | 0.90909 | Delayed | 8
PR01351 | P001 | A042 | 2026-12-06 | 170 | 145.975 | 100 | 85.8677 | 0 | Delayed | 8
PR01352 | P001 | A042 | 2026-12-13 | 170 | 156.9604 | 100 | 92.3296 | 10.9854 | Delayed | 8
PR01353 | P001 | A042 | 2026-12-20 | 170 | 163.8301 | 100 | 96.3707 | 6.8697 | In Progress | 8
PR01354 | P001 | A042 | 2026-12-27 | 170 | 149.9349 | 100 | 88.197 | 0 | Delayed | 8
PR01355 | P001 | A043 | 2026-09-13 | 23.1818 | 22.2957 | 13.6364 | 13.1151 | 22.2957 | In Progress | 5
PR01356 | P001 | A043 | 2026-09-20 | 77.2727 | 70.9322 | 45.4545 | 41.7248 | 48.6365 | In Progress | 5
PR01357 | P001 | A043 | 2026-09-27 | 131.3636 | 121.7062 | 77.2727 | 71.5919 | 50.774 | Delayed | 5
PR01358 | P001 | A043 | 2026-10-04 | 170 | 170 | 100 | 100 | 48.2938 | Completed | 5
PR01359 | P001 | A043 | 2026-10-11 | 170 | 158.2718 | 100 | 93.101 | 0 | Delayed | 5
PR01360 | P001 | A043 | 2026-10-18 | 170 | 164.2502 | 100 | 96.6177 | 5.9784 | In Progress | 5
PR01361 | P001 | A043 | 2026-10-25 | 170 | 150.3663 | 100 | 88.4507 | 0 | Delayed | 5
PR01362 | P001 | A043 | 2026-11-01 | 170 | 170 | 100 | 100 | 19.6337 | Completed | 5
PR01363 | P001 | A043 | 2026-11-08 | 170 | 165.0858 | 100 | 97.1093 | 0 | In Progress | 5
PR01364 | P001 | A043 | 2026-11-15 | 170 | 160.4141 | 100 | 94.3613 | 0 | Delayed | 5
PR01365 | P001 | A043 | 2026-11-22 | 170 | 164.9245 | 100 | 97.0144 | 4.5104 | In Progress | 5
PR01366 | P001 | A043 | 2026-11-29 | 170 | 153.1116 | 100 | 90.0656 | 0 | Delayed | 5
PR01367 | P001 | A043 | 2026-12-06 | 170 | 168.5361 | 100 | 99.1389 | 15.4245 | In Progress | 5
PR01368 | P001 | A043 | 2026-12-13 | 170 | 159.5723 | 100 | 93.8661 | 0 | Delayed | 5
PR01369 | P001 | A043 | 2026-12-20 | 170 | 160.2858 | 100 | 94.2858 | 0.7135 | Delayed | 5
PR01370 | P001 | A043 | 2026-12-27 | 170 | 158.5746 | 100 | 93.2792 | 0 | Delayed | 5
PR01371 | P001 | A044 | 2026-10-04 | 7.7273 | 7.5702 | 4.5455 | 4.4531 | 7.5702 | In Progress | 0
PR01372 | P001 | A044 | 2026-10-11 | 61.8182 | 63.3212 | 36.3636 | 37.2478 | 55.751 | In Progress | 0
PR01373 | P001 | A044 | 2026-10-18 | 115.9091 | 116.9473 | 68.1818 | 68.7925 | 53.6261 | In Progress | 0
PR01374 | P001 | A044 | 2026-10-25 | 170 | 170 | 100 | 100 | 53.0527 | Completed | 0
PR01375 | P001 | A044 | 2026-11-01 | 170 | 169.9477 | 100 | 99.9692 | 0 | Completed | 0
PR01376 | P001 | A044 | 2026-11-08 | 170 | 170 | 100 | 100 | 0.052328 | Completed | 0
PR01377 | P001 | A044 | 2026-11-15 | 170 | 167.5078 | 100 | 98.534 | 0 | In Progress | 0
PR01378 | P001 | A044 | 2026-11-22 | 170 | 170 | 100 | 100 | 2.4922 | Completed | 0
PR01379 | P001 | A044 | 2026-11-29 | 170 | 160.6708 | 100 | 94.5122 | 0 | Delayed | 0
PR01380 | P001 | A044 | 2026-12-06 | 170 | 170 | 100 | 100 | 9.3292 | Completed | 0
PR01381 | P001 | A044 | 2026-12-13 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01382 | P001 | A044 | 2026-12-20 | 170 | 164.9297 | 100 | 97.0174 | 0 | In Progress | 0
PR01383 | P001 | A044 | 2026-12-27 | 170 | 170 | 100 | 100 | 5.0703 | Completed | 0
PR01384 | P001 | A045 | 2026-11-01 | 46.3636 | 47.979 | 27.2727 | 28.223 | 47.979 | In Progress | 0
PR01385 | P001 | A045 | 2026-11-08 | 100.4545 | 103.869 | 59.0909 | 61.0994 | 55.8899 | In Progress | 0
PR01386 | P001 | A045 | 2026-11-15 | 154.5455 | 154.697 | 90.9091 | 90.9983 | 50.828 | In Progress | 0
PR01387 | P001 | A045 | 2026-11-22 | 170 | 168.7075 | 100 | 99.2397 | 14.0105 | In Progress | 0
PR01388 | P001 | A045 | 2026-11-29 | 170 | 168.754 | 100 | 99.2671 | 0.046513 | In Progress | 0
PR01389 | P001 | A045 | 2026-12-06 | 170 | 170 | 100 | 100 | 1.246 | Completed | 0
PR01390 | P001 | A045 | 2026-12-13 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01391 | P001 | A045 | 2026-12-20 | 170 | 170 | 100 | 100 | 0 | Completed | 0
PR01392 | P001 | A045 | 2026-12-27 | 170 | 164.5769 | 100 | 96.8099 | 0 | In Progress | 0
PR01393 | P001 | A046 | 2026-11-22 | 30.9091 | 28.0919 | 18.1818 | 16.5246 | 28.0919 | In Progress | 12
PR01394 | P001 | A046 | 2026-11-29 | 85 | 77.5404 | 50 | 45.612 | 49.4485 | In Progress | 12
PR01395 | P001 | A046 | 2026-12-06 | 139.0909 | 125.587 | 81.8182 | 73.8747 | 48.0466 | Delayed | 12
PR01396 | P001 | A046 | 2026-12-13 | 170 | 154.0357 | 100 | 90.6092 | 28.4487 | Delayed | 12
PR01397 | P001 | A046 | 2026-12-20 | 170 | 147.988 | 100 | 87.0518 | 0 | Delayed | 12
PR01398 | P001 | A046 | 2026-12-27 | 170 | 144.0725 | 100 | 84.7485 | 0 | Delayed | 12
PR01399 | P001 | A047 | 2026-12-13 | 16.1905 | 15.6985 | 9.5238 | 9.2344 | 15.6985 | In Progress | 0
PR01400 | P001 | A047 | 2026-12-20 | 72.8571 | 68.6867 | 42.8571 | 40.4039 | 52.9882 | In Progress | 0
PR01401 | P001 | A047 | 2026-12-27 | 129.5238 | 130.598 | 76.1905 | 76.8223 | 61.9113 | In Progress | 0
PR01402 | P001 | A048 | 2026-04-19 | 10.6667 | 3.3555 | 8.8889 | 2.7963 | 3.3555 | Delayed | 12
PR01403 | P001 | A048 | 2026-04-26 | 29.3333 | 19.3616 | 24.4444 | 16.1347 | 16.0061 | Delayed | 12
PR01404 | P001 | A048 | 2026-05-03 | 48 | 37.2746 | 40 | 31.0621 | 17.9129 | Delayed | 12
PR01405 | P001 | A048 | 2026-05-10 | 66.6667 | 55.7563 | 55.5556 | 46.4635 | 18.4817 | Delayed | 12
PR01406 | P001 | A048 | 2026-05-17 | 85.3333 | 78.4409 | 71.1111 | 65.3674 | 22.6847 | Delayed | 12
PR01407 | P001 | A048 | 2026-05-24 | 104 | 89.1008 | 86.6667 | 74.2506 | 10.6599 | Delayed | 12
PR01408 | P001 | A048 | 2026-05-31 | 120 | 107.1145 | 100 | 89.2621 | 18.0137 | Delayed | 12
PR01409 | P001 | A048 | 2026-06-07 | 120 | 99.7591 | 100 | 83.1326 | 0 | Delayed | 12
PR01410 | P001 | A048 | 2026-06-14 | 120 | 111.6426 | 100 | 93.0355 | 11.8834 | Delayed | 12
PR01411 | P001 | A048 | 2026-06-21 | 120 | 104.9951 | 100 | 87.4959 | 0 | Delayed | 12
PR01412 | P001 | A048 | 2026-06-28 | 120 | 106.8182 | 100 | 89.0151 | 1.8231 | Delayed | 12
PR01413 | P001 | A048 | 2026-07-05 | 120 | 115.3683 | 100 | 96.1402 | 8.5501 | In Progress | 12
PR01414 | P001 | A048 | 2026-07-12 | 120 | 111.969 | 100 | 93.3075 | 0 | Delayed | 12
PR01415 | P001 | A048 | 2026-07-19 | 120 | 104.3124 | 100 | 86.927 | 0 | Delayed | 12
PR01416 | P001 | A048 | 2026-07-26 | 120 | 103.1085 | 100 | 85.9237 | 0 | Delayed | 12
PR01417 | P001 | A048 | 2026-08-02 | 120 | 98.2327 | 100 | 81.8606 | 0 | Delayed | 12
PR01418 | P001 | A048 | 2026-08-09 | 120 | 101.7416 | 100 | 84.7846 | 3.5089 | Delayed | 12
PR01419 | P001 | A048 | 2026-08-16 | 120 | 99.1581 | 100 | 82.6317 | 0 | Delayed | 12
PR01420 | P001 | A048 | 2026-08-23 | 120 | 97.94 | 100 | 81.6166 | 0 | Delayed | 12
PR01421 | P001 | A048 | 2026-08-30 | 120 | 105.7622 | 100 | 88.1351 | 7.8222 | Delayed | 12
PR01422 | P001 | A048 | 2026-09-06 | 120 | 99.1203 | 100 | 82.6003 | 0 | Delayed | 12
PR01423 | P001 | A048 | 2026-09-13 | 120 | 109.2583 | 100 | 91.0486 | 10.138 | Delayed | 12
PR01424 | P001 | A048 | 2026-09-20 | 120 | 99.9811 | 100 | 83.3176 | 0 | Delayed | 12
PR01425 | P001 | A048 | 2026-09-27 | 120 | 107.0983 | 100 | 89.2486 | 7.1172 | Delayed | 12
PR01426 | P001 | A048 | 2026-10-04 | 120 | 107.1007 | 100 | 89.2506 | 0.0024043 | Delayed | 12
PR01427 | P001 | A048 | 2026-10-11 | 120 | 109.6444 | 100 | 91.3704 | 2.5437 | Delayed | 12
PR01428 | P001 | A048 | 2026-10-18 | 120 | 102.5566 | 100 | 85.4639 | 0 | Delayed | 12
PR01429 | P001 | A048 | 2026-10-25 | 120 | 102.0142 | 100 | 85.0118 | 0 | Delayed | 12
PR01430 | P001 | A048 | 2026-11-01 | 120 | 107.5308 | 100 | 89.609 | 5.5166 | Delayed | 12
PR01431 | P001 | A048 | 2026-11-08 | 120 | 109.7519 | 100 | 91.4599 | 2.2212 | Delayed | 12
PR01432 | P001 | A048 | 2026-11-15 | 120 | 105.7691 | 100 | 88.1409 | 0 | Delayed | 12
PR01433 | P001 | A048 | 2026-11-22 | 120 | 100.1971 | 100 | 83.4976 | 0 | Delayed | 12
PR01434 | P001 | A048 | 2026-11-29 | 120 | 99.8869 | 100 | 83.2391 | 0 | Delayed | 12
PR01435 | P001 | A048 | 2026-12-06 | 120 | 99.606 | 100 | 83.005 | 0 | Delayed | 12
PR01436 | P001 | A048 | 2026-12-13 | 120 | 98.176 | 100 | 81.8133 | 0 | Delayed | 12
PR01437 | P001 | A048 | 2026-12-20 | 120 | 106.0598 | 100 | 88.3832 | 7.8839 | Delayed | 12
PR01438 | P001 | A048 | 2026-12-27 | 120 | 110.3252 | 100 | 91.9377 | 4.2653 | Delayed | 12
PR01439 | P001 | A049 | 2026-06-07 | 111.4286 | 105.8048 | 8.5714 | 8.1388 | 105.8048 | In Progress | 5
PR01440 | P001 | A049 | 2026-06-14 | 241.4286 | 210.2566 | 18.5714 | 16.1736 | 104.4518 | In Progress | 5
PR01441 | P001 | A049 | 2026-06-21 | 371.4286 | 350.3773 | 28.5714 | 26.9521 | 140.1206 | In Progress | 5
PR01442 | P001 | A049 | 2026-06-28 | 501.4286 | 473.5 | 38.5714 | 36.4231 | 123.1228 | In Progress | 5
PR01443 | P001 | A049 | 2026-07-05 | 631.4286 | 646.1787 | 48.5714 | 49.7061 | 172.6787 | In Progress | 5
PR01444 | P001 | A049 | 2026-07-12 | 761.4286 | 684.5244 | 58.5714 | 52.6557 | 38.3457 | Delayed | 5
PR01445 | P001 | A049 | 2026-07-19 | 891.4286 | 834.668 | 68.5714 | 64.2052 | 150.1436 | In Progress | 5
PR01446 | P001 | A049 | 2026-07-26 | 1021.4286 | 1031.3414 | 78.5714 | 79.334 | 196.6734 | In Progress | 5
PR01447 | P001 | A049 | 2026-08-02 | 1151.4286 | 1111.9913 | 88.5714 | 85.5378 | 80.6499 | In Progress | 5
PR01448 | P001 | A049 | 2026-08-09 | 1281.4286 | 1242.6217 | 98.5714 | 95.5863 | 130.6305 | In Progress | 5
PR01449 | P001 | A049 | 2026-08-16 | 1300 | 1240.2136 | 100 | 95.401 | 0 | In Progress | 5
PR01450 | P001 | A049 | 2026-08-23 | 1300 | 1250.0124 | 100 | 96.1548 | 9.7988 | In Progress | 5
PR01451 | P001 | A049 | 2026-08-30 | 1300 | 1270.3812 | 100 | 97.7216 | 20.3688 | In Progress | 5
PR01452 | P001 | A049 | 2026-09-06 | 1300 | 1198.1684 | 100 | 92.1668 | 0 | Delayed | 5
PR01453 | P001 | A049 | 2026-09-13 | 1300 | 1274.9517 | 100 | 98.0732 | 76.7833 | In Progress | 5
PR01454 | P001 | A049 | 2026-09-20 | 1300 | 1172.5284 | 100 | 90.1945 | 0 | Delayed | 5
PR01455 | P001 | A049 | 2026-09-27 | 1300 | 1249.9407 | 100 | 96.1493 | 77.4124 | In Progress | 5
PR01456 | P001 | A049 | 2026-10-04 | 1300 | 1243.1327 | 100 | 95.6256 | 0 | In Progress | 5
PR01457 | P001 | A049 | 2026-10-11 | 1300 | 1206.9587 | 100 | 92.843 | 0 | Delayed | 5
PR01458 | P001 | A049 | 2026-10-18 | 1300 | 1233.9678 | 100 | 94.9206 | 27.0092 | Delayed | 5
PR01459 | P001 | A049 | 2026-10-25 | 1300 | 1206.6744 | 100 | 92.8211 | 0 | Delayed | 5
PR01460 | P001 | A049 | 2026-11-01 | 1300 | 1186.2376 | 100 | 91.249 | 0 | Delayed | 5
PR01461 | P001 | A049 | 2026-11-08 | 1300 | 1218.9105 | 100 | 93.7623 | 32.6729 | Delayed | 5
PR01462 | P001 | A049 | 2026-11-15 | 1300 | 1184.7685 | 100 | 91.136 | 0 | Delayed | 5
PR01463 | P001 | A049 | 2026-11-22 | 1300 | 1249.6873 | 100 | 96.1298 | 64.9188 | In Progress | 5
PR01464 | P001 | A049 | 2026-11-29 | 1300 | 1182.6711 | 100 | 90.9747 | 0 | Delayed | 5
PR01465 | P001 | A049 | 2026-12-06 | 1300 | 1267.395 | 100 | 97.4919 | 84.7238 | In Progress | 5
PR01466 | P001 | A049 | 2026-12-13 | 1300 | 1181.2427 | 100 | 90.8648 | 0 | Delayed | 5
PR01467 | P001 | A049 | 2026-12-20 | 1300 | 1209.2336 | 100 | 93.018 | 27.9909 | Delayed | 5
PR01468 | P001 | A049 | 2026-12-27 | 1300 | 1206.5805 | 100 | 92.8139 | 0 | Delayed | 5
PR01469 | P001 | A050 | 2026-06-21 | 72 | 69.5794 | 8 | 7.731 | 69.5794 | In Progress | 8
PR01470 | P001 | A050 | 2026-06-28 | 156 | 145.3234 | 17.3333 | 16.147 | 75.744 | In Progress | 8
PR01471 | P001 | A050 | 2026-07-05 | 240 | 219.0214 | 26.6667 | 24.3357 | 73.6981 | In Progress | 8
PR01472 | P001 | A050 | 2026-07-12 | 324 | 303.7355 | 36 | 33.7484 | 84.714 | In Progress | 8
PR01473 | P001 | A050 | 2026-07-19 | 408 | 345.2693 | 45.3333 | 38.3633 | 41.5338 | Delayed | 8
PR01474 | P001 | A050 | 2026-07-26 | 492 | 451.8972 | 54.6667 | 50.2108 | 106.6279 | In Progress | 8
PR01475 | P001 | A050 | 2026-08-02 | 576 | 570.1899 | 64 | 63.3544 | 118.2926 | In Progress | 8
PR01476 | P001 | A050 | 2026-08-09 | 660 | 610.2572 | 73.3333 | 67.8064 | 40.0673 | Delayed | 8
PR01477 | P001 | A050 | 2026-08-16 | 744 | 686.2485 | 82.6667 | 76.2498 | 75.9913 | Delayed | 8
PR01478 | P001 | A050 | 2026-08-23 | 828 | 777.6448 | 92 | 86.405 | 91.3963 | Delayed | 8
PR01479 | P001 | A050 | 2026-08-30 | 900 | 856.2116 | 100 | 95.1346 | 78.5668 | In Progress | 8
PR01480 | P001 | A050 | 2026-09-06 | 900 | 765.0798 | 100 | 85.0089 | 0 | Delayed | 8
PR01481 | P001 | A050 | 2026-09-13 | 900 | 775.0067 | 100 | 86.1119 | 9.9269 | Delayed | 8
PR01482 | P001 | A050 | 2026-09-20 | 900 | 834.6242 | 100 | 92.736 | 59.6175 | Delayed | 8
PR01483 | P001 | A050 | 2026-09-27 | 900 | 805.4814 | 100 | 89.4979 | 0 | Delayed | 8
PR01484 | P001 | A050 | 2026-10-04 | 900 | 869.3288 | 100 | 96.5921 | 63.8474 | In Progress | 8
PR01485 | P001 | A050 | 2026-10-11 | 900 | 818.072 | 100 | 90.8969 | 0 | Delayed | 8
PR01486 | P001 | A050 | 2026-10-18 | 900 | 767.0623 | 100 | 85.2291 | 0 | Delayed | 8
PR01487 | P001 | A050 | 2026-10-25 | 900 | 788.0576 | 100 | 87.562 | 20.9953 | Delayed | 8
PR01488 | P001 | A050 | 2026-11-01 | 900 | 741.3852 | 100 | 82.3761 | 0 | Delayed | 8
PR01489 | P001 | A050 | 2026-11-08 | 900 | 820.625 | 100 | 91.1806 | 79.2398 | Delayed | 8
PR01490 | P001 | A050 | 2026-11-15 | 900 | 822.0659 | 100 | 91.3407 | 1.4409 | Delayed | 8
PR01491 | P001 | A050 | 2026-11-22 | 900 | 814.6294 | 100 | 90.5144 | 0 | Delayed | 8
PR01492 | P001 | A050 | 2026-11-29 | 900 | 861.9847 | 100 | 95.7761 | 47.3553 | In Progress | 8
PR01493 | P001 | A050 | 2026-12-06 | 900 | 865.7534 | 100 | 96.1948 | 3.7687 | In Progress | 8
PR01494 | P001 | A050 | 2026-12-13 | 900 | 822.6328 | 100 | 91.4036 | 0 | Delayed | 8
PR01495 | P001 | A050 | 2026-12-20 | 900 | 760.7571 | 100 | 84.5286 | 0 | Delayed | 8
PR01496 | P001 | A050 | 2026-12-27 | 900 | 847.4444 | 100 | 94.1605 | 86.6872 | Delayed | 8
PR01497 | P001 | A051 | 2026-07-05 | 10.6667 | 10.0207 | 13.3333 | 12.5258 | 10.0207 | In Progress | 8
PR01498 | P001 | A051 | 2026-07-12 | 29.3333 | 27.3043 | 36.6667 | 34.1304 | 17.2836 | In Progress | 8
PR01499 | P001 | A051 | 2026-07-19 | 48 | 45.8089 | 60 | 57.2611 | 18.5046 | In Progress | 8
PR01500 | P001 | A051 | 2026-07-26 | 66.6667 | 58.6154 | 83.3333 | 73.2693 | 12.8065 | Delayed | 8
PR01501 | P001 | A051 | 2026-08-02 | 80 | 79.2245 | 100 | 99.0306 | 20.6091 | In Progress | 8
PR01502 | P001 | A051 | 2026-08-09 | 80 | 70.9136 | 100 | 88.642 | 0 | Delayed | 8
PR01503 | P001 | A051 | 2026-08-16 | 80 | 75.6978 | 100 | 94.6223 | 4.7842 | Delayed | 8
PR01504 | P001 | A051 | 2026-08-23 | 80 | 68.8754 | 100 | 86.0943 | 0 | Delayed | 8
PR01505 | P001 | A051 | 2026-08-30 | 80 | 70.9953 | 100 | 88.7441 | 2.1198 | Delayed | 8
PR01506 | P001 | A051 | 2026-09-06 | 80 | 77.8458 | 100 | 97.3073 | 6.8506 | In Progress | 8
PR01507 | P001 | A051 | 2026-09-13 | 80 | 72.8695 | 100 | 91.0869 | 0 | Delayed | 8
PR01508 | P001 | A051 | 2026-09-20 | 80 | 75.9518 | 100 | 94.9397 | 3.0823 | Delayed | 8
PR01509 | P001 | A051 | 2026-09-27 | 80 | 74.2635 | 100 | 92.8293 | 0 | Delayed | 8
PR01510 | P001 | A051 | 2026-10-04 | 80 | 73.3061 | 100 | 91.6326 | 0 | Delayed | 8
PR01511 | P001 | A051 | 2026-10-11 | 80 | 77.4188 | 100 | 96.7735 | 4.1127 | In Progress | 8
PR01512 | P001 | A051 | 2026-10-18 | 80 | 72.9374 | 100 | 91.1717 | 0 | Delayed | 8
PR01513 | P001 | A051 | 2026-10-25 | 80 | 68.6139 | 100 | 85.7674 | 0 | Delayed | 8
PR01514 | P001 | A051 | 2026-11-01 | 80 | 71.3509 | 100 | 89.1887 | 2.737 | Delayed | 8
PR01515 | P001 | A051 | 2026-11-08 | 80 | 75.1433 | 100 | 93.9292 | 3.7924 | Delayed | 8
PR01516 | P001 | A051 | 2026-11-15 | 80 | 74.7074 | 100 | 93.3843 | 0 | Delayed | 8
PR01517 | P001 | A051 | 2026-11-22 | 80 | 69.2122 | 100 | 86.5153 | 0 | Delayed | 8
PR01518 | P001 | A051 | 2026-11-29 | 80 | 71.5718 | 100 | 89.4648 | 2.3596 | Delayed | 8
PR01519 | P001 | A051 | 2026-12-06 | 80 | 71.9712 | 100 | 89.964 | 0.39934 | Delayed | 8
PR01520 | P001 | A051 | 2026-12-13 | 80 | 72.5767 | 100 | 90.7209 | 0.6055 | Delayed | 8
PR01521 | P001 | A051 | 2026-12-20 | 80 | 69.7474 | 100 | 87.1843 | 0 | Delayed | 8
PR01522 | P001 | A051 | 2026-12-27 | 80 | 71.8406 | 100 | 89.8007 | 2.0931 | Delayed | 8
PR01523 | P001 | A052 | 2026-08-02 | 240 | 233.8797 | 1.3333 | 1.2993 | 233.8797 | In Progress | 0
PR01524 | P001 | A052 | 2026-08-09 | 1920 | 1971.847 | 10.6667 | 10.9547 | 1737.9674 | In Progress | 0
PR01525 | P001 | A052 | 2026-08-16 | 3600 | 3701.9493 | 20 | 20.5664 | 1730.1023 | In Progress | 0
PR01526 | P001 | A052 | 2026-08-23 | 5280 | 5253.0542 | 29.3333 | 29.1836 | 1551.1049 | In Progress | 0
PR01527 | P001 | A052 | 2026-08-30 | 6960 | 6864.4991 | 38.6667 | 38.1361 | 1611.4449 | In Progress | 0
PR01528 | P001 | A052 | 2026-09-06 | 8640 | 8682.3131 | 48 | 48.2351 | 1817.814 | In Progress | 0
PR01529 | P001 | A052 | 2026-09-13 | 10320 | 10025.0531 | 57.3333 | 55.6947 | 1342.74 | In Progress | 0
PR01530 | P001 | A052 | 2026-09-20 | 12000 | 11518.3305 | 66.6667 | 63.9907 | 1493.2775 | In Progress | 0
PR01531 | P001 | A052 | 2026-09-27 | 13680 | 13229.8221 | 76 | 73.499 | 1711.4916 | In Progress | 0
PR01532 | P001 | A052 | 2026-10-04 | 15360 | 15018.7244 | 85.3333 | 83.4374 | 1788.9024 | In Progress | 0
PR01533 | P001 | A052 | 2026-10-11 | 17040 | 16346.1042 | 94.6667 | 90.8117 | 1327.3798 | In Progress | 0
PR01534 | P001 | A052 | 2026-10-18 | 18000 | 18000 | 100 | 100 | 1653.8958 | Completed | 0
PR01535 | P001 | A052 | 2026-10-25 | 18000 | 18000 | 100 | 100 | 0 | Completed | 0
PR01536 | P001 | A052 | 2026-11-01 | 18000 | 17000.1281 | 100 | 94.4452 | 0 | Delayed | 0
PR01537 | P001 | A052 | 2026-11-08 | 18000 | 18000 | 100 | 100 | 999.8719 | Completed | 0
PR01538 | P001 | A052 | 2026-11-15 | 18000 | 17861.4404 | 100 | 99.2302 | 0 | In Progress | 0
PR01539 | P001 | A052 | 2026-11-22 | 18000 | 18000 | 100 | 100 | 138.5596 | Completed | 0
PR01540 | P001 | A052 | 2026-11-29 | 18000 | 17991.8486 | 100 | 99.9547 | 0 | Completed | 0
PR01541 | P001 | A052 | 2026-12-06 | 18000 | 17084.2325 | 100 | 94.9124 | 0 | Delayed | 0
PR01542 | P001 | A052 | 2026-12-13 | 18000 | 17204.6947 | 100 | 95.5816 | 120.4623 | In Progress | 0
PR01543 | P001 | A052 | 2026-12-20 | 18000 | 18000 | 100 | 100 | 795.3053 | Completed | 0
PR01544 | P001 | A052 | 2026-12-27 | 18000 | 18000 | 100 | 100 | 0 | Completed | 0
PR01545 | P001 | A053 | 2026-08-16 | 184.6154 | 170.3083 | 1.5385 | 1.4192 | 170.3083 | In Progress | 0
PR01546 | P001 | A053 | 2026-08-23 | 1476.9231 | 1494.7945 | 12.3077 | 12.4566 | 1324.4862 | In Progress | 0
PR01547 | P001 | A053 | 2026-08-30 | 2769.2308 | 2884.5326 | 23.0769 | 24.0378 | 1389.7381 | In Progress | 0
PR01548 | P001 | A053 | 2026-09-06 | 4061.5385 | 4039.7852 | 33.8462 | 33.6649 | 1155.2527 | In Progress | 0
PR01549 | P001 | A053 | 2026-09-13 | 5353.8462 | 5456.9456 | 44.6154 | 45.4745 | 1417.1604 | In Progress | 0
PR01550 | P001 | A053 | 2026-09-20 | 6646.1538 | 6482.6092 | 55.3846 | 54.0217 | 1025.6635 | In Progress | 0
PR01551 | P001 | A053 | 2026-09-27 | 7938.4615 | 7905.2961 | 66.1538 | 65.8775 | 1422.6869 | In Progress | 0
PR01552 | P001 | A053 | 2026-10-04 | 9230.7692 | 8707.0895 | 76.9231 | 72.5591 | 801.7934 | In Progress | 0
PR01553 | P001 | A053 | 2026-10-11 | 10523.0769 | 9659.6372 | 87.6923 | 80.497 | 952.5478 | Delayed | 0
PR01554 | P001 | A053 | 2026-10-18 | 11815.3846 | 12000 | 98.4615 | 100 | 2340.3628 | Completed | 0
PR01555 | P001 | A053 | 2026-10-25 | 12000 | 11586.3021 | 100 | 96.5525 | 0 | In Progress | 0
PR01556 | P001 | A053 | 2026-11-01 | 12000 | 11808.6783 | 100 | 98.4057 | 222.3762 | In Progress | 0
PR01557 | P001 | A053 | 2026-11-08 | 12000 | 11417.6943 | 100 | 95.1475 | 0 | In Progress | 0
PR01558 | P001 | A053 | 2026-11-15 | 12000 | 11407.8127 | 100 | 95.0651 | 0 | In Progress | 0
PR01559 | P001 | A053 | 2026-11-22 | 12000 | 11926.9882 | 100 | 99.3916 | 519.1754 | In Progress | 0
PR01560 | P001 | A053 | 2026-11-29 | 12000 | 11693.5776 | 100 | 97.4465 | 0 | In Progress | 0
PR01561 | P001 | A053 | 2026-12-06 | 12000 | 12000 | 100 | 100 | 306.4224 | Completed | 0
PR01562 | P001 | A053 | 2026-12-13 | 12000 | 12000 | 100 | 100 | 0 | Completed | 0
PR01563 | P001 | A053 | 2026-12-20 | 12000 | 12000 | 100 | 100 | 0 | Completed | 0
PR01564 | P001 | A053 | 2026-12-27 | 12000 | 12000 | 100 | 100 | 0 | Completed | 0
PR01565 | P001 | A054 | 2026-08-23 | 154.2857 | 162.8057 | 8.5714 | 9.0448 | 162.8057 | In Progress | 0
PR01566 | P001 | A054 | 2026-08-30 | 514.2857 | 495.069 | 28.5714 | 27.5038 | 332.2634 | In Progress | 0
PR01567 | P001 | A054 | 2026-09-06 | 874.2857 | 872.6047 | 48.5714 | 48.478 | 377.5357 | In Progress | 0
PR01568 | P001 | A054 | 2026-09-13 | 1234.2857 | 1283.2179 | 68.5714 | 71.2899 | 410.6132 | In Progress | 0
PR01569 | P001 | A054 | 2026-09-20 | 1594.2857 | 1664.847 | 88.5714 | 92.4915 | 381.6291 | In Progress | 0
PR01570 | P001 | A054 | 2026-09-27 | 1800 | 1710.4289 | 100 | 95.0238 | 45.5819 | In Progress | 0
PR01571 | P001 | A054 | 2026-10-04 | 1800 | 1780.3216 | 100 | 98.9068 | 69.8927 | In Progress | 0
PR01572 | P001 | A054 | 2026-10-11 | 1800 | 1800 | 100 | 100 | 19.6784 | Completed | 0
PR01573 | P001 | A054 | 2026-10-18 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR01574 | P001 | A054 | 2026-10-25 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR01575 | P001 | A054 | 2026-11-01 | 1800 | 1786.2859 | 100 | 99.2381 | 0 | In Progress | 0
PR01576 | P001 | A054 | 2026-11-08 | 1800 | 1775.8205 | 100 | 98.6567 | 0 | In Progress | 0
PR01577 | P001 | A054 | 2026-11-15 | 1800 | 1800 | 100 | 100 | 24.1795 | Completed | 0
PR01578 | P001 | A054 | 2026-11-22 | 1800 | 1784.1004 | 100 | 99.1167 | 0 | In Progress | 0
PR01579 | P001 | A054 | 2026-11-29 | 1800 | 1797.3175 | 100 | 99.851 | 13.2171 | In Progress | 0
PR01580 | P001 | A054 | 2026-12-06 | 1800 | 1800 | 100 | 100 | 2.6825 | Completed | 0
PR01581 | P001 | A054 | 2026-12-13 | 1800 | 1757.2815 | 100 | 97.6267 | 0 | In Progress | 0
PR01582 | P001 | A054 | 2026-12-20 | 1800 | 1800 | 100 | 100 | 42.7185 | Completed | 0
PR01583 | P001 | A054 | 2026-12-27 | 1800 | 1800 | 100 | 100 | 0 | Completed | 0
PR01584 | P001 | A055 | 2026-11-22 | 166.6667 | 156.3009 | 6.6667 | 6.252 | 156.3009 | In Progress | 0
PR01585 | P001 | A055 | 2026-11-29 | 750 | 758.5053 | 30 | 30.3402 | 602.2044 | In Progress | 0
PR01586 | P001 | A055 | 2026-12-06 | 1333.3333 | 1297.8578 | 53.3333 | 51.9143 | 539.3525 | In Progress | 0
PR01587 | P001 | A055 | 2026-12-13 | 1916.6667 | 1955.4008 | 76.6667 | 78.216 | 657.543 | In Progress | 0
PR01588 | P001 | A055 | 2026-12-20 | 2500 | 2500 | 100 | 100 | 544.5992 | Completed | 0
PR01589 | P001 | A055 | 2026-12-27 | 2500 | 2500 | 100 | 100 | 0 | Completed | 0
PR01590 | P001 | A056 | 2026-09-20 | 705.8824 | 734.9243 | 5.8824 | 6.1244 | 734.9243 | In Progress | 0
PR01591 | P001 | A056 | 2026-09-27 | 1694.1176 | 1705.5271 | 14.1176 | 14.2127 | 970.6028 | In Progress | 0
PR01592 | P001 | A056 | 2026-10-04 | 2682.3529 | 2788.6327 | 22.3529 | 23.2386 | 1083.1056 | In Progress | 0
PR01593 | P001 | A056 | 2026-10-11 | 3670.5882 | 3369.4149 | 30.5882 | 28.0785 | 580.7822 | In Progress | 0
PR01594 | P001 | A056 | 2026-10-18 | 4658.8235 | 4918.1608 | 38.8235 | 40.9847 | 1548.7459 | In Progress | 0
PR01595 | P001 | A056 | 2026-10-25 | 5647.0588 | 5721.1888 | 47.0588 | 47.6766 | 803.0279 | In Progress | 0
PR01596 | P001 | A056 | 2026-11-01 | 6635.2941 | 6885.6074 | 55.2941 | 57.3801 | 1164.4186 | In Progress | 0
PR01597 | P001 | A056 | 2026-11-08 | 7623.5294 | 7298.0379 | 63.5294 | 60.817 | 412.4305 | In Progress | 0
PR01598 | P001 | A056 | 2026-11-15 | 8611.7647 | 8361.3609 | 71.7647 | 69.678 | 1063.323 | In Progress | 0
PR01599 | P001 | A056 | 2026-11-22 | 9600 | 9649.0353 | 80 | 80.4086 | 1287.6744 | In Progress | 0
PR01600 | P001 | A056 | 2026-11-29 | 10588.2353 | 10581.9213 | 88.2353 | 88.1827 | 932.886 | In Progress | 0
PR01601 | P001 | A056 | 2026-12-06 | 11576.4706 | 11691.1633 | 96.4706 | 97.4264 | 1109.2421 | In Progress | 0
PR01602 | P001 | A056 | 2026-12-13 | 12000 | 12000 | 100 | 100 | 308.8367 | Completed | 0
PR01603 | P001 | A056 | 2026-12-20 | 12000 | 11258.6075 | 100 | 93.8217 | 0 | Delayed | 0
PR01604 | P001 | A056 | 2026-12-27 | 12000 | 12000 | 100 | 100 | 741.3925 | Completed | 0
PR01605 | P001 | A057 | 2026-09-27 | 142.8571 | 138.6128 | 2.8571 | 2.7723 | 138.6128 | In Progress | 3
PR01606 | P001 | A057 | 2026-10-04 | 642.8571 | 618.9863 | 12.8571 | 12.3797 | 480.3735 | In Progress | 3
PR01607 | P001 | A057 | 2026-10-11 | 1142.8571 | 1049.7268 | 22.8571 | 20.9945 | 430.7405 | In Progress | 3
PR01608 | P001 | A057 | 2026-10-18 | 1642.8571 | 1622.4967 | 32.8571 | 32.4499 | 572.7699 | In Progress | 3
PR01609 | P001 | A057 | 2026-10-25 | 2142.8571 | 1897.5133 | 42.8571 | 37.9503 | 275.0166 | In Progress | 3
PR01610 | P001 | A057 | 2026-11-01 | 2642.8571 | 2623.5479 | 52.8571 | 52.471 | 726.0345 | In Progress | 3
PR01611 | P001 | A057 | 2026-11-08 | 3142.8571 | 2884.4398 | 62.8571 | 57.6888 | 260.8919 | Delayed | 3
PR01612 | P001 | A057 | 2026-11-15 | 3642.8571 | 3540.3873 | 72.8571 | 70.8077 | 655.9475 | In Progress | 3
PR01613 | P001 | A057 | 2026-11-22 | 4142.8571 | 4001.2919 | 82.8571 | 80.0258 | 460.9046 | In Progress | 3
PR01614 | P001 | A057 | 2026-11-29 | 4642.8571 | 4693.6214 | 92.8571 | 93.8724 | 692.3294 | In Progress | 3
PR01615 | P001 | A057 | 2026-12-06 | 5000 | 4818.7353 | 100 | 96.3747 | 125.114 | In Progress | 3
PR01616 | P001 | A057 | 2026-12-13 | 5000 | 4728.5258 | 100 | 94.5705 | 0 | Delayed | 3
PR01617 | P001 | A057 | 2026-12-20 | 5000 | 4761.3445 | 100 | 95.2269 | 32.8188 | In Progress | 3
PR01618 | P001 | A057 | 2026-12-27 | 5000 | 5000 | 100 | 100 | 238.6555 | Completed | 3
PR01619 | P001 | A058 | 2026-10-18 | 10.1538 | 10.3444 | 4.6154 | 4.702 | 10.3444 | In Progress | 0
PR01620 | P001 | A058 | 2026-10-25 | 33.8462 | 33.3893 | 15.3846 | 15.177 | 23.0449 | In Progress | 0
PR01621 | P001 | A058 | 2026-11-01 | 57.5385 | 57.0623 | 26.1538 | 25.9374 | 23.673 | In Progress | 0
PR01622 | P001 | A058 | 2026-11-08 | 81.2308 | 76.7752 | 36.9231 | 34.8978 | 19.7129 | In Progress | 0
PR01623 | P001 | A058 | 2026-11-15 | 104.9231 | 106.3497 | 47.6923 | 48.3408 | 29.5745 | In Progress | 0
PR01624 | P001 | A058 | 2026-11-22 | 128.6154 | 120.6935 | 58.4615 | 54.8607 | 14.3438 | In Progress | 0
PR01625 | P001 | A058 | 2026-11-29 | 152.3077 | 156.3153 | 69.2308 | 71.0524 | 35.6218 | In Progress | 0
PR01626 | P001 | A058 | 2026-12-06 | 176 | 176.7923 | 80 | 80.3601 | 20.477 | In Progress | 0
PR01627 | P001 | A058 | 2026-12-13 | 199.6923 | 216.3753 | 90.7692 | 98.3524 | 39.583 | In Progress | 0
PR01628 | P001 | A058 | 2026-12-20 | 220 | 211.529 | 100 | 96.1495 | 0 | In Progress | 0
PR01629 | P001 | A058 | 2026-12-27 | 220 | 219.2095 | 100 | 99.6407 | 7.6805 | In Progress | 0
PR01630 | P001 | A059 | 2026-09-27 | 71.4286 | 72.3529 | 2.8571 | 2.8941 | 72.3529 | In Progress | 5
PR01631 | P001 | A059 | 2026-10-04 | 321.4286 | 318.7603 | 12.8571 | 12.7504 | 246.4074 | In Progress | 5
PR01632 | P001 | A059 | 2026-10-11 | 571.4286 | 528.9329 | 22.8571 | 21.1573 | 210.1726 | In Progress | 5
PR01633 | P001 | A059 | 2026-10-18 | 821.4286 | 786.7962 | 32.8571 | 31.4718 | 257.8633 | In Progress | 5
PR01634 | P001 | A059 | 2026-10-25 | 1071.4286 | 1017.9321 | 42.8571 | 40.7173 | 231.1359 | In Progress | 5
PR01635 | P001 | A059 | 2026-11-01 | 1321.4286 | 1268.3976 | 52.8571 | 50.7359 | 250.4655 | In Progress | 5
PR01636 | P001 | A059 | 2026-11-08 | 1571.4286 | 1454.4297 | 62.8571 | 58.1772 | 186.0321 | In Progress | 5
PR01637 | P001 | A059 | 2026-11-15 | 1821.4286 | 1724.663 | 72.8571 | 68.9865 | 270.2332 | In Progress | 5
PR01638 | P001 | A059 | 2026-11-22 | 2071.4286 | 1851.9983 | 82.8571 | 74.0799 | 127.3354 | Delayed | 5
PR01639 | P001 | A059 | 2026-11-29 | 2321.4286 | 2216.3359 | 92.8571 | 88.6534 | 364.3376 | In Progress | 5
PR01640 | P001 | A059 | 2026-12-06 | 2500 | 2414.3768 | 100 | 96.5751 | 198.0409 | In Progress | 5
PR01641 | P001 | A059 | 2026-12-13 | 2500 | 2355.1008 | 100 | 94.204 | 0 | Delayed | 5
PR01642 | P001 | A059 | 2026-12-20 | 2500 | 2233.683 | 100 | 89.3473 | 0 | Delayed | 5
PR01643 | P001 | A059 | 2026-12-27 | 2500 | 2461.4965 | 100 | 98.4599 | 227.8135 | In Progress | 5
PR01644 | P001 | A060 | 2026-10-04 | 937.5 | 902.586 | 3.75 | 3.6103 | 902.586 | In Progress | 5
PR01645 | P001 | A060 | 2026-10-11 | 3125 | 2889.3421 | 12.5 | 11.5574 | 1986.7561 | In Progress | 5
PR01646 | P001 | A060 | 2026-10-18 | 5312.5 | 4994.7009 | 21.25 | 19.9788 | 2105.3588 | In Progress | 5
PR01647 | P001 | A060 | 2026-10-25 | 7500 | 6731.0743 | 30 | 26.9243 | 1736.3734 | In Progress | 5
PR01648 | P001 | A060 | 2026-11-01 | 9687.5 | 8855.4469 | 38.75 | 35.4218 | 2124.3726 | In Progress | 5
PR01649 | P001 | A060 | 2026-11-08 | 11875 | 11057.7222 | 47.5 | 44.2309 | 2202.2753 | In Progress | 5
PR01650 | P001 | A060 | 2026-11-15 | 14062.5 | 13963.9884 | 56.25 | 55.856 | 2906.2662 | In Progress | 5
PR01651 | P001 | A060 | 2026-11-22 | 16250 | 15073.7824 | 65 | 60.2951 | 1109.7941 | In Progress | 5
PR01652 | P001 | A060 | 2026-11-29 | 18437.5 | 17928.7629 | 73.75 | 71.7151 | 2854.9804 | In Progress | 5
PR01653 | P001 | A060 | 2026-12-06 | 20625 | 19205.153 | 82.5 | 76.8206 | 1276.3901 | Delayed | 5
PR01654 | P001 | A060 | 2026-12-13 | 22812.5 | 21869.8456 | 91.25 | 87.4794 | 2664.6926 | In Progress | 5
PR01655 | P001 | A060 | 2026-12-20 | 25000 | 23626.2789 | 100 | 94.5051 | 1756.4333 | Delayed | 5
PR01656 | P001 | A060 | 2026-12-27 | 25000 | 24513.9245 | 100 | 98.0557 | 887.6456 | In Progress | 5
PR01657 | P001 | A061 | 2026-10-18 | 646.1538 | 556.5204 | 4.6154 | 3.9751 | 556.5204 | In Progress | 12
PR01658 | P001 | A061 | 2026-10-25 | 2153.8462 | 1776.8402 | 15.3846 | 12.6917 | 1220.3198 | In Progress | 12
PR01659 | P001 | A061 | 2026-11-01 | 3661.5385 | 3045.0518 | 26.1538 | 21.7504 | 1268.2116 | In Progress | 12
PR01660 | P001 | A061 | 2026-11-08 | 5169.2308 | 4452.6942 | 36.9231 | 31.805 | 1407.6424 | Delayed | 12
PR01661 | P001 | A061 | 2026-11-15 | 6676.9231 | 5583.7966 | 47.6923 | 39.8843 | 1131.1024 | Delayed | 12
PR01662 | P001 | A061 | 2026-11-22 | 8184.6154 | 7319.9715 | 58.4615 | 52.2855 | 1736.1749 | Delayed | 12
PR01663 | P001 | A061 | 2026-11-29 | 9692.3077 | 8371.2279 | 69.2308 | 59.7945 | 1051.2564 | Delayed | 12
PR01664 | P001 | A061 | 2026-12-06 | 11200 | 10786.8458 | 80 | 77.0489 | 2415.6179 | In Progress | 12
PR01665 | P001 | A061 | 2026-12-13 | 12707.6923 | 10409.8872 | 90.7692 | 74.3563 | 0 | Delayed | 12
PR01666 | P001 | A061 | 2026-12-20 | 14000 | 12419.7803 | 100 | 88.7127 | 2009.893 | Delayed | 12
PR01667 | P001 | A061 | 2026-12-27 | 14000 | 11767.303 | 100 | 84.0522 | 0 | Delayed | 12
PR01668 | P001 | A062 | 2026-08-16 | 65 | 60.6275 | 1 | 0.93273 | 60.6275 | In Progress | 5
PR01669 | P001 | A062 | 2026-08-23 | 520 | 496.5738 | 8 | 7.6396 | 435.9463 | In Progress | 5
PR01670 | P001 | A062 | 2026-08-30 | 975 | 846.8967 | 15 | 13.0292 | 350.3229 | In Progress | 5
PR01671 | P001 | A062 | 2026-09-06 | 1430 | 1370.3531 | 22 | 21.0824 | 523.4564 | In Progress | 5
PR01672 | P001 | A062 | 2026-09-13 | 1885 | 1916.2943 | 29 | 29.4815 | 545.9412 | In Progress | 5
PR01673 | P001 | A062 | 2026-09-20 | 2340 | 2185.8634 | 36 | 33.6287 | 269.5691 | In Progress | 5
PR01674 | P001 | A062 | 2026-09-27 | 2795 | 2680.6657 | 43 | 41.241 | 494.8023 | In Progress | 5
PR01675 | P001 | A062 | 2026-10-04 | 3250 | 3204.0848 | 50 | 49.2936 | 523.4191 | In Progress | 5
PR01676 | P001 | A062 | 2026-10-11 | 3705 | 3498.4893 | 57 | 53.8229 | 294.4045 | In Progress | 5
PR01677 | P001 | A062 | 2026-10-18 | 4160 | 3867.4122 | 64 | 59.4986 | 368.9229 | In Progress | 5
PR01678 | P001 | A062 | 2026-10-25 | 4615 | 4016.6617 | 71 | 61.7948 | 149.2495 | Delayed | 5
PR01679 | P001 | A062 | 2026-11-01 | 5070 | 4930.2438 | 78 | 75.8499 | 913.5821 | In Progress | 5
PR01680 | P001 | A062 | 2026-11-08 | 5525 | 5226.8661 | 85 | 80.4133 | 296.6223 | In Progress | 5
PR01681 | P001 | A062 | 2026-11-15 | 5980 | 5469.0453 | 92 | 84.1392 | 242.1792 | Delayed | 5
PR01682 | P001 | A062 | 2026-11-22 | 6435 | 6141.7627 | 99 | 94.4887 | 672.7175 | In Progress | 5
PR01683 | P001 | A062 | 2026-11-29 | 6500 | 6042.2127 | 100 | 92.9571 | 0 | Delayed | 5
PR01684 | P001 | A062 | 2026-12-06 | 6500 | 6054.7831 | 100 | 93.1505 | 12.5703 | Delayed | 5
PR01685 | P001 | A062 | 2026-12-13 | 6500 | 6312.9312 | 100 | 97.122 | 258.1482 | In Progress | 5
PR01686 | P001 | A062 | 2026-12-20 | 6500 | 5870.518 | 100 | 90.3157 | 0 | Delayed | 5
PR01687 | P001 | A062 | 2026-12-27 | 6500 | 6413.2642 | 100 | 98.6656 | 542.7462 | In Progress | 5
PR01688 | P001 | A063 | 2026-10-25 | 16.9231 | 16.0952 | 7.6923 | 7.316 | 16.0952 | In Progress | 0
PR01689 | P001 | A063 | 2026-11-01 | 40.6154 | 39.6733 | 18.4615 | 18.0333 | 23.5781 | In Progress | 0
PR01690 | P001 | A063 | 2026-11-08 | 64.3077 | 68.6358 | 29.2308 | 31.1981 | 28.9625 | In Progress | 0
PR01691 | P001 | A063 | 2026-11-15 | 88 | 91.4723 | 40 | 41.5783 | 22.8365 | In Progress | 0
PR01692 | P001 | A063 | 2026-11-22 | 111.6923 | 112.0739 | 50.7692 | 50.9427 | 20.6016 | In Progress | 0
PR01693 | P001 | A063 | 2026-11-29 | 135.3846 | 130.9279 | 61.5385 | 59.5127 | 18.8541 | In Progress | 0
PR01694 | P001 | A063 | 2026-12-06 | 159.0769 | 156.1301 | 72.3077 | 70.9682 | 25.2021 | In Progress | 0
PR01695 | P001 | A063 | 2026-12-13 | 182.7692 | 183.238 | 83.0769 | 83.29 | 27.1079 | In Progress | 0
PR01696 | P001 | A063 | 2026-12-20 | 206.4615 | 206.7327 | 93.8462 | 93.9694 | 23.4947 | In Progress | 0
PR01697 | P001 | A063 | 2026-12-27 | 220 | 219.3003 | 100 | 99.682 | 12.5676 | In Progress | 0
PR01698 | P001 | A064 | 2026-08-23 | 534.6535 | 469.9181 | 2.9703 | 2.6107 | 469.9181 | In Progress | 12
PR01699 | P001 | A064 | 2026-08-30 | 1782.1782 | 1554.9449 | 9.901 | 8.6386 | 1085.0268 | In Progress | 12
PR01700 | P001 | A064 | 2026-09-06 | 3029.703 | 2513.2318 | 16.8317 | 13.9624 | 958.2868 | In Progress | 12
PR01701 | P001 | A064 | 2026-09-13 | 4277.2277 | 3686.6372 | 23.7624 | 20.4813 | 1173.4054 | In Progress | 12
PR01702 | P001 | A064 | 2026-09-20 | 5524.7525 | 5038.6397 | 30.6931 | 27.9924 | 1352.0025 | In Progress | 12
PR01703 | P001 | A064 | 2026-09-27 | 6772.2772 | 5635.2681 | 37.6238 | 31.307 | 596.6284 | Delayed | 12
PR01704 | P001 | A064 | 2026-10-04 | 8019.802 | 7004.2188 | 44.5545 | 38.9123 | 1368.9507 | Delayed | 12
PR01705 | P001 | A064 | 2026-10-11 | 9267.3267 | 7889.3551 | 51.4851 | 43.8298 | 885.1362 | Delayed | 12
PR01706 | P001 | A064 | 2026-10-18 | 10514.8515 | 9294.0485 | 58.4158 | 51.6336 | 1404.6934 | Delayed | 12
PR01707 | P001 | A064 | 2026-10-25 | 11762.3762 | 10190.8973 | 65.3465 | 56.6161 | 896.8489 | Delayed | 12
PR01708 | P001 | A064 | 2026-11-01 | 13009.901 | 12121.439 | 72.2772 | 67.3413 | 1930.5416 | In Progress | 12
PR01709 | P001 | A064 | 2026-11-08 | 14257.4257 | 12799.3247 | 79.2079 | 71.1074 | 677.8857 | Delayed | 12
PR01710 | P001 | A064 | 2026-11-15 | 15504.9505 | 12932.4759 | 86.1386 | 71.8471 | 133.1513 | Delayed | 12
PR01711 | P001 | A064 | 2026-11-22 | 16752.4752 | 15135.7438 | 93.0693 | 84.0875 | 2203.2679 | Delayed | 12
PR01712 | P001 | A064 | 2026-11-29 | 18000 | 15351.9693 | 100 | 85.2887 | 216.2255 | Delayed | 12
PR01713 | P001 | A064 | 2026-12-06 | 18000 | 15476.4923 | 100 | 85.9805 | 124.523 | Delayed | 12
PR01714 | P001 | A064 | 2026-12-13 | 18000 | 16037.706 | 100 | 89.0984 | 561.2137 | Delayed | 12
PR01715 | P001 | A064 | 2026-12-20 | 18000 | 15530.1991 | 100 | 86.2789 | 0 | Delayed | 12
PR01716 | P001 | A064 | 2026-12-27 | 18000 | 16402.4992 | 100 | 91.125 | 872.3 | Delayed | 12
PR01717 | P001 | A065 | 2026-10-25 | 0 | 0 | 0 | 0 | 0 | Not Started | 0
PR01718 | P001 | A065 | 2026-11-01 | 110.8333 | 108.4323 | 11.6667 | 11.4139 | 108.4323 | In Progress | 0
PR01719 | P001 | A065 | 2026-11-08 | 221.6667 | 216.5743 | 23.3333 | 22.7973 | 108.142 | In Progress | 0
PR01720 | P001 | A065 | 2026-11-15 | 332.5 | 325.9174 | 35 | 34.3071 | 109.3431 | In Progress | 0
PR01721 | P001 | A065 | 2026-11-22 | 443.3333 | 460.3891 | 46.6667 | 48.462 | 134.4717 | In Progress | 0
PR01722 | P001 | A065 | 2026-11-29 | 554.1667 | 566.3627 | 58.3333 | 59.6171 | 105.9736 | In Progress | 0
PR01723 | P001 | A065 | 2026-12-06 | 665 | 704.7989 | 70 | 74.1894 | 138.4363 | In Progress | 0
PR01724 | P001 | A065 | 2026-12-13 | 775.8333 | 837.4093 | 81.6667 | 88.1483 | 132.6104 | In Progress | 0
PR01725 | P001 | A065 | 2026-12-20 | 886.6667 | 854.6801 | 93.3333 | 89.9663 | 17.2708 | In Progress | 0
PR01726 | P001 | A065 | 2026-12-27 | 950 | 950 | 100 | 100 | 95.3199 | Completed | 0
PR01727 | P001 | A066 | 2026-10-18 | 49.0909 | 47.07 | 5.4545 | 5.23 | 47.07 | In Progress | 0
PR01728 | P001 | A066 | 2026-10-25 | 163.6364 | 159.1828 | 18.1818 | 17.687 | 112.1128 | In Progress | 0
PR01729 | P001 | A066 | 2026-11-01 | 278.1818 | 272.0471 | 30.9091 | 30.2275 | 112.8643 | In Progress | 0
PR01730 | P001 | A066 | 2026-11-08 | 392.7273 | 378.1962 | 43.6364 | 42.0218 | 106.1491 | In Progress | 0
PR01731 | P001 | A066 | 2026-11-15 | 507.2727 | 488.5969 | 56.3636 | 54.2885 | 110.4007 | In Progress | 0
PR01732 | P001 | A066 | 2026-11-22 | 621.8182 | 618.678 | 69.0909 | 68.742 | 130.0811 | In Progress | 0
PR01733 | P001 | A066 | 2026-11-29 | 736.3636 | 705.0055 | 81.8182 | 78.3339 | 86.3275 | In Progress | 0
PR01734 | P001 | A066 | 2026-12-06 | 850.9091 | 875.9892 | 94.5455 | 97.3321 | 170.9837 | In Progress | 0
PR01735 | P001 | A066 | 2026-12-13 | 900 | 871.0908 | 100 | 96.7879 | 0 | In Progress | 0
PR01736 | P001 | A066 | 2026-12-20 | 900 | 900 | 100 | 100 | 28.9092 | Completed | 0
PR01737 | P001 | A066 | 2026-12-27 | 900 | 885.7814 | 100 | 98.4202 | 0 | In Progress | 0
PR01738 | P001 | A067 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | Not Started | 12
PR01739 | P001 | A067 | 2026-11-08 | 572.7273 | 478.0343 | 12.7273 | 10.623 | 478.0343 | In Progress | 12
PR01740 | P001 | A067 | 2026-11-15 | 1145.4545 | 1076.3988 | 25.4545 | 23.92 | 598.3645 | In Progress | 12
PR01741 | P001 | A067 | 2026-11-22 | 1718.1818 | 1579.3227 | 38.1818 | 35.0961 | 502.9239 | In Progress | 12
PR01742 | P001 | A067 | 2026-11-29 | 2290.9091 | 2039.8073 | 50.9091 | 45.3291 | 460.4846 | Delayed | 12
PR01743 | P001 | A067 | 2026-12-06 | 2863.6364 | 2385.0137 | 63.6364 | 53.0003 | 345.2064 | Delayed | 12
PR01744 | P001 | A067 | 2026-12-13 | 3436.3636 | 3049.3375 | 76.3636 | 67.7631 | 664.3238 | Delayed | 12
PR01745 | P001 | A067 | 2026-12-20 | 4009.0909 | 3370.6428 | 89.0909 | 74.9032 | 321.3054 | Delayed | 12
PR01746 | P001 | A067 | 2026-12-27 | 4500 | 4190.321 | 100 | 93.1182 | 819.6781 | Delayed | 12
PR01747 | P001 | A068 | 2026-12-06 | 17000 | 17481.4709 | 20 | 20.5664 | 17481.4709 | In Progress | 0
PR01748 | P001 | A068 | 2026-12-13 | 40800 | 40936.2869 | 48 | 48.1603 | 23454.8161 | In Progress | 0
PR01749 | P001 | A068 | 2026-12-20 | 64600 | 59091.3546 | 76 | 69.5192 | 18155.0677 | Delayed | 0
PR01750 | P001 | A068 | 2026-12-27 | 85000 | 82074.3375 | 100 | 96.558 | 22982.9828 | In Progress | 0

## Cost_Transactions
Cost_ID | Project_ID | Activity_ID | Date | Contractor_ID | Cost_Type | Description | Planned_Cost_INR | Actual_Cost_INR | Vendor_or_Source
CT00001 | P001 | A001 | 2026-01-04 | C001 | Other | Site overhead and miscellaneous | 89729.299 | 82559.1116 | Internal Team
CT00002 | P001 | A001 | 2026-01-05 | C001 | Subcontract | Subcontractor work | 108671.9434 | 113353.4018 | C001
CT00003 | P001 | A001 | 2026-01-05 | C001 | Labour | Site labour and workforce cost | 125632.4874 | 116228.1236 | Internal Team
CT00004 | P001 | A001 | 2026-01-06 | C001 | Labour | Site labour and workforce cost | 116436.5383 | 109995.8861 | Internal Team
CT00005 | P001 | A002 | 2026-01-02 | C001 | Subcontract | Subcontractor work | 55774.2091 | 61260.5995 | C001
CT00006 | P001 | A002 | 2026-01-10 | C001 | Equipment | Equipment operation/rental | 50478.1412 | 56107.5274 | BuildPlant Equipment
CT00007 | P001 | A002 | 2026-01-10 | C001 | Subcontract | Subcontractor work | 58339.4481 | 64059.5367 | C001
CT00008 | P001 | A003 | 2026-01-08 | C001 | Other | Site overhead and miscellaneous | 87521.6543 | 84201.0314 | Internal Team
CT00009 | P001 | A003 | 2026-01-14 | C001 | Labour | Site labour and workforce cost | 104122.2371 | 112344.1041 | Internal Team
CT00010 | P001 | A003 | 2026-01-21 | C001 | Labour | Site labour and workforce cost | 124513.9044 | 125047.2867 | Internal Team
CT00011 | P001 | A004 | 2026-01-10 | C001 | Other | Site overhead and miscellaneous | 58320.9264 | 56484.5364 | Internal Team
CT00012 | P001 | A004 | 2026-01-12 | C001 | Labour | Site labour and workforce cost | 48495.2261 | 52263.2749 | Internal Team
CT00013 | P001 | A004 | 2026-01-13 | C001 | Subcontract | Subcontractor work | 62126.1674 | 66162.945 | C001
CT00014 | P001 | A005 | 2026-01-29 | C001 | Equipment | Equipment operation/rental | 420656.9614 | 483509.385 | BuildPlant Equipment
CT00015 | P001 | A005 | 2026-02-04 | C001 | Equipment | Equipment operation/rental | 442806.1622 | 503339.3089 | BuildPlant Equipment
CT00016 | P001 | A005 | 2026-02-06 | C001 | Equipment | Equipment operation/rental | 360414.5338 | 397042.8911 | BuildPlant Equipment
CT00017 | P001 | A005 | 2026-02-09 | C001 | Equipment | Equipment operation/rental | 332465.2163 | 407133.097 | BuildPlant Equipment
CT00018 | P001 | A006 | 2026-02-06 | C001 | Equipment | Equipment operation/rental | 250990.7419 | 243616.09 | BuildPlant Equipment
CT00019 | P001 | A006 | 2026-02-09 | C001 | Transportation | Material/soil transportation | 276705.2328 | 283606.1666 | C001
CT00020 | P001 | A006 | 2026-02-20 | C001 | Equipment | Equipment operation/rental | 292880.1217 | 272493.1713 | BuildPlant Equipment
CT00021 | P001 | A007 | 2026-02-06 | C001 | Labour | Site labour and workforce cost | 113754.5821 | 112747.8637 | Internal Team
CT00022 | P001 | A007 | 2026-02-06 | C001 | Transportation | Material/soil transportation | 104913.9821 | 97726.0674 | C001
CT00023 | P001 | A007 | 2026-02-19 | C001 | Labour | Site labour and workforce cost | 124348.6215 | 132168.7071 | Internal Team
CT00024 | P001 | A008 | 2026-01-20 | C001 | Labour | Site labour and workforce cost | 149603.5884 | 142489.4101 | Internal Team
CT00025 | P001 | A008 | 2026-01-22 | C001 | Other | Site overhead and miscellaneous | 195838.7528 | 202883.2082 | Internal Team
CT00026 | P001 | A008 | 2026-01-30 | C001 | Equipment | Equipment operation/rental | 190348.0306 | 204148.9749 | BuildPlant Equipment
CT00027 | P001 | A009 | 2026-02-23 | C002 | Material | Material purchase and consumption | 753657.0841 | 800157.0663 | C002
CT00028 | P001 | A009 | 2026-02-25 | C002 | Material | Material purchase and consumption | 1078062.057 | 1112192.8573 | C002
CT00029 | P001 | A009 | 2026-03-02 | C002 | Material | Material purchase and consumption | 945349.5252 | 1028503.2693 | C002
CT00030 | P001 | A010 | 2026-02-26 | C002 | Equipment | Equipment operation/rental | 1609105.5575 | 1543599.7813 | BuildPlant Equipment
CT00031 | P001 | A010 | 2026-02-27 | C002 | Labour | Site labour and workforce cost | 1180052.1405 | 1127863.6871 | Internal Team
CT00032 | P001 | A010 | 2026-03-07 | C002 | Material | Material purchase and consumption | 1495494.2173 | 1474899.5437 | C002
CT00033 | P001 | A010 | 2026-03-07 | C002 | Material | Material purchase and consumption | 1282650.2407 | 1349228.1085 | C002
CT00034 | P001 | A011 | 2026-03-14 | C002 | Subcontract | Subcontractor work | 1044260.8179 | 1088206.5373 | C002
CT00035 | P001 | A011 | 2026-03-18 | C002 | Material | Material purchase and consumption | 1705982.9611 | 1816776.9241 | C002
CT00036 | P001 | A011 | 2026-03-24 | C002 | Subcontract | Subcontractor work | 1706334.2051 | 1720073.2001 | C002
CT00037 | P001 | A011 | 2026-03-28 | C002 | Subcontract | Subcontractor work | 1089914.0841 | 1150912.5118 | C002
CT00038 | P001 | A012 | 2026-03-16 | C002 | Labour | Site labour and workforce cost | 545681.3271 | 566615.4113 | Internal Team
CT00039 | P001 | A012 | 2026-03-19 | C002 | Material | Material purchase and consumption | 519755.7114 | 538864.49 | C002
CT00040 | P001 | A012 | 2026-03-28 | C002 | Labour | Site labour and workforce cost | 775162.8795 | 771748.278 | Internal Team
CT00041 | P001 | A013 | 2026-04-04 | C002 | Subcontract | Subcontractor work | 452197.9943 | 431909.1069 | C002
CT00042 | P001 | A013 | 2026-04-04 | C002 | Labour | Site labour and workforce cost | 530259.0172 | 567807.1589 | Internal Team
CT00043 | P001 | A013 | 2026-04-08 | C002 | Material | Material purchase and consumption | 603219.5134 | 575736.2289 | C002
CT00044 | P001 | A014 | 2026-04-13 | C001 | Material | Material purchase and consumption | 54025.8456 | 57714.043 | C001
CT00045 | P001 | A014 | 2026-04-18 | C001 | Subcontract | Subcontractor work | 44826.2972 | 46210.0068 | C001
CT00046 | P001 | A014 | 2026-04-19 | C001 | Material | Material purchase and consumption | 63426.4718 | 59880.6609 | C001
CT00047 | P001 | A015 | 2026-04-02 | C002 | Material | Material purchase and consumption | 304259.0418 | 293798.4893 | C002
CT00048 | P001 | A015 | 2026-04-09 | C002 | Material | Material purchase and consumption | 247731.3285 | 261433.8199 | C002
CT00049 | P001 | A015 | 2026-04-13 | C002 | Material | Material purchase and consumption | 272709.7082 | 287664.3218 | C002
CT00050 | P001 | A016 | 2026-04-20 | C002 | Subcontract | Subcontractor work | 321987.5534 | 321434.5174 | C002
CT00051 | P001 | A016 | 2026-04-28 | C002 | Labour | Site labour and workforce cost | 221621.2607 | 209305.8606 | Internal Team
CT00052 | P001 | A016 | 2026-05-02 | C002 | Material | Material purchase and consumption | 295317.0812 | 273930.1004 | C002
CT00053 | P001 | A017 | 2026-05-14 | C002 | Material | Material purchase and consumption | 240250.9044 | 222262.5923 | C002
CT00054 | P001 | A017 | 2026-05-17 | C002 | Material | Material purchase and consumption | 285442.1244 | 279674.7321 | C002
CT00055 | P001 | A017 | 2026-05-18 | C002 | Material | Material purchase and consumption | 290430.2248 | 272245.4345 | C002
CT00056 | P001 | A018 | 2026-05-28 | C002 | Material | Material purchase and consumption | 311890.845 | 305794.6337 | C002
CT00057 | P001 | A018 | 2026-05-30 | C002 | Material | Material purchase and consumption | 274109.5592 | 278210.9221 | C002
CT00058 | P001 | A018 | 2026-06-04 | C002 | Material | Material purchase and consumption | 205447.2379 | 205944.6955 | C002
CT00059 | P001 | A019 | 2026-06-22 | C002 | Material | Material purchase and consumption | 205506.2908 | 208839.5293 | C002
CT00060 | P001 | A019 | 2026-06-29 | C002 | Equipment | Equipment operation/rental | 305618.9491 | 295096.2485 | BuildPlant Equipment
CT00061 | P001 | A019 | 2026-07-01 | C002 | Subcontract | Subcontractor work | 308820.004 | 315359.8259 | C002
CT00062 | P001 | A020 | 2026-07-09 | C002 | Subcontract | Subcontractor work | 276343.3513 | 260724.1259 | C002
CT00063 | P001 | A020 | 2026-07-12 | C002 | Material | Material purchase and consumption | 247898.5871 | 267240.5252 | C002
CT00064 | P001 | A020 | 2026-07-21 | C002 | Material | Material purchase and consumption | 204691.1116 | 203135.7189 | C002
CT00065 | P001 | A021 | 2026-07-25 | C002 | Material | Material purchase and consumption | 220174.3771 | 204382.4665 | C002
CT00066 | P001 | A021 | 2026-08-02 | C002 | Subcontract | Subcontractor work | 330131.2373 | 317761.0568 | C002
CT00067 | P001 | A021 | 2026-08-08 | C002 | Material | Material purchase and consumption | 270548.6274 | 252831.0153 | C002
CT00068 | P001 | A022 | 2026-08-17 | C002 | Subcontract | Subcontractor work | 237442.811 | 237615.4885 | C002
CT00069 | P001 | A022 | 2026-08-19 | C002 | Material | Material purchase and consumption | 318536.6569 | 315899.2934 | C002
CT00070 | P001 | A022 | 2026-08-21 | C002 | Subcontract | Subcontractor work | 240230.7954 | 253894.1761 | C002
CT00071 | P001 | A023 | 2026-09-05 | C002 | Subcontract | Subcontractor work | 206694.396 | 203117.3497 | C002
CT00072 | P001 | A023 | 2026-09-07 | C002 | Material | Material purchase and consumption | 229524.7631 | 236136.3593 | C002
CT00073 | P001 | A023 | 2026-09-15 | C002 | Material | Material purchase and consumption | 226978.3969 | 233326.9919 | C002
CT00074 | P001 | A024 | 2026-09-23 | C002 | Material | Material purchase and consumption | 265478.7505 | 259587.1993 | C002
CT00075 | P001 | A024 | 2026-09-25 | C002 | Material | Material purchase and consumption | 317604.0671 | 321260.3569 | C002
CT00076 | P001 | A024 | 2026-09-28 | C002 | Labour | Site labour and workforce cost | 231367.1609 | 246178.0382 | Internal Team
CT00077 | P001 | A025 | 2026-10-14 | C002 | Material | Material purchase and consumption | 303359.9678 | 285437.5489 | C002
CT00078 | P001 | A025 | 2026-10-15 | C002 | Material | Material purchase and consumption | 311437.4703 | 333208.5584 | C002
CT00079 | P001 | A025 | 2026-10-21 | C002 | Material | Material purchase and consumption | 284381.8336 | 293953.4068 | C002
CT00080 | P001 | A026 | 2026-04-12 | C002 | Subcontract | Subcontractor work | 318018.8395 | 319710.69 | C002
CT00081 | P001 | A026 | 2026-04-20 | C002 | Material | Material purchase and consumption | 264271.2169 | 269053.8671 | C002
CT00082 | P001 | A026 | 2026-04-26 | C002 | Material | Material purchase and consumption | 238474.6455 | 254792.7368 | C002
CT00083 | P001 | A027 | 2026-05-08 | C002 | Material | Material purchase and consumption | 241417.5749 | 232894.7547 | C002
CT00084 | P001 | A027 | 2026-05-08 | C002 | Material | Material purchase and consumption | 266638.3235 | 261460.0335 | C002
CT00085 | P001 | A027 | 2026-05-15 | C002 | Material | Material purchase and consumption | 296913.9186 | 289265.7838 | C002
CT00086 | P001 | A028 | 2026-05-24 | C002 | Material | Material purchase and consumption | 355422.2848 | 383333.4413 | C002
CT00087 | P001 | A028 | 2026-05-30 | C002 | Material | Material purchase and consumption | 382492.8726 | 382751.0923 | C002
CT00088 | P001 | A028 | 2026-05-30 | C002 | Material | Material purchase and consumption | 320012.2573 | 310518.47 | C002
CT00089 | P001 | A029 | 2026-06-14 | C002 | Equipment | Equipment operation/rental | 357032.902 | 374536.0103 | BuildPlant Equipment
CT00090 | P001 | A029 | 2026-06-15 | C002 | Subcontract | Subcontractor work | 284832.3905 | 304394.3257 | C002
CT00091 | P001 | A029 | 2026-06-29 | C002 | Material | Material purchase and consumption | 251108.7867 | 270967.2401 | C002
CT00092 | P001 | A030 | 2026-07-13 | C002 | Material | Material purchase and consumption | 357554.4445 | 374672.6022 | C002
CT00093 | P001 | A030 | 2026-07-20 | C002 | Labour | Site labour and workforce cost | 331129.6149 | 350036.3419 | Internal Team
CT00094 | P001 | A030 | 2026-07-20 | C002 | Material | Material purchase and consumption | 251666.6166 | 242643.8185 | C002
CT00095 | P001 | A031 | 2026-08-03 | C002 | Material | Material purchase and consumption | 303203.6645 | 321609.909 | C002
CT00096 | P001 | A031 | 2026-08-12 | C002 | Material | Material purchase and consumption | 278828.7029 | 296394.6046 | C002
CT00097 | P001 | A031 | 2026-08-14 | C002 | Material | Material purchase and consumption | 303340.427 | 294983.1662 | C002
CT00098 | P001 | A032 | 2026-08-16 | C002 | Material | Material purchase and consumption | 260158.773 | 253995.2971 | C002
CT00099 | P001 | A032 | 2026-08-26 | C002 | Material | Material purchase and consumption | 325361.9596 | 320854.1734 | C002
CT00100 | P001 | A032 | 2026-08-30 | C002 | Material | Material purchase and consumption | 366016.1969 | 351769.1928 | C002
CT00101 | P001 | A033 | 2026-09-06 | C002 | Subcontract | Subcontractor work | 319167.4643 | 302314.3253 | C002
CT00102 | P001 | A033 | 2026-09-19 | C002 | Equipment | Equipment operation/rental | 365120.808 | 370037.5043 | BuildPlant Equipment
CT00103 | P001 | A033 | 2026-09-25 | C002 | Material | Material purchase and consumption | 277743.267 | 296834.1825 | C002
CT00104 | P001 | A034 | 2026-09-29 | C002 | Labour | Site labour and workforce cost | 330412.3252 | 347112.7501 | Internal Team
CT00105 | P001 | A034 | 2026-10-12 | C002 | Labour | Site labour and workforce cost | 246885.552 | 247369.17 | Internal Team
CT00106 | P001 | A034 | 2026-10-15 | C002 | Material | Material purchase and consumption | 276972.7556 | 284192.857 | C002
CT00107 | P001 | A035 | 2026-10-20 | C002 | Subcontract | Subcontractor work | 328802.5085 | 340274.4194 | C002
CT00108 | P001 | A035 | 2026-10-25 | C002 | Material | Material purchase and consumption | 305968.3224 | 289142.0876 | C002
CT00109 | P001 | A035 | 2026-10-25 | C002 | Material | Material purchase and consumption | 252653.8603 | 272856.6829 | C002
CT00110 | P001 | A036 | 2026-11-17 | C002 | Subcontract | Subcontractor work | 250072.1028 | 234628.4176 | C002
CT00111 | P001 | A036 | 2026-11-23 | C002 | Material | Material purchase and consumption | 382667.0696 | 410065.6059 | C002
CT00112 | P001 | A036 | 2026-11-26 | C002 | Subcontract | Subcontractor work | 285817.998 | 279194.5609 | C002
CT00113 | P001 | A037 | 2026-05-04 | C002 | Material | Material purchase and consumption | 562344.4644 | 523399.247 | C002
CT00114 | P001 | A037 | 2026-05-10 | C002 | Subcontract | Subcontractor work | 392381.5895 | 402032.9507 | C002
CT00115 | P001 | A037 | 2026-05-11 | C002 | Material | Material purchase and consumption | 468949.0437 | 480613.449 | C002
CT00116 | P001 | A038 | 2026-05-20 | C002 | Subcontract | Subcontractor work | 417299.9913 | 405292.4991 | C002
CT00117 | P001 | A038 | 2026-05-27 | C002 | Labour | Site labour and workforce cost | 476427.7619 | 479261.3749 | Internal Team
CT00118 | P001 | A038 | 2026-05-27 | C002 | Subcontract | Subcontractor work | 458201.4638 | 425990.3219 | C002
CT00119 | P001 | A039 | 2026-06-18 | C002 | Material | Material purchase and consumption | 542372.8468 | 532666.8751 | C002
CT00120 | P001 | A039 | 2026-06-20 | C002 | Material | Material purchase and consumption | 470572.7653 | 473125.576 | C002
CT00121 | P001 | A039 | 2026-06-21 | C002 | Material | Material purchase and consumption | 579324.4379 | 568096.4774 | C002
CT00122 | P001 | A040 | 2026-07-08 | C002 | Subcontract | Subcontractor work | 584886.5192 | 543590.6001 | C002
CT00123 | P001 | A040 | 2026-07-09 | C002 | Material | Material purchase and consumption | 491920.2122 | 507529.3056 | C002
CT00124 | P001 | A040 | 2026-07-15 | C002 | Subcontract | Subcontractor work | 634111.5377 | 629888.4858 | C002
CT00125 | P001 | A041 | 2026-07-26 | C002 | Material | Material purchase and consumption | 566974.9989 | 696127.0904 | C002
CT00126 | P001 | A041 | 2026-07-28 | C002 | Equipment | Equipment operation/rental | 542881.7444 | 642834.2463 | BuildPlant Equipment
CT00127 | P001 | A041 | 2026-08-04 | C002 | Material | Material purchase and consumption | 574915.4253 | 703246.5232 | C002
CT00128 | P001 | A042 | 2026-08-29 | C002 | Material | Material purchase and consumption | 601888.2021 | 616179.2127 | C002
CT00129 | P001 | A042 | 2026-08-30 | C002 | Labour | Site labour and workforce cost | 489656.7322 | 465221.2338 | Internal Team
CT00130 | P001 | A042 | 2026-09-06 | C002 | Material | Material purchase and consumption | 468951.0246 | 484240.906 | C002
CT00131 | P001 | A043 | 2026-09-14 | C002 | Subcontract | Subcontractor work | 457039.4436 | 491560.1941 | C002
CT00132 | P001 | A043 | 2026-09-16 | C002 | Equipment | Equipment operation/rental | 563087.0441 | 573044.4055 | BuildPlant Equipment
CT00133 | P001 | A043 | 2026-09-25 | C002 | Material | Material purchase and consumption | 460945.2638 | 446130.4936 | C002
CT00134 | P001 | A044 | 2026-10-03 | C002 | Labour | Site labour and workforce cost | 568521.2474 | 609352.3303 | Internal Team
CT00135 | P001 | A044 | 2026-10-05 | C002 | Material | Material purchase and consumption | 575408.2772 | 572797.3221 | C002
CT00136 | P001 | A044 | 2026-10-18 | C002 | Material | Material purchase and consumption | 506441.5386 | 501266.6317 | C002
CT00137 | P001 | A045 | 2026-10-28 | C002 | Material | Material purchase and consumption | 636227.4014 | 593344.9915 | C002
CT00138 | P001 | A045 | 2026-11-02 | C002 | Labour | Site labour and workforce cost | 480594.2855 | 456042.1611 | Internal Team
CT00139 | P001 | A045 | 2026-11-12 | C002 | Subcontract | Subcontractor work | 472290.7209 | 456230.7974 | C002
CT00140 | P001 | A046 | 2026-11-21 | C002 | Equipment | Equipment operation/rental | 390811.073 | 363734.3071 | BuildPlant Equipment
CT00141 | P001 | A046 | 2026-11-24 | C002 | Material | Material purchase and consumption | 485334.7636 | 452741.8024 | C002
CT00142 | P001 | A046 | 2026-11-29 | C002 | Subcontract | Subcontractor work | 449496.0471 | 484450.9988 | C002
CT00143 | P001 | A047 | 2026-12-13 | C002 | Labour | Site labour and workforce cost | 478567.4959 | 503587.951 | Internal Team
CT00144 | P001 | A047 | 2026-12-15 | C002 | Material | Material purchase and consumption | 417838.0406 | 413050.7964 | C002
CT00145 | P001 | A047 | 2026-12-17 | C002 | Labour | Site labour and workforce cost | 558389.2714 | 591288.3558 | Internal Team
CT00146 | P001 | A048 | 2026-04-23 | C002 | Material | Material purchase and consumption | 293534.3783 | 320330.4588 | C002
CT00147 | P001 | A048 | 2026-05-01 | C002 | Material | Material purchase and consumption | 311856.3097 | 381100.9263 | C002
CT00148 | P001 | A048 | 2026-05-10 | C002 | Material | Material purchase and consumption | 209738.5941 | 227364.7332 | C002
CT00149 | P001 | A048 | 2026-05-10 | C002 | Labour | Site labour and workforce cost | 205430.1233 | 251675.963 | Internal Team
CT00150 | P001 | A048 | 2026-05-22 | C002 | Material | Material purchase and consumption | 228980.8606 | 268641.8257 | C002
CT00151 | P001 | A049 | 2026-06-02 | C003 | Subcontract | Subcontractor work | 1521845.8956 | 1464214.756 | C003
CT00152 | P001 | A049 | 2026-06-20 | C003 | Material | Material purchase and consumption | 1336150.3011 | 1307627.4608 | C003
CT00153 | P001 | A049 | 2026-06-30 | C003 | Labour | Site labour and workforce cost | 1407790.8071 | 1399282.7794 | Internal Team
CT00154 | P001 | A049 | 2026-07-05 | C003 | Material | Material purchase and consumption | 1272304.2093 | 1232706.1556 | C003
CT00155 | P001 | A049 | 2026-07-24 | C003 | Material | Material purchase and consumption | 1219343.9781 | 1193015.3658 | C003
CT00156 | P001 | A049 | 2026-07-26 | C003 | Equipment | Equipment operation/rental | 1149066.3864 | 1217477.9937 | BuildPlant Equipment
CT00157 | P001 | A049 | 2026-08-02 | C003 | Labour | Site labour and workforce cost | 1463976.005 | 1378195.5433 | Internal Team
CT00158 | P001 | A050 | 2026-06-22 | C003 | Material | Material purchase and consumption | 951781.7598 | 930340.6899 | C003
CT00159 | P001 | A050 | 2026-07-02 | C003 | Material | Material purchase and consumption | 637425.5855 | 647133.766 | C003
CT00160 | P001 | A050 | 2026-07-17 | C003 | Labour | Site labour and workforce cost | 1050993.8275 | 1010235.0127 | Internal Team
CT00161 | P001 | A050 | 2026-07-18 | C003 | Subcontract | Subcontractor work | 712754.1326 | 669866.3927 | C003
CT00162 | P001 | A050 | 2026-07-22 | C003 | Material | Material purchase and consumption | 867060.9646 | 880440.7696 | C003
CT00163 | P001 | A050 | 2026-08-06 | C003 | Labour | Site labour and workforce cost | 967051.7594 | 1006209.3522 | Internal Team
CT00164 | P001 | A050 | 2026-08-17 | C003 | Material | Material purchase and consumption | 1009353.4431 | 1058734.6793 | C003
CT00165 | P001 | A050 | 2026-08-26 | C003 | Labour | Site labour and workforce cost | 737128.3007 | 743718.5113 | Internal Team
CT00166 | P001 | A051 | 2026-07-05 | C003 | Subcontract | Subcontractor work | 193556.5695 | 193157.5462 | C003
CT00167 | P001 | A051 | 2026-07-09 | C003 | Labour | Site labour and workforce cost | 152692.2705 | 146259.6992 | Internal Team
CT00168 | P001 | A051 | 2026-07-23 | C003 | Subcontract | Subcontractor work | 192625.4543 | 179291.8989 | C003
CT00169 | P001 | A051 | 2026-07-27 | C003 | Material | Material purchase and consumption | 230988.8833 | 217086.8148 | C003
CT00170 | P001 | A052 | 2026-08-08 | C004 | Labour | Site labour and workforce cost | 574075.9454 | 592195.9556 | Internal Team
CT00171 | P001 | A052 | 2026-08-08 | C004 | Material | Material purchase and consumption | 773946.0492 | 784783.991 | C004
CT00172 | P001 | A052 | 2026-08-12 | C004 | Labour | Site labour and workforce cost | 681768.6336 | 674910.373 | Internal Team
CT00173 | P001 | A052 | 2026-08-15 | C004 | Labour | Site labour and workforce cost | 710678.0551 | 767267.0622 | Internal Team
CT00174 | P001 | A052 | 2026-08-25 | C004 | Labour | Site labour and workforce cost | 523022.6371 | 498118.833 | Internal Team
CT00175 | P001 | A052 | 2026-09-26 | C004 | Labour | Site labour and workforce cost | 642422.894 | 640508.5146 | Internal Team
CT00176 | P001 | A052 | 2026-09-27 | C004 | Labour | Site labour and workforce cost | 652544.4821 | 605464.6034 | Internal Team
CT00177 | P001 | A052 | 2026-10-02 | C004 | Material | Material purchase and consumption | 599847.0837 | 607810.9667 | C004
CT00178 | P001 | A053 | 2026-09-06 | C004 | Labour | Site labour and workforce cost | 556086.797 | 589272.9195 | Internal Team
CT00179 | P001 | A053 | 2026-09-22 | C004 | Labour | Site labour and workforce cost | 597682.7126 | 558513.7509 | Internal Team
CT00180 | P001 | A053 | 2026-09-24 | C004 | Labour | Site labour and workforce cost | 573881.1293 | 548330.8384 | Internal Team
CT00181 | P001 | A053 | 2026-09-26 | C004 | Material | Material purchase and consumption | 612758.8278 | 644861.5915 | C004
CT00182 | P001 | A053 | 2026-09-30 | C004 | Labour | Site labour and workforce cost | 574205.1491 | 582598.89 | Internal Team
CT00183 | P001 | A053 | 2026-10-03 | C004 | Material | Material purchase and consumption | 504299.3673 | 499962.3944 | C004
CT00184 | P001 | A053 | 2026-10-12 | C004 | Material | Material purchase and consumption | 648441.1485 | 671610.7632 | C004
CT00185 | P001 | A054 | 2026-08-29 | C008 | Material | Material purchase and consumption | 230971.5746 | 231162.0207 | C008
CT00186 | P001 | A054 | 2026-09-01 | C008 | Material | Material purchase and consumption | 163942.3954 | 153600.9127 | C008
CT00187 | P001 | A054 | 2026-09-01 | C008 | Material | Material purchase and consumption | 173719.8721 | 182495.6618 | C008
CT00188 | P001 | A054 | 2026-09-07 | C008 | Material | Material purchase and consumption | 177975.894 | 185735.8083 | C008
CT00189 | P001 | A055 | 2026-11-23 | C008 | Labour | Site labour and workforce cost | 340776.9408 | 361696.0803 | Internal Team
CT00190 | P001 | A055 | 2026-12-07 | C008 | Other | Site overhead and miscellaneous | 284363.641 | 286741.063 | Internal Team
CT00191 | P001 | A055 | 2026-12-14 | C008 | Material | Material purchase and consumption | 240713.5926 | 253016.9748 | C008
CT00192 | P001 | A055 | 2026-12-14 | C008 | Material | Material purchase and consumption | 281053.1304 | 260092.3136 | C008
CT00193 | P001 | A056 | 2026-10-08 | C004 | Material | Material purchase and consumption | 1017929.9727 | 974400.3793 | C004
CT00194 | P001 | A056 | 2026-10-27 | C004 | Subcontract | Subcontractor work | 1489608.4758 | 1405197.0828 | C004
CT00195 | P001 | A056 | 2026-11-07 | C004 | Subcontract | Subcontractor work | 1100770.3906 | 1109332.4573 | C004
CT00196 | P001 | A056 | 2026-11-12 | C004 | Material | Material purchase and consumption | 1093396.1515 | 1034476.3892 | C004
CT00197 | P001 | A056 | 2026-11-14 | C004 | Labour | Site labour and workforce cost | 1315364.1041 | 1287603.2439 | Internal Team
CT00198 | P001 | A056 | 2026-11-19 | C004 | Material | Material purchase and consumption | 1355426.5447 | 1444820.7944 | C004
CT00199 | P001 | A056 | 2026-11-24 | C004 | Material | Material purchase and consumption | 1052508.1213 | 1122130.8868 | C004
CT00200 | P001 | A056 | 2026-12-04 | C004 | Material | Material purchase and consumption | 1531587.3542 | 1612231.5752 | C004
CT00201 | P001 | A057 | 2026-10-12 | C004 | Material | Material purchase and consumption | 645168.2526 | 638663.8509 | C004
CT00202 | P001 | A057 | 2026-10-30 | C004 | Other | Site overhead and miscellaneous | 591337.6246 | 567667.665 | Internal Team
CT00203 | P001 | A057 | 2026-11-01 | C004 | Material | Material purchase and consumption | 651710.8525 | 638705.6381 | C004
CT00204 | P001 | A057 | 2026-11-07 | C004 | Labour | Site labour and workforce cost | 793906.6767 | 752360.2456 | Internal Team
CT00205 | P001 | A057 | 2026-11-07 | C004 | Material | Material purchase and consumption | 584892.5039 | 565610.7477 | C004
CT00206 | P001 | A057 | 2026-11-08 | C004 | Material | Material purchase and consumption | 656777.9495 | 656702.3157 | C004
CT00207 | P001 | A057 | 2026-11-08 | C004 | Material | Material purchase and consumption | 689059.4353 | 738671.9099 | C004
CT00208 | P001 | A058 | 2026-10-16 | C004 | Material | Material purchase and consumption | 281026.8945 | 322430.894 | C004
CT00209 | P001 | A058 | 2026-11-02 | C004 | Material | Material purchase and consumption | 205867.3693 | 225834.8192 | C004
CT00210 | P001 | A058 | 2026-11-05 | C004 | Material | Material purchase and consumption | 287845.8842 | 359589.8591 | C004
CT00211 | P001 | A058 | 2026-11-19 | C004 | Labour | Site labour and workforce cost | 202468.0041 | 237857.2234 | Internal Team
CT00212 | P001 | A058 | 2026-11-28 | C004 | Labour | Site labour and workforce cost | 300670.4548 | 366983.841 | Internal Team
CT00213 | P001 | A058 | 2026-11-29 | C004 | Labour | Site labour and workforce cost | 273180.9404 | 323824.7848 | Internal Team
CT00214 | P001 | A058 | 2026-12-18 | C004 | Material | Material purchase and consumption | 293419.6891 | 359739.6579 | C004
CT00215 | P001 | A059 | 2026-09-26 | C004 | Material | Material purchase and consumption | 1766487.2487 | 1842138.4169 | C004
CT00216 | P001 | A059 | 2026-10-03 | C004 | Material | Material purchase and consumption | 2222192.4271 | 2276437.8337 | C004
CT00217 | P001 | A059 | 2026-10-04 | C004 | Material | Material purchase and consumption | 1508381.0752 | 1459000.4908 | C004
CT00218 | P001 | A059 | 2026-10-15 | C004 | Material | Material purchase and consumption | 2240938.4185 | 2093479.1105 | C004
CT00219 | P001 | A059 | 2026-10-21 | C004 | Material | Material purchase and consumption | 1770651.8509 | 1896015.3106 | C004
CT00220 | P001 | A059 | 2026-11-28 | C004 | Material | Material purchase and consumption | 2275617.3528 | 2243286.5382 | C004
CT00221 | P001 | A059 | 2026-11-29 | C004 | Material | Material purchase and consumption | 2012582.8247 | 1998654.3341 | C004
CT00222 | P001 | A060 | 2026-10-03 | C005 | Material | Material purchase and consumption | 560885.5622 | 587680.9639 | C005
CT00223 | P001 | A060 | 2026-10-09 | C005 | Labour | Site labour and workforce cost | 663999.2349 | 733105.676 | Internal Team
CT00224 | P001 | A060 | 2026-10-12 | C005 | Material | Material purchase and consumption | 675604.5942 | 749227.2053 | C005
CT00225 | P001 | A060 | 2026-11-06 | C005 | Subcontract | Subcontractor work | 691761.4487 | 726730.1704 | C005
CT00226 | P001 | A060 | 2026-11-09 | C005 | Labour | Site labour and workforce cost | 683950.5818 | 739630.4427 | Internal Team
CT00227 | P001 | A060 | 2026-11-26 | C005 | Material | Material purchase and consumption | 540701.7424 | 584192.3574 | C005
CT00228 | P001 | A060 | 2026-11-30 | C005 | Labour | Site labour and workforce cost | 518231.9128 | 547237.2341 | Internal Team
CT00229 | P001 | A060 | 2026-12-06 | C005 | Material | Material purchase and consumption | 489744.6576 | 508070.1774 | C005
CT00230 | P001 | A061 | 2026-11-16 | C005 | Material | Material purchase and consumption | 474596.8524 | 480282.0703 | C005
CT00231 | P001 | A061 | 2026-11-19 | C005 | Material | Material purchase and consumption | 496214.5387 | 479625.1223 | C005
CT00232 | P001 | A061 | 2026-11-22 | C005 | Material | Material purchase and consumption | 500139.6165 | 518497.5779 | C005
CT00233 | P001 | A061 | 2026-11-23 | C005 | Material | Material purchase and consumption | 482737.4638 | 495449.2705 | C005
CT00234 | P001 | A061 | 2026-11-24 | C005 | Labour | Site labour and workforce cost | 492732.0336 | 531606.5304 | Internal Team
CT00235 | P001 | A061 | 2026-12-08 | C005 | Material | Material purchase and consumption | 403234.1995 | 423487.2458 | C005
CT00236 | P001 | A061 | 2026-12-11 | C005 | Labour | Site labour and workforce cost | 471361.7495 | 467807.3173 | Internal Team
CT00237 | P001 | A062 | 2026-08-25 | C006 | Material | Material purchase and consumption | 331686.6738 | 335657.4001 | C006
CT00238 | P001 | A062 | 2026-09-04 | C006 | Subcontract | Subcontractor work | 415586.499 | 423185.538 | C006
CT00239 | P001 | A062 | 2026-09-23 | C006 | Material | Material purchase and consumption | 411361.9889 | 404691.002 | C006
CT00240 | P001 | A062 | 2026-09-24 | C006 | Material | Material purchase and consumption | 416559.8005 | 422025.007 | C006
CT00241 | P001 | A062 | 2026-10-07 | C006 | Material | Material purchase and consumption | 422707.7033 | 420823.7425 | C006
CT00242 | P001 | A062 | 2026-10-10 | C006 | Material | Material purchase and consumption | 489642.7092 | 508887.4689 | C006
CT00243 | P001 | A062 | 2026-11-14 | C006 | Subcontract | Subcontractor work | 388991.2069 | 407698.7038 | C006
CT00244 | P001 | A062 | 2026-11-15 | C006 | Subcontract | Subcontractor work | 497208.7038 | 469642.8332 | C006
CT00245 | P001 | A063 | 2026-10-25 | C006 | Labour | Site labour and workforce cost | 242574.051 | 229605.6941 | Internal Team
CT00246 | P001 | A063 | 2026-11-07 | C006 | Material | Material purchase and consumption | 236936.5181 | 219200.3752 | C006
CT00247 | P001 | A063 | 2026-11-12 | C006 | Material | Material purchase and consumption | 193387.2638 | 204858.4819 | C006
CT00248 | P001 | A063 | 2026-11-26 | C006 | Subcontract | Subcontractor work | 223565.4046 | 224736.5449 | C006
CT00249 | P001 | A063 | 2026-12-02 | C006 | Material | Material purchase and consumption | 192831.8254 | 202467.1519 | C006
CT00250 | P001 | A063 | 2026-12-07 | C006 | Subcontract | Subcontractor work | 225690.6084 | 224549.7088 | C006
CT00251 | P001 | A063 | 2026-12-09 | C006 | Other | Site overhead and miscellaneous | 244375.1859 | 233816.1453 | Internal Team
CT00252 | P001 | A064 | 2026-08-27 | C007 | Material | Material purchase and consumption | 430126.7829 | 451285.399 | C007
CT00253 | P001 | A064 | 2026-09-06 | C007 | Material | Material purchase and consumption | 396566.4291 | 390877.5319 | C007
CT00254 | P001 | A064 | 2026-09-13 | C007 | Subcontract | Subcontractor work | 356521.7434 | 370258.6819 | C007
CT00255 | P001 | A064 | 2026-09-24 | C007 | Material | Material purchase and consumption | 488356.5293 | 459966.475 | C007
CT00256 | P001 | A064 | 2026-10-15 | C007 | Material | Material purchase and consumption | 404726.4496 | 430169.4966 | C007
CT00257 | P001 | A064 | 2026-10-23 | C007 | Other | Site overhead and miscellaneous | 321203.6797 | 310861.3874 | Internal Team
CT00258 | P001 | A064 | 2026-11-08 | C007 | Material | Material purchase and consumption | 439265.2884 | 427604.9991 | C007
CT00259 | P001 | A064 | 2026-11-26 | C007 | Labour | Site labour and workforce cost | 378774.6592 | 376352.7731 | Internal Team
CT00260 | P001 | A065 | 2026-10-28 | C007 | Labour | Site labour and workforce cost | 208409.0475 | 197960.6551 | Internal Team
CT00261 | P001 | A065 | 2026-11-04 | C007 | Material | Material purchase and consumption | 243922.4426 | 225694.0605 | C007
CT00262 | P001 | A065 | 2026-11-08 | C007 | Subcontract | Subcontractor work | 210732.7464 | 218285.8211 | C007
CT00263 | P001 | A065 | 2026-11-09 | C007 | Material | Material purchase and consumption | 285494.6963 | 266345.3274 | C007
CT00264 | P001 | A065 | 2026-11-25 | C007 | Subcontract | Subcontractor work | 290953.7774 | 304803.9781 | C007
CT00265 | P001 | A065 | 2026-12-06 | C007 | Material | Material purchase and consumption | 289440.0104 | 298629.3165 | C007
CT00266 | P001 | A065 | 2026-12-11 | C007 | Subcontract | Subcontractor work | 265557.2675 | 266623.458 | C007
CT00267 | P001 | A066 | 2026-10-20 | C001 | Material | Material purchase and consumption | 224190.0223 | 212058.0226 | C001
CT00268 | P001 | A066 | 2026-11-08 | C001 | Material | Material purchase and consumption | 206956.1345 | 219784.8618 | C001
CT00269 | P001 | A066 | 2026-11-17 | C001 | Other | Site overhead and miscellaneous | 139398.7839 | 145065.9703 | Internal Team
CT00270 | P001 | A066 | 2026-11-19 | C001 | Material | Material purchase and consumption | 166925.2789 | 170894.0086 | C001
CT00271 | P001 | A066 | 2026-11-25 | C001 | Labour | Site labour and workforce cost | 181264.3376 | 174296.3118 | Internal Team
CT00272 | P001 | A066 | 2026-12-04 | C001 | Equipment | Equipment operation/rental | 147169.9226 | 138150.1072 | BuildPlant Equipment
CT00273 | P001 | A067 | 2026-11-06 | C001 | Material | Material purchase and consumption | 656961.4607 | 612302.735 | C001
CT00274 | P001 | A067 | 2026-11-06 | C001 | Labour | Site labour and workforce cost | 629952.4952 | 679184.2819 | Internal Team
CT00275 | P001 | A067 | 2026-11-13 | C001 | Labour | Site labour and workforce cost | 659980.7483 | 668393.0973 | Internal Team
CT00276 | P001 | A067 | 2026-11-20 | C001 | Labour | Site labour and workforce cost | 598152.9556 | 584112.1093 | Internal Team
CT00277 | P001 | A067 | 2026-12-06 | C001 | Other | Site overhead and miscellaneous | 612980.2176 | 639499.741 | Internal Team
CT00278 | P001 | A067 | 2026-12-14 | C001 | Material | Material purchase and consumption | 702626.7603 | 701779.4393 | C001
CT00279 | P001 | A068 | 2026-12-02 | C001 | Material | Material purchase and consumption | 214685.5358 | 203204.2546 | C001
CT00280 | P001 | A068 | 2026-12-12 | C001 | Material | Material purchase and consumption | 196982.9409 | 208746.445 | C001
CT00281 | P001 | A068 | 2026-12-15 | C001 | Material | Material purchase and consumption | 279671.9416 | 259085.6912 | C001
CT00282 | P001 | A068 | 2026-12-16 | C001 | Labour | Site labour and workforce cost | 194857.269 | 196686.5671 | Internal Team

## Labour
Labour_ID | Project_ID | Activity_ID | Date | Contractor_ID | Labour_Type | Number_of_Workers | Working_Hours | Man_Hours | Overtime_Hours | Productivity_Quantity | Productivity_Unit | Productivity_Rate
LB00001 | P001 | A001 | 2026-01-03 | C001 | Unskilled | 4 | 9 | 36 | 0 | 0.039586 | lot | 0.0010996
LB00002 | P001 | A001 | 2026-01-06 | C001 | Unskilled | 10 | 9 | 90 | 2 | 0.040597 | lot | 0.00045108
LB00003 | P001 | A001 | 2026-01-06 | C001 | Skilled | 10 | 9 | 90 | 2 | 0.040551 | lot | 0.00045057
LB00004 | P001 | A001 | 2026-01-08 | C001 | Semi-skilled | 13 | 8 | 104 | 0 | 0.037396 | lot | 0.00035958
LB00005 | P001 | A002 | 2026-01-04 | C001 | Skilled | 7 | 8 | 56 | 0 | 385.274 | m² | 6.8799
LB00006 | P001 | A002 | 2026-01-07 | C001 | Semi-skilled | 6 | 8 | 48 | 0 | 430.2052 | m² | 8.9626
LB00007 | P001 | A002 | 2026-01-07 | C001 | Semi-skilled | 6 | 9 | 54 | 0 | 438.1279 | m² | 8.1135
LB00008 | P001 | A002 | 2026-01-08 | C001 | Semi-skilled | 8 | 8 | 64 | 0 | 472.0466 | m² | 7.3757
LB00009 | P001 | A003 | 2026-01-11 | C001 | Unskilled | 7 | 8 | 56 | 1 | 0.047213 | lot | 0.00084309
LB00010 | P001 | A003 | 2026-01-11 | C001 | Semi-skilled | 10 | 8 | 80 | 0 | 0.044649 | lot | 0.00055811
LB00011 | P001 | A003 | 2026-01-13 | C001 | Semi-skilled | 6 | 9 | 54 | 0 | 0.052577 | lot | 0.00097364
LB00012 | P001 | A003 | 2026-01-21 | C001 | Unskilled | 5 | 8 | 40 | 0 | 0.051483 | lot | 0.0012871
LB00013 | P001 | A004 | 2026-01-08 | C001 | Skilled | 3 | 8 | 24 | 0 | 0.13294 | lot | 0.0055392
LB00014 | P001 | A004 | 2026-01-08 | C001 | Skilled | 6 | 8 | 48 | 0 | 0.11316 | lot | 0.0023575
LB00015 | P001 | A004 | 2026-01-11 | C001 | Skilled | 10 | 8 | 80 | 0 | 0.1214 | lot | 0.0015175
LB00016 | P001 | A004 | 2026-01-14 | C001 | Unskilled | 8 | 8 | 64 | 0 | 0.1153 | lot | 0.0018015
LB00017 | P001 | A005 | 2026-01-16 | C001 | Semi-skilled | 19 | 8 | 152 | 2 | 84.4427 | m³ | 0.55554
LB00018 | P001 | A005 | 2026-01-17 | C001 | Semi-skilled | 16 | 8 | 128 | 0 | 98.0086 | m³ | 0.76569
LB00019 | P001 | A005 | 2026-02-07 | C001 | Unskilled | 14 | 8 | 112 | 0 | 111.2896 | m³ | 0.99366
LB00020 | P001 | A005 | 2026-02-10 | C001 | Unskilled | 15 | 8 | 120 | 0 | 99.6949 | m³ | 0.83079
LB00021 | P001 | A006 | 2026-02-04 | C001 | Skilled | 16 | 9 | 144 | 0 | 114.8658 | m³ | 0.79768
LB00022 | P001 | A006 | 2026-02-11 | C001 | Unskilled | 14 | 9 | 126 | 2 | 76.2784 | m³ | 0.60538
LB00023 | P001 | A006 | 2026-02-11 | C001 | Semi-skilled | 14 | 8 | 112 | 0 | 91.3865 | m³ | 0.81595
LB00024 | P001 | A006 | 2026-02-14 | C001 | Semi-skilled | 15 | 8 | 120 | 0 | 95.7399 | m³ | 0.79783
LB00025 | P001 | A007 | 2026-02-09 | C001 | Unskilled | 18 | 9 | 162 | 1 | 129.9113 | m³ | 0.80192
LB00026 | P001 | A007 | 2026-02-13 | C001 | Skilled | 11 | 9 | 99 | 0 | 101.9296 | m³ | 1.0296
LB00027 | P001 | A007 | 2026-02-14 | C001 | Skilled | 7 | 8 | 56 | 2 | 99.1068 | m³ | 1.7698
LB00028 | P001 | A007 | 2026-02-14 | C001 | Semi-skilled | 15 | 8 | 120 | 0 | 133.1109 | m³ | 1.1093
LB00029 | P001 | A008 | 2026-01-20 | C001 | Unskilled | 14 | 8 | 112 | 0 | 109.652 | m³ | 0.97904
LB00030 | P001 | A008 | 2026-01-31 | C001 | Skilled | 13 | 8 | 104 | 0 | 71.3352 | m³ | 0.68592
LB00031 | P001 | A008 | 2026-02-04 | C001 | Unskilled | 12 | 9 | 108 | 0 | 108.001 | m³ | 1
LB00032 | P001 | A008 | 2026-02-06 | C001 | Semi-skilled | 14 | 8 | 112 | 0 | 82.8806 | m³ | 0.74001
LB00033 | P001 | A009 | 2026-02-17 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 29.2192 | m³ | 0.26089
LB00034 | P001 | A009 | 2026-02-18 | C002 | Unskilled | 16 | 8 | 128 | 1 | 26.7375 | m³ | 0.20889
LB00035 | P001 | A009 | 2026-02-25 | C002 | Unskilled | 21 | 8 | 168 | 1 | 21.8799 | m³ | 0.13024
LB00036 | P001 | A009 | 2026-03-04 | C002 | Semi-skilled | 21 | 8 | 168 | 0 | 21.4646 | m³ | 0.12777
LB00037 | P001 | A010 | 2026-02-21 | C002 | Semi-skilled | 16 | 8 | 128 | 1 | 3.8075 | tonne | 0.029746
LB00038 | P001 | A010 | 2026-03-04 | C002 | Semi-skilled | 18 | 9 | 162 | 0 | 3.6827 | tonne | 0.022733
LB00039 | P001 | A010 | 2026-03-05 | C002 | Skilled | 15 | 9 | 135 | 2 | 3.0376 | tonne | 0.022501
LB00040 | P001 | A010 | 2026-03-16 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 3.6909 | tonne | 0.024282
LB00041 | P001 | A011 | 2026-03-03 | C002 | Skilled | 13 | 8 | 104 | 0 | 23.5707 | m³ | 0.22664
LB00042 | P001 | A011 | 2026-03-03 | C002 | Unskilled | 15 | 8 | 120 | 1 | 23.0574 | m³ | 0.19214
LB00043 | P001 | A011 | 2026-03-12 | C002 | Unskilled | 17 | 9 | 153 | 2 | 19.2855 | m³ | 0.12605
LB00044 | P001 | A011 | 2026-03-24 | C002 | Skilled | 18 | 8 | 144 | 0 | 23.4877 | m³ | 0.16311
LB00045 | P001 | A012 | 2026-03-17 | C002 | Skilled | 17 | 8 | 136 | 0 | 11.3686 | m³ | 0.083592
LB00046 | P001 | A012 | 2026-03-25 | C002 | Semi-skilled | 12 | 8 | 96 | 1 | 7.7901 | m³ | 0.081146
LB00047 | P001 | A012 | 2026-03-27 | C002 | Skilled | 16 | 8 | 128 | 2 | 10.6774 | m³ | 0.083418
LB00048 | P001 | A012 | 2026-03-28 | C002 | Skilled | 22 | 8 | 176 | 0 | 10.3599 | m³ | 0.058863
LB00049 | P001 | A013 | 2026-03-29 | C002 | Semi-skilled | 16 | 8 | 128 | 1 | 10.7004 | m³ | 0.083597
LB00050 | P001 | A013 | 2026-04-01 | C002 | Semi-skilled | 13 | 8 | 104 | 2 | 7.7571 | m³ | 0.074588
LB00051 | P001 | A013 | 2026-04-11 | C002 | Skilled | 15 | 9 | 135 | 1 | 11.1606 | m³ | 0.082671
LB00052 | P001 | A013 | 2026-04-12 | C002 | Semi-skilled | 12 | 8 | 96 | 1 | 7.3642 | m³ | 0.076711
LB00053 | P001 | A014 | 2026-04-12 | C001 | Semi-skilled | 20 | 8 | 160 | 0 | 97.5175 | m | 0.60948
LB00054 | P001 | A014 | 2026-04-12 | C001 | Semi-skilled | 23 | 9 | 207 | 0 | 79.548 | m | 0.38429
LB00055 | P001 | A014 | 2026-04-15 | C001 | Semi-skilled | 22 | 8 | 176 | 0 | 100.6235 | m | 0.57172
LB00056 | P001 | A014 | 2026-04-18 | C001 | Unskilled | 18 | 8 | 144 | 2 | 98.4354 | m | 0.68358
LB00057 | P001 | A015 | 2026-04-01 | C002 | Skilled | 21 | 8 | 168 | 0 | 4.0063 | m³ | 0.023847
LB00058 | P001 | A015 | 2026-04-07 | C002 | Unskilled | 16 | 9 | 144 | 1 | 5.0193 | m³ | 0.034856
LB00059 | P001 | A015 | 2026-04-11 | C002 | Semi-skilled | 16 | 8 | 128 | 0 | 5.8179 | m³ | 0.045453
LB00060 | P001 | A015 | 2026-04-12 | C002 | Unskilled | 11 | 8 | 88 | 0 | 3.8568 | m³ | 0.043827
LB00061 | P001 | A016 | 2026-04-21 | C002 | Unskilled | 18 | 8 | 144 | 0 | 5.9086 | m³ | 0.041032
LB00062 | P001 | A016 | 2026-04-24 | C002 | Semi-skilled | 18 | 8 | 144 | 1 | 4.4958 | m³ | 0.031221
LB00063 | P001 | A016 | 2026-04-25 | C002 | Skilled | 19 | 8 | 152 | 2 | 4.429 | m³ | 0.029138
LB00064 | P001 | A016 | 2026-04-27 | C002 | Unskilled | 17 | 8 | 136 | 1 | 4.7654 | m³ | 0.03504
LB00065 | P001 | A017 | 2026-05-11 | C002 | Skilled | 16 | 9 | 144 | 0 | 4.6293 | m³ | 0.032148
LB00066 | P001 | A017 | 2026-05-11 | C002 | Skilled | 19 | 9 | 171 | 0 | 4.7007 | m³ | 0.02749
LB00067 | P001 | A017 | 2026-05-17 | C002 | Semi-skilled | 15 | 8 | 120 | 0 | 5.3 | m³ | 0.044167
LB00068 | P001 | A017 | 2026-05-20 | C002 | Semi-skilled | 14 | 8 | 112 | 2 | 3.9712 | m³ | 0.035457
LB00069 | P001 | A018 | 2026-05-28 | C002 | Unskilled | 18 | 8 | 144 | 0 | 5.498 | m³ | 0.038181
LB00070 | P001 | A018 | 2026-06-01 | C002 | Skilled | 18 | 8 | 144 | 0 | 5.991 | m³ | 0.041604
LB00071 | P001 | A018 | 2026-06-09 | C002 | Unskilled | 15 | 8 | 120 | 1 | 5.4039 | m³ | 0.045033
LB00072 | P001 | A018 | 2026-06-09 | C002 | Unskilled | 20 | 8 | 160 | 0 | 3.7519 | m³ | 0.023449
LB00073 | P001 | A019 | 2026-06-18 | C002 | Skilled | 21 | 8 | 168 | 0 | 3.908 | m³ | 0.023262
LB00074 | P001 | A019 | 2026-06-21 | C002 | Unskilled | 16 | 8 | 128 | 0 | 5.96 | m³ | 0.046563
LB00075 | P001 | A019 | 2026-06-22 | C002 | Skilled | 15 | 8 | 120 | 1 | 5.1018 | m³ | 0.042515
LB00076 | P001 | A019 | 2026-06-26 | C002 | Skilled | 16 | 8 | 128 | 0 | 3.9224 | m³ | 0.030644
LB00077 | P001 | A020 | 2026-07-10 | C002 | Unskilled | 16 | 8 | 128 | 2 | 5.2755 | m³ | 0.041215
LB00078 | P001 | A020 | 2026-07-15 | C002 | Unskilled | 16 | 8 | 128 | 0 | 3.7598 | m³ | 0.029374
LB00079 | P001 | A020 | 2026-07-19 | C002 | Unskilled | 18 | 9 | 162 | 0 | 5.4629 | m³ | 0.033722
LB00080 | P001 | A020 | 2026-07-22 | C002 | Skilled | 15 | 9 | 135 | 0 | 6.059 | m³ | 0.044881
LB00081 | P001 | A021 | 2026-07-26 | C002 | Skilled | 20 | 8 | 160 | 0 | 4.9952 | m³ | 0.03122
LB00082 | P001 | A021 | 2026-07-26 | C002 | Semi-skilled | 14 | 9 | 126 | 0 | 5.6236 | m³ | 0.044632
LB00083 | P001 | A021 | 2026-07-26 | C002 | Skilled | 19 | 8 | 152 | 2 | 5.4634 | m³ | 0.035943
LB00084 | P001 | A021 | 2026-08-08 | C002 | Unskilled | 19 | 8 | 152 | 1 | 5.8385 | m³ | 0.038411
LB00085 | P001 | A022 | 2026-08-12 | C002 | Skilled | 16 | 9 | 144 | 0 | 5.109 | m³ | 0.035479
LB00086 | P001 | A022 | 2026-08-13 | C002 | Unskilled | 21 | 9 | 189 | 0 | 4.5894 | m³ | 0.024283
LB00087 | P001 | A022 | 2026-08-19 | C002 | Skilled | 27 | 9 | 243 | 0 | 5.0556 | m³ | 0.020805
LB00088 | P001 | A022 | 2026-08-27 | C002 | Unskilled | 19 | 8 | 152 | 1 | 5.315 | m³ | 0.034967
LB00089 | P001 | A023 | 2026-09-02 | C002 | Skilled | 15 | 8 | 120 | 1 | 4.8379 | m³ | 0.040316
LB00090 | P001 | A023 | 2026-09-03 | C002 | Skilled | 15 | 8 | 120 | 0 | 3.9748 | m³ | 0.033124
LB00091 | P001 | A023 | 2026-09-14 | C002 | Skilled | 15 | 8 | 120 | 2 | 4.3909 | m³ | 0.036591
LB00092 | P001 | A023 | 2026-09-14 | C002 | Skilled | 20 | 8 | 160 | 2 | 5.0167 | m³ | 0.031354
LB00093 | P001 | A024 | 2026-09-24 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 5.5543 | m³ | 0.049592
LB00094 | P001 | A024 | 2026-10-01 | C002 | Semi-skilled | 18 | 8 | 144 | 2 | 4.9943 | m³ | 0.034682
LB00095 | P001 | A024 | 2026-10-03 | C002 | Semi-skilled | 18 | 8 | 144 | 0 | 5.559 | m³ | 0.038604
LB00096 | P001 | A024 | 2026-10-05 | C002 | Skilled | 13 | 8 | 104 | 0 | 3.8467 | m³ | 0.036987
LB00097 | P001 | A025 | 2026-10-08 | C002 | Semi-skilled | 15 | 9 | 135 | 0 | 4.7961 | m³ | 0.035526
LB00098 | P001 | A025 | 2026-10-09 | C002 | Unskilled | 15 | 8 | 120 | 2 | 4.0654 | m³ | 0.033878
LB00099 | P001 | A025 | 2026-10-10 | C002 | Semi-skilled | 21 | 8 | 168 | 1 | 5.3473 | m³ | 0.031829
LB00100 | P001 | A025 | 2026-10-20 | C002 | Unskilled | 16 | 8 | 128 | 0 | 4.9501 | m³ | 0.038672
LB00101 | P001 | A026 | 2026-04-14 | C002 | Skilled | 16 | 8 | 128 | 0 | 4.1601 | m³ | 0.032501
LB00102 | P001 | A026 | 2026-04-14 | C002 | Semi-skilled | 16 | 8 | 128 | 1 | 4.9322 | m³ | 0.038533
LB00103 | P001 | A026 | 2026-04-18 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 5.6396 | m³ | 0.050353
LB00104 | P001 | A026 | 2026-05-01 | C002 | Semi-skilled | 21 | 8 | 168 | 0 | 6.2204 | m³ | 0.037026
LB00105 | P001 | A027 | 2026-05-10 | C002 | Skilled | 12 | 8 | 96 | 2 | 4.6915 | m³ | 0.04887
LB00106 | P001 | A027 | 2026-05-12 | C002 | Unskilled | 17 | 8 | 136 | 1 | 4.0494 | m³ | 0.029775
LB00107 | P001 | A027 | 2026-05-18 | C002 | Skilled | 13 | 8 | 104 | 0 | 4.1066 | m³ | 0.039486
LB00108 | P001 | A027 | 2026-05-22 | C002 | Unskilled | 20 | 8 | 160 | 0 | 5.3943 | m³ | 0.033714
LB00109 | P001 | A028 | 2026-05-25 | C002 | Skilled | 14 | 8 | 112 | 0 | 4.6728 | m³ | 0.041721
LB00110 | P001 | A028 | 2026-05-29 | C002 | Semi-skilled | 18 | 9 | 162 | 1 | 6.5595 | m³ | 0.040491
LB00111 | P001 | A028 | 2026-06-01 | C002 | Unskilled | 13 | 9 | 117 | 0 | 6.6856 | m³ | 0.057142
LB00112 | P001 | A028 | 2026-06-02 | C002 | Skilled | 17 | 8 | 136 | 2 | 4.5871 | m³ | 0.033729
LB00113 | P001 | A029 | 2026-06-14 | C002 | Semi-skilled | 22 | 8 | 176 | 0 | 6.0239 | m³ | 0.034227
LB00114 | P001 | A029 | 2026-06-15 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 5.8789 | m³ | 0.052491
LB00115 | P001 | A029 | 2026-06-18 | C002 | Skilled | 19 | 8 | 152 | 0 | 5.5248 | m³ | 0.036348
LB00116 | P001 | A029 | 2026-06-27 | C002 | Semi-skilled | 15 | 9 | 135 | 1 | 5.4734 | m³ | 0.040544
LB00117 | P001 | A030 | 2026-07-05 | C002 | Skilled | 14 | 8 | 112 | 0 | 4.7793 | m³ | 0.042672
LB00118 | P001 | A030 | 2026-07-07 | C002 | Semi-skilled | 16 | 8 | 128 | 1 | 5.5132 | m³ | 0.043072
LB00119 | P001 | A030 | 2026-07-15 | C002 | Skilled | 21 | 8 | 168 | 0 | 5.3466 | m³ | 0.031825
LB00120 | P001 | A030 | 2026-07-22 | C002 | Skilled | 21 | 8 | 168 | 1 | 5.467 | m³ | 0.032542
LB00121 | P001 | A031 | 2026-07-28 | C002 | Skilled | 19 | 9 | 171 | 2 | 4.8634 | m³ | 0.028441
LB00122 | P001 | A031 | 2026-08-02 | C002 | Semi-skilled | 17 | 8 | 136 | 0 | 6.1001 | m³ | 0.044854
LB00123 | P001 | A031 | 2026-08-02 | C002 | Unskilled | 24 | 8 | 192 | 0 | 5.9841 | m³ | 0.031167
LB00124 | P001 | A031 | 2026-08-03 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 5.5564 | m³ | 0.036555
LB00125 | P001 | A032 | 2026-08-26 | C002 | Skilled | 19 | 9 | 171 | 0 | 6.2865 | m³ | 0.036763
LB00126 | P001 | A032 | 2026-09-03 | C002 | Skilled | 20 | 8 | 160 | 1 | 6.1274 | m³ | 0.038296
LB00127 | P001 | A032 | 2026-09-03 | C002 | Skilled | 20 | 8 | 160 | 1 | 5.4683 | m³ | 0.034177
LB00128 | P001 | A032 | 2026-09-04 | C002 | Unskilled | 20 | 8 | 160 | 0 | 6.0808 | m³ | 0.038005
LB00129 | P001 | A033 | 2026-09-06 | C002 | Skilled | 17 | 9 | 153 | 0 | 4.6976 | m³ | 0.030703
LB00130 | P001 | A033 | 2026-09-22 | C002 | Skilled | 16 | 8 | 128 | 0 | 4.066 | m³ | 0.031765
LB00131 | P001 | A033 | 2026-09-22 | C002 | Skilled | 19 | 8 | 152 | 1 | 5.7963 | m³ | 0.038133
LB00132 | P001 | A033 | 2026-09-23 | C002 | Unskilled | 20 | 8 | 160 | 2 | 4.7461 | m³ | 0.029663
LB00133 | P001 | A034 | 2026-09-29 | C002 | Semi-skilled | 18 | 8 | 144 | 0 | 6.0129 | m³ | 0.041756
LB00134 | P001 | A034 | 2026-10-02 | C002 | Unskilled | 19 | 8 | 152 | 0 | 5.2548 | m³ | 0.034571
LB00135 | P001 | A034 | 2026-10-05 | C002 | Skilled | 9 | 8 | 72 | 0 | 5.2651 | m³ | 0.073126
LB00136 | P001 | A034 | 2026-10-10 | C002 | Skilled | 14 | 8 | 112 | 0 | 5.3461 | m³ | 0.047733
LB00137 | P001 | A035 | 2026-10-21 | C002 | Semi-skilled | 19 | 8 | 152 | 2 | 4.7329 | m³ | 0.031137
LB00138 | P001 | A035 | 2026-10-23 | C002 | Unskilled | 18 | 8 | 144 | 0 | 5.8786 | m³ | 0.040824
LB00139 | P001 | A035 | 2026-10-24 | C002 | Semi-skilled | 13 | 8 | 104 | 0 | 4.0204 | m³ | 0.038658
LB00140 | P001 | A035 | 2026-11-02 | C002 | Unskilled | 19 | 8 | 152 | 2 | 6.0692 | m³ | 0.039929
LB00141 | P001 | A036 | 2026-11-08 | C002 | Unskilled | 23 | 8 | 184 | 0 | 4.6184 | m³ | 0.0251
LB00142 | P001 | A036 | 2026-11-08 | C002 | Unskilled | 17 | 8 | 136 | 1 | 4.6492 | m³ | 0.034185
LB00143 | P001 | A036 | 2026-11-09 | C002 | Unskilled | 14 | 9 | 126 | 0 | 5.6181 | m³ | 0.044588
LB00144 | P001 | A036 | 2026-11-23 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 4.9589 | m³ | 0.032624
LB00145 | P001 | A037 | 2026-05-04 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 8.2478 | m³ | 0.054262
LB00146 | P001 | A037 | 2026-05-12 | C002 | Semi-skilled | 13 | 8 | 104 | 1 | 8.4025 | m³ | 0.080793
LB00147 | P001 | A037 | 2026-05-13 | C002 | Unskilled | 16 | 9 | 144 | 0 | 8.4695 | m³ | 0.058816
LB00148 | P001 | A037 | 2026-05-14 | C002 | Skilled | 13 | 9 | 117 | 2 | 8.9063 | m³ | 0.076122
LB00149 | P001 | A038 | 2026-05-20 | C002 | Unskilled | 14 | 8 | 112 | 0 | 8.7657 | m³ | 0.078266
LB00150 | P001 | A038 | 2026-05-26 | C002 | Semi-skilled | 18 | 8 | 144 | 0 | 8.0379 | m³ | 0.055818
LB00151 | P001 | A038 | 2026-05-30 | C002 | Semi-skilled | 21 | 8 | 168 | 0 | 8.6118 | m³ | 0.051261
LB00152 | P001 | A038 | 2026-06-04 | C002 | Skilled | 19 | 8 | 152 | 2 | 8.2548 | m³ | 0.054308
LB00153 | P001 | A039 | 2026-06-12 | C002 | Unskilled | 16 | 9 | 144 | 1 | 7.1934 | m³ | 0.049954
LB00154 | P001 | A039 | 2026-06-15 | C002 | Unskilled | 16 | 8 | 128 | 0 | 8.8146 | m³ | 0.068864
LB00155 | P001 | A039 | 2026-07-01 | C002 | Semi-skilled | 23 | 9 | 207 | 0 | 8.2111 | m³ | 0.039667
LB00156 | P001 | A039 | 2026-07-01 | C002 | Skilled | 21 | 8 | 168 | 2 | 7.4798 | m³ | 0.044523
LB00157 | P001 | A040 | 2026-07-03 | C002 | Skilled | 13 | 8 | 104 | 1 | 8.561 | m³ | 0.082317
LB00158 | P001 | A040 | 2026-07-04 | C002 | Semi-skilled | 22 | 9 | 198 | 0 | 7.7075 | m³ | 0.038927
LB00159 | P001 | A040 | 2026-07-13 | C002 | Semi-skilled | 17 | 8 | 136 | 2 | 6.5787 | m³ | 0.048373
LB00160 | P001 | A040 | 2026-07-24 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 9.2645 | m³ | 0.082719
LB00161 | P001 | A041 | 2026-07-28 | C002 | Semi-skilled | 22 | 8 | 176 | 0 | 6.24 | m³ | 0.035454
LB00162 | P001 | A041 | 2026-07-29 | C002 | Semi-skilled | 19 | 8 | 152 | 2 | 6.7826 | m³ | 0.044622
LB00163 | P001 | A041 | 2026-07-31 | C002 | Semi-skilled | 21 | 8 | 168 | 2 | 5.8979 | m³ | 0.035106
LB00164 | P001 | A041 | 2026-08-13 | C002 | Unskilled | 21 | 8 | 168 | 0 | 7.1651 | m³ | 0.042649
LB00165 | P001 | A042 | 2026-08-21 | C002 | Semi-skilled | 14 | 8 | 112 | 0 | 7.1412 | m³ | 0.063761
LB00166 | P001 | A042 | 2026-08-21 | C002 | Skilled | 22 | 8 | 176 | 1 | 6.0518 | m³ | 0.034385
LB00167 | P001 | A042 | 2026-09-03 | C002 | Unskilled | 17 | 8 | 136 | 0 | 8.3077 | m³ | 0.061086
LB00168 | P001 | A042 | 2026-09-08 | C002 | Unskilled | 19 | 9 | 171 | 0 | 8.4141 | m³ | 0.049205
LB00169 | P001 | A043 | 2026-09-16 | C002 | Skilled | 19 | 8 | 152 | 2 | 6.0973 | m³ | 0.040114
LB00170 | P001 | A043 | 2026-09-18 | C002 | Unskilled | 16 | 8 | 128 | 2 | 8.8654 | m³ | 0.069261
LB00171 | P001 | A043 | 2026-09-26 | C002 | Semi-skilled | 19 | 8 | 152 | 0 | 6.2476 | m³ | 0.041103
LB00172 | P001 | A043 | 2026-09-27 | C002 | Skilled | 18 | 8 | 144 | 2 | 5.8094 | m³ | 0.040343
LB00173 | P001 | A044 | 2026-10-06 | C002 | Skilled | 15 | 8 | 120 | 1 | 6.9343 | m³ | 0.057786
LB00174 | P001 | A044 | 2026-10-08 | C002 | Unskilled | 13 | 9 | 117 | 1 | 9.2369 | m³ | 0.078947
LB00175 | P001 | A044 | 2026-10-08 | C002 | Skilled | 21 | 9 | 189 | 0 | 10.2921 | m³ | 0.054456
LB00176 | P001 | A044 | 2026-10-14 | C002 | Skilled | 20 | 8 | 160 | 0 | 8.7008 | m³ | 0.05438
LB00177 | P001 | A045 | 2026-11-02 | C002 | Semi-skilled | 17 | 9 | 153 | 1 | 7.2622 | m³ | 0.047466
LB00178 | P001 | A045 | 2026-11-03 | C002 | Unskilled | 22 | 8 | 176 | 0 | 7.2409 | m³ | 0.041141
LB00179 | P001 | A045 | 2026-11-07 | C002 | Skilled | 15 | 8 | 120 | 2 | 6.5488 | m³ | 0.054573
LB00180 | P001 | A045 | 2026-11-09 | C002 | Semi-skilled | 20 | 8 | 160 | 0 | 5.9005 | m³ | 0.036878
LB00181 | P001 | A046 | 2026-11-20 | C002 | Unskilled | 20 | 8 | 160 | 0 | 7.1493 | m³ | 0.044683
LB00182 | P001 | A046 | 2026-11-21 | C002 | Unskilled | 22 | 9 | 198 | 0 | 7.3421 | m³ | 0.037082
LB00183 | P001 | A046 | 2026-12-02 | C002 | Skilled | 19 | 9 | 171 | 0 | 6.8443 | m³ | 0.040025
LB00184 | P001 | A046 | 2026-12-05 | C002 | Semi-skilled | 19 | 8 | 152 | 2 | 5.9947 | m³ | 0.039439
LB00185 | P001 | A047 | 2026-12-15 | C002 | Semi-skilled | 18 | 8 | 144 | 0 | 7.2553 | m³ | 0.050384
LB00186 | P001 | A047 | 2026-12-15 | C002 | Skilled | 24 | 9 | 216 | 0 | 8.7725 | m³ | 0.040613
LB00187 | P001 | A047 | 2026-12-30 | C002 | Semi-skilled | 24 | 8 | 192 | 0 | 6.9981 | m³ | 0.036448
LB00188 | P001 | A047 | 2026-12-30 | C002 | Unskilled | 16 | 8 | 128 | 0 | 7.7828 | m³ | 0.060803
LB00189 | P001 | A048 | 2026-04-17 | C002 | Skilled | 25 | 9 | 225 | 0 | 2.3429 | m³ | 0.010413
LB00190 | P001 | A048 | 2026-04-27 | C002 | Skilled | 20 | 8 | 160 | 2 | 2.282 | m³ | 0.014262
LB00191 | P001 | A048 | 2026-04-28 | C002 | Semi-skilled | 20 | 8 | 160 | 0 | 2.3469 | m³ | 0.014668
LB00192 | P001 | A048 | 2026-05-24 | C002 | Skilled | 19 | 8 | 152 | 0 | 1.7054 | m³ | 0.01122
LB00193 | P001 | A049 | 2026-06-07 | C003 | Skilled | 17 | 8 | 136 | 0 | 16.6971 | m³ | 0.12277
LB00194 | P001 | A049 | 2026-06-18 | C003 | Unskilled | 18 | 8 | 144 | 0 | 21.1792 | m³ | 0.14708
LB00195 | P001 | A049 | 2026-06-30 | C003 | Unskilled | 26 | 9 | 234 | 2 | 23.6816 | m³ | 0.1012
LB00196 | P001 | A049 | 2026-07-11 | C003 | Unskilled | 21 | 9 | 189 | 0 | 24.4573 | m³ | 0.1294
LB00197 | P001 | A049 | 2026-07-23 | C003 | Semi-skilled | 19 | 8 | 152 | 0 | 21.0408 | m³ | 0.13843
LB00198 | P001 | A049 | 2026-08-01 | C003 | Unskilled | 24 | 8 | 192 | 1 | 21.9672 | m³ | 0.11441
LB00199 | P001 | A049 | 2026-08-09 | C003 | Unskilled | 24 | 8 | 192 | 0 | 21.7532 | m³ | 0.1133
LB00200 | P001 | A050 | 2026-06-27 | C003 | Skilled | 24 | 8 | 192 | 1 | 13.2973 | m³ | 0.069257
LB00201 | P001 | A050 | 2026-07-18 | C003 | Skilled | 22 | 8 | 176 | 0 | 13.6251 | m³ | 0.077415
LB00202 | P001 | A050 | 2026-07-28 | C003 | Skilled | 19 | 8 | 152 | 1 | 10.3509 | m³ | 0.068098
LB00203 | P001 | A050 | 2026-07-28 | C003 | Skilled | 20 | 8 | 160 | 0 | 9.4582 | m³ | 0.059114
LB00204 | P001 | A050 | 2026-08-03 | C003 | Semi-skilled | 19 | 8 | 152 | 1 | 11.5089 | m³ | 0.075716
LB00205 | P001 | A050 | 2026-08-21 | C003 | Skilled | 14 | 8 | 112 | 0 | 14.0104 | m³ | 0.12509
LB00206 | P001 | A050 | 2026-08-22 | C003 | Unskilled | 21 | 8 | 168 | 0 | 9.4773 | m³ | 0.056413
LB00207 | P001 | A051 | 2026-07-02 | C003 | Semi-skilled | 17 | 8 | 136 | 0 | 2.7945 | m³ | 0.020547
LB00208 | P001 | A051 | 2026-07-08 | C003 | Unskilled | 20 | 8 | 160 | 2 | 2.8168 | m³ | 0.017605
LB00209 | P001 | A051 | 2026-07-10 | C003 | Unskilled | 16 | 8 | 128 | 0 | 2.8453 | m³ | 0.022229
LB00210 | P001 | A051 | 2026-07-25 | C003 | Unskilled | 22 | 8 | 176 | 2 | 2.102 | m³ | 0.011943
LB00211 | P001 | A052 | 2026-08-17 | C004 | Unskilled | 12 | 8 | 96 | 2 | 193.8113 | m² | 2.0189
LB00212 | P001 | A052 | 2026-08-21 | C004 | Skilled | 13 | 8 | 104 | 0 | 215.0752 | m² | 2.068
LB00213 | P001 | A052 | 2026-08-27 | C004 | Semi-skilled | 15 | 8 | 120 | 0 | 250.5337 | m² | 2.0878
LB00214 | P001 | A052 | 2026-09-01 | C004 | Semi-skilled | 17 | 8 | 136 | 0 | 209.537 | m² | 1.5407
LB00215 | P001 | A052 | 2026-09-06 | C004 | Skilled | 13 | 8 | 104 | 0 | 199.2463 | m² | 1.9158
LB00216 | P001 | A052 | 2026-10-02 | C004 | Semi-skilled | 17 | 8 | 136 | 1 | 247.9952 | m² | 1.8235
LB00217 | P001 | A052 | 2026-10-09 | C004 | Semi-skilled | 18 | 9 | 162 | 2 | 219.2131 | m² | 1.3532
LB00218 | P001 | A053 | 2026-08-19 | C004 | Skilled | 16 | 8 | 128 | 2 | 195.4382 | m² | 1.5269
LB00219 | P001 | A053 | 2026-08-29 | C004 | Semi-skilled | 14 | 9 | 126 | 0 | 206.0838 | m² | 1.6356
LB00220 | P001 | A053 | 2026-09-04 | C004 | Semi-skilled | 20 | 8 | 160 | 0 | 160.9539 | m² | 1.006
LB00221 | P001 | A053 | 2026-09-12 | C004 | Semi-skilled | 13 | 8 | 104 | 0 | 177.9989 | m² | 1.7115
LB00222 | P001 | A053 | 2026-09-20 | C004 | Semi-skilled | 14 | 8 | 112 | 0 | 162.5795 | m² | 1.4516
LB00223 | P001 | A053 | 2026-09-30 | C004 | Skilled | 19 | 8 | 152 | 0 | 204.51 | m² | 1.3455
LB00224 | P001 | A054 | 2026-08-29 | C008 | Semi-skilled | 8 | 8 | 64 | 2 | 60.7678 | m² | 0.9495
LB00225 | P001 | A054 | 2026-09-01 | C008 | Unskilled | 6 | 8 | 48 | 0 | 44.0393 | m² | 0.91749
LB00226 | P001 | A054 | 2026-09-12 | C008 | Skilled | 12 | 8 | 96 | 2 | 47.0589 | m² | 0.4902
LB00227 | P001 | A054 | 2026-09-19 | C008 | Skilled | 13 | 8 | 104 | 0 | 57.185 | m² | 0.54986
LB00228 | P001 | A055 | 2026-12-03 | C008 | Skilled | 5 | 8 | 40 | 0 | 87.8466 | m² | 2.1962
LB00229 | P001 | A055 | 2026-12-03 | C008 | Skilled | 7 | 8 | 56 | 0 | 83.6427 | m² | 1.4936
LB00230 | P001 | A055 | 2026-12-10 | C008 | Semi-skilled | 4 | 8 | 32 | 2 | 76.3986 | m² | 2.3875
LB00231 | P001 | A055 | 2026-12-11 | C008 | Skilled | 14 | 8 | 112 | 1 | 99.964 | m² | 0.89254
LB00232 | P001 | A056 | 2026-09-15 | C004 | Unskilled | 20 | 8 | 160 | 2 | 151.1716 | m² | 0.94482
LB00233 | P001 | A056 | 2026-09-16 | C004 | Unskilled | 15 | 8 | 120 | 2 | 159.8437 | m² | 1.332
LB00234 | P001 | A056 | 2026-09-27 | C004 | Skilled | 15 | 9 | 135 | 0 | 166.5252 | m² | 1.2335
LB00235 | P001 | A056 | 2026-09-28 | C004 | Unskilled | 16 | 8 | 128 | 1 | 145.2757 | m² | 1.135
LB00236 | P001 | A056 | 2026-10-02 | C004 | Skilled | 16 | 8 | 128 | 0 | 118.1 | m² | 0.92266
LB00237 | P001 | A056 | 2026-10-20 | C004 | Unskilled | 15 | 8 | 120 | 0 | 139.5749 | m² | 1.1631
LB00238 | P001 | A056 | 2026-11-23 | C004 | Unskilled | 14 | 8 | 112 | 0 | 161.8666 | m² | 1.4452
LB00239 | P001 | A056 | 2026-12-04 | C004 | Semi-skilled | 20 | 8 | 160 | 2 | 136.029 | m² | 0.85018
LB00240 | P001 | A057 | 2026-10-07 | C004 | Semi-skilled | 15 | 8 | 120 | 1 | 67.409 | m² | 0.56174
LB00241 | P001 | A057 | 2026-10-14 | C004 | Unskilled | 12 | 8 | 96 | 0 | 83.2375 | m² | 0.86706
LB00242 | P001 | A057 | 2026-10-16 | C004 | Semi-skilled | 13 | 8 | 104 | 0 | 80.2065 | m² | 0.77122
LB00243 | P001 | A057 | 2026-10-22 | C004 | Unskilled | 15 | 8 | 120 | 0 | 72.4107 | m² | 0.60342
LB00244 | P001 | A057 | 2026-10-22 | C004 | Skilled | 15 | 8 | 120 | 0 | 62.0427 | m² | 0.51702
LB00245 | P001 | A057 | 2026-11-02 | C004 | Semi-skilled | 8 | 8 | 64 | 0 | 56.5677 | m² | 0.88387
LB00246 | P001 | A057 | 2026-11-24 | C004 | Skilled | 13 | 9 | 117 | 0 | 82.2644 | m² | 0.70311
LB00247 | P001 | A058 | 2026-10-26 | C004 | Unskilled | 12 | 9 | 108 | 0 | 3.2774 | no. | 0.030346
LB00248 | P001 | A058 | 2026-10-28 | C004 | Unskilled | 18 | 8 | 144 | 0 | 3.1615 | no. | 0.021955
LB00249 | P001 | A058 | 2026-10-28 | C004 | Skilled | 17 | 8 | 136 | 0 | 2.4097 | no. | 0.017718
LB00250 | P001 | A058 | 2026-11-04 | C004 | Skilled | 12 | 9 | 108 | 0 | 2.5581 | no. | 0.023687
LB00251 | P001 | A058 | 2026-12-08 | C004 | Semi-skilled | 14 | 8 | 112 | 0 | 3.1942 | no. | 0.02852
LB00252 | P001 | A058 | 2026-12-11 | C004 | Skilled | 14 | 8 | 112 | 0 | 2.2422 | no. | 0.020019
LB00253 | P001 | A059 | 2026-10-04 | C004 | Semi-skilled | 13 | 8 | 104 | 0 | 30.5501 | m² | 0.29375
LB00254 | P001 | A059 | 2026-10-21 | C004 | Skilled | 12 | 8 | 96 | 0 | 34.2871 | m² | 0.35716
LB00255 | P001 | A059 | 2026-10-29 | C004 | Unskilled | 21 | 9 | 189 | 1 | 37.7835 | m² | 0.19991
LB00256 | P001 | A059 | 2026-11-09 | C004 | Skilled | 17 | 8 | 136 | 1 | 27.0127 | m² | 0.19862
LB00257 | P001 | A059 | 2026-11-09 | C004 | Skilled | 23 | 8 | 184 | 1 | 29.6843 | m² | 0.16133
LB00258 | P001 | A059 | 2026-11-12 | C004 | Unskilled | 11 | 8 | 88 | 0 | 30.6586 | m² | 0.34839
LB00259 | P001 | A059 | 2026-12-01 | C004 | Semi-skilled | 12 | 8 | 96 | 0 | 29.2361 | m² | 0.30454
LB00260 | P001 | A060 | 2026-10-13 | C005 | Semi-skilled | 15 | 9 | 135 | 1 | 350.4089 | m² | 2.5956
LB00261 | P001 | A060 | 2026-10-14 | C005 | Skilled | 18 | 8 | 144 | 2 | 335.8036 | m² | 2.332
LB00262 | P001 | A060 | 2026-10-16 | C005 | Skilled | 13 | 8 | 104 | 1 | 361.2708 | m² | 3.4738
LB00263 | P001 | A060 | 2026-10-20 | C005 | Semi-skilled | 19 | 9 | 171 | 1 | 368.5481 | m² | 2.1553
LB00264 | P001 | A060 | 2026-10-22 | C005 | Semi-skilled | 17 | 8 | 136 | 1 | 284.3053 | m² | 2.0905
LB00265 | P001 | A060 | 2026-10-23 | C005 | Skilled | 15 | 8 | 120 | 1 | 289.602 | m² | 2.4134
LB00266 | P001 | A060 | 2026-11-18 | C005 | Semi-skilled | 19 | 8 | 152 | 2 | 349.9062 | m² | 2.302
LB00267 | P001 | A060 | 2026-12-19 | C005 | Skilled | 15 | 8 | 120 | 1 | 364.4039 | m² | 3.0367
LB00268 | P001 | A061 | 2026-10-30 | C005 | Unskilled | 18 | 8 | 144 | 0 | 253.5769 | m² | 1.761
LB00269 | P001 | A061 | 2026-10-31 | C005 | Semi-skilled | 14 | 8 | 112 | 0 | 241.8096 | m² | 2.159
LB00270 | P001 | A061 | 2026-11-06 | C005 | Unskilled | 17 | 9 | 153 | 0 | 224.8135 | m² | 1.4694
LB00271 | P001 | A061 | 2026-11-15 | C005 | Unskilled | 13 | 9 | 117 | 0 | 199.346 | m² | 1.7038
LB00272 | P001 | A061 | 2026-11-18 | C005 | Unskilled | 11 | 8 | 88 | 1 | 188.8044 | m² | 2.1455
LB00273 | P001 | A061 | 2026-11-26 | C005 | Skilled | 13 | 8 | 104 | 0 | 199.6155 | m² | 1.9194
LB00274 | P001 | A062 | 2026-08-17 | C006 | Semi-skilled | 10 | 8 | 80 | 2 | 53.3201 | m | 0.6665
LB00275 | P001 | A062 | 2026-08-24 | C006 | Skilled | 8 | 8 | 64 | 0 | 70.0812 | m | 1.095
LB00276 | P001 | A062 | 2026-09-01 | C006 | Unskilled | 12 | 8 | 96 | 0 | 64.5238 | m | 0.67212
LB00277 | P001 | A062 | 2026-09-25 | C006 | Skilled | 13 | 8 | 104 | 1 | 51.7028 | m | 0.49714
LB00278 | P001 | A062 | 2026-10-14 | C006 | Skilled | 10 | 9 | 90 | 0 | 62.0592 | m | 0.68955
LB00279 | P001 | A062 | 2026-10-18 | C006 | Semi-skilled | 12 | 8 | 96 | 0 | 68.8376 | m | 0.71706
LB00280 | P001 | A062 | 2026-11-04 | C006 | Semi-skilled | 11 | 9 | 99 | 0 | 73.2621 | m | 0.74002
LB00281 | P001 | A062 | 2026-11-22 | C006 | Skilled | 13 | 8 | 104 | 0 | 69.576 | m | 0.669
LB00282 | P001 | A063 | 2026-11-09 | C006 | Unskilled | 14 | 8 | 112 | 0 | 3.3005 | no. | 0.029469
LB00283 | P001 | A063 | 2026-11-20 | C006 | Semi-skilled | 13 | 9 | 117 | 2 | 4.3382 | no. | 0.037079
LB00284 | P001 | A063 | 2026-11-22 | C006 | Unskilled | 9 | 8 | 72 | 0 | 3.7542 | no. | 0.052142
LB00285 | P001 | A063 | 2026-11-27 | C006 | Unskilled | 12 | 9 | 108 | 0 | 3.1172 | no. | 0.028863
LB00286 | P001 | A063 | 2026-12-06 | C006 | Unskilled | 13 | 8 | 104 | 1 | 3.9224 | no. | 0.037715
LB00287 | P001 | A063 | 2026-12-18 | C006 | Semi-skilled | 11 | 8 | 88 | 0 | 3.3157 | no. | 0.037679
LB00288 | P001 | A064 | 2026-08-22 | C007 | Semi-skilled | 11 | 8 | 88 | 1 | 177.8468 | m | 2.021
LB00289 | P001 | A064 | 2026-08-27 | C007 | Semi-skilled | 12 | 8 | 96 | 0 | 155.6719 | m | 1.6216
LB00290 | P001 | A064 | 2026-09-01 | C007 | Semi-skilled | 10 | 8 | 80 | 2 | 168.6699 | m | 2.1084
LB00291 | P001 | A064 | 2026-09-23 | C007 | Semi-skilled | 10 | 8 | 80 | 1 | 173.3927 | m | 2.1674
LB00292 | P001 | A064 | 2026-10-09 | C007 | Unskilled | 11 | 8 | 88 | 1 | 140.7581 | m | 1.5995
LB00293 | P001 | A064 | 2026-10-10 | C007 | Semi-skilled | 10 | 8 | 80 | 0 | 157.6986 | m | 1.9712
LB00294 | P001 | A064 | 2026-11-04 | C007 | Semi-skilled | 11 | 9 | 99 | 1 | 174.5542 | m | 1.7632
LB00295 | P001 | A064 | 2026-11-14 | C007 | Semi-skilled | 11 | 8 | 88 | 2 | 172.2233 | m | 1.9571
LB00296 | P001 | A065 | 2026-11-06 | C007 | Semi-skilled | 10 | 8 | 80 | 0 | 16.2338 | no. | 0.20292
LB00297 | P001 | A065 | 2026-11-09 | C007 | Unskilled | 12 | 9 | 108 | 1 | 19.1767 | no. | 0.17756
LB00298 | P001 | A065 | 2026-11-12 | C007 | Semi-skilled | 9 | 8 | 72 | 2 | 18.4214 | no. | 0.25585
LB00299 | P001 | A065 | 2026-12-06 | C007 | Skilled | 18 | 9 | 162 | 2 | 13.9174 | no. | 0.08591
LB00300 | P001 | A065 | 2026-12-21 | C007 | Unskilled | 13 | 8 | 104 | 1 | 15.8106 | no. | 0.15202
LB00301 | P001 | A065 | 2026-12-23 | C007 | Semi-skilled | 13 | 9 | 117 | 0 | 14.301 | no. | 0.12223
LB00302 | P001 | A066 | 2026-10-20 | C001 | Unskilled | 10 | 9 | 90 | 0 | 18.8968 | m | 0.20996
LB00303 | P001 | A066 | 2026-10-24 | C001 | Unskilled | 16 | 8 | 128 | 0 | 12.7265 | m | 0.099426
LB00304 | P001 | A066 | 2026-11-20 | C001 | Skilled | 10 | 9 | 90 | 1 | 16.7617 | m | 0.18624
LB00305 | P001 | A066 | 2026-12-02 | C001 | Skilled | 15 | 8 | 120 | 0 | 13.6389 | m | 0.11366
LB00306 | P001 | A066 | 2026-12-03 | C001 | Skilled | 10 | 8 | 80 | 2 | 17.3133 | m | 0.21642
LB00307 | P001 | A067 | 2026-11-01 | C001 | Skilled | 11 | 8 | 88 | 1 | 93.4967 | m² | 1.0625
LB00308 | P001 | A067 | 2026-11-10 | C001 | Semi-skilled | 9 | 8 | 72 | 1 | 70.781 | m² | 0.98307
LB00309 | P001 | A067 | 2026-11-17 | C001 | Unskilled | 10 | 9 | 90 | 1 | 101.052 | m² | 1.1228
LB00310 | P001 | A067 | 2026-11-26 | C001 | Semi-skilled | 12 | 8 | 96 | 0 | 93.3275 | m² | 0.97216
LB00311 | P001 | A067 | 2026-12-12 | C001 | Unskilled | 12 | 8 | 96 | 0 | 91.8536 | m² | 0.95681
LB00312 | P001 | A068 | 2026-12-12 | C001 | Unskilled | 11 | 8 | 88 | 2 | 2581.8038 | m² | 29.3387
LB00313 | P001 | A068 | 2026-12-12 | C001 | Skilled | 13 | 8 | 104 | 0 | 2779.2442 | m² | 26.7235
LB00314 | P001 | A068 | 2026-12-13 | C001 | Unskilled | 13 | 8 | 104 | 2 | 2658.0956 | m² | 25.5586
LB00315 | P001 | A068 | 2026-12-14 | C001 | Unskilled | 8 | 8 | 64 | 0 | 2976.885 | m² | 46.5138

## Materials
Material_ID | Project_ID | Activity_ID | Date | Material_Name | Material_Category | Unit | Planned_Quantity | Actual_Quantity | Unit_Cost_INR | Total_Cost_INR | Supplier | Wastage_Quantity | Wastage_Percentage
MT00001 | P001 | A001 | 2026-01-08 | Temporary Materials | Preliminaries | lot | 0.29856 | 0.31862 | 10391.6275 | 3310.9768 | Simulated Supplier | 0.020059 | 6.7186
MT00002 | P001 | A001 | 2026-01-09 | Temporary Materials | Preliminaries | lot | 0.2478 | 0.25762 | 10560.1536 | 2720.473 | Simulated Supplier | 0.009814 | 3.9604
MT00003 | P001 | A001 | 2026-01-10 | Temporary Materials | Preliminaries | lot | 0.20495 | 0.21786 | 10797.7327 | 2352.3823 | Simulated Supplier | 0.012909 | 6.2986
MT00004 | P001 | A002 | 2026-01-02 | Temporary Materials | Preliminaries | lot | 0.19656 | 0.20144 | 9554.6864 | 1924.6946 | Simulated Supplier | 0.0048771 | 2.4812
MT00005 | P001 | A002 | 2026-01-05 | Temporary Materials | Preliminaries | lot | 0.26923 | 0.28807 | 9875.8343 | 2844.9554 | Simulated Supplier | 0.018839 | 6.9972
MT00006 | P001 | A002 | 2026-01-05 | Temporary Materials | Preliminaries | lot | 0.21739 | 0.21968 | 9961.9738 | 2188.4024 | Simulated Supplier | 0.0022857 | 1.0514
MT00007 | P001 | A003 | 2026-01-07 | Temporary Materials | Preliminaries | lot | 0.34611 | 0.37129 | 9703.1562 | 3602.7011 | Simulated Supplier | 0.025184 | 7.2762
MT00008 | P001 | A003 | 2026-01-17 | Temporary Materials | Preliminaries | lot | 0.19123 | 0.19604 | 10792.5623 | 2115.7315 | Simulated Supplier | 0.0048088 | 2.5147
MT00009 | P001 | A003 | 2026-01-21 | Temporary Materials | Preliminaries | lot | 0.23179 | 0.23548 | 9584.8604 | 2257.0106 | Simulated Supplier | 0.0036864 | 1.5904
MT00010 | P001 | A004 | 2026-01-08 | Temporary Materials | Preliminaries | lot | 0.20289 | 0.21064 | 10078.2865 | 2122.9273 | Simulated Supplier | 0.007752 | 3.8207
MT00011 | P001 | A004 | 2026-01-09 | Temporary Materials | Preliminaries | lot | 0.23431 | 0.2454 | 10394.4803 | 2550.7549 | Simulated Supplier | 0.011086 | 4.7313
MT00012 | P001 | A004 | 2026-01-13 | Temporary Materials | Preliminaries | lot | 0.2554 | 0.27072 | 10796.504 | 2922.8427 | Simulated Supplier | 0.015317 | 5.997
MT00013 | P001 | A005 | 2026-01-21 | Filling Soil | Earthwork | m³ | 1216.5978 | 1275.9021 | 547.1144 | 698064.4424 | Simulated Supplier | 59.3043 | 4.8746
MT00014 | P001 | A005 | 2026-01-22 | Sand | Earthwork | m³ | 296.0555 | 320.9009 | 1526.4693 | 489845.3312 | Simulated Supplier | 24.8453 | 8.3921
MT00015 | P001 | A005 | 2026-01-29 | Filling Soil | Earthwork | m³ | 1068.4512 | 1140.4453 | 522.7189 | 596132.2587 | Simulated Supplier | 71.9941 | 6.7382
MT00016 | P001 | A006 | 2026-02-09 | Sand | Earthwork | m³ | 166.544 | 183.1575 | 1502.4062 | 275176.936 | Simulated Supplier | 16.6135 | 9.9754
MT00017 | P001 | A006 | 2026-02-13 | Filling Soil | Earthwork | m³ | 361.9752 | 379.552 | 566.7256 | 215101.8643 | Simulated Supplier | 17.5769 | 4.8558
MT00018 | P001 | A006 | 2026-02-16 | Filling Soil | Earthwork | m³ | 579.7745 | 607.9328 | 526.7043 | 320200.7802 | Simulated Supplier | 28.1582 | 4.8568
MT00019 | P001 | A007 | 2026-02-06 | Sand | Earthwork | m³ | 153.9606 | 161.2158 | 1608.2454 | 259274.5486 | Simulated Supplier | 7.2552 | 4.7124
MT00020 | P001 | A007 | 2026-02-06 | Filling Soil | Earthwork | m³ | 665.9612 | 694.7201 | 582.5779 | 404728.5883 | Simulated Supplier | 28.7588 | 4.3184
MT00021 | P001 | A007 | 2026-02-17 | Filling Soil | Earthwork | m³ | 704.5856 | 712.8619 | 559.0558 | 398529.5847 | Simulated Supplier | 8.2763 | 1.1746
MT00022 | P001 | A008 | 2026-01-21 | Filling Soil | Earthwork | m³ | 591.5449 | 621.0028 | 539.2521 | 334877.1096 | Simulated Supplier | 29.4579 | 4.9798
MT00023 | P001 | A008 | 2026-01-30 | Sand | Earthwork | m³ | 163.0907 | 180.4557 | 1574.3765 | 284105.227 | Simulated Supplier | 17.365 | 10.6474
MT00024 | P001 | A008 | 2026-02-03 | Sand | Earthwork | m³ | 188.4813 | 207.0019 | 1460.6661 | 302360.6786 | Simulated Supplier | 18.5206 | 9.8262
MT00025 | P001 | A009 | 2026-02-16 | Sand | Aggregate | m³ | 76.2466 | 84.0598 | 1559.8531 | 131120.979 | Simulated Supplier | 7.8133 | 10.2474
MT00026 | P001 | A009 | 2026-03-02 | Sand | Aggregate | m³ | 37.8038 | 40.1466 | 1519.8009 | 61014.8315 | Simulated Supplier | 2.3428 | 6.1972
MT00027 | P001 | A009 | 2026-03-04 | Sand | Aggregate | m³ | 62.7258 | 67.614 | 1553.5961 | 105044.8153 | Simulated Supplier | 4.8882 | 7.7929
MT00028 | P001 | A010 | 2026-03-10 | Coarse Aggregate | Aggregate | m³ | 23.8229 | 25.0921 | 1847.7724 | 46364.4138 | Simulated Supplier | 1.2691 | 5.3273
MT00029 | P001 | A010 | 2026-03-14 | Sand | Aggregate | m³ | 13.0108 | 13.9246 | 1480.3811 | 20613.7571 | Simulated Supplier | 0.91385 | 7.0238
MT00030 | P001 | A010 | 2026-03-16 | Coarse Aggregate | Aggregate | m³ | 16.8478 | 17.3801 | 1848.1858 | 32121.7189 | Simulated Supplier | 0.5323 | 3.1594
MT00031 | P001 | A011 | 2026-03-04 | Reinforcement Steel | Steel | kg | 20011.5054 | 21267.0264 | 64831.6907 | 1378777279.9025 | Simulated Supplier | 1255.521 | 6.274
MT00032 | P001 | A011 | 2026-03-06 | Sand | Aggregate | m³ | 71.9382 | 76.4276 | 1468.8899 | 112263.7757 | Simulated Supplier | 4.4895 | 6.2407
MT00033 | P001 | A011 | 2026-03-07 | Cement | Concrete Materials | bags | 10.3461 | 11.1124 | 425.4516 | 4727.7913 | Simulated Supplier | 0.76633 | 7.4069
MT00034 | P001 | A012 | 2026-03-18 | Coarse Aggregate | Aggregate | m³ | 41.4508 | 42.8631 | 1887.9092 | 80921.6238 | Simulated Supplier | 1.4123 | 3.4071
MT00035 | P001 | A012 | 2026-03-25 | Sand | Aggregate | m³ | 24.4035 | 26.4958 | 1495.0711 | 39613.1411 | Simulated Supplier | 2.0923 | 8.5738
MT00036 | P001 | A012 | 2026-03-26 | Sand | Aggregate | m³ | 32.5548 | 35.581 | 1455.6172 | 51792.2672 | Simulated Supplier | 3.0262 | 9.2956
MT00037 | P001 | A013 | 2026-04-02 | Sand | Aggregate | m³ | 17.0893 | 17.7961 | 1478.261 | 26307.3179 | Simulated Supplier | 0.70681 | 4.136
MT00038 | P001 | A013 | 2026-04-09 | Coarse Aggregate | Aggregate | m³ | 36.8757 | 39.1505 | 1925.098 | 75368.4825 | Simulated Supplier | 2.2748 | 6.1688
MT00039 | P001 | A013 | 2026-04-10 | Reinforcement Steel | Steel | kg | 3336.5398 | 3374.71 | 67882.1195 | 229082467.8692 | Simulated Supplier | 38.1702 | 1.144
MT00040 | P001 | A014 | 2026-04-10 | Sand | Aggregate | m³ | 129.575 | 137.0892 | 1576.1705 | 216076.011 | Simulated Supplier | 7.5142 | 5.7991
MT00041 | P001 | A014 | 2026-04-13 | Sand | Aggregate | m³ | 93.1983 | 97.0174 | 1425.4359 | 138292.131 | Simulated Supplier | 3.8191 | 4.0978
MT00042 | P001 | A014 | 2026-04-16 | Sand | Aggregate | m³ | 112.0102 | 117.9044 | 1544.6508 | 182121.1498 | Simulated Supplier | 5.8942 | 5.2622
MT00043 | P001 | A015 | 2026-04-05 | Reinforcement Steel | Steel | kg | 2350.323 | 2381.047 | 65820.8459 | 156722526.7172 | Simulated Supplier | 30.724 | 1.3072
MT00044 | P001 | A015 | 2026-04-05 | Sand | Aggregate | m³ | 12.6145 | 13.1455 | 1485.0848 | 19522.1219 | Simulated Supplier | 0.53092 | 4.2088
MT00045 | P001 | A015 | 2026-04-10 | Coarse Aggregate | Aggregate | m³ | 14.4171 | 15.0808 | 1844.7451 | 27820.2614 | Simulated Supplier | 0.66376 | 4.604
MT00046 | P001 | A016 | 2026-04-20 | Coarse Aggregate | Aggregate | m³ | 22.4378 | 23.3521 | 1780.6178 | 41581.1274 | Simulated Supplier | 0.91428 | 4.0747
MT00047 | P001 | A016 | 2026-04-30 | Coarse Aggregate | Aggregate | m³ | 27.4536 | 28.6074 | 1915.4318 | 54795.5057 | Simulated Supplier | 1.1538 | 4.2028
MT00048 | P001 | A016 | 2026-05-06 | Sand | Aggregate | m³ | 14.3165 | 15.3482 | 1499.363 | 23012.5133 | Simulated Supplier | 1.0317 | 7.2064
MT00049 | P001 | A017 | 2026-05-17 | Reinforcement Steel | Steel | kg | 3338.8313 | 3535.6786 | 73207.1904 | 258837099.1351 | Simulated Supplier | 196.8473 | 5.8957
MT00050 | P001 | A017 | 2026-05-17 | Sand | Aggregate | m³ | 9.0803 | 9.8633 | 1527.9561 | 15070.6717 | Simulated Supplier | 0.78301 | 8.6232
MT00051 | P001 | A017 | 2026-05-25 | Cement | Concrete Materials | bags | 3.6648 | 3.8513 | 411.0122 | 1582.9351 | Simulated Supplier | 0.18648 | 5.0884
MT00052 | P001 | A018 | 2026-06-03 | Sand | Aggregate | m³ | 10.8165 | 11.4969 | 1614.024 | 18556.3226 | Simulated Supplier | 0.68038 | 6.2902
MT00053 | P001 | A018 | 2026-06-09 | Reinforcement Steel | Steel | kg | 2826.6791 | 2856.618 | 66063.2985 | 188717607.205 | Simulated Supplier | 29.9389 | 1.0592
MT00054 | P001 | A018 | 2026-06-11 | Reinforcement Steel | Steel | kg | 1561.4482 | 1587.186 | 72605.6578 | 115238680.9057 | Simulated Supplier | 25.7378 | 1.6483
MT00055 | P001 | A019 | 2026-06-21 | Cement | Concrete Materials | bags | 4.1198 | 4.3039 | 445.0905 | 1915.634 | Simulated Supplier | 0.18414 | 4.4696
MT00056 | P001 | A019 | 2026-06-27 | Sand | Aggregate | m³ | 9.8565 | 10.4149 | 1586.5569 | 16523.7785 | Simulated Supplier | 0.55836 | 5.6648
MT00057 | P001 | A019 | 2026-07-02 | Reinforcement Steel | Steel | kg | 2204.9788 | 2303.132 | 71587.2533 | 164874894.0972 | Simulated Supplier | 98.1532 | 4.4514
MT00058 | P001 | A020 | 2026-07-09 | Reinforcement Steel | Steel | kg | 2559.4184 | 2698.4157 | 65590.9572 | 176991667.1509 | Simulated Supplier | 138.9973 | 5.4308
MT00059 | P001 | A020 | 2026-07-17 | Coarse Aggregate | Aggregate | m³ | 21.3957 | 22.6228 | 1832.8318 | 41463.8412 | Simulated Supplier | 1.2271 | 5.7353
MT00060 | P001 | A020 | 2026-07-22 | Coarse Aggregate | Aggregate | m³ | 13.1186 | 13.4794 | 1773.5048 | 23905.8615 | Simulated Supplier | 0.36082 | 2.7505
MT00061 | P001 | A021 | 2026-07-24 | Coarse Aggregate | Aggregate | m³ | 18.0826 | 19.528 | 1890.3109 | 36913.9978 | Simulated Supplier | 1.4454 | 7.9934
MT00062 | P001 | A021 | 2026-07-30 | Reinforcement Steel | Steel | kg | 3344.3446 | 3450.8671 | 70063.7727 | 241780765.2578 | Simulated Supplier | 106.5225 | 3.1852
MT00063 | P001 | A021 | 2026-08-08 | Coarse Aggregate | Aggregate | m³ | 24.8968 | 26.0875 | 1806.3274 | 47122.5013 | Simulated Supplier | 1.1906 | 4.7823
MT00064 | P001 | A022 | 2026-08-15 | Reinforcement Steel | Steel | kg | 2468.1008 | 2569.8585 | 69159.0548 | 177728981.5168 | Simulated Supplier | 101.7576 | 4.1229
MT00065 | P001 | A022 | 2026-08-20 | Coarse Aggregate | Aggregate | m³ | 14.0288 | 14.4292 | 1736.7375 | 25059.8155 | Simulated Supplier | 0.4004 | 2.8541
MT00066 | P001 | A022 | 2026-08-27 | Cement | Concrete Materials | bags | 2.8469 | 2.9348 | 451.1622 | 1324.0836 | Simulated Supplier | 0.087962 | 3.0898
MT00067 | P001 | A023 | 2026-09-04 | Sand | Aggregate | m³ | 10.8248 | 11.8438 | 1590.8596 | 18841.8838 | Simulated Supplier | 1.019 | 9.4137
MT00068 | P001 | A023 | 2026-09-05 | Cement | Concrete Materials | bags | 2.2979 | 2.4106 | 448.9823 | 1082.3033 | Simulated Supplier | 0.11271 | 4.9052
MT00069 | P001 | A023 | 2026-09-17 | Coarse Aggregate | Aggregate | m³ | 22.4782 | 23.7944 | 1890.3226 | 44979.0826 | Simulated Supplier | 1.3162 | 5.8553
MT00070 | P001 | A024 | 2026-09-24 | Sand | Aggregate | m³ | 10.2676 | 11.04 | 1442.5607 | 15925.806 | Simulated Supplier | 0.77234 | 7.5221
MT00071 | P001 | A024 | 2026-09-30 | Sand | Aggregate | m³ | 9.0027 | 9.9084 | 1452.5791 | 14392.6651 | Simulated Supplier | 0.90565 | 10.0598
MT00072 | P001 | A024 | 2026-10-01 | Cement | Concrete Materials | bags | 4.0816 | 4.1309 | 463.8219 | 1916.0073 | Simulated Supplier | 0.049283 | 1.2074
MT00073 | P001 | A025 | 2026-10-14 | Cement | Concrete Materials | bags | 3.2485 | 3.5038 | 422.6008 | 1480.7147 | Simulated Supplier | 0.25533 | 7.8601
MT00074 | P001 | A025 | 2026-10-16 | Reinforcement Steel | Steel | kg | 1828.046 | 1864.3566 | 65223.1272 | 121599167.8379 | Simulated Supplier | 36.3106 | 1.9863
MT00075 | P001 | A025 | 2026-10-20 | Reinforcement Steel | Steel | kg | 3413.3201 | 3574.7783 | 66813.3291 | 238842838.5564 | Simulated Supplier | 161.4582 | 4.7302
MT00076 | P001 | A026 | 2026-04-15 | Coarse Aggregate | Aggregate | m³ | 17.9782 | 18.3686 | 1874.6744 | 34435.1251 | Simulated Supplier | 0.39038 | 2.1714
MT00077 | P001 | A026 | 2026-04-25 | Coarse Aggregate | Aggregate | m³ | 15.3553 | 15.9232 | 1774.1718 | 28250.4206 | Simulated Supplier | 0.5679 | 3.6984
MT00078 | P001 | A026 | 2026-04-26 | Coarse Aggregate | Aggregate | m³ | 28.1767 | 30.0431 | 1886.6762 | 56681.6201 | Simulated Supplier | 1.8664 | 6.6241
MT00079 | P001 | A027 | 2026-05-03 | Sand | Aggregate | m³ | 11.1765 | 11.8609 | 1595.8872 | 18928.7038 | Simulated Supplier | 0.68446 | 6.1241
MT00080 | P001 | A027 | 2026-05-07 | Sand | Aggregate | m³ | 15.8119 | 16.8475 | 1590.4904 | 26795.8116 | Simulated Supplier | 1.0356 | 6.5494
MT00081 | P001 | A027 | 2026-05-19 | Coarse Aggregate | Aggregate | m³ | 16.9214 | 17.3535 | 1824.4796 | 31661.1173 | Simulated Supplier | 0.43209 | 2.5535
MT00082 | P001 | A028 | 2026-05-25 | Sand | Aggregate | m³ | 9.6987 | 10.6636 | 1616.3461 | 17236.0465 | Simulated Supplier | 0.96492 | 9.949
MT00083 | P001 | A028 | 2026-05-27 | Sand | Aggregate | m³ | 10.4627 | 11.4444 | 1523.6229 | 17437.0244 | Simulated Supplier | 0.98176 | 9.3834
MT00084 | P001 | A028 | 2026-06-04 | Reinforcement Steel | Steel | kg | 2251.0451 | 2390.269 | 66681.3958 | 159386475.6781 | Simulated Supplier | 139.224 | 6.1849
MT00085 | P001 | A029 | 2026-06-23 | Coarse Aggregate | Aggregate | m³ | 27.0256 | 27.9659 | 1938.862 | 54222.0452 | Simulated Supplier | 0.94032 | 3.4794
MT00086 | P001 | A029 | 2026-07-01 | Sand | Aggregate | m³ | 12.4217 | 13.0766 | 1489.6355 | 19479.4364 | Simulated Supplier | 0.65496 | 5.2727
MT00087 | P001 | A029 | 2026-07-02 | Cement | Concrete Materials | bags | 2.8838 | 3.0989 | 463.6504 | 1436.8287 | Simulated Supplier | 0.21516 | 7.4611
MT00088 | P001 | A030 | 2026-07-12 | Reinforcement Steel | Steel | kg | 2878.3829 | 3051.089 | 66525.3373 | 202974728.0824 | Simulated Supplier | 172.7061 | 6.0001
MT00089 | P001 | A030 | 2026-07-12 | Sand | Aggregate | m³ | 16.7604 | 18.5727 | 1593.507 | 29595.7093 | Simulated Supplier | 1.8123 | 10.8128
MT00090 | P001 | A030 | 2026-07-18 | Reinforcement Steel | Steel | kg | 2204.1704 | 2276.2276 | 67456.4533 | 153546239.5551 | Simulated Supplier | 72.0572 | 3.2691
MT00091 | P001 | A031 | 2026-07-31 | Sand | Aggregate | m³ | 11.3912 | 12.2029 | 1524.8764 | 18607.9312 | Simulated Supplier | 0.81175 | 7.1262
MT00092 | P001 | A031 | 2026-08-01 | Cement | Concrete Materials | bags | 4.005 | 4.3082 | 444.1972 | 1913.6834 | Simulated Supplier | 0.30319 | 7.5703
MT00093 | P001 | A031 | 2026-08-06 | Coarse Aggregate | Aggregate | m³ | 29.7049 | 31.5941 | 1908.7741 | 60306.094 | Simulated Supplier | 1.8892 | 6.36
MT00094 | P001 | A032 | 2026-08-22 | Reinforcement Steel | Steel | kg | 3027.2554 | 3085.0922 | 68553.2388 | 211493062.1398 | Simulated Supplier | 57.8368 | 1.9105
MT00095 | P001 | A032 | 2026-09-02 | Cement | Concrete Materials | bags | 3.6229 | 3.7279 | 444.7518 | 1657.9948 | Simulated Supplier | 0.10502 | 2.8989
MT00096 | P001 | A032 | 2026-09-02 | Coarse Aggregate | Aggregate | m³ | 23.8562 | 25.4852 | 1751.1488 | 44628.3907 | Simulated Supplier | 1.629 | 6.8283
MT00097 | P001 | A033 | 2026-09-07 | Sand | Aggregate | m³ | 18.879 | 20.2603 | 1432.597 | 29024.8141 | Simulated Supplier | 1.3813 | 7.3164
MT00098 | P001 | A033 | 2026-09-10 | Cement | Concrete Materials | bags | 3.7965 | 4.0989 | 459.8383 | 1884.8186 | Simulated Supplier | 0.30234 | 7.9636
MT00099 | P001 | A033 | 2026-09-25 | Cement | Concrete Materials | bags | 3.6735 | 3.8294 | 455.7027 | 1745.0836 | Simulated Supplier | 0.15597 | 4.2459
MT00100 | P001 | A034 | 2026-10-01 | Reinforcement Steel | Steel | kg | 3471.5618 | 3572.8316 | 72291.6432 | 258285866.4526 | Simulated Supplier | 101.2698 | 2.9171
MT00101 | P001 | A034 | 2026-10-08 | Cement | Concrete Materials | bags | 2.4484 | 2.4913 | 440.6032 | 1097.6604 | Simulated Supplier | 0.042885 | 1.7516
MT00102 | P001 | A034 | 2026-10-13 | Reinforcement Steel | Steel | kg | 2188.2736 | 2328.6521 | 68620.1605 | 159792479.2937 | Simulated Supplier | 140.3785 | 6.415
MT00103 | P001 | A035 | 2026-10-19 | Reinforcement Steel | Steel | kg | 2677.457 | 2829.4373 | 67608.6451 | 191294420.1667 | Simulated Supplier | 151.9803 | 5.6763
MT00104 | P001 | A035 | 2026-10-21 | Sand | Aggregate | m³ | 9.2201 | 9.7655 | 1455.7159 | 14215.8191 | Simulated Supplier | 0.54545 | 5.9159
MT00105 | P001 | A035 | 2026-10-21 | Reinforcement Steel | Steel | kg | 3829.546 | 3904.9391 | 70435.4399 | 275046106.5876 | Simulated Supplier | 75.3931 | 1.9687
MT00106 | P001 | A036 | 2026-11-10 | Cement | Concrete Materials | bags | 4.3491 | 4.4162 | 457.3921 | 2019.932 | Simulated Supplier | 0.0671 | 1.5429
MT00107 | P001 | A036 | 2026-11-14 | Cement | Concrete Materials | bags | 2.3629 | 2.3943 | 450.988 | 1079.7864 | Simulated Supplier | 0.031331 | 1.3259
MT00108 | P001 | A036 | 2026-11-21 | Reinforcement Steel | Steel | kg | 1816.6989 | 1860.9372 | 67123.8995 | 124913363.8825 | Simulated Supplier | 44.2383 | 2.4351
MT00109 | P001 | A037 | 2026-05-01 | Reinforcement Steel | Steel | kg | 3446.5973 | 3560.3821 | 66761.9355 | 237698002.839 | Simulated Supplier | 113.7848 | 3.3014
MT00110 | P001 | A037 | 2026-05-04 | Coarse Aggregate | Aggregate | m³ | 29.0533 | 31.3723 | 1803.5886 | 56582.6752 | Simulated Supplier | 2.3189 | 7.9817
MT00111 | P001 | A037 | 2026-05-11 | Reinforcement Steel | Steel | kg | 4364.1146 | 4510.2886 | 69240.2078 | 312293323.1164 | Simulated Supplier | 146.174 | 3.3495
MT00112 | P001 | A038 | 2026-06-01 | Reinforcement Steel | Steel | kg | 4213.3016 | 4314.2609 | 67902.5445 | 292949295.9643 | Simulated Supplier | 100.9593 | 2.3962
MT00113 | P001 | A038 | 2026-06-04 | Coarse Aggregate | Aggregate | m³ | 46.8696 | 48.7812 | 1730.2287 | 84402.6608 | Simulated Supplier | 1.9116 | 4.0786
MT00114 | P001 | A038 | 2026-06-06 | Sand | Aggregate | m³ | 25.4824 | 27.1196 | 1579.7477 | 42842.136 | Simulated Supplier | 1.6372 | 6.4248
MT00115 | P001 | A039 | 2026-06-15 | Reinforcement Steel | Steel | kg | 3103.6538 | 3226.8225 | 66313.1267 | 213980686.1525 | Simulated Supplier | 123.1686 | 3.9685
MT00116 | P001 | A039 | 2026-06-19 | Sand | Aggregate | m³ | 21.645 | 23.4053 | 1523.7892 | 35664.7895 | Simulated Supplier | 1.7603 | 8.1326
MT00117 | P001 | A039 | 2026-06-20 | Reinforcement Steel | Steel | kg | 4205.3031 | 4365.1663 | 66963.2212 | 292305598.3896 | Simulated Supplier | 159.8632 | 3.8015
MT00118 | P001 | A040 | 2026-07-06 | Coarse Aggregate | Aggregate | m³ | 38.7484 | 41.7049 | 1770.6726 | 73845.7141 | Simulated Supplier | 2.9565 | 7.6299
MT00119 | P001 | A040 | 2026-07-16 | Cement | Concrete Materials | bags | 4.7271 | 4.9101 | 426.1901 | 2092.6199 | Simulated Supplier | 0.18295 | 3.8702
MT00120 | P001 | A040 | 2026-07-24 | Reinforcement Steel | Steel | kg | 4575.3493 | 4651.1505 | 72638.2236 | 337851312.6591 | Simulated Supplier | 75.8012 | 1.6567
MT00121 | P001 | A041 | 2026-08-03 | Coarse Aggregate | Aggregate | m³ | 51.3478 | 52.8463 | 1859.3716 | 98260.9812 | Simulated Supplier | 1.4986 | 2.9184
MT00122 | P001 | A041 | 2026-08-11 | Sand | Aggregate | m³ | 24.4542 | 25.8186 | 1576.932 | 40714.1786 | Simulated Supplier | 1.3644 | 5.5795
MT00123 | P001 | A041 | 2026-08-15 | Reinforcement Steel | Steel | kg | 5948.9563 | 5964.1276 | 68517.6934 | 408648263.8831 | Simulated Supplier | 15.1712 | 0.25502
MT00124 | P001 | A042 | 2026-08-24 | Reinforcement Steel | Steel | kg | 5701.8517 | 5780.3497 | 69283.4374 | 400482494.7668 | Simulated Supplier | 78.498 | 1.3767
MT00125 | P001 | A042 | 2026-08-30 | Coarse Aggregate | Aggregate | m³ | 37.8585 | 39.8944 | 1926.2452 | 76846.4502 | Simulated Supplier | 2.0359 | 5.3778
MT00126 | P001 | A042 | 2026-08-31 | Cement | Concrete Materials | bags | 5.4467 | 5.8784 | 412.1456 | 2422.7768 | Simulated Supplier | 0.43171 | 7.9261
MT00127 | P001 | A043 | 2026-09-21 | Reinforcement Steel | Steel | kg | 4026.1573 | 4285.9954 | 69084.744 | 296096897.329 | Simulated Supplier | 259.8381 | 6.4538
MT00128 | P001 | A043 | 2026-09-30 | Sand | Aggregate | m³ | 20.0513 | 21.2358 | 1553.4693 | 32989.1222 | Simulated Supplier | 1.1845 | 5.9074
MT00129 | P001 | A043 | 2026-09-30 | Cement | Concrete Materials | bags | 6.4905 | 6.8778 | 444.5045 | 3057.1939 | Simulated Supplier | 0.38722 | 5.9659
MT00130 | P001 | A044 | 2026-10-08 | Sand | Aggregate | m³ | 19.9232 | 20.7286 | 1439.6247 | 29841.3803 | Simulated Supplier | 0.80538 | 4.0424
MT00131 | P001 | A044 | 2026-10-11 | Cement | Concrete Materials | bags | 5.38 | 5.4646 | 423.9097 | 2316.5136 | Simulated Supplier | 0.084651 | 1.5734
MT00132 | P001 | A044 | 2026-10-15 | Coarse Aggregate | Aggregate | m³ | 39.6982 | 43.2645 | 1924.4147 | 83258.8944 | Simulated Supplier | 3.5663 | 8.9835
MT00133 | P001 | A045 | 2026-10-30 | Reinforcement Steel | Steel | kg | 3164.1528 | 3234.7858 | 71226.4308 | 230402250.0674 | Simulated Supplier | 70.6331 | 2.2323
MT00134 | P001 | A045 | 2026-11-07 | Coarse Aggregate | Aggregate | m³ | 46.7274 | 49.9011 | 1824.9131 | 91065.1797 | Simulated Supplier | 3.1737 | 6.7919
MT00135 | P001 | A045 | 2026-11-09 | Coarse Aggregate | Aggregate | m³ | 40.9307 | 44.4866 | 1783.9046 | 79359.8927 | Simulated Supplier | 3.5559 | 8.6877
MT00136 | P001 | A046 | 2026-11-18 | Coarse Aggregate | Aggregate | m³ | 34.5385 | 37.2665 | 1887.3724 | 70335.7484 | Simulated Supplier | 2.728 | 7.8985
MT00137 | P001 | A046 | 2026-11-21 | Cement | Concrete Materials | bags | 5.3535 | 5.4853 | 411.075 | 2254.8719 | Simulated Supplier | 0.13176 | 2.4611
MT00138 | P001 | A046 | 2026-11-23 | Reinforcement Steel | Steel | kg | 3266.3704 | 3433.2092 | 68212.0308 | 234186169.249 | Simulated Supplier | 166.8388 | 5.1078
MT00139 | P001 | A047 | 2026-12-20 | Reinforcement Steel | Steel | kg | 3811.6157 | 3949.6929 | 70619.7447 | 278926304.0081 | Simulated Supplier | 138.0772 | 3.6225
MT00140 | P001 | A047 | 2026-12-23 | Reinforcement Steel | Steel | kg | 4014.2908 | 4278.6029 | 68383.7691 | 292586991.0653 | Simulated Supplier | 264.312 | 6.5843
MT00141 | P001 | A047 | 2026-12-26 | Cement | Concrete Materials | bags | 6.3569 | 6.6432 | 438.718 | 2914.4962 | Simulated Supplier | 0.28633 | 4.5042
MT00142 | P001 | A048 | 2026-04-15 | Reinforcement Steel | Steel | kg | 3429.6602 | 3589.2878 | 70823.6453 | 254206445.0074 | Simulated Supplier | 159.6276 | 4.6543
MT00143 | P001 | A048 | 2026-05-09 | Sand | Aggregate | m³ | 14.4623 | 15.4479 | 1459.8903 | 22552.3092 | Simulated Supplier | 0.98563 | 6.8152
MT00144 | P001 | A048 | 2026-05-25 | Coarse Aggregate | Aggregate | m³ | 19.7513 | 21.403 | 1848.9055 | 39572.1665 | Simulated Supplier | 1.6518 | 8.3628
MT00145 | P001 | A049 | 2026-06-03 | Bricks | Masonry Materials | no. | 123929.1613 | 134246.8706 | 11.632 | 1561554.6907 | Simulated Supplier | 10317.7093 | 8.3255
MT00146 | P001 | A049 | 2026-06-07 | Bricks | Masonry Materials | no. | 231018.8265 | 246868.5556 | 10.6731 | 2634850.7901 | Simulated Supplier | 15849.729 | 6.8608
MT00147 | P001 | A049 | 2026-06-21 | Cement | Masonry Materials | bags | 20.2461 | 21.0509 | 423.8687 | 8922.8069 | Simulated Supplier | 0.80476 | 3.9749
MT00148 | P001 | A049 | 2026-06-29 | Bricks | Masonry Materials | no. | 158772.262 | 171649.0603 | 10.6472 | 1827581.2572 | Simulated Supplier | 12876.7983 | 8.1102
MT00149 | P001 | A050 | 2026-06-23 | Bricks | Masonry Materials | no. | 130432.0925 | 144935.6183 | 11.602 | 1681541.3236 | Simulated Supplier | 14503.5258 | 11.1196
MT00150 | P001 | A050 | 2026-06-25 | Bricks | Masonry Materials | no. | 140821.6599 | 150126.0573 | 11.8079 | 1772671.8304 | Simulated Supplier | 9304.3974 | 6.6072
MT00151 | P001 | A050 | 2026-07-17 | Sand | Masonry Materials | m³ | 92.2403 | 96.0801 | 1479.3485 | 142135.9219 | Simulated Supplier | 3.8398 | 4.1628
MT00152 | P001 | A050 | 2026-07-17 | Sand | Masonry Materials | m³ | 100.8418 | 111.1312 | 1477.9307 | 164244.1907 | Simulated Supplier | 10.2894 | 10.2035
MT00153 | P001 | A050 | 2026-08-03 | Bricks | Masonry Materials | no. | 90268.0201 | 96412.4698 | 10.8695 | 1047957.895 | Simulated Supplier | 6144.4497 | 6.8069
MT00154 | P001 | A051 | 2026-07-08 | Cement | Masonry Materials | bags | 1.4526 | 1.5112 | 422.1696 | 637.9655 | Simulated Supplier | 0.058596 | 4.0339
MT00155 | P001 | A051 | 2026-07-12 | Sand | Masonry Materials | m³ | 7.8472 | 8.4821 | 1526.2662 | 12945.9683 | Simulated Supplier | 0.63494 | 8.0913
MT00156 | P001 | A051 | 2026-07-24 | Cement | Masonry Materials | bags | 2.0217 | 2.1382 | 430.1613 | 919.7612 | Simulated Supplier | 0.11651 | 5.763
MT00157 | P001 | A052 | 2026-08-12 | Paint | Finishing Materials | litre | 584.9591 | 616.4422 | 191.1205 | 117814.7454 | Simulated Supplier | 31.4831 | 5.3821
MT00158 | P001 | A052 | 2026-08-28 | Cement | Finishing Materials | bags | 285.92 | 290.9619 | 447.3526 | 130162.5593 | Simulated Supplier | 5.0419 | 1.7634
MT00159 | P001 | A052 | 2026-09-11 | Paint | Finishing Materials | litre | 458.2531 | 479.2189 | 177.5643 | 85092.1577 | Simulated Supplier | 20.9658 | 4.5752
MT00160 | P001 | A052 | 2026-09-14 | Cement | Finishing Materials | bags | 376.3408 | 387.1832 | 447.1824 | 173141.5353 | Simulated Supplier | 10.8424 | 2.881
MT00161 | P001 | A052 | 2026-10-06 | Tiles | Finishing Materials | m² | 5805.283 | 6243.2695 | 905.711 | 5654598.1416 | Simulated Supplier | 437.9865 | 7.5446
MT00162 | P001 | A053 | 2026-09-15 | Cement | Finishing Materials | bags | 285.2492 | 291.6936 | 457.6016 | 133479.4633 | Simulated Supplier | 6.4444 | 2.2592
MT00163 | P001 | A053 | 2026-09-30 | Tiles | Finishing Materials | m² | 2902.8885 | 3197.7071 | 820.9468 | 2625147.3142 | Simulated Supplier | 294.8186 | 10.156
MT00164 | P001 | A053 | 2026-09-30 | Paint | Finishing Materials | litre | 369.4364 | 386.1238 | 173.8215 | 67116.6151 | Simulated Supplier | 16.6874 | 4.517
MT00165 | P001 | A053 | 2026-10-05 | Tiles | Finishing Materials | m² | 3342.2726 | 3696.1597 | 843.2997 | 3116970.4891 | Simulated Supplier | 353.887 | 10.5882
MT00166 | P001 | A054 | 2026-08-22 | Waterproofing Material | Waterproofing | kg | 479.598 | 520.0896 | 160.4848 | 83466.4839 | Simulated Supplier | 40.4915 | 8.4428
MT00167 | P001 | A054 | 2026-09-05 | Cement | Waterproofing | bags | 39.2476 | 40.0823 | 423.9151 | 16991.4746 | Simulated Supplier | 0.83465 | 2.1266
MT00168 | P001 | A054 | 2026-09-17 | Cement | Waterproofing | bags | 36.7052 | 37.9493 | 420.5807 | 15960.7613 | Simulated Supplier | 1.2441 | 3.3895
MT00169 | P001 | A055 | 2026-12-04 | Waterproofing Material | Waterproofing | kg | 892.8369 | 958.0499 | 165.0996 | 158173.6377 | Simulated Supplier | 65.2129 | 7.304
MT00170 | P001 | A055 | 2026-12-09 | Cement | Waterproofing | bags | 41.1295 | 42.2632 | 443.7745 | 18755.3286 | Simulated Supplier | 1.1337 | 2.7564
MT00171 | P001 | A055 | 2026-12-16 | Cement | Waterproofing | bags | 55.6887 | 59.0693 | 443.8103 | 26215.5729 | Simulated Supplier | 3.3806 | 6.0705
MT00172 | P001 | A056 | 2026-09-28 | Cement | Finishing Materials | bags | 224.0035 | 241.6701 | 438.2111 | 105902.5221 | Simulated Supplier | 17.6666 | 7.8867
MT00173 | P001 | A056 | 2026-09-30 | Tiles | Finishing Materials | m² | 2496.9321 | 2700.8383 | 894.0313 | 2414633.8572 | Simulated Supplier | 203.9061 | 8.1663
MT00174 | P001 | A056 | 2026-10-18 | Paint | Finishing Materials | litre | 367.3419 | 384.2201 | 188.3586 | 72371.1599 | Simulated Supplier | 16.8782 | 4.5947
MT00175 | P001 | A056 | 2026-10-29 | Cement | Finishing Materials | bags | 298.7183 | 322.211 | 421.2333 | 135726.0014 | Simulated Supplier | 23.4927 | 7.8645
MT00176 | P001 | A056 | 2026-11-26 | Paint | Finishing Materials | litre | 330.968 | 346.5265 | 179.4451 | 62182.4882 | Simulated Supplier | 15.5585 | 4.7009
MT00177 | P001 | A057 | 2026-10-10 | Tiles | Finishing Materials | m² | 1713.0102 | 1839.8502 | 834.4285 | 1535223.3867 | Simulated Supplier | 126.84 | 7.4045
MT00178 | P001 | A057 | 2026-10-11 | Tiles | Finishing Materials | m² | 2017.6311 | 2150.6565 | 842.6667 | 1812286.5911 | Simulated Supplier | 133.0254 | 6.5931
MT00179 | P001 | A057 | 2026-11-11 | Tiles | Finishing Materials | m² | 1966.4793 | 2130.6534 | 876.7454 | 1868040.5765 | Simulated Supplier | 164.1741 | 8.3486
MT00180 | P001 | A057 | 2026-11-14 | Paint | Finishing Materials | litre | 202.8324 | 221.3097 | 184.6227 | 40858.8019 | Simulated Supplier | 18.4773 | 9.1096
MT00181 | P001 | A058 | 2026-10-18 | Cement | Finishing Materials | bags | 5.6323 | 6.0087 | 459.5929 | 2761.5574 | Simulated Supplier | 0.37642 | 6.6832
MT00182 | P001 | A058 | 2026-10-19 | Tiles | Finishing Materials | m² | 70.7484 | 75.1172 | 825.2488 | 61990.4154 | Simulated Supplier | 4.3688 | 6.1752
MT00183 | P001 | A058 | 2026-11-10 | Paint | Finishing Materials | litre | 9.0016 | 9.4814 | 185.8147 | 1761.7799 | Simulated Supplier | 0.47975 | 5.3296
MT00184 | P001 | A058 | 2026-11-10 | Cement | Finishing Materials | bags | 3.3472 | 3.4048 | 408.8845 | 1392.1645 | Simulated Supplier | 0.057628 | 1.7217
MT00185 | P001 | A059 | 2026-10-08 | Paint | Finishing Materials | litre | 98.147 | 105.1827 | 176.2309 | 18536.4384 | Simulated Supplier | 7.0357 | 7.1685
MT00186 | P001 | A059 | 2026-10-13 | Paint | Finishing Materials | litre | 89.4352 | 94.3294 | 185.3964 | 17488.3275 | Simulated Supplier | 4.8942 | 5.4723
MT00187 | P001 | A059 | 2026-10-18 | Tiles | Finishing Materials | m² | 808.3824 | 878.2307 | 892.2382 | 783590.9521 | Simulated Supplier | 69.8482 | 8.6405
MT00188 | P001 | A059 | 2026-11-23 | Cement | Finishing Materials | bags | 76.0001 | 79.0987 | 451.7679 | 35734.2699 | Simulated Supplier | 3.0986 | 4.0771
MT00189 | P001 | A060 | 2026-10-14 | Paint | Finishing Materials | litre | 1092.0993 | 1165.5152 | 175.7822 | 204876.7764 | Simulated Supplier | 73.4159 | 6.7225
MT00190 | P001 | A060 | 2026-11-22 | Cement | Finishing Materials | bags | 427.4704 | 437.639 | 424.7816 | 185900.9839 | Simulated Supplier | 10.1685 | 2.3788
MT00191 | P001 | A060 | 2026-11-24 | Paint | Finishing Materials | litre | 883.8094 | 947.4962 | 181.2362 | 171720.6215 | Simulated Supplier | 63.6868 | 7.2059
MT00192 | P001 | A060 | 2026-11-26 | Cement | Finishing Materials | bags | 380.3424 | 406.5082 | 457.6424 | 186035.4013 | Simulated Supplier | 26.1658 | 6.8795
MT00193 | P001 | A060 | 2026-12-07 | Cement | Finishing Materials | bags | 454.0271 | 477.9288 | 432.81 | 206852.3855 | Simulated Supplier | 23.9018 | 5.2644
MT00194 | P001 | A061 | 2026-11-04 | Cement | Finishing Materials | bags | 434.6821 | 439.2558 | 456.1068 | 200347.5586 | Simulated Supplier | 4.5737 | 1.0522
MT00195 | P001 | A061 | 2026-11-11 | Tiles | Finishing Materials | m² | 3504.823 | 3795.8956 | 829.3979 | 3148307.9107 | Simulated Supplier | 291.0726 | 8.3049
MT00196 | P001 | A061 | 2026-11-24 | Tiles | Finishing Materials | m² | 2752.9343 | 2899.6841 | 905.2389 | 2624906.8758 | Simulated Supplier | 146.7499 | 5.3307
MT00197 | P001 | A061 | 2026-12-01 | Paint | Finishing Materials | litre | 608.2746 | 632.9414 | 178.3998 | 112916.6509 | Simulated Supplier | 24.6668 | 4.0552
MT00198 | P001 | A062 | 2026-08-30 | Sanitary Fixtures | MEP | no. | 2038.284 | 2177.1817 | 6309.4545 | 13736828.8758 | Simulated Supplier | 138.8977 | 6.8144
MT00199 | P001 | A062 | 2026-09-08 | Electrical Cables | MEP | m | 2046.232 | 2127.0954 | 194.2965 | 413287.2641 | Simulated Supplier | 80.8634 | 3.9518
MT00200 | P001 | A062 | 2026-09-23 | Sanitary Fixtures | MEP | no. | 2272.0463 | 2424.6765 | 6407.1093 | 15535167.3824 | Simulated Supplier | 152.6302 | 6.7177
MT00201 | P001 | A062 | 2026-09-26 | Pipes | MEP | m | 1566.6798 | 1648.4367 | 497.7509 | 820510.7864 | Simulated Supplier | 81.7569 | 5.2185
MT00202 | P001 | A062 | 2026-10-09 | Electrical Cables | MEP | m | 2162.4454 | 2208.4697 | 187.9607 | 415105.4322 | Simulated Supplier | 46.0243 | 2.1283
MT00203 | P001 | A062 | 2026-10-30 | Electrical Cables | MEP | m | 1234.3888 | 1291.0556 | 195.9023 | 252920.7777 | Simulated Supplier | 56.6669 | 4.5907
MT00204 | P001 | A063 | 2026-10-22 | Pipes | MEP | m | 54.8693 | 56.5484 | 517.2305 | 29248.5529 | Simulated Supplier | 1.6791 | 3.0603
MT00205 | P001 | A063 | 2026-10-29 | Pipes | MEP | m | 54.7645 | 59.0855 | 509.0966 | 30080.2406 | Simulated Supplier | 4.321 | 7.8902
MT00206 | P001 | A063 | 2026-11-12 | Electrical Cables | MEP | m | 55.5005 | 56.6364 | 189.145 | 10712.4832 | Simulated Supplier | 1.1359 | 2.0466
MT00207 | P001 | A063 | 2026-11-14 | Sanitary Fixtures | MEP | no. | 72.7661 | 76.4549 | 6527.1124 | 499029.9452 | Simulated Supplier | 3.6888 | 5.0695
MT00208 | P001 | A064 | 2026-08-25 | Electrical Cables | MEP | m | 3709.9789 | 3855.1947 | 203.6528 | 785121.1937 | Simulated Supplier | 145.2158 | 3.9142
MT00209 | P001 | A064 | 2026-08-28 | Sanitary Fixtures | MEP | no. | 4817.095 | 5121.1524 | 6465.3989 | 33110292.998 | Simulated Supplier | 304.0574 | 6.312
MT00210 | P001 | A064 | 2026-09-25 | Pipes | MEP | m | 5009.6419 | 5408.5978 | 531.5595 | 2874991.7891 | Simulated Supplier | 398.956 | 7.9638
MT00211 | P001 | A064 | 2026-10-31 | Pipes | MEP | m | 4062.8508 | 4338.9405 | 552.2594 | 2396220.5926 | Simulated Supplier | 276.0898 | 6.7955
MT00212 | P001 | A064 | 2026-11-14 | Sanitary Fixtures | MEP | no. | 4296.1802 | 4427.7246 | 6194.2662 | 27426504.9517 | Simulated Supplier | 131.5444 | 3.0619
MT00213 | P001 | A064 | 2026-11-22 | Sanitary Fixtures | MEP | no. | 3617.0679 | 3767.3129 | 6314.1767 | 23787478.9784 | Simulated Supplier | 150.245 | 4.1538
MT00214 | P001 | A065 | 2026-11-11 | Electrical Cables | MEP | m | 189.6191 | 193.795 | 195.6201 | 37910.2044 | Simulated Supplier | 4.1759 | 2.2023
MT00215 | P001 | A065 | 2026-11-28 | Sanitary Fixtures | MEP | no. | 178.9703 | 182.2221 | 6957.8009 | 1267864.9803 | Simulated Supplier | 3.2518 | 1.8169
MT00216 | P001 | A065 | 2026-11-30 | Sanitary Fixtures | MEP | no. | 220.7043 | 234.7563 | 6220.4396 | 1460287.4297 | Simulated Supplier | 14.052 | 6.3669
MT00217 | P001 | A065 | 2026-12-13 | Electrical Cables | MEP | m | 217.4964 | 224.3428 | 191.1618 | 42885.7644 | Simulated Supplier | 6.8464 | 3.1478
MT00218 | P001 | A066 | 2026-10-29 | Sand | External Works | m³ | 154.2514 | 165.1668 | 1466.6945 | 242249.191 | Simulated Supplier | 10.9154 | 7.0764
MT00219 | P001 | A066 | 2026-11-11 | Cement | External Works | bags | 13.7141 | 14.7887 | 425.2503 | 6288.9008 | Simulated Supplier | 1.0746 | 7.8361
MT00220 | P001 | A066 | 2026-11-14 | Sand | External Works | m³ | 128.2249 | 137.6421 | 1595.5286 | 219611.9007 | Simulated Supplier | 9.4172 | 7.3443
MT00221 | P001 | A067 | 2026-11-10 | Cement | External Works | bags | 137.4226 | 140.9842 | 455.6109 | 64233.9459 | Simulated Supplier | 3.5616 | 2.5917
MT00222 | P001 | A067 | 2026-11-28 | Paving Blocks | External Works | m² | 1031.0597 | 1082.0013 | 743.5995 | 804575.6912 | Simulated Supplier | 50.9416 | 4.9407
MT00223 | P001 | A067 | 2026-12-24 | Sand | External Works | m³ | 579.6422 | 636.7057 | 1599.7012 | 1018538.8138 | Simulated Supplier | 57.0635 | 9.8446
MT00224 | P001 | A068 | 2026-12-13 | Cement | External Works | bags | 2041.7907 | 2156.3155 | 413.4172 | 891457.8473 | Simulated Supplier | 114.5247 | 5.609
MT00225 | P001 | A068 | 2026-12-20 | Sand | External Works | m³ | 9753.168 | 10291.6719 | 1437.2388 | 14791590.5198 | Simulated Supplier | 538.5039 | 5.5213
MT00226 | P001 | A068 | 2026-12-24 | Cement | External Works | bags | 1957.2534 | 2057.5962 | 433.9474 | 892888.4604 | Simulated Supplier | 100.3428 | 5.1267

## Quality
Inspection_ID | Project_ID | Activity_ID | Date | Contractor_ID | Inspection_Type | Test_or_Check | Result | Defect_Type | Defect_Severity | Rework_Required | Rework_Cost_INR | Remarks
Q00001 | P001 | A001 | 2026-01-01 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00002 | P001 | A001 | 2026-01-01 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00003 | P001 | A001 | 2026-01-04 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00004 | P001 | A001 | 2026-01-10 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00005 | P001 | A001 | 2026-01-10 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00006 | P001 | A002 | 2026-01-04 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00007 | P001 | A002 | 2026-01-07 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00008 | P001 | A002 | 2026-01-08 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00009 | P001 | A002 | 2026-01-08 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00010 | P001 | A002 | 2026-01-09 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00011 | P001 | A003 | 2026-01-05 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00012 | P001 | A003 | 2026-01-13 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00013 | P001 | A003 | 2026-01-15 | C001 | Setting out check | Setting out check | Conditional Pass | Crack | Low | No | 2652.3756 | Inspection completed; corrective action tracked where required.
Q00014 | P001 | A003 | 2026-01-18 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00015 | P001 | A003 | 2026-01-24 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00016 | P001 | A004 | 2026-01-08 | C001 | Site inspection | Site inspection | Conditional Pass | Honeycombing | Low | No | 1722.5243 | Inspection completed; corrective action tracked where required.
Q00017 | P001 | A004 | 2026-01-09 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00018 | P001 | A004 | 2026-01-09 | C001 | Setting out check | Setting out check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00019 | P001 | A004 | 2026-01-12 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00020 | P001 | A004 | 2026-01-13 | C001 | Site inspection | Site inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00021 | P001 | A005 | 2026-01-12 | C001 | Level check | Level check | Conditional Pass | Crack | Low | No | 365.9035 | Inspection completed; corrective action tracked where required.
Q00022 | P001 | A005 | 2026-01-17 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00023 | P001 | A005 | 2026-01-17 | C001 | Compaction test | Compaction test | Fail | Workmanship | Low | Yes | 18461.9456 | Inspection completed; corrective action tracked where required.
Q00024 | P001 | A005 | 2026-01-23 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00025 | P001 | A005 | 2026-01-31 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00026 | P001 | A006 | 2026-02-01 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00027 | P001 | A006 | 2026-02-02 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00028 | P001 | A006 | 2026-02-03 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00029 | P001 | A006 | 2026-02-03 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00030 | P001 | A006 | 2026-02-10 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00031 | P001 | A007 | 2026-02-06 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00032 | P001 | A007 | 2026-02-07 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00033 | P001 | A007 | 2026-02-09 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00034 | P001 | A007 | 2026-02-18 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00035 | P001 | A007 | 2026-02-20 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00036 | P001 | A008 | 2026-01-21 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00037 | P001 | A008 | 2026-01-22 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00038 | P001 | A008 | 2026-01-24 | C001 | Level check | Level check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00039 | P001 | A008 | 2026-01-30 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00040 | P001 | A008 | 2026-01-31 | C001 | Compaction test | Compaction test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00041 | P001 | A009 | 2026-02-16 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00042 | P001 | A009 | 2026-02-18 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00043 | P001 | A009 | 2026-02-23 | C002 | Rebar inspection | Rebar inspection | Conditional Pass | Workmanship | Medium | No | 2114.5297 | Inspection completed; corrective action tracked where required.
Q00044 | P001 | A009 | 2026-02-27 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00045 | P001 | A009 | 2026-03-01 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00046 | P001 | A010 | 2026-02-23 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00047 | P001 | A010 | 2026-02-28 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00048 | P001 | A010 | 2026-03-02 | C002 | RCC inspection | RCC inspection | Conditional Pass | Honeycombing | Low | No | 4781.6997 | Inspection completed; corrective action tracked where required.
Q00049 | P001 | A010 | 2026-03-06 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Reinforcement Issue | Medium | No | 1909.3771 | Inspection completed; corrective action tracked where required.
Q00050 | P001 | A010 | 2026-03-13 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00051 | P001 | A011 | 2026-03-18 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00052 | P001 | A011 | 2026-03-22 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00053 | P001 | A011 | 2026-03-23 | C002 | Concrete inspection | Concrete inspection | Fail | Honeycombing | Low | Yes | 8368.5869 | Inspection completed; corrective action tracked where required.
Q00054 | P001 | A011 | 2026-03-28 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00055 | P001 | A011 | 2026-03-28 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00056 | P001 | A012 | 2026-03-22 | C002 | Rebar inspection | Rebar inspection | Conditional Pass | Surface Finish | Medium | No | 3812.0092 | Inspection completed; corrective action tracked where required.
Q00057 | P001 | A012 | 2026-03-26 | C002 | Concrete inspection | Concrete inspection | Fail | Reinforcement Issue | Low | Yes | 12868.7348 | Inspection completed; corrective action tracked where required.
Q00058 | P001 | A012 | 2026-03-27 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00059 | P001 | A012 | 2026-03-28 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00060 | P001 | A012 | 2026-03-31 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00061 | P001 | A013 | 2026-03-25 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00062 | P001 | A013 | 2026-03-28 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00063 | P001 | A013 | 2026-04-01 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00064 | P001 | A013 | 2026-04-06 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00065 | P001 | A013 | 2026-04-08 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00066 | P001 | A014 | 2026-04-11 | C001 | Rebar inspection | Rebar inspection | Conditional Pass | Crack | Low | No | 1640.7176 | Inspection completed; corrective action tracked where required.
Q00067 | P001 | A014 | 2026-04-13 | C001 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00068 | P001 | A014 | 2026-04-13 | C001 | RCC inspection | RCC inspection | Conditional Pass | Dimension | Low | No | 731.9491 | Inspection completed; corrective action tracked where required.
Q00069 | P001 | A014 | 2026-04-13 | C001 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00070 | P001 | A014 | 2026-04-16 | C001 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00071 | P001 | A015 | 2026-04-03 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00072 | P001 | A015 | 2026-04-07 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00073 | P001 | A015 | 2026-04-11 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00074 | P001 | A015 | 2026-04-14 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00075 | P001 | A015 | 2026-04-17 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00076 | P001 | A016 | 2026-04-24 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Crack | Medium | No | 1490.6115 | Inspection completed; corrective action tracked where required.
Q00077 | P001 | A016 | 2026-04-24 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00078 | P001 | A016 | 2026-04-26 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00079 | P001 | A016 | 2026-05-01 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00080 | P001 | A016 | 2026-05-05 | C002 | Rebar inspection | Rebar inspection | Conditional Pass | Surface Finish | Medium | No | 3254.7196 | Inspection completed; corrective action tracked where required.
Q00081 | P001 | A017 | 2026-05-14 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00082 | P001 | A017 | 2026-05-22 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00083 | P001 | A017 | 2026-05-23 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00084 | P001 | A017 | 2026-05-25 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00085 | P001 | A017 | 2026-05-25 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Honeycombing | Medium | No | 4759.1622 | Inspection completed; corrective action tracked where required.
Q00086 | P001 | A018 | 2026-05-28 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00087 | P001 | A018 | 2026-06-01 | C002 | Rebar inspection | Rebar inspection | Fail | Honeycombing | Low | Yes | 22920.0776 | Inspection completed; corrective action tracked where required.
Q00088 | P001 | A018 | 2026-06-04 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00089 | P001 | A018 | 2026-06-04 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00090 | P001 | A018 | 2026-06-11 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00091 | P001 | A019 | 2026-06-19 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00092 | P001 | A019 | 2026-06-19 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00093 | P001 | A019 | 2026-06-26 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00094 | P001 | A019 | 2026-06-28 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00095 | P001 | A019 | 2026-06-30 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00096 | P001 | A020 | 2026-07-08 | C002 | Rebar inspection | Rebar inspection | Fail | Dimension | Low | Yes | 18012.0492 | Inspection completed; corrective action tracked where required.
Q00097 | P001 | A020 | 2026-07-08 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00098 | P001 | A020 | 2026-07-10 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00099 | P001 | A020 | 2026-07-15 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00100 | P001 | A020 | 2026-07-21 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00101 | P001 | A021 | 2026-07-27 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00102 | P001 | A021 | 2026-07-28 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00103 | P001 | A021 | 2026-07-30 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00104 | P001 | A021 | 2026-08-04 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00105 | P001 | A021 | 2026-08-06 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00106 | P001 | A022 | 2026-08-13 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00107 | P001 | A022 | 2026-08-17 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00108 | P001 | A022 | 2026-08-22 | C002 | Rebar inspection | Rebar inspection | Conditional Pass | Surface Finish | Low | No | 1923.9732 | Inspection completed; corrective action tracked where required.
Q00109 | P001 | A022 | 2026-08-24 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00110 | P001 | A022 | 2026-08-25 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00111 | P001 | A023 | 2026-09-02 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00112 | P001 | A023 | 2026-09-11 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Honeycombing | Low | No | 2214.5703 | Inspection completed; corrective action tracked where required.
Q00113 | P001 | A023 | 2026-09-14 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00114 | P001 | A023 | 2026-09-16 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00115 | P001 | A023 | 2026-09-16 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00116 | P001 | A024 | 2026-09-19 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00117 | P001 | A024 | 2026-09-22 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00118 | P001 | A024 | 2026-09-27 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00119 | P001 | A024 | 2026-09-28 | C002 | RCC inspection | RCC inspection | Fail | Workmanship | Low | Yes | 29799.4622 | Inspection completed; corrective action tracked where required.
Q00120 | P001 | A024 | 2026-10-03 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00121 | P001 | A025 | 2026-10-08 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00122 | P001 | A025 | 2026-10-09 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00123 | P001 | A025 | 2026-10-14 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00124 | P001 | A025 | 2026-10-16 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00125 | P001 | A025 | 2026-10-19 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00126 | P001 | A026 | 2026-04-13 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00127 | P001 | A026 | 2026-04-14 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00128 | P001 | A026 | 2026-04-24 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00129 | P001 | A026 | 2026-04-24 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00130 | P001 | A026 | 2026-04-25 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00131 | P001 | A027 | 2026-05-04 | C002 | Rebar inspection | Rebar inspection | Conditional Pass | Crack | Low | No | 3414.4733 | Inspection completed; corrective action tracked where required.
Q00132 | P001 | A027 | 2026-05-05 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00133 | P001 | A027 | 2026-05-10 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00134 | P001 | A027 | 2026-05-15 | C002 | Rebar inspection | Rebar inspection | Fail | Reinforcement Issue | Low | Yes | 5009.4326 | Inspection completed; corrective action tracked where required.
Q00135 | P001 | A027 | 2026-05-16 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00136 | P001 | A028 | 2026-05-24 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00137 | P001 | A028 | 2026-05-29 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00138 | P001 | A028 | 2026-05-31 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00139 | P001 | A028 | 2026-06-10 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00140 | P001 | A028 | 2026-06-11 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00141 | P001 | A029 | 2026-06-18 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00142 | P001 | A029 | 2026-06-19 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00143 | P001 | A029 | 2026-06-21 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00144 | P001 | A029 | 2026-06-23 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00145 | P001 | A029 | 2026-07-01 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00146 | P001 | A030 | 2026-07-07 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00147 | P001 | A030 | 2026-07-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00148 | P001 | A030 | 2026-07-12 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00149 | P001 | A030 | 2026-07-15 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00150 | P001 | A030 | 2026-07-22 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00151 | P001 | A031 | 2026-07-28 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00152 | P001 | A031 | 2026-07-30 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00153 | P001 | A031 | 2026-08-02 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00154 | P001 | A031 | 2026-08-04 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00155 | P001 | A031 | 2026-08-14 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00156 | P001 | A032 | 2026-08-17 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00157 | P001 | A032 | 2026-08-21 | C002 | RCC inspection | RCC inspection | Conditional Pass | Leakage | Low | No | 4207.1593 | Inspection completed; corrective action tracked where required.
Q00158 | P001 | A032 | 2026-08-24 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00159 | P001 | A032 | 2026-09-02 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00160 | P001 | A032 | 2026-09-03 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00161 | P001 | A033 | 2026-09-10 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00162 | P001 | A033 | 2026-09-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00163 | P001 | A033 | 2026-09-15 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00164 | P001 | A033 | 2026-09-15 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00165 | P001 | A033 | 2026-09-18 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00166 | P001 | A034 | 2026-09-28 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00167 | P001 | A034 | 2026-10-09 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00168 | P001 | A034 | 2026-10-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00169 | P001 | A034 | 2026-10-12 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00170 | P001 | A034 | 2026-10-16 | C002 | RCC inspection | RCC inspection | Conditional Pass | Leakage | Low | No | 3351.8225 | Inspection completed; corrective action tracked where required.
Q00171 | P001 | A035 | 2026-10-20 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00172 | P001 | A035 | 2026-10-23 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00173 | P001 | A035 | 2026-10-23 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00174 | P001 | A035 | 2026-10-24 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00175 | P001 | A035 | 2026-11-05 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00176 | P001 | A036 | 2026-11-09 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00177 | P001 | A036 | 2026-11-10 | C002 | RCC inspection | RCC inspection | Conditional Pass | Leakage | Low | No | 4911.1541 | Inspection completed; corrective action tracked where required.
Q00178 | P001 | A036 | 2026-11-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00179 | P001 | A036 | 2026-11-19 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00180 | P001 | A036 | 2026-11-25 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00181 | P001 | A037 | 2026-05-02 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00182 | P001 | A037 | 2026-05-03 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00183 | P001 | A037 | 2026-05-06 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00184 | P001 | A037 | 2026-05-08 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00185 | P001 | A037 | 2026-05-15 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00186 | P001 | A038 | 2026-05-24 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00187 | P001 | A038 | 2026-05-30 | C002 | RCC inspection | RCC inspection | Conditional Pass | Material Quality | Low | No | 2872.3383 | Inspection completed; corrective action tracked where required.
Q00188 | P001 | A038 | 2026-05-30 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00189 | P001 | A038 | 2026-05-31 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00190 | P001 | A038 | 2026-06-04 | C002 | RCC inspection | RCC inspection | Conditional Pass | Leakage | Low | No | 2782.7776 | Inspection completed; corrective action tracked where required.
Q00191 | P001 | A039 | 2026-06-11 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00192 | P001 | A039 | 2026-06-11 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00193 | P001 | A039 | 2026-06-20 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00194 | P001 | A039 | 2026-06-22 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00195 | P001 | A039 | 2026-06-23 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00196 | P001 | A040 | 2026-07-04 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00197 | P001 | A040 | 2026-07-06 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00198 | P001 | A040 | 2026-07-12 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00199 | P001 | A040 | 2026-07-21 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00200 | P001 | A040 | 2026-07-24 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00201 | P001 | A041 | 2026-07-27 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00202 | P001 | A041 | 2026-08-02 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00203 | P001 | A041 | 2026-08-08 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00204 | P001 | A041 | 2026-08-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00205 | P001 | A041 | 2026-08-11 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00206 | P001 | A042 | 2026-08-20 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00207 | P001 | A042 | 2026-08-23 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00208 | P001 | A042 | 2026-08-28 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00209 | P001 | A042 | 2026-08-29 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00210 | P001 | A042 | 2026-09-02 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00211 | P001 | A043 | 2026-09-11 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00212 | P001 | A043 | 2026-09-22 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00213 | P001 | A043 | 2026-09-26 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00214 | P001 | A043 | 2026-09-28 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00215 | P001 | A043 | 2026-10-01 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00216 | P001 | A044 | 2026-10-06 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00217 | P001 | A044 | 2026-10-18 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00218 | P001 | A044 | 2026-10-20 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00219 | P001 | A044 | 2026-10-20 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00220 | P001 | A044 | 2026-10-23 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00221 | P001 | A045 | 2026-10-31 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00222 | P001 | A045 | 2026-11-02 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Material Quality | Low | No | 2745.7029 | Inspection completed; corrective action tracked where required.
Q00223 | P001 | A045 | 2026-11-08 | C002 | RCC inspection | RCC inspection | Conditional Pass | Reinforcement Issue | Low | No | 2890.3038 | Inspection completed; corrective action tracked where required.
Q00224 | P001 | A045 | 2026-11-14 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00225 | P001 | A045 | 2026-11-15 | C002 | Concrete inspection | Concrete inspection | Conditional Pass | Reinforcement Issue | Low | No | 2920.2418 | Inspection completed; corrective action tracked where required.
Q00226 | P001 | A046 | 2026-11-18 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00227 | P001 | A046 | 2026-11-26 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00228 | P001 | A046 | 2026-11-27 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00229 | P001 | A046 | 2026-12-06 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00230 | P001 | A046 | 2026-12-06 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00231 | P001 | A047 | 2026-12-11 | C002 | RCC inspection | RCC inspection | Conditional Pass | Honeycombing | Medium | No | 268.5768 | Inspection completed; corrective action tracked where required.
Q00232 | P001 | A047 | 2026-12-14 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00233 | P001 | A047 | 2026-12-17 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00234 | P001 | A047 | 2026-12-22 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00235 | P001 | A047 | 2026-12-26 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00236 | P001 | A048 | 2026-04-17 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00237 | P001 | A048 | 2026-05-05 | C002 | Concrete inspection | Concrete inspection | Fail | Reinforcement Issue | Medium | Yes | 8124.2904 | Inspection completed; corrective action tracked where required.
Q00238 | P001 | A048 | 2026-05-12 | C002 | Rebar inspection | Rebar inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00239 | P001 | A048 | 2026-05-19 | C002 | RCC inspection | RCC inspection | Fail | Honeycombing | Low | Yes | 27901.6116 | Inspection completed; corrective action tracked where required.
Q00240 | P001 | A048 | 2026-05-21 | C002 | RCC inspection | RCC inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00241 | P001 | A048 | 2026-05-22 | C002 | RCC inspection | RCC inspection | Conditional Pass | Crack | Medium | No | 4407.816 | Inspection completed; corrective action tracked where required.
Q00242 | P001 | A048 | 2026-05-25 | C002 | Concrete inspection | Concrete inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00243 | P001 | A049 | 2026-06-10 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00244 | P001 | A049 | 2026-06-11 | C003 | Dimensional check | Dimensional check | Conditional Pass | Poor Compaction | Medium | No | 4570.3029 | Inspection completed; corrective action tracked where required.
Q00245 | P001 | A049 | 2026-06-20 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00246 | P001 | A049 | 2026-06-21 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00247 | P001 | A049 | 2026-06-22 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00248 | P001 | A049 | 2026-06-29 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00249 | P001 | A049 | 2026-07-12 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00250 | P001 | A049 | 2026-07-16 | C003 | Brickwork inspection | Brickwork inspection | Conditional Pass | Honeycombing | High | Yes | 34022.3994 | Inspection completed; corrective action tracked where required.
Q00251 | P001 | A049 | 2026-07-18 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00252 | P001 | A049 | 2026-08-02 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00253 | P001 | A049 | 2026-08-03 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00254 | P001 | A050 | 2026-06-16 | C003 | Brickwork inspection | Brickwork inspection | Conditional Pass | Dimension | High | Yes | 19099.698 | Inspection completed; corrective action tracked where required.
Q00255 | P001 | A050 | 2026-06-18 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00256 | P001 | A050 | 2026-06-25 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00257 | P001 | A050 | 2026-07-01 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00258 | P001 | A050 | 2026-07-02 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00259 | P001 | A050 | 2026-07-09 | C003 | Dimensional check | Dimensional check | Conditional Pass | Leakage | Low | No | 1117.2231 | Inspection completed; corrective action tracked where required.
Q00260 | P001 | A050 | 2026-07-17 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00261 | P001 | A050 | 2026-07-21 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00262 | P001 | A050 | 2026-07-30 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00263 | P001 | A050 | 2026-08-05 | C003 | Dimensional check | Dimensional check | Fail | Crack | High | Yes | 18949.9948 | Inspection completed; corrective action tracked where required.
Q00264 | P001 | A050 | 2026-08-10 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00265 | P001 | A050 | 2026-08-10 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00266 | P001 | A051 | 2026-07-24 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00267 | P001 | A051 | 2026-07-25 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00268 | P001 | A051 | 2026-07-25 | C003 | Dimensional check | Dimensional check | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00269 | P001 | A051 | 2026-07-27 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00270 | P001 | A051 | 2026-07-30 | C003 | Brickwork inspection | Brickwork inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00271 | P001 | A052 | 2026-08-30 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00272 | P001 | A052 | 2026-09-01 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00273 | P001 | A052 | 2026-09-08 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00274 | P001 | A052 | 2026-09-08 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00275 | P001 | A052 | 2026-09-12 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00276 | P001 | A052 | 2026-09-15 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00277 | P001 | A052 | 2026-09-15 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00278 | P001 | A052 | 2026-09-19 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00279 | P001 | A052 | 2026-09-19 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00280 | P001 | A052 | 2026-09-29 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00281 | P001 | A052 | 2026-10-06 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00282 | P001 | A052 | 2026-10-08 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00283 | P001 | A053 | 2026-08-22 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00284 | P001 | A053 | 2026-08-26 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00285 | P001 | A053 | 2026-09-03 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00286 | P001 | A053 | 2026-09-07 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00287 | P001 | A053 | 2026-09-13 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00288 | P001 | A053 | 2026-09-15 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00289 | P001 | A053 | 2026-09-16 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00290 | P001 | A053 | 2026-09-29 | C004 | Flooring inspection | Flooring inspection | Conditional Pass | Leakage | Low | No | 992.1967 | Inspection completed; corrective action tracked where required.
Q00291 | P001 | A053 | 2026-09-30 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00292 | P001 | A053 | 2026-10-08 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00293 | P001 | A054 | 2026-08-25 | C008 | Waterproofing inspection | Waterproofing inspection | Conditional Pass | Leakage | Low | No | 500.5271 | Inspection completed; corrective action tracked where required.
Q00294 | P001 | A054 | 2026-08-31 | C008 | Leakage test | Leakage test | Fail | Workmanship | Medium | Yes | 5710.9221 | Inspection completed; corrective action tracked where required.
Q00295 | P001 | A054 | 2026-09-05 | C008 | Leakage test | Leakage test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00296 | P001 | A054 | 2026-09-08 | C008 | Waterproofing inspection | Waterproofing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00297 | P001 | A054 | 2026-09-11 | C008 | Leakage test | Leakage test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00298 | P001 | A055 | 2026-11-27 | C008 | Waterproofing inspection | Waterproofing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00299 | P001 | A055 | 2026-12-03 | C008 | Leakage test | Leakage test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00300 | P001 | A055 | 2026-12-06 | C008 | Leakage test | Leakage test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00301 | P001 | A055 | 2026-12-07 | C008 | Leakage test | Leakage test | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00302 | P001 | A055 | 2026-12-18 | C008 | Waterproofing inspection | Waterproofing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00303 | P001 | A056 | 2026-09-21 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00304 | P001 | A056 | 2026-09-25 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00305 | P001 | A056 | 2026-09-25 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00306 | P001 | A056 | 2026-09-25 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00307 | P001 | A056 | 2026-09-28 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00308 | P001 | A056 | 2026-10-01 | C004 | Flooring inspection | Flooring inspection | Conditional Pass | Workmanship | Low | No | 210.1532 | Inspection completed; corrective action tracked where required.
Q00309 | P001 | A056 | 2026-10-03 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00310 | P001 | A056 | 2026-10-09 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00311 | P001 | A056 | 2026-10-25 | C004 | Painting inspection | Painting inspection | Fail | Crack | Medium | Yes | 20532.1936 | Inspection completed; corrective action tracked where required.
Q00312 | P001 | A056 | 2026-11-01 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00313 | P001 | A056 | 2026-11-03 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00314 | P001 | A056 | 2026-11-05 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00315 | P001 | A056 | 2026-11-08 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00316 | P001 | A056 | 2026-11-24 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00317 | P001 | A057 | 2026-09-26 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00318 | P001 | A057 | 2026-09-29 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00319 | P001 | A057 | 2026-10-04 | C004 | Painting inspection | Painting inspection | Fail | Honeycombing | Low | Yes | 20870.318 | Inspection completed; corrective action tracked where required.
Q00320 | P001 | A057 | 2026-10-13 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00321 | P001 | A057 | 2026-10-27 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00322 | P001 | A057 | 2026-11-01 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00323 | P001 | A057 | 2026-11-13 | C004 | Painting inspection | Painting inspection | Conditional Pass | Alignment | Low | No | 46.6729 | Inspection completed; corrective action tracked where required.
Q00324 | P001 | A057 | 2026-11-18 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00325 | P001 | A057 | 2026-11-19 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00326 | P001 | A057 | 2026-11-21 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00327 | P001 | A057 | 2026-11-25 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00328 | P001 | A058 | 2026-10-17 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00329 | P001 | A058 | 2026-10-22 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00330 | P001 | A058 | 2026-10-31 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00331 | P001 | A058 | 2026-10-31 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00332 | P001 | A058 | 2026-11-25 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00333 | P001 | A058 | 2026-11-25 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00334 | P001 | A058 | 2026-12-07 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00335 | P001 | A058 | 2026-12-09 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00336 | P001 | A058 | 2026-12-11 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00337 | P001 | A058 | 2026-12-18 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00338 | P001 | A059 | 2026-09-28 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00339 | P001 | A059 | 2026-10-11 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00340 | P001 | A059 | 2026-10-19 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00341 | P001 | A059 | 2026-10-20 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00342 | P001 | A059 | 2026-10-26 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00343 | P001 | A059 | 2026-10-27 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00344 | P001 | A059 | 2026-10-30 | C004 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00345 | P001 | A059 | 2026-11-01 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00346 | P001 | A059 | 2026-11-09 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00347 | P001 | A059 | 2026-11-17 | C004 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00348 | P001 | A059 | 2026-11-27 | C004 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00349 | P001 | A060 | 2026-10-04 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00350 | P001 | A060 | 2026-10-15 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00351 | P001 | A060 | 2026-10-18 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00352 | P001 | A060 | 2026-10-24 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00353 | P001 | A060 | 2026-10-31 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00354 | P001 | A060 | 2026-11-01 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00355 | P001 | A060 | 2026-11-08 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00356 | P001 | A060 | 2026-11-12 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00357 | P001 | A060 | 2026-11-19 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00358 | P001 | A060 | 2026-11-24 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00359 | P001 | A060 | 2026-11-29 | C005 | Flooring inspection | Flooring inspection | Fail | Material Quality | High | Yes | 22158.8251 | Inspection completed; corrective action tracked where required.
Q00360 | P001 | A060 | 2026-12-17 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00361 | P001 | A060 | 2026-12-19 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00362 | P001 | A061 | 2026-10-19 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00363 | P001 | A061 | 2026-10-19 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00364 | P001 | A061 | 2026-10-22 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00365 | P001 | A061 | 2026-11-07 | C005 | Flooring inspection | Flooring inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00366 | P001 | A061 | 2026-11-13 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00367 | P001 | A061 | 2026-11-17 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00368 | P001 | A061 | 2026-11-20 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00369 | P001 | A061 | 2026-11-22 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00370 | P001 | A061 | 2026-12-07 | C005 | Painting inspection | Painting inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00371 | P001 | A061 | 2026-12-09 | C005 | Plaster inspection | Plaster inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00372 | P001 | A062 | 2026-08-25 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00373 | P001 | A062 | 2026-08-27 | C006 | Electrical inspection | Electrical inspection | Conditional Pass | Alignment | Low | No | 2279.9242 | Inspection completed; corrective action tracked where required.
Q00374 | P001 | A062 | 2026-08-28 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00375 | P001 | A062 | 2026-09-30 | C006 | Electrical inspection | Electrical inspection | Fail | Crack | Medium | Yes | 32370.1379 | Inspection completed; corrective action tracked where required.
Q00376 | P001 | A062 | 2026-10-05 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00377 | P001 | A062 | 2026-10-05 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00378 | P001 | A062 | 2026-10-18 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00379 | P001 | A062 | 2026-10-24 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00380 | P001 | A062 | 2026-10-27 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00381 | P001 | A062 | 2026-10-28 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00382 | P001 | A062 | 2026-11-06 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00383 | P001 | A062 | 2026-11-10 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00384 | P001 | A062 | 2026-11-10 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00385 | P001 | A062 | 2026-11-12 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00386 | P001 | A062 | 2026-11-17 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00387 | P001 | A062 | 2026-11-20 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00388 | P001 | A063 | 2026-10-22 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00389 | P001 | A063 | 2026-10-27 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00390 | P001 | A063 | 2026-10-28 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00391 | P001 | A063 | 2026-11-04 | C006 | Plumbing inspection | Plumbing inspection | Conditional Pass | Dimension | Low | No | 1444.0053 | Inspection completed; corrective action tracked where required.
Q00392 | P001 | A063 | 2026-11-12 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00393 | P001 | A063 | 2026-11-26 | C006 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00394 | P001 | A063 | 2026-12-01 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00395 | P001 | A063 | 2026-12-11 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00396 | P001 | A063 | 2026-12-16 | C006 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00397 | P001 | A063 | 2026-12-19 | C006 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00398 | P001 | A064 | 2026-08-23 | C007 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00399 | P001 | A064 | 2026-08-26 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00400 | P001 | A064 | 2026-08-26 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00401 | P001 | A064 | 2026-08-28 | C007 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00402 | P001 | A064 | 2026-08-29 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00403 | P001 | A064 | 2026-08-30 | C007 | Electrical inspection | Electrical inspection | Fail | Material Quality | Low | Yes | 6952.3288 | Inspection completed; corrective action tracked where required.
Q00404 | P001 | A064 | 2026-08-31 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00405 | P001 | A064 | 2026-09-06 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00406 | P001 | A064 | 2026-09-08 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00407 | P001 | A064 | 2026-10-16 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00408 | P001 | A064 | 2026-10-22 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00409 | P001 | A064 | 2026-10-25 | C007 | Sanitary inspection | Sanitary inspection | Fail | Alignment | Low | Yes | 16031.4141 | Inspection completed; corrective action tracked where required.
Q00410 | P001 | A064 | 2026-10-28 | C007 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00411 | P001 | A064 | 2026-11-14 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00412 | P001 | A064 | 2026-11-17 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00413 | P001 | A064 | 2026-11-23 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00414 | P001 | A065 | 2026-10-29 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00415 | P001 | A065 | 2026-11-01 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00416 | P001 | A065 | 2026-11-17 | C007 | Plumbing inspection | Plumbing inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00417 | P001 | A065 | 2026-11-21 | C007 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00418 | P001 | A065 | 2026-11-22 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00419 | P001 | A065 | 2026-11-25 | C007 | Sanitary inspection | Sanitary inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00420 | P001 | A065 | 2026-12-04 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00421 | P001 | A065 | 2026-12-09 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00422 | P001 | A065 | 2026-12-15 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00423 | P001 | A065 | 2026-12-21 | C007 | Electrical inspection | Electrical inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00424 | P001 | A066 | 2026-10-25 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00425 | P001 | A066 | 2026-10-25 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00426 | P001 | A066 | 2026-10-28 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00427 | P001 | A066 | 2026-10-29 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00428 | P001 | A066 | 2026-10-30 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00429 | P001 | A066 | 2026-11-19 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00430 | P001 | A066 | 2026-11-30 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00431 | P001 | A066 | 2026-12-01 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00432 | P001 | A066 | 2026-12-06 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00433 | P001 | A067 | 2026-11-06 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00434 | P001 | A067 | 2026-11-12 | C001 | Drainage inspection | Drainage inspection | Conditional Pass | Honeycombing | Medium | No | 1705.5102 | Inspection completed; corrective action tracked where required.
Q00435 | P001 | A067 | 2026-11-16 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00436 | P001 | A067 | 2026-11-24 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00437 | P001 | A067 | 2026-11-25 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00438 | P001 | A067 | 2026-12-01 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00439 | P001 | A067 | 2026-12-10 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00440 | P001 | A067 | 2026-12-17 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00441 | P001 | A067 | 2026-12-22 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00442 | P001 | A068 | 2026-12-06 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00443 | P001 | A068 | 2026-12-11 | C001 | Paving inspection | Paving inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00444 | P001 | A068 | 2026-12-11 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00445 | P001 | A068 | 2026-12-20 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.
Q00446 | P001 | A068 | 2026-12-20 | C001 | Drainage inspection | Drainage inspection | Pass | None | None | No | 0 | Inspection completed; corrective action tracked where required.

## Equipment
Equipment_ID | Project_ID | Activity_ID | Date | Equipment_Name | Equipment_Type | Operating_Hours | Downtime_Hours | Fuel_Consumption_Litres | Rental_Cost_INR | Maintenance_Cost_INR | Equipment_Status
EQ00001 | P001 | A001 | 2026-01-07 | Tower Crane | Lifting | 8.3682 | 0 | 46.6547 | 14307.4309 | 0 | Operational
EQ00002 | P001 | A001 | 2026-01-07 | Generator | Power | 9.0387 | 0 | 46.7215 | 13845.1618 | 0 | Operational
EQ00003 | P001 | A001 | 2026-01-07 | Tower Crane | Lifting | 6.4936 | 0 | 31.7684 | 9726.9279 | 0 | Operational
EQ00004 | P001 | A002 | 2026-01-01 | Tower Crane | Lifting | 7.3528 | 0 | 37.6169 | 8024.1646 | 0 | Operational
EQ00005 | P001 | A002 | 2026-01-06 | Tower Crane | Lifting | 5.7394 | 0 | 24.0388 | 11478.1084 | 0 | Operational
EQ00006 | P001 | A002 | 2026-01-08 | Tower Crane | Lifting | 6.2919 | 1 | 47.7691 | 7688.6231 | 810.7993 | Maintenance
EQ00007 | P001 | A003 | 2026-01-11 | Generator | Power | 5.173 | 0.5 | 34.4929 | 6108.0907 | 815.0494 | Operational
EQ00008 | P001 | A003 | 2026-01-15 | Tower Crane | Lifting | 4.8756 | 0.5 | 22.8207 | 7465.5654 | 561.5991 | Idle
EQ00009 | P001 | A003 | 2026-01-18 | Generator | Power | 6.7135 | 0 | 63.4262 | 10318.0533 | 0 | Operational
EQ00010 | P001 | A004 | 2026-01-09 | Tower Crane | Lifting | 4.4505 | 0 | 29.0375 | 7874.3777 | 0 | Idle
EQ00011 | P001 | A004 | 2026-01-11 | Tower Crane | Lifting | 7.8404 | 0.5 | 39.7009 | 7435.6174 | 1041.6881 | Operational
EQ00012 | P001 | A004 | 2026-01-13 | Tower Crane | Lifting | 4.547 | 0 | 43.7667 | 9787.8082 | 0 | Idle
EQ00013 | P001 | A005 | 2026-01-17 | Compactor | Earthwork | 5.2283 | 0 | 32.1129 | 10908.9414 | 0 | Operational
EQ00014 | P001 | A005 | 2026-01-19 | Loader | Earthwork | 7.9053 | 1 | 54.4926 | 9636.0016 | 2269.8313 | Maintenance
EQ00015 | P001 | A005 | 2026-01-23 | Excavator | Earthwork | 4.8304 | 0.5 | 39.7378 | 7193.804 | 1088.3649 | Idle
EQ00016 | P001 | A006 | 2026-02-02 | Excavator | Earthwork | 4.224 | 1 | 17.6074 | 6334.7898 | 942.5826 | Maintenance
EQ00017 | P001 | A006 | 2026-02-02 | Loader | Earthwork | 4.1549 | 0.5 | 17.5018 | 7667.0117 | 460.1652 | Idle
EQ00018 | P001 | A006 | 2026-02-04 | Loader | Earthwork | 8.4995 | 0.5 | 37.0239 | 16154.8935 | 518.4212 | Operational
EQ00019 | P001 | A007 | 2026-02-11 | Excavator | Earthwork | 9.0318 | 0 | 63.4753 | 19500.7079 | 0 | Operational
EQ00020 | P001 | A007 | 2026-02-12 | Loader | Earthwork | 9.3447 | 0.5 | 89.4395 | 19438.2587 | 1241.0298 | Operational
EQ00021 | P001 | A007 | 2026-02-17 | Compactor | Earthwork | 4.7901 | 0 | 42.2817 | 8323.6191 | 0 | Idle
EQ00022 | P001 | A008 | 2026-01-27 | Compactor | Earthwork | 6.9975 | 0 | 49.8843 | 7769.8181 | 0 | Operational
EQ00023 | P001 | A008 | 2026-02-03 | Compactor | Earthwork | 8.1586 | 0 | 74.1754 | 11048.4833 | 0 | Operational
EQ00024 | P001 | A008 | 2026-02-06 | Compactor | Earthwork | 9.0757 | 0 | 88.1449 | 9969.6662 | 0 | Operational
EQ00025 | P001 | A009 | 2026-02-15 | Tower Crane | Lifting | 8.2389 | 2 | 62.6321 | 9888.1375 | 2514.0264 | Breakdown
EQ00026 | P001 | A009 | 2026-02-16 | Tower Crane | Lifting | 9.1914 | 0 | 69.7212 | 10474.3209 | 0 | Operational
EQ00027 | P001 | A009 | 2026-02-24 | Concrete Mixer | Concrete | 7.4743 | 0 | 41.1006 | 10971.4576 | 0 | Operational
EQ00028 | P001 | A010 | 2026-02-26 | Tower Crane | Lifting | 8.4776 | 0 | 53.1911 | 12340.4905 | 0 | Operational
EQ00029 | P001 | A010 | 2026-03-02 | Tower Crane | Lifting | 8.2829 | 0 | 76.5186 | 17205.7305 | 0 | Operational
EQ00030 | P001 | A010 | 2026-03-04 | Concrete Pump | Concrete | 5.7044 | 0 | 44.6514 | 12213.7782 | 0 | Operational
EQ00031 | P001 | A011 | 2026-03-15 | Bar Cutting Machine | Rebar | 8.6352 | 0.5 | 14.2034 | 12634.6134 | 523.6065 | Operational
EQ00032 | P001 | A011 | 2026-03-16 | Needle Vibrator | Concrete | 6.9993 | 0 | 13.3977 | 10921.3813 | 0 | Operational
EQ00033 | P001 | A011 | 2026-03-23 | Concrete Pump | Concrete | 6.0892 | 0 | 43.3568 | 6501.8019 | 0 | Operational
EQ00034 | P001 | A012 | 2026-03-22 | Bar Cutting Machine | Rebar | 5.234 | 0 | 6.9617 | 9487.5273 | 0 | Operational
EQ00035 | P001 | A012 | 2026-03-29 | Transit Mixer | Concrete | 9.84 | 0 | 80.9133 | 12492.7379 | 0 | Operational
EQ00036 | P001 | A012 | 2026-04-03 | Concrete Pump | Concrete | 9.2544 | 0 | 53.1972 | 13896.9632 | 0 | Operational
EQ00037 | P001 | A013 | 2026-03-27 | Bar Cutting Machine | Rebar | 8.5187 | 0.5 | 15.4708 | 10720.1733 | 378.3782 | Operational
EQ00038 | P001 | A013 | 2026-04-01 | Transit Mixer | Concrete | 9.8575 | 0 | 47.5121 | 16893.9926 | 0 | Operational
EQ00039 | P001 | A013 | 2026-04-11 | Transit Mixer | Concrete | 4.8001 | 0 | 41.0596 | 9269.7418 | 0 | Idle
EQ00040 | P001 | A014 | 2026-04-10 | Tower Crane | Lifting | 4.9665 | 1 | 26.0548 | 4485.439 | 1549.2683 | Maintenance
EQ00041 | P001 | A014 | 2026-04-15 | Transit Mixer | Concrete | 8.3455 | 0 | 81.5625 | 9775.7174 | 0 | Operational
EQ00042 | P001 | A014 | 2026-04-16 | Concrete Mixer | Concrete | 4.108 | 0 | 35.1292 | 6015.0188 | 0 | Idle
EQ00043 | P001 | A015 | 2026-04-10 | Transit Mixer | Concrete | 6.6986 | 0 | 62.0842 | 12045.3331 | 0 | Operational
EQ00044 | P001 | A015 | 2026-04-10 | Transit Mixer | Concrete | 7.1669 | 1 | 62.3318 | 7196.9612 | 545.0377 | Maintenance
EQ00045 | P001 | A015 | 2026-04-17 | Bar Cutting Machine | Rebar | 4.6867 | 0 | 5.6243 | 5049.4686 | 0 | Idle
EQ00046 | P001 | A016 | 2026-04-27 | Concrete Pump | Concrete | 9.5 | 0 | 72.151 | 13348.3573 | 0 | Operational
EQ00047 | P001 | A016 | 2026-04-27 | Needle Vibrator | Concrete | 9.126 | 0 | 12.4344 | 14084.7236 | 0 | Operational
EQ00048 | P001 | A016 | 2026-04-30 | Bar Cutting Machine | Rebar | 8.8768 | 2 | 7.4424 | 9756.1487 | 3760.3861 | Breakdown
EQ00049 | P001 | A017 | 2026-05-09 | Bar Cutting Machine | Rebar | 8.5638 | 0 | 7.9384 | 13171.7621 | 0 | Operational
EQ00050 | P001 | A017 | 2026-05-17 | Concrete Pump | Concrete | 8.0038 | 2 | 54.6836 | 14734.461 | 3041.7503 | Breakdown
EQ00051 | P001 | A017 | 2026-05-18 | Bar Bending Machine | Rebar | 8.2772 | 2 | 13.312 | 15144.5274 | 2066.4228 | Breakdown
EQ00052 | P001 | A018 | 2026-05-28 | Concrete Pump | Concrete | 5.4971 | 2 | 46.2632 | 11764.7324 | 4464.9677 | Breakdown
EQ00053 | P001 | A018 | 2026-06-01 | Bar Bending Machine | Rebar | 7.6432 | 0 | 15.1921 | 12527.0411 | 0 | Operational
EQ00054 | P001 | A018 | 2026-06-07 | Concrete Mixer | Concrete | 8.7419 | 0 | 57.1874 | 10672.5919 | 0 | Operational
EQ00055 | P001 | A019 | 2026-06-17 | Tower Crane | Lifting | 9.211 | 1 | 90.6738 | 18929.1044 | 1009.0944 | Maintenance
EQ00056 | P001 | A019 | 2026-06-28 | Bar Bending Machine | Rebar | 7.9544 | 0 | 15.8026 | 9857.8958 | 0 | Operational
EQ00057 | P001 | A019 | 2026-06-29 | Concrete Mixer | Concrete | 9.0949 | 0.5 | 82.6481 | 8330.2149 | 691.9771 | Operational
EQ00058 | P001 | A020 | 2026-07-07 | Transit Mixer | Concrete | 7.5183 | 0 | 71.3416 | 9962.4042 | 0 | Operational
EQ00059 | P001 | A020 | 2026-07-09 | Tower Crane | Lifting | 8.638 | 2 | 36.663 | 18361.1159 | 1186.5876 | Breakdown
EQ00060 | P001 | A020 | 2026-07-13 | Bar Cutting Machine | Rebar | 7.4521 | 0.5 | 12.5165 | 8144.9899 | 429.3704 | Operational
EQ00061 | P001 | A021 | 2026-07-27 | Transit Mixer | Concrete | 6.8167 | 0.5 | 53.9025 | 8001.3089 | 553.9603 | Operational
EQ00062 | P001 | A021 | 2026-07-27 | Bar Bending Machine | Rebar | 9.8138 | 0 | 5.5614 | 11633.9296 | 0 | Operational
EQ00063 | P001 | A021 | 2026-08-06 | Tower Crane | Lifting | 9.9969 | 0 | 41.571 | 15663.1805 | 0 | Operational
EQ00064 | P001 | A022 | 2026-08-16 | Concrete Pump | Concrete | 8.2278 | 2 | 35.4126 | 12204.2821 | 1686.5501 | Breakdown
EQ00065 | P001 | A022 | 2026-08-17 | Tower Crane | Lifting | 7.5224 | 0 | 52.912 | 14034.7274 | 0 | Operational
EQ00066 | P001 | A022 | 2026-08-17 | Transit Mixer | Concrete | 9.538 | 0 | 67.7953 | 11793.5382 | 0 | Operational
EQ00067 | P001 | A023 | 2026-08-31 | Tower Crane | Lifting | 8.3297 | 2 | 76.4748 | 10098.7132 | 4359.4971 | Breakdown
EQ00068 | P001 | A023 | 2026-08-31 | Transit Mixer | Concrete | 4.4713 | 1 | 28.106 | 8988.4692 | 789.1707 | Maintenance
EQ00069 | P001 | A023 | 2026-09-17 | Transit Mixer | Concrete | 9.2526 | 0.5 | 62.1319 | 12570.2034 | 368.1262 | Operational
EQ00070 | P001 | A024 | 2026-09-23 | Bar Cutting Machine | Rebar | 8.142 | 0 | 11.0967 | 12638.243 | 0 | Operational
EQ00071 | P001 | A024 | 2026-09-28 | Bar Bending Machine | Rebar | 8.1959 | 2 | 10.6441 | 14250.5087 | 3425.5771 | Breakdown
EQ00072 | P001 | A024 | 2026-10-05 | Concrete Pump | Concrete | 7.7486 | 0 | 51.6166 | 14605.296 | 0 | Operational
EQ00073 | P001 | A025 | 2026-10-08 | Bar Bending Machine | Rebar | 7.6106 | 0.5 | 5.8378 | 11588.7722 | 507.3048 | Operational
EQ00074 | P001 | A025 | 2026-10-14 | Bar Bending Machine | Rebar | 4.021 | 0 | 7.2207 | 6304.1096 | 0 | Idle
EQ00075 | P001 | A025 | 2026-10-25 | Needle Vibrator | Concrete | 8.1579 | 0 | 13.9093 | 17942.1622 | 0 | Operational
EQ00076 | P001 | A026 | 2026-04-16 | Needle Vibrator | Concrete | 4.5601 | 0 | 4.9754 | 4207.3672 | 0 | Idle
EQ00077 | P001 | A026 | 2026-04-20 | Needle Vibrator | Concrete | 4.9592 | 0 | 7.9259 | 5144.0856 | 0 | Idle
EQ00078 | P001 | A026 | 2026-04-27 | Concrete Mixer | Concrete | 4.6515 | 0 | 18.8882 | 8511.2389 | 0 | Idle
EQ00079 | P001 | A027 | 2026-05-06 | Concrete Mixer | Concrete | 9.9118 | 1 | 64.1446 | 19894.3643 | 989.7739 | Maintenance
EQ00080 | P001 | A027 | 2026-05-11 | Concrete Mixer | Concrete | 5.6018 | 0.5 | 31.5945 | 5062.5576 | 677.9137 | Operational
EQ00081 | P001 | A027 | 2026-05-13 | Bar Bending Machine | Rebar | 4.0752 | 0 | 5.9609 | 6756.3683 | 0 | Idle
EQ00082 | P001 | A028 | 2026-05-31 | Bar Cutting Machine | Rebar | 4.3628 | 1 | 7.9458 | 7212.7133 | 2084.9338 | Maintenance
EQ00083 | P001 | A028 | 2026-06-06 | Tower Crane | Lifting | 4.7323 | 0 | 38.8743 | 9143.0028 | 0 | Idle
EQ00084 | P001 | A028 | 2026-06-11 | Bar Cutting Machine | Rebar | 8.9095 | 0 | 7.2091 | 11945.369 | 0 | Operational
EQ00085 | P001 | A029 | 2026-06-14 | Concrete Mixer | Concrete | 4.1542 | 2 | 24.3782 | 7306.6813 | 4956.941 | Breakdown
EQ00086 | P001 | A029 | 2026-06-15 | Needle Vibrator | Concrete | 8.0167 | 0.5 | 10.2724 | 11143.1578 | 849.7797 | Operational
EQ00087 | P001 | A029 | 2026-06-15 | Tower Crane | Lifting | 9.7527 | 0.5 | 63.8352 | 12992.3995 | 1133.5315 | Operational
EQ00088 | P001 | A030 | 2026-07-07 | Bar Bending Machine | Rebar | 5.5305 | 2 | 8.7019 | 10773.817 | 2907.9861 | Breakdown
EQ00089 | P001 | A030 | 2026-07-11 | Concrete Mixer | Concrete | 9.0686 | 0 | 56.2712 | 11942.3058 | 0 | Operational
EQ00090 | P001 | A030 | 2026-07-20 | Tower Crane | Lifting | 8.0983 | 0 | 39.0597 | 11875.3387 | 0 | Operational
EQ00091 | P001 | A031 | 2026-07-26 | Tower Crane | Lifting | 7.9632 | 0 | 60.2234 | 15702.0569 | 0 | Operational
EQ00092 | P001 | A031 | 2026-07-28 | Needle Vibrator | Concrete | 6.1169 | 0 | 11.1875 | 9941.9649 | 0 | Operational
EQ00093 | P001 | A031 | 2026-08-07 | Needle Vibrator | Concrete | 6.7064 | 1 | 12.3302 | 13168.6578 | 1412.5023 | Maintenance
EQ00094 | P001 | A032 | 2026-08-16 | Bar Bending Machine | Rebar | 4.739 | 0 | 7.5003 | 7694.5167 | 0 | Idle
EQ00095 | P001 | A032 | 2026-08-17 | Concrete Pump | Concrete | 9.8754 | 0.5 | 46.7537 | 14773.8717 | 744.1588 | Operational
EQ00096 | P001 | A032 | 2026-08-21 | Tower Crane | Lifting | 7.1895 | 0 | 54.8979 | 7941.1264 | 0 | Operational
EQ00097 | P001 | A033 | 2026-09-18 | Concrete Pump | Concrete | 7.782 | 0 | 70.3106 | 14489.0186 | 0 | Operational
EQ00098 | P001 | A033 | 2026-09-23 | Bar Cutting Machine | Rebar | 7.7513 | 0 | 8.4516 | 10795.5198 | 0 | Operational
EQ00099 | P001 | A033 | 2026-09-23 | Tower Crane | Lifting | 4.7759 | 0 | 30.263 | 4512.912 | 0 | Idle
EQ00100 | P001 | A034 | 2026-09-29 | Concrete Mixer | Concrete | 8.837 | 0.5 | 64.1224 | 17765.1097 | 1046.0671 | Operational
EQ00101 | P001 | A034 | 2026-10-05 | Tower Crane | Lifting | 9.862 | 0 | 40.3208 | 16527.6858 | 0 | Operational
EQ00102 | P001 | A034 | 2026-10-12 | Concrete Pump | Concrete | 7.5914 | 0 | 46.8598 | 7430.4766 | 0 | Operational
EQ00103 | P001 | A035 | 2026-10-19 | Concrete Mixer | Concrete | 7.6653 | 0 | 51.609 | 13793.761 | 0 | Operational
EQ00104 | P001 | A035 | 2026-10-25 | Tower Crane | Lifting | 5.6259 | 0 | 53.2202 | 8269.1605 | 0 | Operational
EQ00105 | P001 | A035 | 2026-11-06 | Bar Bending Machine | Rebar | 8.7924 | 0 | 9.8518 | 10694.7062 | 0 | Operational
EQ00106 | P001 | A036 | 2026-11-13 | Bar Cutting Machine | Rebar | 8.0673 | 2 | 7.8727 | 14002.9037 | 4328.2736 | Breakdown
EQ00107 | P001 | A036 | 2026-11-19 | Concrete Pump | Concrete | 8.9185 | 0 | 56.6454 | 12067.23 | 0 | Operational
EQ00108 | P001 | A036 | 2026-11-25 | Needle Vibrator | Concrete | 9.8627 | 0 | 12.5708 | 13814.8771 | 0 | Operational
EQ00109 | P001 | A037 | 2026-04-26 | Concrete Pump | Concrete | 8.3374 | 0 | 52.5664 | 14190.866 | 0 | Operational
EQ00110 | P001 | A037 | 2026-04-29 | Concrete Pump | Concrete | 7.9321 | 0 | 53.2893 | 14555.6868 | 0 | Operational
EQ00111 | P001 | A037 | 2026-05-07 | Tower Crane | Lifting | 9.0776 | 0 | 54.1225 | 16599.6417 | 0 | Operational
EQ00112 | P001 | A038 | 2026-05-21 | Transit Mixer | Concrete | 8.6362 | 0.5 | 44.392 | 14011.5255 | 408.1018 | Operational
EQ00113 | P001 | A038 | 2026-05-26 | Tower Crane | Lifting | 7.984 | 0 | 55.5558 | 11125.4048 | 0 | Operational
EQ00114 | P001 | A038 | 2026-05-31 | Transit Mixer | Concrete | 7.1577 | 1 | 69.4324 | 10390.7182 | 2076.1459 | Maintenance
EQ00115 | P001 | A039 | 2026-06-13 | Concrete Pump | Concrete | 6.0285 | 0 | 42.2649 | 6932.4178 | 0 | Operational
EQ00116 | P001 | A039 | 2026-06-23 | Concrete Mixer | Concrete | 5.1406 | 0 | 50.4521 | 9025.3347 | 0 | Operational
EQ00117 | P001 | A039 | 2026-06-26 | Concrete Mixer | Concrete | 6.9393 | 0 | 51.6718 | 11282.1486 | 0 | Operational
EQ00118 | P001 | A040 | 2026-07-03 | Bar Bending Machine | Rebar | 8.4681 | 0.5 | 10.508 | 14429.0719 | 507.4699 | Operational
EQ00119 | P001 | A040 | 2026-07-17 | Bar Bending Machine | Rebar | 6.4043 | 2 | 4.7615 | 6229.4183 | 3544.6877 | Breakdown
EQ00120 | P001 | A040 | 2026-07-21 | Concrete Pump | Concrete | 9.3748 | 2 | 76.9915 | 20509.9025 | 3891.313 | Breakdown
EQ00121 | P001 | A041 | 2026-07-29 | Bar Cutting Machine | Rebar | 4.4786 | 0.5 | 5.0443 | 5205.7634 | 1203.501 | Idle
EQ00122 | P001 | A041 | 2026-07-31 | Transit Mixer | Concrete | 9.9736 | 2 | 82.3357 | 14263.2436 | 1558.0368 | Breakdown
EQ00123 | P001 | A041 | 2026-08-02 | Concrete Pump | Concrete | 6.0216 | 1 | 35.9395 | 7102.6011 | 724.6902 | Maintenance
EQ00124 | P001 | A042 | 2026-08-22 | Bar Bending Machine | Rebar | 4.5113 | 2 | 4.4533 | 7159.4125 | 2418.0506 | Breakdown
EQ00125 | P001 | A042 | 2026-08-23 | Transit Mixer | Concrete | 4.2605 | 0.5 | 33.6215 | 6955.3951 | 930.9663 | Idle
EQ00126 | P001 | A042 | 2026-08-25 | Concrete Pump | Concrete | 6.6274 | 0.5 | 40.4329 | 7915.5652 | 750.0677 | Operational
EQ00127 | P001 | A043 | 2026-09-10 | Concrete Pump | Concrete | 8.0672 | 2 | 35.3131 | 14100.1708 | 2591.0989 | Breakdown
EQ00128 | P001 | A043 | 2026-09-29 | Concrete Mixer | Concrete | 8.811 | 1 | 85.8384 | 12804.6959 | 1028.6544 | Maintenance
EQ00129 | P001 | A043 | 2026-09-30 | Needle Vibrator | Concrete | 7.6517 | 0 | 10.9688 | 10087.3063 | 0 | Operational
EQ00130 | P001 | A044 | 2026-10-07 | Transit Mixer | Concrete | 4.7434 | 0 | 45.336 | 4354.4523 | 0 | Idle
EQ00131 | P001 | A044 | 2026-10-16 | Tower Crane | Lifting | 6.1603 | 2 | 44.1238 | 11116.4108 | 2268.6788 | Breakdown
EQ00132 | P001 | A044 | 2026-10-19 | Concrete Mixer | Concrete | 8.9026 | 0 | 75.4242 | 17368.8656 | 0 | Operational
EQ00133 | P001 | A045 | 2026-11-03 | Bar Bending Machine | Rebar | 7.6167 | 0.5 | 12.2615 | 14278.666 | 1135.7451 | Operational
EQ00134 | P001 | A045 | 2026-11-04 | Bar Cutting Machine | Rebar | 6.0959 | 0 | 5.6109 | 10198.1211 | 0 | Operational
EQ00135 | P001 | A045 | 2026-11-09 | Bar Cutting Machine | Rebar | 8.746 | 0.5 | 11.0469 | 11667.2147 | 419.0363 | Operational
EQ00136 | P001 | A046 | 2026-11-23 | Tower Crane | Lifting | 5.8538 | 2 | 57.6516 | 7106.0747 | 3892.2843 | Breakdown
EQ00137 | P001 | A046 | 2026-11-25 | Needle Vibrator | Concrete | 8.1812 | 0.5 | 11.9932 | 14879.7839 | 1155.547 | Operational
EQ00138 | P001 | A046 | 2026-11-27 | Needle Vibrator | Concrete | 4.4071 | 0.5 | 3.9939 | 8023.9261 | 744.0746 | Idle
EQ00139 | P001 | A047 | 2026-12-17 | Bar Cutting Machine | Rebar | 6.2958 | 1 | 9.9807 | 11512.3876 | 1930.6203 | Maintenance
EQ00140 | P001 | A047 | 2026-12-21 | Bar Bending Machine | Rebar | 9.3421 | 2 | 18.2229 | 9855.5036 | 3527.8359 | Breakdown
EQ00141 | P001 | A047 | 2026-12-22 | Bar Cutting Machine | Rebar | 8.3016 | 0 | 7.7396 | 13407.4224 | 0 | Operational
EQ00142 | P001 | A048 | 2026-04-25 | Concrete Pump | Concrete | 5.0542 | 0 | 37.6962 | 7150.6928 | 0 | Operational
EQ00143 | P001 | A048 | 2026-05-06 | Needle Vibrator | Concrete | 7.2271 | 0.5 | 5.4911 | 12119.3019 | 817.359 | Operational
EQ00144 | P001 | A048 | 2026-05-25 | Bar Bending Machine | Rebar | 6.1694 | 1 | 5.3868 | 13181.4946 | 1622.435 | Maintenance
EQ00145 | P001 | A049 | 2026-06-02 | Tower Crane | Lifting | 8.7162 | 0 | 85.5312 | 18785.6556 | 0 | Operational
EQ00146 | P001 | A049 | 2026-07-20 | Generator | Power | 8.5987 | 2 | 66.8565 | 14420.6168 | 1218.1741 | Breakdown
EQ00147 | P001 | A049 | 2026-07-28 | Tower Crane | Lifting | 4.0311 | 0.5 | 19.2188 | 4978.1881 | 1156.9552 | Idle
EQ00148 | P001 | A049 | 2026-07-28 | Tower Crane | Lifting | 7.1118 | 1 | 64.2186 | 13195.4115 | 1282.7702 | Maintenance
EQ00149 | P001 | A049 | 2026-07-31 | Generator | Power | 9.1832 | 0.5 | 77.6795 | 19027.9282 | 848.6635 | Operational
EQ00150 | P001 | A050 | 2026-06-15 | Tower Crane | Lifting | 8.8694 | 0 | 35.5463 | 14073.827 | 0 | Operational
EQ00151 | P001 | A050 | 2026-06-29 | Tower Crane | Lifting | 9.8593 | 0.5 | 81.9196 | 11992.8026 | 1217.552 | Operational
EQ00152 | P001 | A050 | 2026-07-24 | Tower Crane | Lifting | 6.2892 | 0.5 | 26.1734 | 10184.7194 | 1236.712 | Operational
EQ00153 | P001 | A050 | 2026-08-09 | Tower Crane | Lifting | 9.8786 | 1 | 68.1253 | 10180.854 | 1544.3537 | Maintenance
EQ00154 | P001 | A050 | 2026-08-10 | Tower Crane | Lifting | 7.5982 | 0 | 58.2987 | 15725.259 | 0 | Operational
EQ00155 | P001 | A050 | 2026-08-20 | Tower Crane | Lifting | 5.3736 | 0 | 25.4887 | 5996.5729 | 0 | Operational
EQ00156 | P001 | A051 | 2026-07-04 | Generator | Power | 9.3221 | 1 | 89.1152 | 16390.4449 | 894.7928 | Maintenance
EQ00157 | P001 | A051 | 2026-07-06 | Tower Crane | Lifting | 5.3921 | 0 | 52.6907 | 11598.777 | 0 | Operational
EQ00158 | P001 | A051 | 2026-07-07 | Tower Crane | Lifting | 7.0601 | 0 | 40.5963 | 15345.48 | 0 | Operational
EQ00159 | P001 | A052 | 2026-08-03 | Tower Crane | Lifting | 9.1404 | 0 | 44.2593 | 15165.9865 | 0 | Operational
EQ00160 | P001 | A052 | 2026-08-10 | Tower Crane | Lifting | 4.074 | 0 | 22.9777 | 3994.0752 | 0 | Idle
EQ00161 | P001 | A052 | 2026-08-28 | Tower Crane | Lifting | 8.3181 | 1 | 80.5551 | 12103.8509 | 1915.6028 | Maintenance
EQ00162 | P001 | A052 | 2026-09-02 | Tower Crane | Lifting | 5.3023 | 0.5 | 30.8672 | 8424.1444 | 1046.6573 | Operational
EQ00163 | P001 | A052 | 2026-09-09 | Tower Crane | Lifting | 5.3664 | 0 | 53.4541 | 5636.1264 | 0 | Operational
EQ00164 | P001 | A052 | 2026-10-14 | Generator | Power | 9.0334 | 1 | 79.2181 | 10574.6533 | 1765.1648 | Maintenance
EQ00165 | P001 | A053 | 2026-08-25 | Tower Crane | Lifting | 5.0867 | 2 | 34.9919 | 8372.3026 | 4347.8014 | Breakdown
EQ00166 | P001 | A053 | 2026-08-28 | Tower Crane | Lifting | 8.6142 | 2 | 48.0753 | 13115.5123 | 2341.7435 | Breakdown
EQ00167 | P001 | A053 | 2026-10-01 | Generator | Power | 5.4096 | 1 | 32.6563 | 6669.7344 | 1643.8047 | Maintenance
EQ00168 | P001 | A053 | 2026-10-02 | Tower Crane | Lifting | 4.3738 | 1 | 18.6701 | 7583.5021 | 1636.3791 | Maintenance
EQ00169 | P001 | A053 | 2026-10-03 | Tower Crane | Lifting | 6.0249 | 0 | 58.7276 | 9999.5549 | 0 | Operational
EQ00170 | P001 | A054 | 2026-08-22 | Generator | Power | 9.3783 | 1 | 59.0481 | 16853.0783 | 959.775 | Maintenance
EQ00171 | P001 | A054 | 2026-08-25 | Tower Crane | Lifting | 6.3949 | 0.5 | 25.8399 | 13699.1391 | 1118.4415 | Operational
EQ00172 | P001 | A054 | 2026-09-07 | Tower Crane | Lifting | 9.9865 | 0 | 58.9482 | 14944.8374 | 0 | Operational
EQ00173 | P001 | A055 | 2026-11-29 | Tower Crane | Lifting | 7.9935 | 2 | 52.2305 | 10409.4288 | 3707.0972 | Breakdown
EQ00174 | P001 | A055 | 2026-12-03 | Tower Crane | Lifting | 4.8158 | 0 | 39.8184 | 5312.2869 | 0 | Idle
EQ00175 | P001 | A055 | 2026-12-19 | Tower Crane | Lifting | 8.2773 | 0 | 37.8213 | 16617.4288 | 0 | Operational
EQ00176 | P001 | A056 | 2026-09-27 | Tower Crane | Lifting | 7.3509 | 0.5 | 61.8079 | 16164.879 | 828.5522 | Operational
EQ00177 | P001 | A056 | 2026-10-13 | Generator | Power | 8.4656 | 1 | 77.3324 | 18123.9439 | 886.1664 | Maintenance
EQ00178 | P001 | A056 | 2026-10-14 | Tower Crane | Lifting | 7.5181 | 0 | 50.3395 | 12344.2834 | 0 | Operational
EQ00179 | P001 | A056 | 2026-10-14 | Tower Crane | Lifting | 6.5045 | 2 | 54.0367 | 7518.1486 | 3138.2078 | Breakdown
EQ00180 | P001 | A056 | 2026-11-15 | Tower Crane | Lifting | 7.0225 | 0 | 51.0678 | 13034.3206 | 0 | Operational
EQ00181 | P001 | A056 | 2026-11-18 | Generator | Power | 4.0344 | 0 | 18.933 | 8734.3591 | 0 | Idle
EQ00182 | P001 | A056 | 2026-11-19 | Generator | Power | 5.5531 | 0 | 36.7533 | 9978.5195 | 0 | Operational
EQ00183 | P001 | A057 | 2026-09-27 | Tower Crane | Lifting | 5.9496 | 0 | 47.3173 | 9427.8248 | 0 | Operational
EQ00184 | P001 | A057 | 2026-09-29 | Tower Crane | Lifting | 7.3232 | 0 | 64.2671 | 15691.9494 | 0 | Operational
EQ00185 | P001 | A057 | 2026-10-10 | Tower Crane | Lifting | 9.3035 | 0 | 75.8729 | 12900.1244 | 0 | Operational
EQ00186 | P001 | A057 | 2026-10-23 | Generator | Power | 4.0338 | 0.5 | 30.8146 | 5740.2597 | 793.7688 | Idle
EQ00187 | P001 | A057 | 2026-12-03 | Generator | Power | 4.2432 | 2 | 32.8428 | 6655.5707 | 4148.2993 | Breakdown
EQ00188 | P001 | A058 | 2026-10-26 | Generator | Power | 4.4096 | 1 | 35.9174 | 8070.7103 | 1050.3271 | Maintenance
EQ00189 | P001 | A058 | 2026-11-23 | Tower Crane | Lifting | 5.2831 | 0 | 27.4133 | 8352.1653 | 0 | Operational
EQ00190 | P001 | A058 | 2026-11-26 | Generator | Power | 4.6305 | 0.5 | 19.2689 | 6089.4255 | 441.8597 | Idle
EQ00191 | P001 | A058 | 2026-12-15 | Generator | Power | 5.818 | 2 | 31.0237 | 6724.4232 | 2495.4116 | Breakdown
EQ00192 | P001 | A058 | 2026-12-17 | Generator | Power | 8.6917 | 0.5 | 53.7793 | 14895.459 | 732.0599 | Operational
EQ00193 | P001 | A059 | 2026-10-02 | Tower Crane | Lifting | 8.2215 | 1 | 55.8459 | 17950.5161 | 2258.1938 | Maintenance
EQ00194 | P001 | A059 | 2026-10-21 | Generator | Power | 5.1817 | 2 | 39.4107 | 8266.1759 | 3055.7543 | Breakdown
EQ00195 | P001 | A059 | 2026-11-03 | Generator | Power | 9.1205 | 0 | 65.9066 | 8787.7329 | 0 | Operational
EQ00196 | P001 | A059 | 2026-11-23 | Generator | Power | 9.4482 | 2 | 40.6816 | 19361.2578 | 4306.6689 | Breakdown
EQ00197 | P001 | A059 | 2026-11-30 | Generator | Power | 7.2801 | 0 | 53.6877 | 7068.733 | 0 | Operational
EQ00198 | P001 | A060 | 2026-10-02 | Tower Crane | Lifting | 9.1601 | 0.5 | 37.7972 | 11095.2795 | 959.8623 | Operational
EQ00199 | P001 | A060 | 2026-10-27 | Generator | Power | 8.5411 | 0 | 67.8205 | 14483.9796 | 0 | Operational
EQ00200 | P001 | A060 | 2026-10-30 | Tower Crane | Lifting | 8.312 | 0 | 41.14 | 8914.9434 | 0 | Operational
EQ00201 | P001 | A060 | 2026-11-20 | Tower Crane | Lifting | 9.4813 | 0 | 44.5649 | 15611.3895 | 0 | Operational
EQ00202 | P001 | A060 | 2026-11-24 | Generator | Power | 6.2103 | 0 | 55.7287 | 6755.4864 | 0 | Operational
EQ00203 | P001 | A060 | 2026-12-13 | Tower Crane | Lifting | 9.9034 | 0.5 | 44.3215 | 20601.0292 | 893.0797 | Operational
EQ00204 | P001 | A061 | 2026-10-28 | Tower Crane | Lifting | 6.8628 | 2 | 49.3291 | 10213.0383 | 1290.3657 | Breakdown
EQ00205 | P001 | A061 | 2026-11-13 | Generator | Power | 4.7585 | 1 | 30.2992 | 6675.514 | 1060.0816 | Maintenance
EQ00206 | P001 | A061 | 2026-11-26 | Tower Crane | Lifting | 7.7081 | 0 | 45.2334 | 8665.9001 | 0 | Operational
EQ00207 | P001 | A061 | 2026-11-28 | Tower Crane | Lifting | 6.7515 | 2 | 40.2533 | 6493.1007 | 1147.4062 | Breakdown
EQ00208 | P001 | A061 | 2026-12-02 | Tower Crane | Lifting | 9.5815 | 0 | 80.3333 | 12973.7676 | 0 | Operational
EQ00209 | P001 | A062 | 2026-08-29 | Tower Crane | Lifting | 6.167 | 2 | 49.0145 | 8669.3863 | 4606.9257 | Breakdown
EQ00210 | P001 | A062 | 2026-09-05 | Tower Crane | Lifting | 6.9295 | 0.5 | 33.2122 | 14361.3545 | 796.8169 | Operational
EQ00211 | P001 | A062 | 2026-09-11 | Tower Crane | Lifting | 9.2676 | 0 | 40.0974 | 12124.7504 | 0 | Operational
EQ00212 | P001 | A062 | 2026-09-22 | Tower Crane | Lifting | 6.8604 | 0 | 38.3215 | 7334.5146 | 0 | Operational
EQ00213 | P001 | A062 | 2026-09-26 | Generator | Power | 9.7177 | 0 | 72.4202 | 14922.936 | 0 | Operational
EQ00214 | P001 | A062 | 2026-09-26 | Generator | Power | 4.8476 | 1 | 27.4216 | 8496.1808 | 1458.1287 | Maintenance
EQ00215 | P001 | A062 | 2026-10-12 | Generator | Power | 9.3827 | 1 | 83.8832 | 10691.2588 | 682.9405 | Maintenance
EQ00216 | P001 | A062 | 2026-10-17 | Generator | Power | 8.7012 | 0 | 82.5132 | 18299.3171 | 0 | Operational
EQ00217 | P001 | A063 | 2026-10-22 | Generator | Power | 7.2902 | 0.5 | 32.6259 | 15632.9713 | 675.8026 | Operational
EQ00218 | P001 | A063 | 2026-10-24 | Tower Crane | Lifting | 6.1031 | 0.5 | 38.2886 | 12990.474 | 312.7046 | Operational
EQ00219 | P001 | A063 | 2026-11-23 | Tower Crane | Lifting | 4.7144 | 0 | 34.3982 | 5030.6914 | 0 | Idle
EQ00220 | P001 | A063 | 2026-12-13 | Generator | Power | 5.3454 | 2 | 21.8375 | 6312.4847 | 3953.2757 | Breakdown
EQ00221 | P001 | A063 | 2026-12-15 | Tower Crane | Lifting | 9.1326 | 2 | 57.896 | 12011.5439 | 4999.4434 | Breakdown
EQ00222 | P001 | A064 | 2026-09-05 | Tower Crane | Lifting | 7.0922 | 0 | 28.9508 | 15228.4846 | 0 | Operational
EQ00223 | P001 | A064 | 2026-09-09 | Generator | Power | 7.5349 | 0.5 | 64.7246 | 14003.2807 | 345.158 | Operational
EQ00224 | P001 | A064 | 2026-09-14 | Tower Crane | Lifting | 7.57 | 0.5 | 68.2312 | 8841.1039 | 1127.6348 | Operational
EQ00225 | P001 | A064 | 2026-09-24 | Generator | Power | 6.7689 | 0 | 31.3652 | 7832.5884 | 0 | Operational
EQ00226 | P001 | A064 | 2026-10-13 | Tower Crane | Lifting | 6.9784 | 0 | 35.7321 | 15285.894 | 0 | Operational
EQ00227 | P001 | A064 | 2026-11-05 | Generator | Power | 7.5963 | 2 | 68.3288 | 13234.6429 | 3861.972 | Breakdown
EQ00228 | P001 | A064 | 2026-11-18 | Generator | Power | 4.8052 | 2 | 31.7381 | 4883.9176 | 2431.0102 | Breakdown
EQ00229 | P001 | A064 | 2026-11-22 | Tower Crane | Lifting | 5.3425 | 0 | 49.5798 | 10495.9279 | 0 | Operational
EQ00230 | P001 | A065 | 2026-10-27 | Generator | Power | 7.8535 | 0.5 | 48.8219 | 11894.1421 | 739.1494 | Operational
EQ00231 | P001 | A065 | 2026-11-03 | Generator | Power | 5.885 | 0 | 38.3133 | 9911.1206 | 0 | Operational
EQ00232 | P001 | A065 | 2026-12-07 | Tower Crane | Lifting | 8.387 | 0.5 | 74.1578 | 8785.8731 | 903.1247 | Operational
EQ00233 | P001 | A065 | 2026-12-08 | Generator | Power | 7.4346 | 0 | 31.452 | 15449.6672 | 0 | Operational
EQ00234 | P001 | A065 | 2026-12-18 | Tower Crane | Lifting | 5.2767 | 0 | 26.812 | 10108.6473 | 0 | Operational
EQ00235 | P001 | A066 | 2026-10-24 | Tower Crane | Lifting | 6.7651 | 0 | 42.7817 | 10674.0011 | 0 | Operational
EQ00236 | P001 | A066 | 2026-11-02 | Tower Crane | Lifting | 6.5473 | 0 | 61.8725 | 10173.0047 | 0 | Operational
EQ00237 | P001 | A066 | 2026-11-28 | Tower Crane | Lifting | 8.6129 | 0.5 | 49.6237 | 16601.6953 | 514.3216 | Operational
EQ00238 | P001 | A066 | 2026-12-08 | Generator | Power | 4.9644 | 0 | 20.5025 | 10579.981 | 0 | Idle
EQ00239 | P001 | A067 | 2026-11-05 | Tower Crane | Lifting | 8.4627 | 2 | 50.7207 | 13142.1788 | 3647.0374 | Breakdown
EQ00240 | P001 | A067 | 2026-11-06 | Tower Crane | Lifting | 7.0092 | 0 | 58.8382 | 8023.4341 | 0 | Operational
EQ00241 | P001 | A067 | 2026-11-15 | Generator | Power | 8.4134 | 0.5 | 82.3395 | 16849.9904 | 871.5184 | Operational
EQ00242 | P001 | A067 | 2026-12-12 | Tower Crane | Lifting | 7.6191 | 0.5 | 55.3992 | 7445.1889 | 948.2964 | Operational
EQ00243 | P001 | A068 | 2026-12-12 | Generator | Power | 9.2223 | 0 | 56.957 | 8536.2091 | 0 | Operational
EQ00244 | P001 | A068 | 2026-12-18 | Generator | Power | 6.1108 | 0 | 30.5614 | 7003.7397 | 0 | Operational
EQ00245 | P001 | A068 | 2026-12-20 | Tower Crane | Lifting | 8.6831 | 1 | 54.6829 | 9760.4219 | 721.8168 | Maintenance

## Weather
Weather_ID | Date | Location | Temperature_C | Rainfall_mm | Humidity_Percentage | Weather_Condition | Working_Days_Lost | Weather_Impact
W001 | 2026-01-01 | Kolkata | 22.3656 | 0.034248 | 69.5956 | Clear | 0 | Low
W002 | 2026-01-02 | Kolkata | 21.4416 | 0.66921 | 52.7602 | Clear | 0 | Low
W003 | 2026-01-03 | Kolkata | 22.4773 | 0.40495 | 56.0539 | Clear | 0 | Low
W004 | 2026-01-04 | Kolkata | 20.91 | 0.7362 | 60.5537 | Clear | 0 | Low
W005 | 2026-01-05 | Kolkata | 22.4253 | 1.2687 | 64.8081 | Light Rain | 0 | Low
W006 | 2026-01-06 | Kolkata | 20.549 | 0.2676 | 54.919 | Clear | 0 | Low
W007 | 2026-01-07 | Kolkata | 19.2553 | 0.51177 | 60.5525 | Clear | 0 | Low
W008 | 2026-01-08 | Kolkata | 22.5319 | 3.9896 | 61.4225 | Light Rain | 0 | Low
W009 | 2026-01-09 | Kolkata | 21.0323 | 0.0051799 | 64.0069 | Clear | 0 | Low
W010 | 2026-01-10 | Kolkata | 21.4051 | 2.107 | 70.8299 | Light Rain | 0 | Low
W011 | 2026-01-11 | Kolkata | 20.3992 | 1.0283 | 46.763 | Light Rain | 0 | Low
W012 | 2026-01-12 | Kolkata | 22.7815 | 2.322 | 53.6184 | Light Rain | 0 | Low
W013 | 2026-01-13 | Kolkata | 18.0925 | 0.44242 | 58.4032 | Clear | 0 | Low
W014 | 2026-01-14 | Kolkata | 21.4715 | 0.86626 | 58.9554 | Clear | 0 | Low
W015 | 2026-01-15 | Kolkata | 17.8181 | 0.30355 | 63.4481 | Clear | 0 | Low
W016 | 2026-01-16 | Kolkata | 19.4172 | 0.46264 | 69.4583 | Clear | 0 | Low
W017 | 2026-01-17 | Kolkata | 16.1902 | 1.588 | 67.5518 | Light Rain | 0 | Low
W018 | 2026-01-18 | Kolkata | 19.1046 | 0.07376 | 57.0309 | Clear | 0 | Low
W019 | 2026-01-19 | Kolkata | 23.3961 | 0.013093 | 61.4778 | Clear | 0 | Low
W020 | 2026-01-20 | Kolkata | 22.6793 | 9.6978e-05 | 49.1482 | Clear | 0 | Low
W021 | 2026-01-21 | Kolkata | 19.735 | 0.0060927 | 55.4956 | Clear | 0 | Low
W022 | 2026-01-22 | Kolkata | 21.2644 | 0.4075 | 63.1165 | Clear | 0 | Low
W023 | 2026-01-23 | Kolkata | 22.7355 | 0.0095952 | 61.3587 | Clear | 0 | Low
W024 | 2026-01-24 | Kolkata | 23.6937 | 0.077652 | 64.4486 | Clear | 0 | Low
W025 | 2026-01-25 | Kolkata | 20.7247 | 0.53471 | 60.8254 | Clear | 0 | Low
W026 | 2026-01-26 | Kolkata | 20.5374 | 5.0187 | 58.8404 | Light Rain | 0 | Low
W027 | 2026-01-27 | Kolkata | 21.4837 | 7.7758 | 56.4055 | Light Rain | 0 | Low
W028 | 2026-01-28 | Kolkata | 19.7795 | 0.64292 | 59.6177 | Clear | 0 | Low
W029 | 2026-01-29 | Kolkata | 19.2376 | 0.44964 | 54.7587 | Clear | 0 | Low
W030 | 2026-01-30 | Kolkata | 21.6622 | 2.5524 | 61.1081 | Light Rain | 0 | Low
W031 | 2026-01-31 | Kolkata | 20.6211 | 0.79754 | 63.0407 | Clear | 0 | Low
W032 | 2026-02-01 | Kolkata | 24.9486 | 0.56135 | 61.3285 | Clear | 0 | Low
W033 | 2026-02-02 | Kolkata | 24.9259 | 0.48345 | 62.1625 | Clear | 0 | Low
W034 | 2026-02-03 | Kolkata | 20.7041 | 2.5605 | 68.8666 | Light Rain | 0 | Low
W035 | 2026-02-04 | Kolkata | 24.7151 | 0.016777 | 48.8838 | Clear | 0 | Low
W036 | 2026-02-05 | Kolkata | 23.1143 | 0.21997 | 53.8908 | Clear | 0 | Low
W037 | 2026-02-06 | Kolkata | 23.504 | 0.32219 | 63.3035 | Clear | 0 | Low
W038 | 2026-02-07 | Kolkata | 24.2947 | 0.51251 | 62.6916 | Clear | 0 | Low
W039 | 2026-02-08 | Kolkata | 27.3669 | 2.3799 | 54.6547 | Light Rain | 0 | Low
W040 | 2026-02-09 | Kolkata | 22.2228 | 1.1414 | 55.523 | Light Rain | 0 | Low
W041 | 2026-02-10 | Kolkata | 24.5857 | 3.8971 | 66.8616 | Light Rain | 0 | Low
W042 | 2026-02-11 | Kolkata | 22.7721 | 0.0051596 | 61.1716 | Clear | 0 | Low
W043 | 2026-02-12 | Kolkata | 23.9507 | 0.2047 | 67.4108 | Clear | 0 | Low
W044 | 2026-02-13 | Kolkata | 25.4675 | 0.39431 | 45.4937 | Clear | 0 | Low
W045 | 2026-02-14 | Kolkata | 21.8604 | 0.034931 | 49.7045 | Clear | 0 | Low
W046 | 2026-02-15 | Kolkata | 24.2605 | 3.2359 | 55.0592 | Light Rain | 0 | Low
W047 | 2026-02-16 | Kolkata | 21.618 | 0.66246 | 55.2319 | Clear | 0 | Low
W048 | 2026-02-17 | Kolkata | 25.8733 | 2.7797 | 57.9503 | Light Rain | 0 | Low
W049 | 2026-02-18 | Kolkata | 21.4355 | 0.11144 | 70.9347 | Clear | 0 | Low
W050 | 2026-02-19 | Kolkata | 26.5959 | 3.2816 | 54.3259 | Light Rain | 0 | Low
W051 | 2026-02-20 | Kolkata | 25.8307 | 0.35457 | 56.2149 | Clear | 0 | Low
W052 | 2026-02-21 | Kolkata | 23.635 | 0.33032 | 60.3052 | Clear | 0 | Low
W053 | 2026-02-22 | Kolkata | 20.2887 | 1.433 | 56.6748 | Light Rain | 0 | Low
W054 | 2026-02-23 | Kolkata | 23.1607 | 1.2098 | 54.6277 | Light Rain | 0 | Low
W055 | 2026-02-24 | Kolkata | 25.4569 | 0.29562 | 55.1284 | Clear | 0 | Low
W056 | 2026-02-25 | Kolkata | 21.0692 | 0.081506 | 52.2341 | Clear | 0 | Low
W057 | 2026-02-26 | Kolkata | 27.0238 | 0.036229 | 57.0191 | Clear | 0 | Low
W058 | 2026-02-27 | Kolkata | 23.9566 | 1.5393 | 57.5387 | Light Rain | 0 | Low
W059 | 2026-02-28 | Kolkata | 23.0912 | 0.023702 | 58.2353 | Clear | 0 | Low
W060 | 2026-03-01 | Kolkata | 26.6329 | 0.24882 | 55.912 | Clear | 0 | Low
W061 | 2026-03-02 | Kolkata | 26.4721 | 0.8914 | 68.4828 | Clear | 0 | Low
W062 | 2026-03-03 | Kolkata | 30.2794 | 0.18825 | 57.7605 | Clear | 0 | Low
W063 | 2026-03-04 | Kolkata | 25.1784 | 0.064393 | 60.5654 | Clear | 0 | Low
W064 | 2026-03-05 | Kolkata | 27.3684 | 0.11934 | 65.7256 | Clear | 0 | Low
W065 | 2026-03-06 | Kolkata | 24.6573 | 0.21361 | 63.7084 | Clear | 0 | Low
W066 | 2026-03-07 | Kolkata | 28.5431 | 1.9816 | 58.7092 | Light Rain | 0 | Low
W067 | 2026-03-08 | Kolkata | 30.0876 | 0.31424 | 57.7416 | Clear | 0 | Low
W068 | 2026-03-09 | Kolkata | 26.876 | 0.15956 | 60.4321 | Clear | 0 | Low
W069 | 2026-03-10 | Kolkata | 27.0979 | 0.045366 | 74.2933 | Clear | 0 | Low
W070 | 2026-03-11 | Kolkata | 26.7597 | 0.026112 | 69.2199 | Clear | 0 | Low
W071 | 2026-03-12 | Kolkata | 25.4543 | 5.5036 | 71.144 | Light Rain | 0 | Low
W072 | 2026-03-13 | Kolkata | 25.1253 | 2.5346 | 63.1944 | Light Rain | 0 | Low
W073 | 2026-03-14 | Kolkata | 31.5603 | 0.45445 | 60.4774 | Clear | 0 | Low
W074 | 2026-03-15 | Kolkata | 27.3561 | 0.014008 | 61.0991 | Clear | 0 | Low
W075 | 2026-03-16 | Kolkata | 25.8498 | 2.3502 | 69.5491 | Light Rain | 0 | Low
W076 | 2026-03-17 | Kolkata | 23.4979 | 1.3839 | 65.078 | Light Rain | 0 | Low
W077 | 2026-03-18 | Kolkata | 29.369 | 1.048 | 52.9111 | Light Rain | 0 | Low
W078 | 2026-03-19 | Kolkata | 30.8662 | 1.048 | 63.3035 | Light Rain | 0 | Low
W079 | 2026-03-20 | Kolkata | 27.3773 | 0.94865 | 65.6772 | Clear | 0 | Low
W080 | 2026-03-21 | Kolkata | 28.2935 | 3.9381 | 55.3285 | Light Rain | 0 | Low
W081 | 2026-03-22 | Kolkata | 27.9163 | 2.6518 | 65.8785 | Light Rain | 0 | Low
W082 | 2026-03-23 | Kolkata | 27.4684 | 0.21107 | 69.4117 | Clear | 0 | Low
W083 | 2026-03-24 | Kolkata | 25.6271 | 0.67654 | 61.5471 | Clear | 0 | Low
W084 | 2026-03-25 | Kolkata | 27.4831 | 34.5829 | 54.1885 | Thunderstorm | 0.5 | Medium
W085 | 2026-03-26 | Kolkata | 27.2638 | 6.3529 | 59.5167 | Light Rain | 0 | Low
W086 | 2026-03-27 | Kolkata | 27.1046 | 4.6703 | 70.2007 | Light Rain | 0 | Low
W087 | 2026-03-28 | Kolkata | 29.3708 | 5.6141 | 55.7109 | Light Rain | 0 | Low
W088 | 2026-03-29 | Kolkata | 30.1344 | 0.038823 | 60.9771 | Clear | 0 | Low
W089 | 2026-03-30 | Kolkata | 25.2267 | 0.5985 | 64.7442 | Clear | 0 | Low
W090 | 2026-03-31 | Kolkata | 29.5728 | 1.9676 | 57.5946 | Light Rain | 0 | Low
W091 | 2026-04-01 | Kolkata | 31.0369 | 1.3193 | 74.9704 | Light Rain | 0 | Low
W092 | 2026-04-02 | Kolkata | 30.9819 | 5.6295 | 72.7121 | Light Rain | 0 | Low
W093 | 2026-04-03 | Kolkata | 35.5526 | 3.9564 | 82.8554 | Light Rain | 0 | Low
W094 | 2026-04-04 | Kolkata | 28.3882 | 6.3568 | 58.816 | Light Rain | 0 | Low
W095 | 2026-04-05 | Kolkata | 31.0245 | 14.0144 | 51.2977 | Rain | 0 | Low
W096 | 2026-04-06 | Kolkata | 33.1891 | 3.9558 | 72.0368 | Light Rain | 0 | Low
W097 | 2026-04-07 | Kolkata | 32.3847 | 7.0497 | 76.7163 | Light Rain | 0 | Low
W098 | 2026-04-08 | Kolkata | 31.0295 | 3.1641 | 66.3614 | Light Rain | 0 | Low
W099 | 2026-04-09 | Kolkata | 28.7467 | 11.8493 | 65.4777 | Rain | 0 | Low
W100 | 2026-04-10 | Kolkata | 29.2697 | 0.96006 | 74.1164 | Clear | 0 | Low
W101 | 2026-04-11 | Kolkata | 30.9468 | 4.5467 | 64.0605 | Light Rain | 0 | Low
W102 | 2026-04-12 | Kolkata | 32.1405 | 4.7988 | 62.3108 | Light Rain | 0 | Low
W103 | 2026-04-13 | Kolkata | 31.1341 | 9.6074 | 78.6467 | Light Rain | 0 | Low
W104 | 2026-04-14 | Kolkata | 30.9908 | 59.1521 | 64.6422 | Thunderstorm | 1 | High
W105 | 2026-04-15 | Kolkata | 28.0913 | 2.4517 | 73.5724 | Light Rain | 0 | Low
W106 | 2026-04-16 | Kolkata | 33.3808 | 76.0916 | 64.3506 | Thunderstorm | 1 | High
W107 | 2026-04-17 | Kolkata | 27.8967 | 2.0238 | 60.101 | Light Rain | 0 | Low
W108 | 2026-04-18 | Kolkata | 28.5842 | 3.6571 | 64.6543 | Light Rain | 0 | Low
W109 | 2026-04-19 | Kolkata | 35.9931 | 2.2243 | 67.8599 | Light Rain | 0 | Low
W110 | 2026-04-20 | Kolkata | 30.2249 | 12.6515 | 56.8159 | Rain | 0 | Low
W111 | 2026-04-21 | Kolkata | 34.8193 | 4.9058 | 64.2371 | Light Rain | 0 | Low
W112 | 2026-04-22 | Kolkata | 33.3984 | 0.42533 | 62.8662 | Clear | 0 | Low
W113 | 2026-04-23 | Kolkata | 32.6907 | 2.6321 | 67.3718 | Light Rain | 0 | Low
W114 | 2026-04-24 | Kolkata | 27.8204 | 75.2641 | 72.1942 | Heavy Rain | 1 | High
W115 | 2026-04-25 | Kolkata | 34.6169 | 3.0718 | 67.8441 | Light Rain | 0 | Low
W116 | 2026-04-26 | Kolkata | 30.6929 | 6.5683 | 70.3432 | Light Rain | 0 | Low
W117 | 2026-04-27 | Kolkata | 27.6083 | 8.978 | 82.3641 | Light Rain | 0 | Low
W118 | 2026-04-28 | Kolkata | 30.5986 | 1.2062 | 72.3765 | Light Rain | 0 | Low
W119 | 2026-04-29 | Kolkata | 32.0139 | 1.8186 | 66.1268 | Light Rain | 0 | Low
W120 | 2026-04-30 | Kolkata | 34.8054 | 8.8486 | 63.7188 | Light Rain | 0 | Low
W121 | 2026-05-01 | Kolkata | 31.0162 | 83.7823 | 68.0277 | Heavy Rain | 1 | High
W122 | 2026-05-02 | Kolkata | 30.8491 | 6.8155 | 73.3699 | Light Rain | 0 | Low
W123 | 2026-05-03 | Kolkata | 36.845 | 3.2417 | 64.1347 | Light Rain | 0 | Low
W124 | 2026-05-04 | Kolkata | 28.0957 | 2.491 | 76.9815 | Light Rain | 0 | Low
W125 | 2026-05-05 | Kolkata | 30.4811 | 6.1601 | 82.5108 | Light Rain | 0 | Low
W126 | 2026-05-06 | Kolkata | 31.218 | 2.9381 | 68.4421 | Light Rain | 0 | Low
W127 | 2026-05-07 | Kolkata | 27.2675 | 3.9738 | 75.038 | Light Rain | 0 | Low
W128 | 2026-05-08 | Kolkata | 32.2934 | 0.96356 | 82.0444 | Cloudy | 0 | Low
W129 | 2026-05-09 | Kolkata | 27.7759 | 17.2702 | 79.2227 | Rain | 0 | Low
W130 | 2026-05-10 | Kolkata | 33.0789 | 2.7911 | 80.4069 | Light Rain | 0 | Low
W131 | 2026-05-11 | Kolkata | 31.6683 | 5.9684 | 77.7895 | Light Rain | 0 | Low
W132 | 2026-05-12 | Kolkata | 30.7112 | 5.9071 | 64.3131 | Light Rain | 0 | Low
W133 | 2026-05-13 | Kolkata | 31.28 | 6.3252 | 79.2954 | Light Rain | 0 | Low
W134 | 2026-05-14 | Kolkata | 24.6266 | 0.12917 | 67.1623 | Clear | 0 | Low
W135 | 2026-05-15 | Kolkata | 32.9408 | 12.5162 | 75.5057 | Rain | 0 | Low
W136 | 2026-05-16 | Kolkata | 29.6088 | 8.11 | 82.8444 | Light Rain | 0 | Low
W137 | 2026-05-17 | Kolkata | 28.9017 | 16.8353 | 82.9388 | Rain | 0 | Low
W138 | 2026-05-18 | Kolkata | 31.9365 | 8.0305 | 66.4031 | Light Rain | 0 | Low
W139 | 2026-05-19 | Kolkata | 32.5588 | 8.6684 | 64.3258 | Light Rain | 0 | Low
W140 | 2026-05-20 | Kolkata | 30.8698 | 5.8697 | 83.8947 | Light Rain | 0 | Low
W141 | 2026-05-21 | Kolkata | 28.8225 | 8.5462 | 82.5689 | Light Rain | 0 | Low
W142 | 2026-05-22 | Kolkata | 33.2792 | 1.0159 | 78.2999 | Light Rain | 0 | Low
W143 | 2026-05-23 | Kolkata | 39.8568 | 7.4464 | 78.839 | Light Rain | 0 | Low
W144 | 2026-05-24 | Kolkata | 30.5298 | 5.3401 | 70.2578 | Light Rain | 0 | Low
W145 | 2026-05-25 | Kolkata | 30.6506 | 4.7547 | 65.542 | Light Rain | 0 | Low
W146 | 2026-05-26 | Kolkata | 32.5673 | 14.8392 | 81.1798 | Rain | 0 | Low
W147 | 2026-05-27 | Kolkata | 32.5998 | 46.2672 | 70.7217 | Heavy Rain | 1 | High
W148 | 2026-05-28 | Kolkata | 31.5555 | 1.1696 | 80.4572 | Light Rain | 0 | Low
W149 | 2026-05-29 | Kolkata | 27.6495 | 2.6594 | 82.7602 | Light Rain | 0 | Low
W150 | 2026-05-30 | Kolkata | 29.2036 | 14.6648 | 72.5296 | Rain | 0 | Low
W151 | 2026-05-31 | Kolkata | 32.4286 | 0.85309 | 66.653 | Clear | 0 | Low
W152 | 2026-06-01 | Kolkata | 31.2521 | 8.9772 | 87.4101 | Light Rain | 0 | Low
W153 | 2026-06-02 | Kolkata | 29.7322 | 7.5784 | 79.7271 | Light Rain | 0 | Low
W154 | 2026-06-03 | Kolkata | 29.6107 | 78.447 | 74.8499 | Thunderstorm | 1 | High
W155 | 2026-06-04 | Kolkata | 29.5739 | 12.4822 | 67.7969 | Rain | 0 | Low
W156 | 2026-06-05 | Kolkata | 33.4861 | 5.0093 | 71.9069 | Light Rain | 0 | Low
W157 | 2026-06-06 | Kolkata | 29.9306 | 9.204 | 72.0615 | Light Rain | 0 | Low
W158 | 2026-06-07 | Kolkata | 28.417 | 0.75356 | 77.7158 | Cloudy | 0 | Low
W159 | 2026-06-08 | Kolkata | 28.4991 | 4.3479 | 78.8823 | Light Rain | 0 | Low
W160 | 2026-06-09 | Kolkata | 26.4501 | 3.9346 | 82.9273 | Light Rain | 0 | Low
W161 | 2026-06-10 | Kolkata | 33.8677 | 8.0426 | 72.5108 | Light Rain | 0 | Low
W162 | 2026-06-11 | Kolkata | 33.7551 | 8.8637 | 83.9315 | Light Rain | 0 | Low
W163 | 2026-06-12 | Kolkata | 30.3598 | 2.5743 | 70.9484 | Light Rain | 0 | Low
W164 | 2026-06-13 | Kolkata | 26.2547 | 1.3254 | 83.481 | Light Rain | 0 | Low
W165 | 2026-06-14 | Kolkata | 27.528 | 1.8205 | 80.5306 | Light Rain | 0 | Low
W166 | 2026-06-15 | Kolkata | 29.6663 | 1.5834 | 84.1426 | Light Rain | 0 | Low
W167 | 2026-06-16 | Kolkata | 27.5807 | 1.3851 | 72.2999 | Light Rain | 0 | Low
W168 | 2026-06-17 | Kolkata | 28.6379 | 10.2241 | 73.6739 | Rain | 0 | Low
W169 | 2026-06-18 | Kolkata | 31.2676 | 19.8802 | 70.5067 | Rain | 0 | Low
W170 | 2026-06-19 | Kolkata | 30.5456 | 75.7453 | 80.5484 | Thunderstorm | 1 | High
W171 | 2026-06-20 | Kolkata | 30.9038 | 3.5188 | 81.3885 | Light Rain | 0 | Low
W172 | 2026-06-21 | Kolkata | 33.2377 | 1.0462 | 81.0669 | Light Rain | 0 | Low
W173 | 2026-06-22 | Kolkata | 27.9245 | 3.0789 | 72.0423 | Light Rain | 0 | Low
W174 | 2026-06-23 | Kolkata | 29.633 | 14.546 | 76.3107 | Rain | 0 | Low
W175 | 2026-06-24 | Kolkata | 31.2622 | 14.574 | 74.8146 | Rain | 0 | Low
W176 | 2026-06-25 | Kolkata | 30.5559 | 5.8495 | 79.6797 | Light Rain | 0 | Low
W177 | 2026-06-26 | Kolkata | 32.9422 | 5.5008 | 71.7434 | Light Rain | 0 | Low
W178 | 2026-06-27 | Kolkata | 36.0579 | 43.905 | 84.2989 | Thunderstorm | 1 | High
W179 | 2026-06-28 | Kolkata | 29.3085 | 12.7971 | 84.9837 | Rain | 0 | Low
W180 | 2026-06-29 | Kolkata | 29.1776 | 7.1218 | 78.741 | Light Rain | 0 | Low
W181 | 2026-06-30 | Kolkata | 31.6772 | 9.3412 | 75.445 | Light Rain | 0 | Low
W182 | 2026-07-01 | Kolkata | 28.0802 | 7.5244 | 84.2503 | Light Rain | 0 | Low
W183 | 2026-07-02 | Kolkata | 27.8696 | 34.4763 | 79.9219 | Thunderstorm | 0.5 | Medium
W184 | 2026-07-03 | Kolkata | 25.9266 | 2.4476 | 86.6342 | Light Rain | 0 | Low
W185 | 2026-07-04 | Kolkata | 29.0184 | 0.68265 | 73.94 | Clear | 0 | Low
W186 | 2026-07-05 | Kolkata | 27.6642 | 5.4603 | 86.1823 | Light Rain | 0 | Low
W187 | 2026-07-06 | Kolkata | 30.1628 | 7.5953 | 87.8784 | Light Rain | 0 | Low
W188 | 2026-07-07 | Kolkata | 27.7566 | 4.1615 | 86.8075 | Light Rain | 0 | Low
W189 | 2026-07-08 | Kolkata | 30.9017 | 3.8355 | 74.6813 | Light Rain | 0 | Low
W190 | 2026-07-09 | Kolkata | 31.8061 | 26.4096 | 82.4082 | Rain | 0.5 | Medium
W191 | 2026-07-10 | Kolkata | 32.307 | 13.1351 | 90.9018 | Rain | 0 | Low
W192 | 2026-07-11 | Kolkata | 24.9935 | 4.6809 | 89.6156 | Light Rain | 0 | Low
W193 | 2026-07-12 | Kolkata | 25.8613 | 0.45958 | 84.6685 | Cloudy | 0 | Low
W194 | 2026-07-13 | Kolkata | 27.3339 | 3.3711 | 66.2865 | Light Rain | 0 | Low
W195 | 2026-07-14 | Kolkata | 28.3434 | 24.0156 | 89.115 | Rain | 0.5 | Medium
W196 | 2026-07-15 | Kolkata | 27.7486 | 2.72 | 79.3167 | Light Rain | 0 | Low
W197 | 2026-07-16 | Kolkata | 27.9625 | 6.4234 | 83.8916 | Light Rain | 0 | Low
W198 | 2026-07-17 | Kolkata | 25.0575 | 15.3284 | 79.7075 | Rain | 0 | Low
W199 | 2026-07-18 | Kolkata | 28.7883 | 4.9707 | 93.1968 | Light Rain | 0 | Low
W200 | 2026-07-19 | Kolkata | 29.4059 | 1.9102 | 93.9604 | Light Rain | 0 | Low
W201 | 2026-07-20 | Kolkata | 27.3708 | 7.3902 | 81.4199 | Light Rain | 0 | Low
W202 | 2026-07-21 | Kolkata | 27.5221 | 1.0811 | 86.4906 | Light Rain | 0 | Low
W203 | 2026-07-22 | Kolkata | 31.55 | 1.1092 | 80.2508 | Light Rain | 0 | Low
W204 | 2026-07-23 | Kolkata | 29.2419 | 8.6528 | 71.3562 | Light Rain | 0 | Low
W205 | 2026-07-24 | Kolkata | 30.5185 | 11.682 | 77.5869 | Rain | 0 | Low
W206 | 2026-07-25 | Kolkata | 31.0601 | 1.5868 | 81.7526 | Light Rain | 0 | Low
W207 | 2026-07-26 | Kolkata | 28.1772 | 11.8119 | 84.627 | Rain | 0 | Low
W208 | 2026-07-27 | Kolkata | 29.102 | 13.3885 | 83.8722 | Rain | 0 | Low
W209 | 2026-07-28 | Kolkata | 29.4718 | 19.2199 | 78.0869 | Rain | 0 | Low
W210 | 2026-07-29 | Kolkata | 30.6483 | 4.0319 | 75.2352 | Light Rain | 0 | Low
W211 | 2026-07-30 | Kolkata | 31.94 | 11.4026 | 93.243 | Rain | 0 | Low
W212 | 2026-07-31 | Kolkata | 32.0707 | 6.2493 | 88.0965 | Light Rain | 0 | Low
W213 | 2026-08-01 | Kolkata | 27.879 | 0.80358 | 74.7926 | Clear | 0 | Low
W214 | 2026-08-02 | Kolkata | 30.6355 | 7.7639 | 78.0349 | Light Rain | 0 | Low
W215 | 2026-08-03 | Kolkata | 29.3214 | 1.1609 | 72.5967 | Light Rain | 0 | Low
W216 | 2026-08-04 | Kolkata | 27.2656 | 3.6966 | 73.8221 | Light Rain | 0 | Low
W217 | 2026-08-05 | Kolkata | 27.8732 | 4.9112 | 84.0848 | Light Rain | 0 | Low
W218 | 2026-08-06 | Kolkata | 29.447 | 16.6193 | 96.3077 | Rain | 0 | Low
W219 | 2026-08-07 | Kolkata | 29.2109 | 0.86498 | 83.3598 | Cloudy | 0 | Low
W220 | 2026-08-08 | Kolkata | 28.7412 | 12.8823 | 79.549 | Rain | 0 | Low
W221 | 2026-08-09 | Kolkata | 33.5188 | 2.2336 | 85.2076 | Light Rain | 0 | Low
W222 | 2026-08-10 | Kolkata | 31.1662 | 9.0564 | 96.0609 | Light Rain | 0 | Low
W223 | 2026-08-11 | Kolkata | 29.4614 | 16.4585 | 76.7254 | Rain | 0 | Low
W224 | 2026-08-12 | Kolkata | 28.3576 | 0.63748 | 71.7139 | Clear | 0 | Low
W225 | 2026-08-13 | Kolkata | 28.1856 | 4.6522 | 79.7533 | Light Rain | 0 | Low
W226 | 2026-08-14 | Kolkata | 24.6312 | 2.3915 | 82.023 | Light Rain | 0 | Low
W227 | 2026-08-15 | Kolkata | 26.9806 | 5.3215 | 81.9488 | Light Rain | 0 | Low
W228 | 2026-08-16 | Kolkata | 28.883 | 2.9713 | 98 | Light Rain | 0 | Low
W229 | 2026-08-17 | Kolkata | 30.6091 | 3.9377 | 84.0264 | Light Rain | 0 | Low
W230 | 2026-08-18 | Kolkata | 29.7161 | 5.8502 | 96.2005 | Light Rain | 0 | Low
W231 | 2026-08-19 | Kolkata | 27.0878 | 13.5622 | 80.1764 | Rain | 0 | Low
W232 | 2026-08-20 | Kolkata | 27.9361 | 11.1507 | 97.2696 | Rain | 0 | Low
W233 | 2026-08-21 | Kolkata | 29.5416 | 5.3222 | 79.8616 | Light Rain | 0 | Low
W234 | 2026-08-22 | Kolkata | 28.2246 | 11.1053 | 88.4055 | Rain | 0 | Low
W235 | 2026-08-23 | Kolkata | 31.4276 | 4.224 | 78.8525 | Light Rain | 0 | Low
W236 | 2026-08-24 | Kolkata | 29.2732 | 5.9543 | 82.2198 | Light Rain | 0 | Low
W237 | 2026-08-25 | Kolkata | 30.0011 | 1.468 | 68.2265 | Light Rain | 0 | Low
W238 | 2026-08-26 | Kolkata | 25.034 | 1.371 | 82.2221 | Light Rain | 0 | Low
W239 | 2026-08-27 | Kolkata | 29.6565 | 18.2033 | 75.0772 | Rain | 0 | Low
W240 | 2026-08-28 | Kolkata | 30.3192 | 1.0206 | 76.994 | Light Rain | 0 | Low
W241 | 2026-08-29 | Kolkata | 27.1874 | 9.1937 | 82.5482 | Light Rain | 0 | Low
W242 | 2026-08-30 | Kolkata | 29.0493 | 3.9032 | 85.7809 | Light Rain | 0 | Low
W243 | 2026-08-31 | Kolkata | 27.7767 | 73.9741 | 81.5842 | Thunderstorm | 1 | High
W244 | 2026-09-01 | Kolkata | 27.8926 | 3.3266 | 76.4941 | Light Rain | 0 | Low
W245 | 2026-09-02 | Kolkata | 28.7076 | 3.2302 | 55.2955 | Light Rain | 0 | Low
W246 | 2026-09-03 | Kolkata | 31.8799 | 5.1198 | 78.686 | Light Rain | 0 | Low
W247 | 2026-09-04 | Kolkata | 27.7406 | 10.0587 | 71.7071 | Rain | 0 | Low
W248 | 2026-09-05 | Kolkata | 32.2923 | 3.9772 | 74.7589 | Light Rain | 0 | Low
W249 | 2026-09-06 | Kolkata | 29.4767 | 12.0312 | 84.6304 | Rain | 0 | Low
W250 | 2026-09-07 | Kolkata | 32.8096 | 6.1737 | 75.9134 | Light Rain | 0 | Low
W251 | 2026-09-08 | Kolkata | 28.7116 | 0.26063 | 83.8932 | Cloudy | 0 | Low
W252 | 2026-09-09 | Kolkata | 32.2335 | 2.919 | 80.2105 | Light Rain | 0 | Low
W253 | 2026-09-10 | Kolkata | 26.5153 | 0.94826 | 69.0639 | Clear | 0 | Low
W254 | 2026-09-11 | Kolkata | 29.6461 | 8.6791 | 81.3169 | Light Rain | 0 | Low
W255 | 2026-09-12 | Kolkata | 28.7922 | 8.4408 | 78.3165 | Light Rain | 0 | Low
W256 | 2026-09-13 | Kolkata | 30.6515 | 7.8525 | 80.5665 | Light Rain | 0 | Low
W257 | 2026-09-14 | Kolkata | 28.5643 | 16.6817 | 60.0477 | Rain | 0 | Low
W258 | 2026-09-15 | Kolkata | 29.3363 | 3.3994 | 84.871 | Light Rain | 0 | Low
W259 | 2026-09-16 | Kolkata | 29.5114 | 15.4636 | 70.8285 | Rain | 0 | Low
W260 | 2026-09-17 | Kolkata | 26.9161 | 2.5633 | 77.9142 | Light Rain | 0 | Low
W261 | 2026-09-18 | Kolkata | 30.4109 | 4.0841 | 88.166 | Light Rain | 0 | Low
W262 | 2026-09-19 | Kolkata | 25.9456 | 3.3818 | 71.5034 | Light Rain | 0 | Low
W263 | 2026-09-20 | Kolkata | 27.9513 | 4.8788 | 78.4879 | Light Rain | 0 | Low
W264 | 2026-09-21 | Kolkata | 26.0401 | 8.2316 | 75.998 | Light Rain | 0 | Low
W265 | 2026-09-22 | Kolkata | 31.7195 | 13.2399 | 75.9035 | Rain | 0 | Low
W266 | 2026-09-23 | Kolkata | 25.7032 | 15.7135 | 96.0265 | Rain | 0 | Low
W267 | 2026-09-24 | Kolkata | 30.5451 | 6.9981 | 89.1766 | Light Rain | 0 | Low
W268 | 2026-09-25 | Kolkata | 30.4659 | 2.2537 | 79.8394 | Light Rain | 0 | Low
W269 | 2026-09-26 | Kolkata | 27.0899 | 6.3506 | 85.533 | Light Rain | 0 | Low
W270 | 2026-09-27 | Kolkata | 29.9508 | 16.478 | 80.0567 | Rain | 0 | Low
W271 | 2026-09-28 | Kolkata | 29.8089 | 1.9209 | 79.7903 | Light Rain | 0 | Low
W272 | 2026-09-29 | Kolkata | 33.3351 | 0.082466 | 75.1095 | Cloudy | 0 | Low
W273 | 2026-09-30 | Kolkata | 31.6723 | 10.4447 | 77.5783 | Rain | 0 | Low
W274 | 2026-10-01 | Kolkata | 30.4007 | 0.74311 | 70.2033 | Clear | 0 | Low
W275 | 2026-10-02 | Kolkata | 27.0263 | 0.0063337 | 81.7168 | Cloudy | 0 | Low
W276 | 2026-10-03 | Kolkata | 24.2012 | 1.1151 | 79.3258 | Light Rain | 0 | Low
W277 | 2026-10-04 | Kolkata | 28.3483 | 0.41029 | 56.0319 | Clear | 0 | Low
W278 | 2026-10-05 | Kolkata | 31.7102 | 0.48781 | 65.4579 | Clear | 0 | Low
W279 | 2026-10-06 | Kolkata | 30.2283 | 1.1309 | 77.4541 | Light Rain | 0 | Low
W280 | 2026-10-07 | Kolkata | 30.5477 | 0.00076161 | 78.1968 | Cloudy | 0 | Low
W281 | 2026-10-08 | Kolkata | 27.5806 | 0.0065298 | 72.5413 | Clear | 0 | Low
W282 | 2026-10-09 | Kolkata | 27.4206 | 7.9474 | 77.4565 | Light Rain | 0 | Low
W283 | 2026-10-10 | Kolkata | 28.9286 | 2.3793 | 78.7197 | Light Rain | 0 | Low
W284 | 2026-10-11 | Kolkata | 25.2427 | 1.5657 | 73.7935 | Light Rain | 0 | Low
W285 | 2026-10-12 | Kolkata | 27.3904 | 0.029171 | 74.297 | Clear | 0 | Low
W286 | 2026-10-13 | Kolkata | 29.5389 | 0.56005 | 62.5241 | Clear | 0 | Low
W287 | 2026-10-14 | Kolkata | 25.4405 | 0.011137 | 85.0187 | Cloudy | 0 | Low
W288 | 2026-10-15 | Kolkata | 27.0899 | 0.28032 | 64.4678 | Clear | 0 | Low
W289 | 2026-10-16 | Kolkata | 30.85 | 0.89096 | 82.7195 | Cloudy | 0 | Low
W290 | 2026-10-17 | Kolkata | 30.7143 | 1.1057 | 78.2406 | Light Rain | 0 | Low
W291 | 2026-10-18 | Kolkata | 24.8832 | 0.59621 | 66.9651 | Clear | 0 | Low
W292 | 2026-10-19 | Kolkata | 31.3615 | 0.94458 | 78.2274 | Cloudy | 0 | Low
W293 | 2026-10-20 | Kolkata | 27.9462 | 1.2322 | 84.7813 | Light Rain | 0 | Low
W294 | 2026-10-21 | Kolkata | 31.1819 | 1.3578 | 85.2376 | Light Rain | 0 | Low
W295 | 2026-10-22 | Kolkata | 25.7267 | 0.056309 | 76.8322 | Cloudy | 0 | Low
W296 | 2026-10-23 | Kolkata | 26.9005 | 2.424 | 74.4997 | Light Rain | 0 | Low
W297 | 2026-10-24 | Kolkata | 31.948 | 0.16355 | 73.8794 | Clear | 0 | Low
W298 | 2026-10-25 | Kolkata | 27.6078 | 0.8103 | 80.0403 | Cloudy | 0 | Low
W299 | 2026-10-26 | Kolkata | 30.7925 | 1.5258 | 81.2303 | Light Rain | 0 | Low
W300 | 2026-10-27 | Kolkata | 32.642 | 2.3219 | 64.3131 | Light Rain | 0 | Low
W301 | 2026-10-28 | Kolkata | 28.417 | 0.58766 | 81.9951 | Cloudy | 0 | Low
W302 | 2026-10-29 | Kolkata | 29.7169 | 1.0307 | 64.1694 | Light Rain | 0 | Low
W303 | 2026-10-30 | Kolkata | 27.6503 | 0.34557 | 78.9912 | Cloudy | 0 | Low
W304 | 2026-10-31 | Kolkata | 29.2428 | 0.24226 | 79.2917 | Cloudy | 0 | Low
W305 | 2026-11-01 | Kolkata | 23.938 | 1.3985 | 65.9375 | Light Rain | 0 | Low
W306 | 2026-11-02 | Kolkata | 22.8143 | 0.50238 | 65.6986 | Clear | 0 | Low
W307 | 2026-11-03 | Kolkata | 27.973 | 1.5351 | 77.4459 | Light Rain | 0 | Low
W308 | 2026-11-04 | Kolkata | 27.4693 | 0.34037 | 79.1388 | Cloudy | 0 | Low
W309 | 2026-11-05 | Kolkata | 24.1903 | 4.235 | 65.0795 | Light Rain | 0 | Low
W310 | 2026-11-06 | Kolkata | 22.0288 | 0.30784 | 74.0383 | Clear | 0 | Low
W311 | 2026-11-07 | Kolkata | 23.668 | 0.42938 | 75.2659 | Cloudy | 0 | Low
W312 | 2026-11-08 | Kolkata | 25.8009 | 0.10555 | 67.42 | Clear | 0 | Low
W313 | 2026-11-09 | Kolkata | 25.7909 | 0.63809 | 60.0927 | Clear | 0 | Low
W314 | 2026-11-10 | Kolkata | 22.4291 | 0.43599 | 60.1734 | Clear | 0 | Low
W315 | 2026-11-11 | Kolkata | 20.575 | 0.98945 | 63.821 | Clear | 0 | Low
W316 | 2026-11-12 | Kolkata | 25.4557 | 0.7032 | 70.5659 | Clear | 0 | Low
W317 | 2026-11-13 | Kolkata | 22.8071 | 0.19223 | 60.3205 | Clear | 0 | Low
W318 | 2026-11-14 | Kolkata | 28.1368 | 0.52632 | 68.0505 | Clear | 0 | Low
W319 | 2026-11-15 | Kolkata | 28.1619 | 0.46482 | 68.7085 | Clear | 0 | Low
W320 | 2026-11-16 | Kolkata | 27.6111 | 33.6698 | 87.0948 | Heavy Rain | 0.5 | Medium
W321 | 2026-11-17 | Kolkata | 28.4207 | 0.096466 | 60.7957 | Clear | 0 | Low
W322 | 2026-11-18 | Kolkata | 24.5609 | 0.013145 | 65.1673 | Clear | 0 | Low
W323 | 2026-11-19 | Kolkata | 29.6895 | 2.1268 | 71.0719 | Light Rain | 0 | Low
W324 | 2026-11-20 | Kolkata | 23.4094 | 0.36547 | 70.7682 | Clear | 0 | Low
W325 | 2026-11-21 | Kolkata | 27.5899 | 0.20239 | 73.35 | Clear | 0 | Low
W326 | 2026-11-22 | Kolkata | 22.8193 | 1.053 | 64.0496 | Light Rain | 0 | Low
W327 | 2026-11-23 | Kolkata | 23.8724 | 1.988 | 68.6827 | Light Rain | 0 | Low
W328 | 2026-11-24 | Kolkata | 25.9225 | 0.41984 | 62.8536 | Clear | 0 | Low
W329 | 2026-11-25 | Kolkata | 26.0286 | 2.8337 | 71.1642 | Light Rain | 0 | Low
W330 | 2026-11-26 | Kolkata | 24.7373 | 4.0256 | 72.4741 | Light Rain | 0 | Low
W331 | 2026-11-27 | Kolkata | 27.312 | 1.0419 | 63.3442 | Light Rain | 0 | Low
W332 | 2026-11-28 | Kolkata | 21.3294 | 0.28937 | 61.6497 | Clear | 0 | Low
W333 | 2026-11-29 | Kolkata | 27.3316 | 0.11205 | 63.9654 | Clear | 0 | Low
W334 | 2026-11-30 | Kolkata | 23.3771 | 0.44387 | 66.103 | Clear | 0 | Low
W335 | 2026-12-01 | Kolkata | 20.7029 | 4.961 | 50.0694 | Light Rain | 0 | Low
W336 | 2026-12-02 | Kolkata | 18.0693 | 26.8266 | 58.1565 | Rain | 0.5 | Medium
W337 | 2026-12-03 | Kolkata | 21.0169 | 0.33541 | 61.6674 | Clear | 0 | Low
W338 | 2026-12-04 | Kolkata | 22.9251 | 5.2975 | 65.6074 | Light Rain | 0 | Low
W339 | 2026-12-05 | Kolkata | 23.1983 | 1.6859 | 67.8194 | Light Rain | 0 | Low
W340 | 2026-12-06 | Kolkata | 20.0793 | 0.73104 | 52.7563 | Clear | 0 | Low
W341 | 2026-12-07 | Kolkata | 20.1926 | 1.0522 | 64.7843 | Light Rain | 0 | Low
W342 | 2026-12-08 | Kolkata | 19.7344 | 2.5269 | 64.8648 | Light Rain | 0 | Low
W343 | 2026-12-09 | Kolkata | 24.0962 | 0.015346 | 62.6474 | Clear | 0 | Low
W344 | 2026-12-10 | Kolkata | 19.7532 | 0.87702 | 60.7535 | Clear | 0 | Low
W345 | 2026-12-11 | Kolkata | 17.9257 | 1.9768 | 65.6452 | Light Rain | 0 | Low
W346 | 2026-12-12 | Kolkata | 24.383 | 0.28489 | 66.1714 | Clear | 0 | Low
W347 | 2026-12-13 | Kolkata | 22.5451 | 0.23871 | 62.6707 | Clear | 0 | Low
W348 | 2026-12-14 | Kolkata | 23.0359 | 0.21533 | 63.4058 | Clear | 0 | Low
W349 | 2026-12-15 | Kolkata | 24.8192 | 3.545 | 56.8618 | Light Rain | 0 | Low
W350 | 2026-12-16 | Kolkata | 20.07 | 0.1571 | 59.3809 | Clear | 0 | Low
W351 | 2026-12-17 | Kolkata | 21.6936 | 0.62781 | 63.4247 | Clear | 0 | Low
W352 | 2026-12-18 | Kolkata | 24.6199 | 33.1352 | 59.4435 | Thunderstorm | 0.5 | Medium
W353 | 2026-12-19 | Kolkata | 24.308 | 0.14978 | 72.9914 | Clear | 0 | Low
W354 | 2026-12-20 | Kolkata | 20.6293 | 2.0458 | 60.12 | Light Rain | 0 | Low
W355 | 2026-12-21 | Kolkata | 19.1376 | 0.56338 | 62.0697 | Clear | 0 | Low
W356 | 2026-12-22 | Kolkata | 25.6079 | 1.4361 | 77.156 | Light Rain | 0 | Low
W357 | 2026-12-23 | Kolkata | 22.5649 | 6.6394 | 55.2772 | Light Rain | 0 | Low
W358 | 2026-12-24 | Kolkata | 21.3707 | 0.72421 | 55.4023 | Clear | 0 | Low
W359 | 2026-12-25 | Kolkata | 21.8991 | 0.14056 | 57.3725 | Clear | 0 | Low
W360 | 2026-12-26 | Kolkata | 26.6057 | 1.3606 | 52.0372 | Light Rain | 0 | Low
W361 | 2026-12-27 | Kolkata | 21.0994 | 0.54259 | 61.7654 | Clear | 0 | Low
W362 | 2026-12-28 | Kolkata | 20.3045 | 0.69656 | 53.4947 | Clear | 0 | Low
W363 | 2026-12-29 | Kolkata | 22.9514 | 0.2671 | 62.845 | Clear | 0 | Low
W364 | 2026-12-30 | Kolkata | 22.0141 | 0.19499 | 67.7097 | Clear | 0 | Low
W365 | 2026-12-31 | Kolkata | 20.363 | 1.2491 | 66.2958 | Light Rain | 0 | Low

## Calendar
Date | Year | Month | Month_Number | Quarter | Week_Number | Day_Name | Is_Weekend | Is_Working_Day
2026-01-01 | 2026 | January | 1 | 1 | 1 | Thursday | FALSE | TRUE
2026-01-02 | 2026 | January | 1 | 1 | 1 | Friday | FALSE | TRUE
2026-01-03 | 2026 | January | 1 | 1 | 1 | Saturday | TRUE | FALSE
2026-01-04 | 2026 | January | 1 | 1 | 1 | Sunday | TRUE | FALSE
2026-01-05 | 2026 | January | 1 | 1 | 2 | Monday | FALSE | TRUE
2026-01-06 | 2026 | January | 1 | 1 | 2 | Tuesday | FALSE | TRUE
2026-01-07 | 2026 | January | 1 | 1 | 2 | Wednesday | FALSE | TRUE
2026-01-08 | 2026 | January | 1 | 1 | 2 | Thursday | FALSE | TRUE
2026-01-09 | 2026 | January | 1 | 1 | 2 | Friday | FALSE | TRUE
2026-01-10 | 2026 | January | 1 | 1 | 2 | Saturday | TRUE | FALSE
2026-01-11 | 2026 | January | 1 | 1 | 2 | Sunday | TRUE | FALSE
2026-01-12 | 2026 | January | 1 | 1 | 3 | Monday | FALSE | TRUE
2026-01-13 | 2026 | January | 1 | 1 | 3 | Tuesday | FALSE | TRUE
2026-01-14 | 2026 | January | 1 | 1 | 3 | Wednesday | FALSE | TRUE
2026-01-15 | 2026 | January | 1 | 1 | 3 | Thursday | FALSE | TRUE
2026-01-16 | 2026 | January | 1 | 1 | 3 | Friday | FALSE | TRUE
2026-01-17 | 2026 | January | 1 | 1 | 3 | Saturday | TRUE | FALSE
2026-01-18 | 2026 | January | 1 | 1 | 3 | Sunday | TRUE | FALSE
2026-01-19 | 2026 | January | 1 | 1 | 4 | Monday | FALSE | TRUE
2026-01-20 | 2026 | January | 1 | 1 | 4 | Tuesday | FALSE | TRUE
2026-01-21 | 2026 | January | 1 | 1 | 4 | Wednesday | FALSE | TRUE
2026-01-22 | 2026 | January | 1 | 1 | 4 | Thursday | FALSE | TRUE
2026-01-23 | 2026 | January | 1 | 1 | 4 | Friday | FALSE | TRUE
2026-01-24 | 2026 | January | 1 | 1 | 4 | Saturday | TRUE | FALSE
2026-01-25 | 2026 | January | 1 | 1 | 4 | Sunday | TRUE | FALSE
2026-01-26 | 2026 | January | 1 | 1 | 5 | Monday | FALSE | TRUE
2026-01-27 | 2026 | January | 1 | 1 | 5 | Tuesday | FALSE | TRUE
2026-01-28 | 2026 | January | 1 | 1 | 5 | Wednesday | FALSE | TRUE
2026-01-29 | 2026 | January | 1 | 1 | 5 | Thursday | FALSE | TRUE
2026-01-30 | 2026 | January | 1 | 1 | 5 | Friday | FALSE | TRUE
2026-01-31 | 2026 | January | 1 | 1 | 5 | Saturday | TRUE | FALSE
2026-02-01 | 2026 | February | 2 | 1 | 5 | Sunday | TRUE | FALSE
2026-02-02 | 2026 | February | 2 | 1 | 6 | Monday | FALSE | TRUE
2026-02-03 | 2026 | February | 2 | 1 | 6 | Tuesday | FALSE | TRUE
2026-02-04 | 2026 | February | 2 | 1 | 6 | Wednesday | FALSE | TRUE
2026-02-05 | 2026 | February | 2 | 1 | 6 | Thursday | FALSE | TRUE
2026-02-06 | 2026 | February | 2 | 1 | 6 | Friday | FALSE | TRUE
2026-02-07 | 2026 | February | 2 | 1 | 6 | Saturday | TRUE | FALSE
2026-02-08 | 2026 | February | 2 | 1 | 6 | Sunday | TRUE | FALSE
2026-02-09 | 2026 | February | 2 | 1 | 7 | Monday | FALSE | TRUE
2026-02-10 | 2026 | February | 2 | 1 | 7 | Tuesday | FALSE | TRUE
2026-02-11 | 2026 | February | 2 | 1 | 7 | Wednesday | FALSE | TRUE
2026-02-12 | 2026 | February | 2 | 1 | 7 | Thursday | FALSE | TRUE
2026-02-13 | 2026 | February | 2 | 1 | 7 | Friday | FALSE | TRUE
2026-02-14 | 2026 | February | 2 | 1 | 7 | Saturday | TRUE | FALSE
2026-02-15 | 2026 | February | 2 | 1 | 7 | Sunday | TRUE | FALSE
2026-02-16 | 2026 | February | 2 | 1 | 8 | Monday | FALSE | TRUE
2026-02-17 | 2026 | February | 2 | 1 | 8 | Tuesday | FALSE | TRUE
2026-02-18 | 2026 | February | 2 | 1 | 8 | Wednesday | FALSE | TRUE
2026-02-19 | 2026 | February | 2 | 1 | 8 | Thursday | FALSE | TRUE
2026-02-20 | 2026 | February | 2 | 1 | 8 | Friday | FALSE | TRUE
2026-02-21 | 2026 | February | 2 | 1 | 8 | Saturday | TRUE | FALSE
2026-02-22 | 2026 | February | 2 | 1 | 8 | Sunday | TRUE | FALSE
2026-02-23 | 2026 | February | 2 | 1 | 9 | Monday | FALSE | TRUE
2026-02-24 | 2026 | February | 2 | 1 | 9 | Tuesday | FALSE | TRUE
2026-02-25 | 2026 | February | 2 | 1 | 9 | Wednesday | FALSE | TRUE
2026-02-26 | 2026 | February | 2 | 1 | 9 | Thursday | FALSE | TRUE
2026-02-27 | 2026 | February | 2 | 1 | 9 | Friday | FALSE | TRUE
2026-02-28 | 2026 | February | 2 | 1 | 9 | Saturday | TRUE | FALSE
2026-03-01 | 2026 | March | 3 | 1 | 9 | Sunday | TRUE | FALSE
2026-03-02 | 2026 | March | 3 | 1 | 10 | Monday | FALSE | TRUE
2026-03-03 | 2026 | March | 3 | 1 | 10 | Tuesday | FALSE | TRUE
2026-03-04 | 2026 | March | 3 | 1 | 10 | Wednesday | FALSE | TRUE
2026-03-05 | 2026 | March | 3 | 1 | 10 | Thursday | FALSE | TRUE
2026-03-06 | 2026 | March | 3 | 1 | 10 | Friday | FALSE | TRUE
2026-03-07 | 2026 | March | 3 | 1 | 10 | Saturday | TRUE | FALSE
2026-03-08 | 2026 | March | 3 | 1 | 10 | Sunday | TRUE | FALSE
2026-03-09 | 2026 | March | 3 | 1 | 11 | Monday | FALSE | TRUE
2026-03-10 | 2026 | March | 3 | 1 | 11 | Tuesday | FALSE | TRUE
2026-03-11 | 2026 | March | 3 | 1 | 11 | Wednesday | FALSE | TRUE
2026-03-12 | 2026 | March | 3 | 1 | 11 | Thursday | FALSE | TRUE
2026-03-13 | 2026 | March | 3 | 1 | 11 | Friday | FALSE | TRUE
2026-03-14 | 2026 | March | 3 | 1 | 11 | Saturday | TRUE | FALSE
2026-03-15 | 2026 | March | 3 | 1 | 11 | Sunday | TRUE | FALSE
2026-03-16 | 2026 | March | 3 | 1 | 12 | Monday | FALSE | TRUE
2026-03-17 | 2026 | March | 3 | 1 | 12 | Tuesday | FALSE | TRUE
2026-03-18 | 2026 | March | 3 | 1 | 12 | Wednesday | FALSE | TRUE
2026-03-19 | 2026 | March | 3 | 1 | 12 | Thursday | FALSE | TRUE
2026-03-20 | 2026 | March | 3 | 1 | 12 | Friday | FALSE | TRUE
2026-03-21 | 2026 | March | 3 | 1 | 12 | Saturday | TRUE | FALSE
2026-03-22 | 2026 | March | 3 | 1 | 12 | Sunday | TRUE | FALSE
2026-03-23 | 2026 | March | 3 | 1 | 13 | Monday | FALSE | TRUE
2026-03-24 | 2026 | March | 3 | 1 | 13 | Tuesday | FALSE | TRUE
2026-03-25 | 2026 | March | 3 | 1 | 13 | Wednesday | FALSE | TRUE
2026-03-26 | 2026 | March | 3 | 1 | 13 | Thursday | FALSE | TRUE
2026-03-27 | 2026 | March | 3 | 1 | 13 | Friday | FALSE | TRUE
2026-03-28 | 2026 | March | 3 | 1 | 13 | Saturday | TRUE | FALSE
2026-03-29 | 2026 | March | 3 | 1 | 13 | Sunday | TRUE | FALSE
2026-03-30 | 2026 | March | 3 | 1 | 14 | Monday | FALSE | TRUE
2026-03-31 | 2026 | March | 3 | 1 | 14 | Tuesday | FALSE | TRUE
2026-04-01 | 2026 | April | 4 | 2 | 14 | Wednesday | FALSE | TRUE
2026-04-02 | 2026 | April | 4 | 2 | 14 | Thursday | FALSE | TRUE
2026-04-03 | 2026 | April | 4 | 2 | 14 | Friday | FALSE | TRUE
2026-04-04 | 2026 | April | 4 | 2 | 14 | Saturday | TRUE | FALSE
2026-04-05 | 2026 | April | 4 | 2 | 14 | Sunday | TRUE | FALSE
2026-04-06 | 2026 | April | 4 | 2 | 15 | Monday | FALSE | TRUE
2026-04-07 | 2026 | April | 4 | 2 | 15 | Tuesday | FALSE | TRUE
2026-04-08 | 2026 | April | 4 | 2 | 15 | Wednesday | FALSE | TRUE
2026-04-09 | 2026 | April | 4 | 2 | 15 | Thursday | FALSE | TRUE
2026-04-10 | 2026 | April | 4 | 2 | 15 | Friday | FALSE | TRUE
2026-04-11 | 2026 | April | 4 | 2 | 15 | Saturday | TRUE | FALSE
2026-04-12 | 2026 | April | 4 | 2 | 15 | Sunday | TRUE | FALSE
2026-04-13 | 2026 | April | 4 | 2 | 16 | Monday | FALSE | TRUE
2026-04-14 | 2026 | April | 4 | 2 | 16 | Tuesday | FALSE | TRUE
2026-04-15 | 2026 | April | 4 | 2 | 16 | Wednesday | FALSE | TRUE
2026-04-16 | 2026 | April | 4 | 2 | 16 | Thursday | FALSE | TRUE
2026-04-17 | 2026 | April | 4 | 2 | 16 | Friday | FALSE | TRUE
2026-04-18 | 2026 | April | 4 | 2 | 16 | Saturday | TRUE | FALSE
2026-04-19 | 2026 | April | 4 | 2 | 16 | Sunday | TRUE | FALSE
2026-04-20 | 2026 | April | 4 | 2 | 17 | Monday | FALSE | TRUE
2026-04-21 | 2026 | April | 4 | 2 | 17 | Tuesday | FALSE | TRUE
2026-04-22 | 2026 | April | 4 | 2 | 17 | Wednesday | FALSE | TRUE
2026-04-23 | 2026 | April | 4 | 2 | 17 | Thursday | FALSE | TRUE
2026-04-24 | 2026 | April | 4 | 2 | 17 | Friday | FALSE | TRUE
2026-04-25 | 2026 | April | 4 | 2 | 17 | Saturday | TRUE | FALSE
2026-04-26 | 2026 | April | 4 | 2 | 17 | Sunday | TRUE | FALSE
2026-04-27 | 2026 | April | 4 | 2 | 18 | Monday | FALSE | TRUE
2026-04-28 | 2026 | April | 4 | 2 | 18 | Tuesday | FALSE | TRUE
2026-04-29 | 2026 | April | 4 | 2 | 18 | Wednesday | FALSE | TRUE
2026-04-30 | 2026 | April | 4 | 2 | 18 | Thursday | FALSE | TRUE
2026-05-01 | 2026 | May | 5 | 2 | 18 | Friday | FALSE | TRUE
2026-05-02 | 2026 | May | 5 | 2 | 18 | Saturday | TRUE | FALSE
2026-05-03 | 2026 | May | 5 | 2 | 18 | Sunday | TRUE | FALSE
2026-05-04 | 2026 | May | 5 | 2 | 19 | Monday | FALSE | TRUE
2026-05-05 | 2026 | May | 5 | 2 | 19 | Tuesday | FALSE | TRUE
2026-05-06 | 2026 | May | 5 | 2 | 19 | Wednesday | FALSE | TRUE
2026-05-07 | 2026 | May | 5 | 2 | 19 | Thursday | FALSE | TRUE
2026-05-08 | 2026 | May | 5 | 2 | 19 | Friday | FALSE | TRUE
2026-05-09 | 2026 | May | 5 | 2 | 19 | Saturday | TRUE | FALSE
2026-05-10 | 2026 | May | 5 | 2 | 19 | Sunday | TRUE | FALSE
2026-05-11 | 2026 | May | 5 | 2 | 20 | Monday | FALSE | TRUE
2026-05-12 | 2026 | May | 5 | 2 | 20 | Tuesday | FALSE | TRUE
2026-05-13 | 2026 | May | 5 | 2 | 20 | Wednesday | FALSE | TRUE
2026-05-14 | 2026 | May | 5 | 2 | 20 | Thursday | FALSE | TRUE
2026-05-15 | 2026 | May | 5 | 2 | 20 | Friday | FALSE | TRUE
2026-05-16 | 2026 | May | 5 | 2 | 20 | Saturday | TRUE | FALSE
2026-05-17 | 2026 | May | 5 | 2 | 20 | Sunday | TRUE | FALSE
2026-05-18 | 2026 | May | 5 | 2 | 21 | Monday | FALSE | TRUE
2026-05-19 | 2026 | May | 5 | 2 | 21 | Tuesday | FALSE | TRUE
2026-05-20 | 2026 | May | 5 | 2 | 21 | Wednesday | FALSE | TRUE
2026-05-21 | 2026 | May | 5 | 2 | 21 | Thursday | FALSE | TRUE
2026-05-22 | 2026 | May | 5 | 2 | 21 | Friday | FALSE | TRUE
2026-05-23 | 2026 | May | 5 | 2 | 21 | Saturday | TRUE | FALSE
2026-05-24 | 2026 | May | 5 | 2 | 21 | Sunday | TRUE | FALSE
2026-05-25 | 2026 | May | 5 | 2 | 22 | Monday | FALSE | TRUE
2026-05-26 | 2026 | May | 5 | 2 | 22 | Tuesday | FALSE | TRUE
2026-05-27 | 2026 | May | 5 | 2 | 22 | Wednesday | FALSE | TRUE
2026-05-28 | 2026 | May | 5 | 2 | 22 | Thursday | FALSE | TRUE
2026-05-29 | 2026 | May | 5 | 2 | 22 | Friday | FALSE | TRUE
2026-05-30 | 2026 | May | 5 | 2 | 22 | Saturday | TRUE | FALSE
2026-05-31 | 2026 | May | 5 | 2 | 22 | Sunday | TRUE | FALSE
2026-06-01 | 2026 | June | 6 | 2 | 23 | Monday | FALSE | TRUE
2026-06-02 | 2026 | June | 6 | 2 | 23 | Tuesday | FALSE | TRUE
2026-06-03 | 2026 | June | 6 | 2 | 23 | Wednesday | FALSE | TRUE
2026-06-04 | 2026 | June | 6 | 2 | 23 | Thursday | FALSE | TRUE
2026-06-05 | 2026 | June | 6 | 2 | 23 | Friday | FALSE | TRUE
2026-06-06 | 2026 | June | 6 | 2 | 23 | Saturday | TRUE | FALSE
2026-06-07 | 2026 | June | 6 | 2 | 23 | Sunday | TRUE | FALSE
2026-06-08 | 2026 | June | 6 | 2 | 24 | Monday | FALSE | TRUE
2026-06-09 | 2026 | June | 6 | 2 | 24 | Tuesday | FALSE | TRUE
2026-06-10 | 2026 | June | 6 | 2 | 24 | Wednesday | FALSE | TRUE
2026-06-11 | 2026 | June | 6 | 2 | 24 | Thursday | FALSE | TRUE
2026-06-12 | 2026 | June | 6 | 2 | 24 | Friday | FALSE | TRUE
2026-06-13 | 2026 | June | 6 | 2 | 24 | Saturday | TRUE | FALSE
2026-06-14 | 2026 | June | 6 | 2 | 24 | Sunday | TRUE | FALSE
2026-06-15 | 2026 | June | 6 | 2 | 25 | Monday | FALSE | TRUE
2026-06-16 | 2026 | June | 6 | 2 | 25 | Tuesday | FALSE | TRUE
2026-06-17 | 2026 | June | 6 | 2 | 25 | Wednesday | FALSE | TRUE
2026-06-18 | 2026 | June | 6 | 2 | 25 | Thursday | FALSE | TRUE
2026-06-19 | 2026 | June | 6 | 2 | 25 | Friday | FALSE | TRUE
2026-06-20 | 2026 | June | 6 | 2 | 25 | Saturday | TRUE | FALSE
2026-06-21 | 2026 | June | 6 | 2 | 25 | Sunday | TRUE | FALSE
2026-06-22 | 2026 | June | 6 | 2 | 26 | Monday | FALSE | TRUE
2026-06-23 | 2026 | June | 6 | 2 | 26 | Tuesday | FALSE | TRUE
2026-06-24 | 2026 | June | 6 | 2 | 26 | Wednesday | FALSE | TRUE
2026-06-25 | 2026 | June | 6 | 2 | 26 | Thursday | FALSE | TRUE
2026-06-26 | 2026 | June | 6 | 2 | 26 | Friday | FALSE | TRUE
2026-06-27 | 2026 | June | 6 | 2 | 26 | Saturday | TRUE | FALSE
2026-06-28 | 2026 | June | 6 | 2 | 26 | Sunday | TRUE | FALSE
2026-06-29 | 2026 | June | 6 | 2 | 27 | Monday | FALSE | TRUE
2026-06-30 | 2026 | June | 6 | 2 | 27 | Tuesday | FALSE | TRUE
2026-07-01 | 2026 | July | 7 | 3 | 27 | Wednesday | FALSE | TRUE
2026-07-02 | 2026 | July | 7 | 3 | 27 | Thursday | FALSE | TRUE
2026-07-03 | 2026 | July | 7 | 3 | 27 | Friday | FALSE | TRUE
2026-07-04 | 2026 | July | 7 | 3 | 27 | Saturday | TRUE | FALSE
2026-07-05 | 2026 | July | 7 | 3 | 27 | Sunday | TRUE | FALSE
2026-07-06 | 2026 | July | 7 | 3 | 28 | Monday | FALSE | TRUE
2026-07-07 | 2026 | July | 7 | 3 | 28 | Tuesday | FALSE | TRUE
2026-07-08 | 2026 | July | 7 | 3 | 28 | Wednesday | FALSE | TRUE
2026-07-09 | 2026 | July | 7 | 3 | 28 | Thursday | FALSE | TRUE
2026-07-10 | 2026 | July | 7 | 3 | 28 | Friday | FALSE | TRUE
2026-07-11 | 2026 | July | 7 | 3 | 28 | Saturday | TRUE | FALSE
2026-07-12 | 2026 | July | 7 | 3 | 28 | Sunday | TRUE | FALSE
2026-07-13 | 2026 | July | 7 | 3 | 29 | Monday | FALSE | TRUE
2026-07-14 | 2026 | July | 7 | 3 | 29 | Tuesday | FALSE | TRUE
2026-07-15 | 2026 | July | 7 | 3 | 29 | Wednesday | FALSE | TRUE
2026-07-16 | 2026 | July | 7 | 3 | 29 | Thursday | FALSE | TRUE
2026-07-17 | 2026 | July | 7 | 3 | 29 | Friday | FALSE | TRUE
2026-07-18 | 2026 | July | 7 | 3 | 29 | Saturday | TRUE | FALSE
2026-07-19 | 2026 | July | 7 | 3 | 29 | Sunday | TRUE | FALSE
2026-07-20 | 2026 | July | 7 | 3 | 30 | Monday | FALSE | TRUE
2026-07-21 | 2026 | July | 7 | 3 | 30 | Tuesday | FALSE | TRUE
2026-07-22 | 2026 | July | 7 | 3 | 30 | Wednesday | FALSE | TRUE
2026-07-23 | 2026 | July | 7 | 3 | 30 | Thursday | FALSE | TRUE
2026-07-24 | 2026 | July | 7 | 3 | 30 | Friday | FALSE | TRUE
2026-07-25 | 2026 | July | 7 | 3 | 30 | Saturday | TRUE | FALSE
2026-07-26 | 2026 | July | 7 | 3 | 30 | Sunday | TRUE | FALSE
2026-07-27 | 2026 | July | 7 | 3 | 31 | Monday | FALSE | TRUE
2026-07-28 | 2026 | July | 7 | 3 | 31 | Tuesday | FALSE | TRUE
2026-07-29 | 2026 | July | 7 | 3 | 31 | Wednesday | FALSE | TRUE
2026-07-30 | 2026 | July | 7 | 3 | 31 | Thursday | FALSE | TRUE
2026-07-31 | 2026 | July | 7 | 3 | 31 | Friday | FALSE | TRUE
2026-08-01 | 2026 | August | 8 | 3 | 31 | Saturday | TRUE | FALSE
2026-08-02 | 2026 | August | 8 | 3 | 31 | Sunday | TRUE | FALSE
2026-08-03 | 2026 | August | 8 | 3 | 32 | Monday | FALSE | TRUE
2026-08-04 | 2026 | August | 8 | 3 | 32 | Tuesday | FALSE | TRUE
2026-08-05 | 2026 | August | 8 | 3 | 32 | Wednesday | FALSE | TRUE
2026-08-06 | 2026 | August | 8 | 3 | 32 | Thursday | FALSE | TRUE
2026-08-07 | 2026 | August | 8 | 3 | 32 | Friday | FALSE | TRUE
2026-08-08 | 2026 | August | 8 | 3 | 32 | Saturday | TRUE | FALSE
2026-08-09 | 2026 | August | 8 | 3 | 32 | Sunday | TRUE | FALSE
2026-08-10 | 2026 | August | 8 | 3 | 33 | Monday | FALSE | TRUE
2026-08-11 | 2026 | August | 8 | 3 | 33 | Tuesday | FALSE | TRUE
2026-08-12 | 2026 | August | 8 | 3 | 33 | Wednesday | FALSE | TRUE
2026-08-13 | 2026 | August | 8 | 3 | 33 | Thursday | FALSE | TRUE
2026-08-14 | 2026 | August | 8 | 3 | 33 | Friday | FALSE | TRUE
2026-08-15 | 2026 | August | 8 | 3 | 33 | Saturday | TRUE | FALSE
2026-08-16 | 2026 | August | 8 | 3 | 33 | Sunday | TRUE | FALSE
2026-08-17 | 2026 | August | 8 | 3 | 34 | Monday | FALSE | TRUE
2026-08-18 | 2026 | August | 8 | 3 | 34 | Tuesday | FALSE | TRUE
2026-08-19 | 2026 | August | 8 | 3 | 34 | Wednesday | FALSE | TRUE
2026-08-20 | 2026 | August | 8 | 3 | 34 | Thursday | FALSE | TRUE
2026-08-21 | 2026 | August | 8 | 3 | 34 | Friday | FALSE | TRUE
2026-08-22 | 2026 | August | 8 | 3 | 34 | Saturday | TRUE | FALSE
2026-08-23 | 2026 | August | 8 | 3 | 34 | Sunday | TRUE | FALSE
2026-08-24 | 2026 | August | 8 | 3 | 35 | Monday | FALSE | TRUE
2026-08-25 | 2026 | August | 8 | 3 | 35 | Tuesday | FALSE | TRUE
2026-08-26 | 2026 | August | 8 | 3 | 35 | Wednesday | FALSE | TRUE
2026-08-27 | 2026 | August | 8 | 3 | 35 | Thursday | FALSE | TRUE
2026-08-28 | 2026 | August | 8 | 3 | 35 | Friday | FALSE | TRUE
2026-08-29 | 2026 | August | 8 | 3 | 35 | Saturday | TRUE | FALSE
2026-08-30 | 2026 | August | 8 | 3 | 35 | Sunday | TRUE | FALSE
2026-08-31 | 2026 | August | 8 | 3 | 36 | Monday | FALSE | TRUE
2026-09-01 | 2026 | September | 9 | 3 | 36 | Tuesday | FALSE | TRUE
2026-09-02 | 2026 | September | 9 | 3 | 36 | Wednesday | FALSE | TRUE
2026-09-03 | 2026 | September | 9 | 3 | 36 | Thursday | FALSE | TRUE
2026-09-04 | 2026 | September | 9 | 3 | 36 | Friday | FALSE | TRUE
2026-09-05 | 2026 | September | 9 | 3 | 36 | Saturday | TRUE | FALSE
2026-09-06 | 2026 | September | 9 | 3 | 36 | Sunday | TRUE | FALSE
2026-09-07 | 2026 | September | 9 | 3 | 37 | Monday | FALSE | TRUE
2026-09-08 | 2026 | September | 9 | 3 | 37 | Tuesday | FALSE | TRUE
2026-09-09 | 2026 | September | 9 | 3 | 37 | Wednesday | FALSE | TRUE
2026-09-10 | 2026 | September | 9 | 3 | 37 | Thursday | FALSE | TRUE
2026-09-11 | 2026 | September | 9 | 3 | 37 | Friday | FALSE | TRUE
2026-09-12 | 2026 | September | 9 | 3 | 37 | Saturday | TRUE | FALSE
2026-09-13 | 2026 | September | 9 | 3 | 37 | Sunday | TRUE | FALSE
2026-09-14 | 2026 | September | 9 | 3 | 38 | Monday | FALSE | TRUE
2026-09-15 | 2026 | September | 9 | 3 | 38 | Tuesday | FALSE | TRUE
2026-09-16 | 2026 | September | 9 | 3 | 38 | Wednesday | FALSE | TRUE
2026-09-17 | 2026 | September | 9 | 3 | 38 | Thursday | FALSE | TRUE
2026-09-18 | 2026 | September | 9 | 3 | 38 | Friday | FALSE | TRUE
2026-09-19 | 2026 | September | 9 | 3 | 38 | Saturday | TRUE | FALSE
2026-09-20 | 2026 | September | 9 | 3 | 38 | Sunday | TRUE | FALSE
2026-09-21 | 2026 | September | 9 | 3 | 39 | Monday | FALSE | TRUE
2026-09-22 | 2026 | September | 9 | 3 | 39 | Tuesday | FALSE | TRUE
2026-09-23 | 2026 | September | 9 | 3 | 39 | Wednesday | FALSE | TRUE
2026-09-24 | 2026 | September | 9 | 3 | 39 | Thursday | FALSE | TRUE
2026-09-25 | 2026 | September | 9 | 3 | 39 | Friday | FALSE | TRUE
2026-09-26 | 2026 | September | 9 | 3 | 39 | Saturday | TRUE | FALSE
2026-09-27 | 2026 | September | 9 | 3 | 39 | Sunday | TRUE | FALSE
2026-09-28 | 2026 | September | 9 | 3 | 40 | Monday | FALSE | TRUE
2026-09-29 | 2026 | September | 9 | 3 | 40 | Tuesday | FALSE | TRUE
2026-09-30 | 2026 | September | 9 | 3 | 40 | Wednesday | FALSE | TRUE
2026-10-01 | 2026 | October | 10 | 4 | 40 | Thursday | FALSE | TRUE
2026-10-02 | 2026 | October | 10 | 4 | 40 | Friday | FALSE | TRUE
2026-10-03 | 2026 | October | 10 | 4 | 40 | Saturday | TRUE | FALSE
2026-10-04 | 2026 | October | 10 | 4 | 40 | Sunday | TRUE | FALSE
2026-10-05 | 2026 | October | 10 | 4 | 41 | Monday | FALSE | TRUE
2026-10-06 | 2026 | October | 10 | 4 | 41 | Tuesday | FALSE | TRUE
2026-10-07 | 2026 | October | 10 | 4 | 41 | Wednesday | FALSE | TRUE
2026-10-08 | 2026 | October | 10 | 4 | 41 | Thursday | FALSE | TRUE
2026-10-09 | 2026 | October | 10 | 4 | 41 | Friday | FALSE | TRUE
2026-10-10 | 2026 | October | 10 | 4 | 41 | Saturday | TRUE | FALSE
2026-10-11 | 2026 | October | 10 | 4 | 41 | Sunday | TRUE | FALSE
2026-10-12 | 2026 | October | 10 | 4 | 42 | Monday | FALSE | TRUE
2026-10-13 | 2026 | October | 10 | 4 | 42 | Tuesday | FALSE | TRUE
2026-10-14 | 2026 | October | 10 | 4 | 42 | Wednesday | FALSE | TRUE
2026-10-15 | 2026 | October | 10 | 4 | 42 | Thursday | FALSE | TRUE
2026-10-16 | 2026 | October | 10 | 4 | 42 | Friday | FALSE | TRUE
2026-10-17 | 2026 | October | 10 | 4 | 42 | Saturday | TRUE | FALSE
2026-10-18 | 2026 | October | 10 | 4 | 42 | Sunday | TRUE | FALSE
2026-10-19 | 2026 | October | 10 | 4 | 43 | Monday | FALSE | TRUE
2026-10-20 | 2026 | October | 10 | 4 | 43 | Tuesday | FALSE | TRUE
2026-10-21 | 2026 | October | 10 | 4 | 43 | Wednesday | FALSE | TRUE
2026-10-22 | 2026 | October | 10 | 4 | 43 | Thursday | FALSE | TRUE
2026-10-23 | 2026 | October | 10 | 4 | 43 | Friday | FALSE | TRUE
2026-10-24 | 2026 | October | 10 | 4 | 43 | Saturday | TRUE | FALSE
2026-10-25 | 2026 | October | 10 | 4 | 43 | Sunday | TRUE | FALSE
2026-10-26 | 2026 | October | 10 | 4 | 44 | Monday | FALSE | TRUE
2026-10-27 | 2026 | October | 10 | 4 | 44 | Tuesday | FALSE | TRUE
2026-10-28 | 2026 | October | 10 | 4 | 44 | Wednesday | FALSE | TRUE
2026-10-29 | 2026 | October | 10 | 4 | 44 | Thursday | FALSE | TRUE
2026-10-30 | 2026 | October | 10 | 4 | 44 | Friday | FALSE | TRUE
2026-10-31 | 2026 | October | 10 | 4 | 44 | Saturday | TRUE | FALSE
2026-11-01 | 2026 | November | 11 | 4 | 44 | Sunday | TRUE | FALSE
2026-11-02 | 2026 | November | 11 | 4 | 45 | Monday | FALSE | TRUE
2026-11-03 | 2026 | November | 11 | 4 | 45 | Tuesday | FALSE | TRUE
2026-11-04 | 2026 | November | 11 | 4 | 45 | Wednesday | FALSE | TRUE
2026-11-05 | 2026 | November | 11 | 4 | 45 | Thursday | FALSE | TRUE
2026-11-06 | 2026 | November | 11 | 4 | 45 | Friday | FALSE | TRUE
2026-11-07 | 2026 | November | 11 | 4 | 45 | Saturday | TRUE | FALSE
2026-11-08 | 2026 | November | 11 | 4 | 45 | Sunday | TRUE | FALSE
2026-11-09 | 2026 | November | 11 | 4 | 46 | Monday | FALSE | TRUE
2026-11-10 | 2026 | November | 11 | 4 | 46 | Tuesday | FALSE | TRUE
2026-11-11 | 2026 | November | 11 | 4 | 46 | Wednesday | FALSE | TRUE
2026-11-12 | 2026 | November | 11 | 4 | 46 | Thursday | FALSE | TRUE
2026-11-13 | 2026 | November | 11 | 4 | 46 | Friday | FALSE | TRUE
2026-11-14 | 2026 | November | 11 | 4 | 46 | Saturday | TRUE | FALSE
2026-11-15 | 2026 | November | 11 | 4 | 46 | Sunday | TRUE | FALSE
2026-11-16 | 2026 | November | 11 | 4 | 47 | Monday | FALSE | TRUE
2026-11-17 | 2026 | November | 11 | 4 | 47 | Tuesday | FALSE | TRUE
2026-11-18 | 2026 | November | 11 | 4 | 47 | Wednesday | FALSE | TRUE
2026-11-19 | 2026 | November | 11 | 4 | 47 | Thursday | FALSE | TRUE
2026-11-20 | 2026 | November | 11 | 4 | 47 | Friday | FALSE | TRUE
2026-11-21 | 2026 | November | 11 | 4 | 47 | Saturday | TRUE | FALSE
2026-11-22 | 2026 | November | 11 | 4 | 47 | Sunday | TRUE | FALSE
2026-11-23 | 2026 | November | 11 | 4 | 48 | Monday | FALSE | TRUE
2026-11-24 | 2026 | November | 11 | 4 | 48 | Tuesday | FALSE | TRUE
2026-11-25 | 2026 | November | 11 | 4 | 48 | Wednesday | FALSE | TRUE
2026-11-26 | 2026 | November | 11 | 4 | 48 | Thursday | FALSE | TRUE
2026-11-27 | 2026 | November | 11 | 4 | 48 | Friday | FALSE | TRUE
2026-11-28 | 2026 | November | 11 | 4 | 48 | Saturday | TRUE | FALSE
2026-11-29 | 2026 | November | 11 | 4 | 48 | Sunday | TRUE | FALSE
2026-11-30 | 2026 | November | 11 | 4 | 49 | Monday | FALSE | TRUE
2026-12-01 | 2026 | December | 12 | 4 | 49 | Tuesday | FALSE | TRUE
2026-12-02 | 2026 | December | 12 | 4 | 49 | Wednesday | FALSE | TRUE
2026-12-03 | 2026 | December | 12 | 4 | 49 | Thursday | FALSE | TRUE
2026-12-04 | 2026 | December | 12 | 4 | 49 | Friday | FALSE | TRUE
2026-12-05 | 2026 | December | 12 | 4 | 49 | Saturday | TRUE | FALSE
2026-12-06 | 2026 | December | 12 | 4 | 49 | Sunday | TRUE | FALSE
2026-12-07 | 2026 | December | 12 | 4 | 50 | Monday | FALSE | TRUE
2026-12-08 | 2026 | December | 12 | 4 | 50 | Tuesday | FALSE | TRUE
2026-12-09 | 2026 | December | 12 | 4 | 50 | Wednesday | FALSE | TRUE
2026-12-10 | 2026 | December | 12 | 4 | 50 | Thursday | FALSE | TRUE
2026-12-11 | 2026 | December | 12 | 4 | 50 | Friday | FALSE | TRUE
2026-12-12 | 2026 | December | 12 | 4 | 50 | Saturday | TRUE | FALSE
2026-12-13 | 2026 | December | 12 | 4 | 50 | Sunday | TRUE | FALSE
2026-12-14 | 2026 | December | 12 | 4 | 51 | Monday | FALSE | TRUE
2026-12-15 | 2026 | December | 12 | 4 | 51 | Tuesday | FALSE | TRUE
2026-12-16 | 2026 | December | 12 | 4 | 51 | Wednesday | FALSE | TRUE
2026-12-17 | 2026 | December | 12 | 4 | 51 | Thursday | FALSE | TRUE
2026-12-18 | 2026 | December | 12 | 4 | 51 | Friday | FALSE | TRUE
2026-12-19 | 2026 | December | 12 | 4 | 51 | Saturday | TRUE | FALSE
2026-12-20 | 2026 | December | 12 | 4 | 51 | Sunday | TRUE | FALSE
2026-12-21 | 2026 | December | 12 | 4 | 52 | Monday | FALSE | TRUE
2026-12-22 | 2026 | December | 12 | 4 | 52 | Tuesday | FALSE | TRUE
2026-12-23 | 2026 | December | 12 | 4 | 52 | Wednesday | FALSE | TRUE
2026-12-24 | 2026 | December | 12 | 4 | 52 | Thursday | FALSE | TRUE
2026-12-25 | 2026 | December | 12 | 4 | 52 | Friday | FALSE | TRUE
2026-12-26 | 2026 | December | 12 | 4 | 52 | Saturday | TRUE | FALSE
2026-12-27 | 2026 | December | 12 | 4 | 52 | Sunday | TRUE | FALSE
2026-12-28 | 2026 | December | 12 | 4 | 53 | Monday | FALSE | TRUE
2026-12-29 | 2026 | December | 12 | 4 | 53 | Tuesday | FALSE | TRUE
2026-12-30 | 2026 | December | 12 | 4 | 53 | Wednesday | FALSE | TRUE
2026-12-31 | 2026 | December | 12 | 4 | 53 | Thursday | FALSE | TRUE